## Cover Page
Casa Spotify Miami (CSMIA26)
EXECUTIVE PRODUCTION PLAYBOOK & OPERATING SPECIFICATION
GHXSTSHIP Experiential Operating System (XOS 4.0 Standard) • Single Source of Truth (SSOT)
EVENT PARAMETERS & TIMELINE |  |  | CREATIVE & MARKETING NARRATIVE |  |  | KEY CONTACTS & GOVERNANCE
Project Code | CSMIA26 |  | Concept & Theme | Art, Music & Technology Convergence in Wynwood; flagship production |  | Executive Producer | Julian Clarkson (julian.clarkson@ghxstship.pro)
Event Title | Casa Spotify Miami |  | Experience Tier | Tier 06 Theatrical |  | Organization | GHXSTSHIP
Event Anchor Date (T-0) | 2026-10-16 | (Anchor / Opening Day) | Visual Identity | Wynwood Industrial Brutalism, LED Arrays, Neon |  | Operating Standard | XOS 4.0 Experiential Operating System
Show Dates | 2026-08-21 to 2026-10-30 |  | Audience Target | 35,000 Daily Cap / 105,000 Weekend Aggregate |  | Jurisdiction & Code | US-FL-MIAMI-DADE (FBC / NFPA / City of Miami)
Venue & Location | Mana Wynwood Convention Center & Grounds, Miami, FL |  | Acoustic Footprint | Multi-Zone High-SPL Controlled Environments |  | Governing Gate | Gate 05 Build
STAGE & PRODUCTION FOOTPRINT |  |  | CURATED TALENT ROSTER & HIGHLIGHTS |  |  | OPERATIONAL EXECUTION CADENCE
Main Stage (Zone B) | 60ft x 40ft Proscenium, Flown Line Arrays & 4K LED Backdrop |  | Headlining Acts | Latin & Global Headliners (TBA) |  | Pre-Production Advance | Gates 1–3: Scope, Engage, Advance (T-8W to T-4W)
Stage 2 - Tent Deck | 40ft x 30ft Covered Deck, Moving Head Rig & Cardioid Subs |  | DJ & Electronic Sets | DJ SWVNLVKE & Resident Electronic Lineup |  | Site Build & Load-In | Gates 4–6: Procure, Build, Install (T-3W to T-1W)
VIP Oasis Lounge & El Patio | Curated Hospitality Terrace, Acoustic Salon & DJ Booth |  | Special Performances | Pop-Up Acoustic Sessions & Featured Artist Showcases |  | Event Operations | Gate 7: Operate (T-0, Live Run)
Activation Compounds | Sponsor brand footprints, retail hubs & food villages |  | Broadcast & Sensory | Live Multicam 4K Stream, Spatial Audio & Cold-Air Scent |  | Strike & Reconciliation | Gates 8–9: Strike, Amplify, Close (T+1W to T+2W)
EXECUTIVE KPI SCOREBOARD & SYSTEM METRICS
REVISED TOTAL BUDGET |  | COMMITTED EXPENDITURE |  | APPROVED CHANGE ORDERS |  | PRODUCTION SCHEDULE TASKS
4500000 |  | 46600 |  | 1200 |  | 3
Approved Budget Envelope (Projects!K) |  | Committed Spend (Projects!L) |  | Approved Change Orders (Projects!N) |  | Active Production Tasks (Projects!O)
PROCUREMENT CATALOG ITEMS |  | CRITICAL PATH MILESTONES |  |  |  | SCHEDULE WORKBACK ENGINE
1211 |  | 20 |  |  |  | T-0 Locked: 2026-10-16 (T-8 Days)
SYSTEM MODULE DIRECTORY & WORKBOOK NAVIGATION INDEX
Functional Domain | Primary Module | Secondary Module | Grain & Schema Scope |  | Posture | Governance & Classification
Executive & Governance | Projects | Activity Log | Master project portfolio, executive controls, governing gates & audit log |  | Active Registry | Executive Governance SSOT
Production Planning & ROS | Production Schedule | Run of Show | 90 gated workback milestones, cue-by-cue run of show, tasks & work orders |  | Dynamic Engine | Production Operational SSOT
Field Logistics & Assets | Locations | Shipping Manifest | Site locations, freight manifests, yard logs, advance hospitality & asset tracking |  | Active Log | Operational Field SSOT
Workforce & Access | Personnel Roster | Credential Issuance | Staff roster, staffing requisitions, shift logs, rate cards & access grid |  | Active Roster | Workforce Governance
Financial Controls & Commercial | Budget Expenses | Purchase Orders | Cost center x GL x URID expenses, POs, change orders, procurement & vendors |  | Active Ledger | Fiscal Control Standard
Safety & Compliance | Inspection Compliance | Incident CAD Log | Agency safety inspections, incident CAD, emergency codes & comms channels |  | Life Safety Standard | Regulatory Compliance Standard
Master Reference & Standards | GL Accounts | Categories & URID Master | Chart of Accounts, 10 departments, 79 canon disciplines & matrix taxonomy |  | Core Master | Core Architecture Master

## Projects
PROJECT ID | PROJECT NAME | CLIENT NAME | ORGANIZATION | VENUE | LOCATION | START DATE | END DATE | ANCHOR DATE | TIER | BUDGET ENVELOPE | COMMITTED AMOUNT | ACTUAL SPEND | APPROVED CHANGE ORDERS | PRODUCTION TASKS | OPERATIONAL STATE | GOVERNING GATE | EXECUTIVE PRODUCER | NOTES
CSMIA26 | Casa Spotify Miami | Spotify | GHXSTSHIP | Mana Wynwood Convention Center & Grounds | Miami, FL | 2026-08-21 | 2026-10-30 | 2026-10-16 | Tier 06 Theatrical | 4500000 | 46600 | 0 | 1200 | 3 | Active | Gate 05 Build | Julian Clarkson | Art, Music & Technology Convergence in Wynwood; flagship production
SXSW26 | Spotify House Austin | Spotify | GHXSTSHIP | Clive Bar & Rainey Footprint | Austin, TX | 2026-02-01 | 2026-03-22 | 2026-03-13 | Tier 05 Experiential | 2800000 | 0 | 0 | 0 | 0 | Complete | Gate 09 Close | Julian Clarkson | Interactive music showcase and brand activation; archived
EDCLV26 | Electric Daisy Carnival KineticFIELD | Insomniac Events | GHXSTSHIP | Las Vegas Motor Speedway | Las Vegas, NV | 2026-04-10 | 2026-05-25 | 2026-05-15 | Tier 06 Theatrical | 6200000 | 0 | 0 | 0 | 0 | Complete | Gate 09 Close | Tigre JC | Mainstage scenic production, AVL engineering, and site ops
ABMIA26 | Art Basel Wynwood Experiential Pavilion | Art Basel / UBS | GHXSTSHIP | Wynwood Arts District Pavilion | Miami, FL | 2026-10-01 | 2026-12-10 | 2026-12-03 | Tier 05 Experiential | 3400000 | 0 | 0 | 0 | 0 | Active | Gate 03 Advance | Bex Izzy | Immersive art installations, VIP hospitality lounge, and sensory exhibits
NYFW26 | NYFW Runway & Digital Immersion | IMG Fashion | GHXSTSHIP | Spring Studios | New York, NY | 2026-11-15 | 2027-02-20 | 2027-02-11 | Tier 06 Theatrical | 3900000 | 0 | 0 | 0 | 0 | Scheduled | Gate 02 Engage | Julian Clarkson | High-concept fashion runway, broadcast capture, and digital streaming

## Activity Log
RECORD ID | ORGANIZATION | PROJECT | DEPARTMENT | CATEGORY | SUB CATEGORY | TIMESTAMP | LOCATION / ZONE | SUBJECT / ITEM | DESCRIPTION | PARTY INVOLVED | QTY / VALUE | PRIORITY | LOGGED BY | REFERENCE ID | STATUS | FLAG | NOTES | CREATED BY | CREATED AT | UPDATED AT

## Production Schedule
ACTIVITY ID | PROJECT ID | PARENT ACTIVITY ID | WBS CODE | PHASE CODE | PHASE | ACT | GATE | ACTIVITY NAME | ACTIVITY TYPE | DELIVERABLE | SOP ID | OWNER ROLE | PERSONNEL ID | START DATE | END DATE | DURATION (DAYS) | CRITICAL PATH | TOTAL TASKS | COMPLETED TASKS | PROGRESS (%) | STATUS | FLAG | NOTES
0000-SCP-001 | CSMIA26 | G1-GATE-001 | 1.1 | SCP | Scope | PLAN | 1 | Approve event budget envelope and spend authority | Summary Activity | Event budget envelope memo | SOP-022 | TIGRE/JC | P-021 | 2026-08-21 | 2026-09-03 | 14 | Y | 2 | 2 | 100% | Complete | FALSE | Spend authority thresholds approved
1000-SCP-001 | CSMIA26 | G1-GATE-001 | 1.2 | SCP | Scope | PLAN | 1 | Define event creative concept & visual identity | Summary Activity | Creative brief & narrative deck |  | BEX/IZZY | P-006 | 2026-08-21 | 2026-09-03 | 14 | Y | 1 | 1 | 100% | Complete | FALSE | Creative lock validated at Gate 1
2000-SCP-001 | CSMIA26 | G1-GATE-001 | 1.3 | SCP | Scope | PLAN | 1 | Lock talent lineup, set times & performance format | Summary Activity | Lineup curation memo |  | IZZY | P-005 | 2026-08-21 | 2026-09-03 | 14 | Y | 0 | 0 | 100% | Complete | FALSE | Headliner and support roster locked
G1-GATE-001 | CSMIA26 |  | 1 | SCP | Scope | PLAN | 1 | Gate 1 Exit: Scope & Budget Lock Ratified | Milestone Gate | Gate 1 ratification memo |  | TIGRE/JC | P-021 | 2026-09-03 | 2026-09-03 | 0 | Y | 3 | 3 | 100% | Complete | FALSE | Go/no-go milestone satisfied
0000-ENG-002 | CSMIA26 | G2-GATE-002 | 2.1 | ENG | Engage | PLAN | 2 | Execute master co-promoter & host agreements | Summary Activity | Executed co-promoter agreement | SOP-022 | JC/TIGRE | P-021 | 2026-09-04 | 2026-09-17 | 14 | Y | 2 | 2 | 100% | Complete | FALSE | Spotify and Tigre legal signoff complete
2000-ENG-002 | CSMIA26 | G2-GATE-002 | 2.2 | ENG | Engage | PLAN | 2 | Issue talent offers & execute performance contracts | Summary Activity | Executed talent contracts | SOP-031 | IZZY/TIGRE | P-005 | 2026-09-04 | 2026-09-17 | 14 | Y | 1 | 1 | 100% | Complete | FALSE | Deposit releases unblocked on execution
G2-GATE-002 | CSMIA26 | G1-GATE-001 | 2 | ENG | Engage | PLAN | 2 | Gate 2 Exit: Contracting & Accountable Parties | Milestone Gate | Contract execution binder | SOP-022 | TIGRE/JC | P-001 | 2026-09-17 | 2026-09-17 | 0 | Y | 3 | 3 | 100% | Complete | FALSE | Zero unassigned scope requirements
0000-ADV-003 | CSMIA26 | G3-GATE-003 | 3.1 | ADV | Advance | PLAN | 3 | Confirm event certificates of insurance & endorsements | Summary Activity | Event COI binder | SOP-022 | TIGRE | P-001 | 2026-09-18 | 2026-09-24 | 7 | Y | 1 | 1 | 100% | Complete | FALSE | GL & liquor liability additional insureds on file
3000-ADV-003 | CSMIA26 | G3-GATE-003 | 3.2 | ADV | Advance | PLAN | 3 | Launch RSVP platform, ticketing tiers & invite list | Summary Activity | Live RSVP system | SOP-028 | JC/BEX | P-006 | 2026-09-18 | 2026-09-24 | 7 | Y | 1 | 1 | 100% | Complete | FALSE | Guest allocations verified
G3-GATE-003 | CSMIA26 | G2-GATE-002 | 3 | ADV | Advance | PLAN | 3 | Gate 3 Exit: Advance & Baseline PO Lock | Milestone Gate | PO baseline register |  | JC | P-021 | 2026-09-24 | 2026-09-24 | 0 | Y | 2 | 2 | 100% | Complete | FALSE | Permits filed; rigging verified
4000-PRC-004 | CSMIA26 | G4-GATE-004 | 4.1 | PRC | Procure | BUILD | 4 | Issue purchase orders for scenic, millwork & FF&E | Summary Activity | Fabrication purchase orders | SOP-009 | SMC/JC | P-021 | 2026-09-25 | 2026-10-01 | 7 | Y | 2 | 2 | 100% | Complete | FALSE | 3-week fabrication lead time lock
G4-GATE-004 | CSMIA26 | G3-GATE-003 | 4 | PRC | Procure | BUILD | 4 | Gate 4 Exit: All Awards & Deposits Released | Milestone Gate | Deposit disbursements confirmation |  | TIGRE | P-001 | 2026-10-01 | 2026-10-01 | 0 | Y | 2 | 2 | 100% | Complete | FALSE | All vendor awards issued
4000-BLD-005 | CSMIA26 | G5-GATE-005 | 5.1 | BLD | Build | BUILD | 5 | Pre-assemble modular bar wraps, DJ altar & lounge scenic | Summary Activity | Prefabricated components | SOP-009 | VENDOR/SMC | P-021 | 2026-10-02 | 2026-10-11 | 10 | Y | 2 | 0 | 0% | Active | FALSE | Shop prep and finishing off-site
5000-BLD-005 | CSMIA26 | G5-GATE-005 | 5.2 | BLD | Build | BUILD | 5 | Build stage decks, erect truss towers & hang line arrays | Summary Activity | Staging & truss structure | SOP-001 | VENDOR/JC | P-021 | 2026-10-02 | 2026-10-11 | 10 | Y | 2 | 1 | 50% | Active | FALSE | Rigging certification stamped
G5-GATE-005 | CSMIA26 | G4-GATE-004 | 5 | BLD | Build | BUILD | 5 | Gate 5 Exit: Fabrication & Shop QC Pass | Milestone Gate | Shop QC signoff memo | SOP-001 | JC | P-021 | 2026-10-11 | 2026-10-11 | 0 | Y | 4 | 1 | 25% | Active | FALSE | Load-in dispatch unblocked
5000-INS-006 | CSMIA26 | G6-GATE-006 | 6.1 | INS | Install | BUILD | 6 | Connect power distro, commission audio & lighting timecode | Summary Activity | Commissioned AVL production rig | SOP-002 | JC | P-021 | 2026-10-12 | 2026-10-15 | 4 | Y | 2 | 0 | 0% | Scheduled | FALSE | Soundcheck & decibel compliance validated
6000-INS-006 | CSMIA26 | G6-GATE-006 | 6.2 | INS | Install | BUILD | 6 | Conduct safety & egress inspection with City of Miami Fire | Summary Activity | Fire Marshal inspection signoff | SOP-005 | JC/TIGRE | P-021 | 2026-10-12 | 2026-10-15 | 4 | Y | 2 | 0 | 0% | Scheduled | FALSE | Assembly occupancy permit granted
G6-GATE-006 | CSMIA26 | G5-GATE-005 | 6 | INS | Install | BUILD | 6 | Gate 6 Exit: Operational Readiness Signoff | Milestone Gate | Readiness signoff memo | SOP-004 | JC/SPOTIFY | P-021 | 2026-10-15 | 2026-10-15 | 0 | Y | 4 | 0 | 0% | Scheduled | FALSE | Final go/no-go gate exit satisfied
7000-OPR-007 | CSMIA26 | G7-GATE-007 | 7.1 | OPR | Operate | SHOW | 7 | Host guest check-in, VIP activations & show live operations | Summary Activity | Incident log & daily ops report | SOP-006 | BEX/JC | P-006 | 2026-10-16 | 2026-10-16 | 1 | Y | 2 | 0 | 0% | Ready | FALSE | Doors open at 19:00 EDT
9000-AMP-008 | CSMIA26 | G7-GATE-007 | 8.1 | AMP | Amplify | SHOW | 8 | Broadcast distribution, media recap & footfall analytics | Summary Activity | Event data & analytics recap | SOP-007 | JC/BEX | P-021 | 2026-10-17 | 2026-10-23 | 7 | N | 2 | 0 | 0% | Ready | FALSE | Audience dwell & stream peak concurrents
0000-CLS-009 | CSMIA26 | G7-GATE-007 | 9.1 | CLS | Close | SHOW | 9 | Complete production strike, final ledger & closeouts | Summary Activity | Final financial cost report | SOP-008 | JC/TIGRE | P-021 | 2026-10-24 | 2026-10-30 | 7 | Y | 2 | 0 | 0% | Ready | FALSE | Reconciliation against Gate 3 baseline

## Production Tasks
TASK ID | PROJECT ID | ACTIVITY ID | WBS CODE | TASK NAME | DESCRIPTION | RECORD KIND | RECORD SUBTYPE | TEAM CODE | LOCATION ID | PERSONNEL ID | ASSIGNEE NAME | START DATE | END DATE | DURATION (DAYS) | PREDECESSORS | PRIORITY | DELIVERABLE | LINKED WORK ORDER ID | SOP ID | PROGRESS (%) | STATUS | FLAG | NOTES
TSK-001 | CSMIA26 | 0000-SCP-001 | 1.1.1 | Draft spend envelope and authority matrix | Define baseline budget limits and executive delegation of authority | Task | Define | 0000-T01 | LOC-03 | P-021 | Julian Clarkson | 2026-08-21 | 2026-08-27 | 7 |  | Critical | Approved spend thresholds memo |  | SOP-022 | 100% | Complete | FALSE | Governed by SOP-022; Board envelope threshold sign-off
TSK-002 | CSMIA26 | 0000-SCP-001 | 1.1.2 | Establish WBS chart of accounts mapping | Align project expense items to master GL accounts and cost centers | Task | Coordinate | 0000-T02 | LOC-03 | P-021 | Julian Clarkson | 2026-08-28 | 2026-09-03 | 7 | TSK-001 | High | Chart of accounts ledger map |  |  | 100% | Complete | FALSE | Reconciled with CC-VENUE and CC-CORP
TSK-003 | CSMIA26 | 0000-ENG-002 | 1.2.1 | Negotiate co-promoter master agreement | Finalize legal terms and liability provisions with co-promoter | Task | Coordinate | 0000-T04 | LOC-03 | P-001 | Ashley Sumner | 2026-09-04 | 2026-09-10 | 7 | TSK-002 | Critical | Executed co-promoter contract |  | SOP-031 | 100% | Complete | FALSE | Governed by SOP-031; Spotify and Tigre legal review
TSK-004 | CSMIA26 | 0000-ENG-002 | 1.2.2 | Issue venue license and occupancy agreement | Finalize primary site lease terms and indemnification clauses | Task | Execute | 0000-T04 | LOC-03 | P-001 | Ashley Sumner | 2026-09-11 | 2026-09-17 | 7 | TSK-003 | High | Countersigned venue agreement |  | SOP-034 | 100% | Complete | FALSE | Governed by SOP-034; Premises occupancy rider verified
TSK-005 | CSMIA26 | 0000-ADV-003 | 1.3.1 | Bind general liability and excess umbrella policy | Secure certificate of insurance with additional insured endorsements | Task | Verify | 0000-T03 | LOC-03 | P-001 | Ashley Sumner | 2026-09-18 | 2026-09-24 | 7 | TSK-004 | Critical | Certificate of Insurance binder |  | SOP-022 | 100% | Complete | FALSE | Governed by SOP-022; $5M aggregate limit compliance
TSK-006 | CSMIA26 | 1000-SCP-001 | 2.1.1 | Publish creative identity guidelines and mood boards | Establish color system, typographic hierarchy, and environmental guidelines | Task | Produce | 1000-T01 | LOC-03 | P-006 | Rebecca Bex | 2026-08-21 | 2026-09-03 | 14 |  | High | Visual identity brief deck |  |  | 100% | Complete | FALSE | Wynwood aesthetic alignment
TSK-007 | CSMIA26 | 2000-ENG-002 | 2.2.1 | Issue artist offers and confirm headline performance | Finalize talent deal memos, hospitality riders, and deposit schedules | Task | Execute | 2000-T03 | LOC-06 | P-005 | Isabella Acker | 2026-09-04 | 2026-09-17 | 14 | TSK-006 | Critical | Executed artist performance contracts |  | SOP-031 | 100% | Complete | FALSE | Governed by SOP-031; 50% deposit release authorized
TSK-008 | CSMIA26 | 3000-ADV-003 | 2.3.1 | Deploy ticketing tiers and influencer RSVP portal | Set up guest registration portal, VIP allocations, and tier validation | Task | Systems | 3000-T01 | LOC-03 | P-006 | Rebecca Bex | 2026-09-18 | 2026-09-24 | 7 | TSK-007 | High | Live RSVP ticketing engine |  | SOP-028 | 100% | Complete | FALSE | Governed by SOP-028; Capacity caps keyed to venue limits
TSK-009 | CSMIA26 | 4000-PRC-004 | 3.1.1 | Order modular scenic wall panels and graphic skins | Transmit fabrication specifications for stage backdrops and partitions | Build | Scenic | 4000-T03 | LOC-16 | P-021 | Julian Clarkson | 2026-09-25 | 2026-10-01 | 7 | TSK-008 | High | Scenic fabrication purchase orders | WO-002 | SOP-009 | 100% | Complete | FALSE | Governed by SOP-009; Material flame-spread certification verified
TSK-010 | CSMIA26 | 4000-PRC-004 | 3.1.2 | Contract FF&E lounge furniture and patio shade fixtures | Procure designer sectionals, cocktail tables, and outdoor canopy hardware | Task | Coordinate | 4000-T06 | LOC-06 | P-021 | Julian Clarkson | 2026-09-25 | 2026-10-01 | 7 | TSK-009 | Medium | FF&E vendor dispatch schedule |  | SOP-009 | 100% | Complete | FALSE | Governed by SOP-009; Coordinated with SMC design specs
TSK-011 | CSMIA26 | 4000-BLD-005 | 3.2.1 | Off-site fabrication of modular bar facades and DJ altar | Millwork assembly, paint finishing, and edge LED channel integration | Build | Scenic | 4000-T03 | LOC-22 | P-021 | Julian Clarkson | 2026-10-02 | 2026-10-08 | 7 | TSK-010 | High | Completed modular bar components | WO-002 | SOP-009 | 80% | Active | FALSE | Governed by SOP-009; Shop QC passed; awaiting load-in dispatch
TSK-012 | CSMIA26 | 4000-BLD-005 | 3.2.2 | Pre-assemble neon signage frames and backdrop mounts | Wire low-voltage transformers and test illuminated neon phrase fixtures | Build | Systems | 4000-T07 | LOC-16 | P-006 | Rebecca Bex | 2026-10-06 | 2026-10-11 | 6 | TSK-011 | Medium | Pre-tested neon display assemblies |  | SOP-002 | 60% | Active | FALSE | Governed by SOP-002; Exhibition room feature installation
TSK-013 | CSMIA26 | 5000-BLD-005 | 3.3.1 | Erect stage decking and ground-support truss towers | Assemble 4x8 decks with guardrails, ballast plates, and vertical motor masts | Build | Structural | 5000-T05 | LOC-01 | P-021 | Julian Clarkson | 2026-10-02 | 2026-10-06 | 5 | TSK-010 | Critical | Structural stage and truss signoff | WO-002 | SOP-001 | 100% | Complete | FALSE | Governed by SOP-001; Rigging cert stamped by structural engineer
TSK-014 | CSMIA26 | 5000-BLD-005 | 3.3.2 | Hang line array audio clusters and cardioid subwoofers | Fly primary PA hangs, connect speaker multicores, and align front fills | Build | Systems | 5000-T01 | LOC-01 | P-024 | David Miller | 2026-10-07 | 2026-10-11 | 5 | TSK-013 | High | Flown audio rig ready for tuning | WO-001 | SOP-001 | 75% | Active | FALSE | Governed by SOP-001; David Miller leading A1 hang
TSK-015 | CSMIA26 | 5000-INS-006 | 3.4.1 | Connect temporary generator power distro and branch circuits | Tie in primary 200A distro panels, test grounding, and balance phase loads | Build | Systems | 5000-T04 | LOC-01 | P-021 | Julian Clarkson | 2026-10-12 | 2026-10-13 | 2 | TSK-014 | Critical | Certified power distribution network | WO-001 | SOP-002 | 0% | Scheduled | FALSE | Governed by SOP-002; Master electrician inspection prerequisite
TSK-016 | CSMIA26 | 5000-INS-006 | 3.4.2 | Tune acoustic room curves and program lighting timecode | Execute pink noise room alignment, timecode sync tests, and mover fixture presets | Build | Commissioning | 5000-T01 | LOC-01 | P-024 | David Miller | 2026-10-14 | 2026-10-15 | 2 | TSK-015 | High | Commissioned AVL production system | WO-001 | SOP-003 | 0% | Scheduled | FALSE | Governed by SOP-003; Decibel limits validated for City of Miami noise variance
TSK-017 | CSMIA26 | 6000-INS-006 | 3.5.1 | Conduct municipal life safety and fire marshal walkthrough | Inspect egress corridors, fire extinguishers, panic hardware, and crowd barricades | Inspection | Safety | 6000-T03 | LOC-17 | P-021 | Julian Clarkson | 2026-10-14 | 2026-10-15 | 2 | TSK-016 | Critical | Fire Marshal assembly occupancy permit |  | SOP-005 | 0% | Scheduled | FALSE | Governed by SOP-005; AHJ signoff required prior to public doors
TSK-018 | CSMIA26 | 6000-INS-006 | 3.5.2 | Brief security detail, crowd managers, and medical staff | Review radio protocol, emergency evacuation routes, and threat escalation procedures | Task | Coordinate | 6000-T05 | LOC-03 | P-016 | Mary Christianson | 2026-10-15 | 2026-10-15 | 1 | TSK-017 | High | Security deployment roster & sign-in |  | SOP-004 | 0% | Scheduled | FALSE | Governed by SOP-004; City of Miami PD off-duty coordination
TSK-019 | CSMIA26 | 7000-OPR-007 | 4.1.1 | Manage guest check-in, VIP wristbands, and credential scanning | Operate front-of-house arrival portal, ticket scanners, and swag gift distribution | Shift | Show | 7000-T03 | LOC-02 | P-006 | Rebecca Bex | 2026-10-16 | 2026-10-16 | 1 | TSK-018 | High | Guest entry log & scan counts |  | SOP-028 | 0% | Ready | FALSE | Governed by SOP-028; Continuous sync with live attendance dashboard
TSK-020 | CSMIA26 | 7000-OPR-007 | 4.1.2 | Direct main stage live performance and DJ show calling | Coordinate stage management, cue lights, lighting presets, and talent changeovers | Shift | Show | 2000-T01 | LOC-01 | P-021 | Julian Clarkson | 2026-10-16 | 2026-10-16 | 1 | TSK-016 | Critical | Flawless live show execution |  | SOP-006 | 0% | Ready | FALSE | Governed by SOP-006; Run of show cues strictly maintained
TSK-021 | CSMIA26 | 9000-AMP-008 | 4.2.1 | Ingest live multicam footage and encode press social reels | Edit same-day highlights, color grade clips, and push media assets to PR distribution | Task | Produce | 3000-T02 | LOC-03 | P-006 | Rebecca Bex | 2026-10-17 | 2026-10-20 | 4 | TSK-020 | High | Post-event media highlight reel |  | SOP-007 | 0% | Ready | FALSE | Governed by SOP-007; Cleared usage rights on all tracks
TSK-022 | CSMIA26 | 9000-AMP-008 | 4.2.2 | Aggregate attendance footfall and stream viewer analytics | Compile RFID scan metrics, dwell heatmap reports, and social impression tallies | Task | Produce | 9000-T04 | LOC-03 | P-021 | Julian Clarkson | 2026-10-17 | 2026-10-23 | 7 | TSK-021 | Medium | Analytics & ROI recap report |  | SOP-028 | 0% | Ready | FALSE | Governed by SOP-028; Measures against Gate 1 KPI targets
TSK-023 | CSMIA26 | 0000-CLS-009 | 4.3.1 | Strike production rigging and return equipment rentals | De-rig line arrays, pack truss, disassemble staging, and load out carrier trucks | Strike | Show Strike | 5000-T05 | LOC-01 | P-021 | Julian Clarkson | 2026-10-17 | 2026-10-20 | 4 | TSK-020 | High | Rental equipment return manifests | WO-002 | SOP-008 | 0% | Ready | FALSE | Governed by SOP-008; Zero damage disposition signoff
TSK-024 | CSMIA26 | 0000-CLS-009 | 4.3.2 | Execute post-event financial settlement and bond releases | Reconcile PO actuals against budget baseline and secure municipal deposit returns | Task | Verify | 0000-T02 | LOC-03 | P-001 | Ashley Sumner | 2026-10-24 | 2026-10-30 | 7 | TSK-023 | High | Final financial reconciliation ledger |  | SOP-034 | 0% | Ready | FALSE | Governed by SOP-034; Closeout signoff by Executive Producer

## Work Orders
RECORD ID | PROJECT ID | DEPARTMENT | CATEGORY | SUB CATEGORY | WORK ORDER TYPE | PRIORITY | LOCATION ID | LOCATION NAME | ITEM ID | TEAM CODE | PERSONNEL ID | LEAD ASSIGNEE NAME | TASK TITLE | DESCRIPTION | SCOPE OF WORK | SCHEDULED START DATE | SCHEDULED END DATE | ACTUAL START DATE | ACTUAL END DATE | ESTIMATED HOURS | ACTUAL HOURS | LABOR RATE | TOTAL LABOR COST | SAFETY HAZARD LEVEL | COMPLETION PERCENTAGE | STATUS | FLAG | RESOLUTION NOTES | NOTES | CREATED BY | CREATED AT | UPDATED AT
WO-001 | CSMIA26 | 5000 Production | 5000.01 Audio | Audio Infrastructure | AVL Installation | Critical | LOC-01 | Zone B - Main Stage | 5000.01.02-XPMS-004 | 5000-T01 | P-024 | David Miller | Main PA Line Array Hang and Calibration | Install and tune main FOH line array system | Acoustic sweep, time alignment, and safety cable inspection | 2026-10-15 | 2026-10-16 | 2026-10-15 | 2026-10-16 | 16 | 14.5 | 75 | 1087.5 | Medium | 100% | Completed | FALSE | System calibrated to 102 dBA target | Signed off by Technical Production Manager | Julian Clarkson | 2026-10-01 | 2026-10-16
WO-002 | CSMIA26 | 4000 Environment | 4000.01 Construction & Carpentry | General Tools & Hardware | Facility Setup | High | LOC-01 | Zone B - Main Stage | 4000.08.01-XPMS-001 | 4000-T04 | P-021 | Julian Clarkson | Stage Decks and Barricade Erection | Assemble 4x8 modular stage decking and Mojo safety barricade | Leveling, clamp torquing, and stage skirt attachment | 2026-10-18 | 2026-10-19 | 2026-10-18 | 2026-10-19 | 24 | 22 | 65 | 1430 | High | 100% | Completed | FALSE | Structural stability certified | Stagehand union crew utilized | Julian Clarkson | 2026-10-05 | 2026-10-19
WO-003 | CSMIA26 | 9000 Technology | 9000.52 Venue IT | Network Provision | Network Deployment | High | LOC-03 | Production Office / Quartermaster | 9000.01.01-XPMS-005 | 9000-T06 | P-021 | Julian Clarkson | Production Network VLAN Configuration | Configure segregated VLANs for guest WiFi and broadcast telemetry | Fiber patch to switches, router config, and bandwidth test | 2026-10-20 | 2026-10-21 | 2026-10-20 | 2026-10-21 | 12 | 11.5 | 85 | 977.5 | Low | 100% | Completed | FALSE | Network throughput validated at 1 Gbps | Tested with Toast POS hardware | Julian Clarkson | 2026-10-10 | 2026-10-21
WO-004 | CSMIA26 | 6000 Operations | 6000.04 Security & Access Control | Security & Access Control | Security Commissioning | Medium | LOC-08 | Gate 2 - South Gate | 9000.04.01-XPMS-002 | 6000-T07 | P-016 | Mary Christianson | Access Control and Magnetometer Deployment | Install walk-through metal detectors and set ingress gates | Power tie-in, sensitivity calibration, and barrier alignment | 2026-10-22 | 2026-10-23 | 2026-10-22 |  | 10 | 6 | 55 | 330 | Medium | 60% | In Progress | FALSE | Hardware operational; awaiting final shift walk | Coordinated with City Fire Inspector | Julian Clarkson | 2026-10-12 | 2026-10-22
WO-005 | CSMIA26 | 5000 Production | 5000.02 Lighting | Lighting Control | Rigging & Focus | High | LOC-01 | Zone B - Main Stage | 5000.02.02-XPMS-004 | 5000-T03 | P-021 | Julian Clarkson | Overhead Lighting Truss Focus and DMX Addressing | Hang moving heads and test Art-Net lighting universe control | Safety wire secondary attachments, lamp check, and cue recording | 2026-10-25 | 2026-10-26 |  |  | 18 | 0 | 75 | 0 | High | 0% | Scheduled | FALSE | Pending rigger signoff | Focus scheduled for dark hours | Julian Clarkson | 2026-10-14 | 2026-10-14

## Run of Show
RECORD ID | ORGANIZATION | PROJECT ID | SCHEDULE RECORD ID | CUE ID | ACT | SCENE | DESCRIPTION | START TIME | END TIME | DURATION (MIN) | LOCATION ID | PERSONNEL ID | AUDIO CUE | LIGHTING CUE | VIDEO CUE | SFX CUE | STAGE CUE | STATUS | FLAG | NOTES | CREATED BY | CREATED AT | UPDATED AT
ROS-001 | GHXSTSHIP | CSMIA26 | 5000-OPR-007 | CUE-01 | Act I · Ingress & Warm-Up | Doors Open & Guest Check-In | Front of house doors open; guest credentials check and initial lounge activation | 18:00 | 18:30 | 30 | LOC-02 | P-016 | Ambient background music at 72 dBA; FOH mix standby | Look 01 - Warm architectural wash & amber accents | Looping Casa Spotify brand reel & sponsor logo matrix | Baseline atmospheric scent diffusion active; haze standby | Stage dark; DJ gear line check verified; green rooms active | Scheduled | FALSE | Coordinate arrival pace with door security; RFID scanning active | Julian Clarkson | 2026-10-02 09:55 | 2026-10-02 09:55
ROS-002 | GHXSTSHIP | CSMIA26 | 5000-OPR-007 | CUE-02 | Act I · Ingress & Warm-Up | Support DJ Set & Cocktail Reception | Opening support DJ set building energy across the sanctuary floor and patio | 18:30 | 19:30 | 60 | LOC-01 | P-024 | DJ direct input hot; live stereo mains at 85 dBA | Look 02 - Subtle tempo-synced movers & neon perimeter glow | Generative ambient visuals mapped across primary LED wall | Low haze output (15%) for beam visibility | Support DJ on riser; stage monitors balanced | Scheduled | FALSE | Beverage and canapé service in full circulation across El Patio | Julian Clarkson | 2026-10-02 09:55 | 2026-10-02 09:55
ROS-003 | GHXSTSHIP | CSMIA26 | 5000-OPR-007 | CUE-03 | Act II · Official Opening & Remarks | Executive Welcome & Opening Remarks | Formal welcome remarks by Isabella Acker (Spotify) and Ashley Sumner (Tigre) | 19:30 | 19:45 | 15 | LOC-01 | P-021 | DJ track fade to bed; wireless handheld mics 1 & 2 live at 82 dBA | Look 03 - Crisp keylight wash center-stage; house ambient dimmed 50% | Presentation title slide; live IMAG feed on stage side blades | Haze paused; clear atmosphere for clear sightlines | Speakers escorted to downstage right; lectern placed center | Scheduled | FALSE | Broadcast feed live recording enabled; timecode sync verified | Julian Clarkson | 2026-10-02 09:55 | 2026-10-02 09:55
ROS-004 | GHXSTSHIP | CSMIA26 | 5000-OPR-007 | CUE-04 | Act II · Official Opening & Remarks | Brand Sizzle & Artist Video Reveal | Dynamic video sizzle reveal showcasing Casa Spotify artist partnerships | 19:45 | 20:00 | 15 | LOC-01 | P-021 | 5.1 surround sizzle audio playback from media server at 90 dBA | Look 04 - Complete blackout into pulsing emerald/cyan strobes | Full-resolution 4K branded sizzle reel playing on main LED wall | Cryo CO2 jet single burst on final beat drop | Lectern struck to stage left; headline backline powered hot | Scheduled | FALSE | Headliner escorted from Artist Village Green Room (LOC-06) to stage wing | Julian Clarkson | 2026-10-02 09:55 | 2026-10-02 09:55
ROS-005 | GHXSTSHIP | CSMIA26 | 5000-OPR-007 | CUE-05 | Act III · Headline Performance | Headliner Live Performance (Set 1) | Featured headliner live performance and full concert presentation | 20:00 | 21:15 | 75 | LOC-01 | P-024 | Full line array concert mix, cardioid sub engagement at 98 dBA | Look 05 - High-energy programmed movers, beam sweeps & pixel tape | Live artist-synced reactive visuals & dynamic multi-cam IMAG | Cold-spark fountains on track climax; medium atmospheric haze (30%) | Headliner on stage; audio tech standing by stage left | Scheduled | FALSE | Noise monitor logging compliance at Biscayne property perimeter | Julian Clarkson | 2026-10-02 09:55 | 2026-10-02 09:55
ROS-006 | GHXSTSHIP | CSMIA26 | 5000-OPR-007 | CUE-06 | Act III · Headline Performance | Guest Artist Collab & Show Finale | Surprise guest artist collaboration and peak performance finale | 21:15 | 22:00 | 45 | LOC-01 | P-024 | Guest wireless vocal channels unmuted; peak concert mix at 100 dBA | Look 06 - Audience blinders full, laser aerial fan & 360 strobe sweeps | High-contrast synchronized strobe visual packages across all screens | Continuous CO2 cryo cannon bursts & biodegradable confetti drop | Guest artist escort onto stage right; stagehands on perimeter | Scheduled | FALSE | Photographers alerted for hero capture moment; security perimeter alert | Julian Clarkson | 2026-10-02 09:55 | 2026-10-02 09:55
ROS-007 | GHXSTSHIP | CSMIA26 | 5000-OPR-007 | CUE-07 | Act IV · Cool-Down & Egress | After-Show DJ & Late-Night Bites | Artist bow, transition to after-hours lounge format, and late-night food cart | 22:00 | 23:00 | 60 | LOC-01 | P-021 | Live PA transition to downtempo lounge playlist at 80 dBA | Look 07 - Warm golden-hour lounge state; stage movers to static focus | Event recap reel loop & partner appreciation graphic credits | SFX systems fully safe and isolated; haze exhausted | Headliners escorted to private hospitality lounge; backline isolated | Scheduled | FALSE | Late-night street food carts active on El Patio; rideshare hub dispatch | Julian Clarkson | 2026-10-02 09:55 | 2026-10-02 09:55
ROS-008 | GHXSTSHIP | CSMIA26 | 5000-OPR-007 | CUE-08 | Act IV · Cool-Down & Egress | Final Egress, Load-Out & Space Restoration | Venue doors close; orderly patron egress, initial strike, and custodial turnaround | 23:00 | 23:45 | 45 | LOC-17 | P-016 | Curfew audio mute; system standby and console shutdown | Look 08 - Full work lights up; exterior security flood illumination | Displays powered down into standby mode | Systems depressurized and lockbox secured | Overhire stagehands load-in; rolling backline cases to dock A | Scheduled | FALSE | Incident CAD log closed; security sweep verified; venue dark call | Julian Clarkson | 2026-10-02 09:55 | 2026-10-02 09:55

## SOP Library
SOP ID | TITLE | OPERATIONAL DOMAIN | REVISION | ORGANIZATION | PROJECT | DEPARTMENT | CATEGORY | SUB CATEGORY | ACCOUNTABLE ROLE CODE | ACCOUNTABLE ROLE TITLE | REQUIRED PPE / COMPLIANCE TAG | PREREQUISITES & HAZARDS | PROCEDURE STEP 1 | PROCEDURE STEP 2 | PROCEDURE STEP 3 | PROCEDURE STEP 4 | REFERENCE DOC ID | REFERENCE DOCUMENT NAME | STATUS | FLAG | NOTES | CREATED BY | CREATED AT | UPDATED AT
SOP-001 | Overhead Rigging & Motor Inspection Protocol | Structural & Rigging Safety | v2.0 |  |  | 5000 Production | 5000.05.02 | Overhead Rigging | 5000.51.02 | Head Arena / Festival Rigger | TAG-002 OSHA · TAG-022 ETCP · Hard Hat, ANSI Steel-Toe Boots, High-Vis Vest, Fall Arrest Harness | Verify structural stamped load capacity (DOC-004), verify clear drop zone below trusses, and lock out ground personnel. | Pre-Rig Inspection: Inspect all 1-ton CM lodestar chain hoists, steel cables, shackles, and Spansets for wear, deformation, or certification expiration. | Bridle & Point Hanging: Attach engineered beam clamps to approved building structural nodes per stamped plot; rig motor hoist cables with safety secondary. | Truss Assembly & Dead-Hang Proof: Pin 20.5-inch box truss sections; run cable looms; perform dead-lift test bump to 3 feet; verify shackle mousing and weight distribution. | Trim Height Lockout: Hoist rig to final trim elevation (22 ft); engage secondary safety safeties/steel chokers; tag out controller box at FOH. | DOC-004 | Overhead Rigging Plot & Stamped Structural Analysis | Active | FALSE | OSHA & ETCP compliant overhead rigging inspection procedure. | Julian Clarkson | 2026-10-02 09:55 | 2026-10-02
SOP-002 | Temporary Event Power Distribution & Generator Energization | High-Voltage Electrical Safety | v1.2 |  |  | 5000 Production | 5000.06.01 | Electrical Distribution | 5000.50.02 | Master Electrician / Power Lead | TAG-002 OSHA · TAG-041 NEC · NFPA 70E Arc-Flash Face Shield, Class 0 Insulated Gloves, Safety Glasses | Permit EL-2026-04421 on file (DOC-003); 400A diesel generator grounded to 25 ohms or less; lockout/tagout in effect. | Grounding & Feeder Lay: Drive copper grounding rod; test soil resistance with earth ground meter; lay 4/0 AWG feeder runs in heavy-duty yellow jacket cable ramps. | Cam-Lock Connection Sequence: Connect Ground (Green), Neutral (White), Phase C (Blue), Phase B (Red), Phase A (Black) in strict NEC sequence. | Energization & Phase Rotation: Power generator to 60 Hz idle; verify phase voltage (120V/208V 3-phase) and rotation meter before closing main distribution breaker. | Sub-Distro Branch Load Balancing: Energize audio, lighting, and video distribution boxes sequentially; monitor balanced amp draw across all 3 legs (max 80% derate). | DOC-003 | Temporary Power & Generator Tie-In Permit & Load Calc | Active | FALSE | NEC & NFPA 70E temporary power tie-in and generator energization protocol. | Julian Clarkson | 2026-10-02 09:55 | 2026-10-02
SOP-003 | Concert Line Array Tuning & Perimeter SPL Curfew Enforcement | Acoustic Systems & Municipal Compliance | v2.0 |  |  | 5000 Production | 5000.01.02 | Audio Engineering | 9000.50.02 | Audio Engineer - A1/FOH | TAG-002 OSHA · Hearing Protection (Custom Molded / High-Fidelity Earplugs) | EASE plot alignment confirmed (DOC-005); SMAART acoustic measurement rig calibrated; stage clear of non-audio crew. | Pink Noise Line Check & Phase Verification: Sweep pink noise through individual speaker elements (tops, downfills, subs); confirm polarity and phase coherence in SMAART. | Cardioid Sub Optimization: Align delay and phase cancellation on rear-facing sub elements to create 18dB rear rejection toward Biscayne property boundary. | System EQ & Target Curve Voicing: Apply room curve filtering for vocal clarity and dynamic range; tune FOH mix position to target 98 dBA Leq (15 min). | Perimeter Curfew Logging: Deploy remote Type 2 sound level meter at property edge; continuously record calibrated SPL to verify <78 dBA compliance through midnight. | DOC-005 | Acoustic Sound Modeling & SPL Compliance Plan | Active | FALSE | Acoustic line array tuning and Biscayne perimeter SPL curfew compliance. | Julian Clarkson | 2026-10-02 09:55 | 2026-10-02
SOP-004 | Severe Weather Monitoring & Temporary Structure Evacuation | Life Safety & Weather Trigger Management | v1.5 |  |  | 6000 Operations | 6000.05.01 | Severe Weather & Egress | 6000.50.02 | Site Safety & Security Lead | TAG-002 OSHA · TAG-019 NFPA · Weatherproof Tactical Hi-Vis Outerwear, Flashlight, Two-Way Radio (Channel 1) | On-site calibrated anemometer active; live radar weather monitoring feed connected; Emergency Action Plan active (DOC-008). | Advisory State (25 MPH Gusts / Lightning <15 Miles): Notify Executive Producer and Department Heads via Radio Ch 1; inspect tent ballasts and loose signage. | Restricted State (35 MPH Gusts / Lightning <8 Miles): Pause high-altitude staging/aerial lifts; lower flying LED walls to safety deck; pause patio dining service. | Evacuation Trigger (45 MPH Gusts / Lightning <5 Miles): Trigger mass notification; illuminate emergency work lights; activate orderly egress toward indoor sanctuary (LOC-01). | Post-Storm All-Clear & Inspection: Conduct structural engineering inspection of outdoor canopies, rigging points, and electrical lines before re-admitting guests. | DOC-008 | Comprehensive Emergency Action & Severe Weather Plan | Active | FALSE | Severe weather action levels and temporary structure evacuation protocol. | Julian Clarkson | 2026-10-02 09:55 | 2026-10-02
SOP-005 | Assembly Occupancy Ingress & Egress Door Control | Crowd Management & Fire Code Compliance | v1.0 |  |  | 6000 Operations | 6000.50.01 | House Management | 6000.50.01 | House Manager | TAG-002 OSHA · TAG-006 ADA · Certified Crowd Manager Badge, Hi-Vis Identification Lanyard | Assembly permit BD-2026-08914 approved (DOC-002); master egress widths verified (DOC-001); minimum 8 crowd managers on post. | Pre-Ingress Life Safety Walk: Walk all exit corridors, panic hardware, emergency illuminated exit signs, and fire extinguisher stations; verify zero pathway obstructions. | Queue Line Stanchion Configuration: Establish ADA-compliant arrival switchbacks (36-inch clear path); position RFID scanners; open check-in gates at T-00:30 (18:00). | Capacity Flow Tracking: Monitor real-time headcount dashboard; maintain headcount under 350 occupant maximum; enforce 1-in-1-out policy if capacity reached. | Egress Call & Doors Clearance: At event conclusion (23:00), prop all double exit doors fully open; guide patron flow toward rideshare dispatch hub on 76th St. | DOC-002 | City of Miami Special Assembly Occupancy Permit | Active | FALSE | Assembly occupancy door control and crowd manager egress coordination. | Julian Clarkson | 2026-10-02 09:55 | 2026-10-02
SOP-006 | Live Performance Show Calling & Cue Execution Sequence | Stage Management & Live Production Control | v3.1 |  |  | 9000 Technology | 9000.50.01 | Show Calling | 9000.50.01 | Production Stage Manager | TAG-002 OSHA · Clear-Com Headset, Production Flashlight with Red Filter | Run of Show cue list locked; SMPTE timecode sync verified with playback and lighting consoles; talent green room escorts standby. | Comms Line Check (T-00:15): Establish multi-channel comms check with Audio (Ch A), Lighting (Ch B), Video (Ch C), and Stage Deck (Ch D); verify cue lights green. | Standby Call Cadence: Issue standard verbal standbys precisely 30 seconds prior to cue trigger: \"Standby Audio Cue 05, Standby Lighting Look 05, Standby Video Blade 05\". | Cue Execution Call: Call crisp execution trigger on downbeat or timecode mark: \"Audio, Lights, Video... GO.\" Confirm acknowledge from all discipline operators. | Hold & Abort Protocol: In the event of deck hazard, performer distress, or safety breach, immediately call \"HOLD, HOLD, HOLD\" on all channels and take stage to safe wash. | DOC-007 | Artist Sizzle Reel & Main LED Key Visual Master 4K | Active | FALSE | Live performance cue execution sequence and emergency hold protocol. | Julian Clarkson | 2026-10-02 09:55 | 2026-10-02
SOP-007 | Real-Time Media Ingest, Checksum Verification & Social Reel Delivery | Digital Asset Management & PR Workflow | v1.0 |  |  | 3000 Marketing | 3000.50.02 | Media Production | 3000.50.02 | Lead Cinematographer / Video Shooter | TAG-026 PCI · Anti-Static Handling Wrist Strap, Media Hard Drive Vault Bags | 10GbE NAS network connected; cleared artist music sync rights on file; Casa Spotify Brand Toolkit active (DOC-006). | CFexpress / SD Card Offload: Ingest raw 4K camera cards via ShotPut Pro; compute MD5/xxHash checksum verification to primary NVMe RAID storage. | Secondary Cloud Backup: Trigger automated parallel upload to Google Drive archive directory and off-site cloud bucket with version tagging. | Editorial & Color Grading: Conform footage in Premiere Pro / DaVinci Resolve using Casa Spotify Wynwood LUT; apply official Spotify logo bugs and artist titles. | PR & Social Master Handoff: Export 9x16 vertical reels (H.264/ProRes) within 90 minutes of set completion; push assets to PR distribution team with cleared usage metadata. | DOC-006 | Casa Spotify Wynwood Brand Toolkit & Style Guide | Active | FALSE | Real-time media card offload, checksum verification, and PR reel delivery. | Julian Clarkson | 2026-10-02 09:55 | 2026-10-02
SOP-008 | Post-Show Strike Sequence & Venue Space Restoration | Load-Out Logistics & Space Handover | v2.0 |  |  | 5000 Production | 5000.51.01 | Stage & Rig Strike | 5000.51.01 | Lead Stagehand / Deck Crew Chief | TAG-002 OSHA · Steel-Toe Boots, Heavy Leather Rigging Gloves, High-Vis Vest, Hard Hat | Audience 100% egressed; venue power isolated; truck staging bay active in Marshalling Yard; Work Order WO-002 active. | Backline & Microphones Strike: Disconnect instrument mics, pack artist backline into ATA flight cases; secure high-value wireless gear into locked Pelican cases. | LED Wall & Lighting Truss Drop: Lower overhead trusses to 4 ft service height; de-cable pixel tape and DMX looms; pack LED video tiles into custom road cases. | Motor De-Rig & Cable Pull: Slack chain hoists; derig beam clamps; coil 4/0 feeder cables into rolltainers; strike temporary distro boxes to staging dock. | Sanitation Sweep & Venue Handover: Conduct sweeping and debris removal across sanctuary floor and El Patio; conduct joint walk with venue manager for damage sign-off. | DOC-001 | Master Architectural Site Plan & Life Safety CAD | Active | FALSE | Post-show stage strike, equipment packing, and venue space restoration. | Julian Clarkson | 2026-10-02 09:55 | 2026-10-02
SOP-009 | Temporary Demountable Structures (TDS) Ballast & Wind Bracing Protocol | Temporary Structures & Wind Engineering | v1.4 |  |  | 4000 Environment | 4000.08.02 | Tents & Temporary Structures | 4000.50.01 | Structural Carpenter / Build Lead | TAG-002 OSHA · TAG-008 TENT_PERMIT · TAG-036 STRUCT_ENG · Hard Hat, Steel-Toe Boots, High-Vis Vest | Stamped engineering ballast calculation on file (DOC-009); calibrated water meter/crane scale for weight verification; anemometer active. | Pre-Erection Footing Inspection: Verify subgrade compaction, asphalt integrity, and laser-level baseplate pads; position pre-cast concrete ballast blocks per structural plot. | Frame Truss Pinning & Squaring: Assemble structural aluminum box arches on ground; verify diagonal squareness within 0.25 in; insert all structural pins and safety R-clips. | Ballast Rigging & Guying: Connect high-tensile ratchet straps and 3/8-in wire rope guying to concrete weights; tension each guy wire to engineered load specification. | Membrane Tensioning & Flame Cert Log: Pull fire-retardant vinyl canopies through keder rails; ratchet tension to prevent wind pocketing; post NFPA 701 flame cert tag at mast. | DOC-009 | Temporary Demountable Structures (TDS) Wind Stability & Ballast Analysis | Active | FALSE | ANSI ES1.7 & Florida Building Code temporary structure ballast and guy wire protocol. | Julian Clarkson | 2026-10-02 09:55 | 2026-10-02
SOP-010 | Stage Pyrotechnics, Flame Effects & Cold Spark Safety Sequence | Pyrotechnics & Atmospheric Effects Safety | v1.0 |  |  | 5000 Production | 5000.07.01 | Atmospheric Effects | 5000.52.01 | Special Effects / Pyro Lead | TAG-002 OSHA · TAG-019 NFPA · TAG-038 PYRO_LICENSE · Nomex Flame-Resistant Jacket, Safety Glasses, 2A-10BC Extinguisher | City of Miami Fire-Rescue permit active (DOC-010); designated 15-foot separation safety zone established; Miami Fire watch on duty. | Hardware & Fuel Integrity Inspection: Inspect LP-gas hoses, solenoid valves, and titanium cold-spark granules; verify pressure regulators and emergency deadman switches. | Perimeter Barrier & Line-of-Sight Lock: Establish physical stanchions 15 ft from discharge nozzles; verify clear overhead clearance to trussing (>25 ft) and drapery. | Arming Sequence & Pyro Controller Link: Connect digital firing controller via isolated dry-contact DMX line; verify continuity; arm system only on stage manager verbal standby. | Post-Fire Safe Depressurization & Canister Lock: Disarm firing console immediately post-cue; vent residual gas lines; vacuum titanium dust; lock canisters in pyro vault. | DOC-010 | Miami Fire-Rescue Special Effects & Flame Effects Permit | Active | FALSE | NFPA 160 & NFPA 1126 stage flame effects and cold spark firing procedure. | Julian Clarkson | 2026-10-02 09:55 | 2026-10-02
SOP-011 | Class 3B/4 Audience-Scanned Laser Alignment & Termination Safety | Optical Radiation & Laser Safety | v1.0 |  |  | 5000 Production | 5000.07.01 | Atmospheric Effects | 9000.50.03 | Lighting Designer / LD | TAG-002 OSHA · TAG-018 ANSI · Laser Safety Eyewear (OD 7+ @ 520nm/450nm/638nm) | FDA CDRH variance valid (DOC-011); certified Laser Safety Officer (LSO) on site; hard mechanical beam stops anchored. | Physical Rigging & E-Stop Verification: Mount RGB projector to rigid truss with secondary safety cable; wire hardwired emergency mushroom e-stop at FOH control position. | Scan-Fail Circuit & Masking Calibration: Calibrate hardware scan-fail interlock boards; configure geometric software masking zones to prevent exposure below 10 ft from floor. | Low-Power Beam Alignment & Termination Proof: Power up laser in 1% alignment mode; verify all bounce mirrors and strike non-reflective fire-rated beam dumps. | Full-Power Exposure Metering & LSO Sign-Off: Measure Maximum Permissible Exposure (MPE) at closest patron boundary using calibrated laser power meter; record LSO log. | DOC-011 | FDA CDRH Class 3B/4 Audience-Scanned Laser Variance | Active | FALSE | ANSI Z136.1 & FDA CDRH 21 CFR 1040.10 outdoor entertainment laser safety protocol. | Julian Clarkson | 2026-10-02 09:55 | 2026-10-02
SOP-012 | Environmental Noise Monitoring & Wynwood Perimeter SPL Curfew Enforcement | Acoustic Systems & Municipal Compliance | v2.0 |  |  | 5000 Production | 5000.01.02 | Audio Engineering | 9000.50.02 | Audio Engineer - A1/FOH | TAG-002 OSHA · Type 1/2 Calibrated Sound Level Meter, High-Vis Vest, Two-Way Radio | Municipal sound variance on file (DOC-012); acoustical calibrator (94 dB / 114 dB) checked; remote logging telemetry online. | Field Calibrator Verification: Mount microphone on remote perimeter meter; apply 94.0 dB acoustical calibrator; log reference drift within +/-0.3 dB before event start. | FOH Leq Ceiling Enforcement: Set software limiter threshold at FOH console to cap continuous mix volume at 98 dBA Leq (15-min rolling window). | Boundary Telemetry Real-Time Tracking: Continuously monitor property boundary meters along Biscayne Blvd; alert FOH A1 if 5-min Leq approaches 76 dBA. | Midnight Curfew Step-Down Execution: At 23:59 EDT, execute programmed console master mute on all outdoor PA elements; file continuous SPL audit log to city compliance portal. | DOC-012 | City of Miami Code Compliance Noise Variance & Perimeter Curfew Permit | Active | FALSE | City of Miami Chapter 36 Noise Ordinance and perimeter SPL monitoring procedure. | Julian Clarkson | 2026-10-02 09:55 | 2026-10-02
SOP-013 | Temporary Commercial Kitchen Sanitation & Food Safety Inspection | Culinary Health & Sanitary Compliance | v1.0 |  |  | 8000 Hospitality | 8000.01.01 | Catering & Culinary | 8000.51.01 | Executive Catering Captain | TAG-002 OSHA · TAG-010 HEALTH_DEPT · TAG-011 SERVSAFE · Non-Slip Shoes, Food-Grade Nitrile Gloves, Beard Net / Hair Net | Florida DBPR food service license posted (DOC-013); potable hot water station operational (min 100 deg F); digital stem thermometers calibrated in ice bath. | Cold-Chain Receiving & Temperature Verification: Probe all incoming TCS foods (poultry, beef, seafood, dairy); verify internal temp <41 deg F; reject out-of-spec shipments. | Handwashing & 3-Compartment Sink Setup: Establish dedicated handwash station with warm water, soap, single-use paper towels; set wash/rinse/sanitize (200 ppm Quat) sink bays. | Holding Temperature & Cross-Contamination Control: Monitor hot holding units (>135 deg F) and refrigerated prep tables (<41 deg F) every 2 hours; enforce allergen color-coding. | Shift Waste Disposal & Sanitizing Break-Down: Discard holding foods at 4-hour mark; sanitize stainless steel prep surfaces with quaternary solution; seal trash cans. | DOC-013 | Florida DBPR Division of Hotels & Restaurants Temporary Food Service License | Active | FALSE | Florida Administrative Code 61C-4 & FDA Food Code temporary food establishment protocol. | Julian Clarkson | 2026-10-02 09:55 | 2026-10-02
SOP-014 | Alcoholic Beverage Dispensing, Age Verification & Intoxication Interception | Alcohol Governance & Hospitality Compliance | v1.1 |  |  | 8000 Hospitality | 8000.02.01 | Bar & Beverage | 8000.50.01 | Head Beverage Director / Bar Manager | TAG-012 TIPS · TAG-013 LIQUOR_LICENSE · Certified TIPS/ServSafe Alcohol Badge, Bar Apron | Florida DBPR ABT permit posted (DOC-014); electronic ID barcode scanners active at all bar stations; security liaison assigned to bar perimeter. | 100% ID Scanning & Wristband Verification: Inspect physical photo ID for all patrons requesting alcohol; verify age 21+ via optical scanner; confirm intact 21+ wristband. | Standard Pour Volume & Recipe Control: Utilize measured jiggers for all spirit pours (1.5 oz spirit maximum per drink); enforce strict 2-drink maximum per transaction. | Behavioral Intoxication Assessment: Monitor guests for slurred speech, motor instability, or combative behavior; refuse service tactfully using non-confrontational phrasing. | Cut-Off Protocol & Security Dispatch: In event of refused service, immediately notify Bar Manager and dispatch roving Security Officer to offer hydration and rideshare escort. | DOC-014 | Florida DBPR Division of ABT Special Event Alcoholic Beverage Permit (ODP) | Active | FALSE | Florida Statute 561 & 562 beverage law compliance and responsible vendor procedure. | Julian Clarkson | 2026-10-02 09:55 | 2026-10-02
SOP-015 | Mass-Gathering Emergency Medical Dispatch, Triage & Heat Illness Protocol | Emergency Medical Services & Life Safety | v2.1 |  |  | 6000 Operations | 6000.05.02 | Medical & EMS | 7000.51.01 | Lead Event Paramedic / EMT | TAG-002 OSHA · TAG-028 HIPAA · Nitrile Exam Gloves, N95 Mask, High-Vis Medical Vest, Two-Way Radio (Channel 2) | Miami-Dade Fire Rescue medical plan active (DOC-015); on-site air-conditioned medical tent established; dedicated ALS ambulance parked in dock bay. | Triage Bay Readiness & Equipment Check: Perform daily operational bump check on Zoll AED, oxygen cylinders, suction units, and trauma jump kits; confirm cold IV saline stores. | Roving Medic Rapid-Response Cadence: Deploy pairs of EMTs across Main Stage and El Patio; maintain 3-minute maximum response radius to any distress call on Radio Ch 2. | Heat Illness & Substance Harm Reduction: Triage symptomatic patrons; initiate rapid evaporative cooling, electrolyte fluid replacement, and vital signs monitoring every 10 min. | 911 Escalation & Secure Transport Handoff: For red-tier critical patients, coordinate seamless patient transfer to Miami-Dade Fire Rescue ALS transport unit via Gate 3 access lane. | DOC-015 | Event Mass-Gathering Medical Action Plan & Miami-Dade EMS Detail | Active | FALSE | Florida EMS Chapter 401 & NFPA 3000 mass gathering emergency medical protocol. | Julian Clarkson | 2026-10-02 09:55 | 2026-10-02
SOP-016 | Physical Security Perimeter Access, Metal Detection & Bag Inspection | Security Operations & Threat Mitigation | v2.0 |  |  | 6000 Operations | 6000.04.01 | Security & Access Control | 6000.52.01 | Security Supervisor | TAG-002 OSHA · TAG-021 BG_CHECK · Uniformed Security Officer Attire, Flashlight, Two-Way Radio (Channel 1) | City of Miami approved security overlay on file (DOC-016); walk-through magnetometers calibrated; prohibited items amnesty bins staged outside entry switchbacks. | Entry Lane Divestment Screening: Instruct arriving patrons to divest metallic items into inspection trays; visually inspect clear bags (12x6x12 in max) with wooden inspection dowel. | Walk-Through Magnetometer Processing: Guide patrons through magnetometer at standard cadence; conduct secondary screening with handheld wand if zone alert triggers. | Prohibited Item Confiscation & Chain of Custody: Safely confiscate contraband, weapons, or unauthorized recording rigs; deposit into locked evidence locker; log owner info. | Threat Interception & Law Enforcement Handover: If illegal firearms or hostile behavior detected, immediately detain subject, initiate ICS emergency call, and hand over to on-site MPD. | DOC-016 | Event Physical Security, Crowd Management & Evacuation Routing Plan | Active | FALSE | DHS Active Shooter & Florida Class D security guard screening standards. | Julian Clarkson | 2026-10-02 09:55 | 2026-10-02
SOP-017 | Public Right-of-Way Traffic Control & Marshalling Yard Truck Staging | Traffic Engineering & Logistics Coordination | v1.3 |  |  | 6000 Operations | 6000.02.07 | Trucks & Transport | 6000.51.02 | Marshalling Yard & Dock Master | TAG-002 OSHA · TAG-016 DOT · ANSI Class 3 High-Vis Vest, Steel-Toe Boots, Hard Hat, Traffic Wand, Radio (Channel 3) | City of Miami / FDOT MOT permit active (DOC-017); certified traffic flaggers positioned; Type II traffic cones and electronic arrow board deployed along 76th St. | Street Closure Signage & Arrow Board Activation: Deploy advance warning signs ('ROAD WORK AHEAD', 'LANE CLOSED') per FDOT index; power electronic directional arrow board. | Carrier Dispatch & Marshalling Check-In: Intercept arriving 53-ft tractor-trailers at holding yard; verify carrier Bill of Lading (BOL), driver phone, and assigned dock appointment. | Dock Call & Reversing Spotter Escort: Guide truck from holding bay into loading dock; assign 2 ground spotters with safety whistles to clear pedestrian sidewalk traffic. | Wheels Chocking & Loading Ramp Deployment: Place heavy-duty rubber wheel chocks under rear trailer tandem; engage dock leveler lip before authorizing forklift load-in. | DOC-017 | Public Right-of-Way Closure & Maintenance of Traffic (MOT) Plan | Active | FALSE | FDOT Standard Plans Index 102 & MUTCD Part 6 traffic control and freight staging procedure. | Julian Clarkson | 2026-10-02 09:55 | 2026-10-02
SOP-018 | Commercial Drone Aerial Video Capture & Airspace Safety Protocol | Aviation Safety & UAS Operations | v1.0 |  |  | 5000 Production | 5000.08.01 | Cameras & Capture | 3000.50.02 | Lead Cinematographer / Video Shooter | TAG-003 FAA · TAG-023 FAA_PART107 · High-Vis Flight Crew Vest, Safety Glasses, Two-Way Radio | FAA Part 107 waiver on file (DOC-018); LAANC airspace authorization verified; dedicated Visual Observer (VO) positioned on sanctuary roof deck. | Pre-Flight Airspace & Telemetry Inspection: Conduct pre-flight drone inspection (rotors, gimbal, obstacle sensors); confirm GPS lock (>16 satellites); set Return-to-Home altitude to 150 ft. | Visual Observer Comms & Geo-Fence Setup: Establish continuous voice comms between Pilot in Command (PIC) and VO; lock geofence boundaries to prevent flight over unshielded crowds. | In-Flight Mission Execution & Battery Thresholds: Execute programmed sweeping cinematic passes; initiate mandatory return and landing sequence when battery telemetry reaches 25%. | Post-Flight Media Offload & Flight Logging: Power down aircraft; offload flight logs and micro-SD footage cards; log total flight hours and airspace compliance into ops portal. | DOC-018 | FAA Part 107 Airspace Authorization & UAS Night Flight Waiver | Active | FALSE | FAA Part 107 federal regulations and commercial UAS safe flight operation protocol. | Julian Clarkson | 2026-10-02 09:55 | 2026-10-02
SOP-019 | ADA Accessibility, Companion Seating & Barrier-Free Path Management | Universal Accessibility & Guest Services | v2.0 |  |  | 7000 Experience | 7000.01.01 | Guest Experience & Journey | 7000.50.01 | Front of House Lead / Box Office Manager | TAG-006 ADA · Front-of-House Credential Badge, Digital Ingress Scanner | Master ADA survey on file (DOC-019); wheelchair viewing platforms inspected; clear accessible path (min 36 inches) marked throughout all activation zones. | Pre-Event Route & Ramp Verification: Walk all accessible routes from public sidewalk to stage viewing areas; verify ramp slopes do not exceed 1:12; verify zero lip thresholds >0.25 in. | Elevated Viewing Platform Setup: Configure ADA viewing riser with code-compliant handrails, edge protection kick plates, and paired companion chairs with unobstructed sightlines. | Assisted Listening & Sensory Kit Distribution: Inspect RF assisted listening receivers and neck loops; stage sensory kits (noise-canceling headphones, sunglasses) at FOH guest desk. | Accessible Egress Escort & Dedicated Exit Clearance: During show egress, position dedicated guest ambassadors along primary ramp routes to ensure unimpeded wheelchair flow to rideshare hub. | DOC-019 | ADA Accessibility, Companion Seating & Accessible Route Survey | Active | FALSE | 2010 ADA Standards for Accessible Design & Florida Accessibility Code protocol. | Julian Clarkson | 2026-10-02 09:55 | 2026-10-02
SOP-020 | Radio Frequency (RF) Spectrum Coordination & Wireless Intercom Intermodulation | Communications Infrastructure & Spectrum Control | v1.5 |  |  | 9000 Technology | 9000.03.01 | Two-Way Radios | 9000.52.01 | Lead Network & Comms Engineer | TAG-033 FCC · TAG-034 FCC_PART74 · RF Analyzer Wand, High-Fidelity Test Headphones | FCC Part 74 license active (DOC-020); RF spectrum analyzer calibrated; Shure Wireless Workbench environment loaded with Miami broadcast exclusions. | Wideband Spectrum Sweep (470-608 MHz): Perform RF spectrum sweep across Wynwood venue airspace; identify active DTV broadcast channels and unauthorized rogue transmitters. | Intermodulation Calculation & Frequency Deployment: Compute intermodulation distortion profiles; coordinate compatible frequencies for 16x wireless mics and 8x IEM transmitters. | Axient Digital ShowLink & FreeSpeak Pairing: Deploy networked antenna distro (distro4); pair digital transmitters via IR sync; verify ShowLink automated interference avoidance. | Walk-Test RF Coverage & Shadow Mapping: Walk venue boundaries with test transmitter; verify zero dropouts across sanctuary, stage, and BOH green rooms; log RF stability report. | DOC-020 | FCC Part 74 Wireless Microphone & Comms Frequency Coordination | Active | FALSE | FCC Part 74 Subpart H & AES recommended wireless audio frequency coordination protocol. | Julian Clarkson | 2026-10-02 09:55 | 2026-10-02
SOP-021 | Generator Diesel Fueling, Spill Containment & Secondary HazMat Handling | Hazardous Materials & Fuel Safety | v1.0 |  |  | 6000 Operations | 6000.09.01 | Waste Management | 5000.50.02 | Master Electrician / Power Lead | TAG-002 OSHA · TAG-040 EPA · Chemical Nitrile Gloves, Safety Splash Goggles, Fuel-Resistant Apron | Environmental containment plan active (DOC-021); 55-gallon universal spill kit staged within 15 ft of fuel port; fire extinguisher (20BC) charged on post. | Pre-Fueling Ground Berm & Pad Inspection: Inspect secondary containment berm under 400A diesel generator; verify rubber liner intact with zero tears, water, or oil residue. | Bonding & Static Ground Wire Attachment: Attach heavy-duty copper static bonding cable from fuel supply truck chassis to generator ground lug prior to opening fuel cap. | Monitored Delivery & Cam-Lock Tightness: Execute controlled fuel pumping at low velocity (<25 GPM); monitor mechanical sight gauge; stop transfer at 90% tank capacity. | Nozzle Capping & Containment Log Clearance: Wipe fuel nozzle; disconnect bonding clamp; inspect spill berm for drips; record delivered gallons and date into HazMat binder. | DOC-021 | Hazardous Materials & Diesel Fuel Storage Environmental Plan | Active | FALSE | EPA SPCC Rule 40 CFR 112 & Miami-Dade DERM temporary fuel transfer protocol. | Julian Clarkson | 2026-10-02 09:55 | 2026-10-02
SOP-022 | Commercial Insurance Endorsement Verification & Subcontractor COI Audit | Risk Governance & Insurance Compliance | v1.0 |  |  | 0000 Executive | 0000.06.01 | Insurance | 0000.51.01 | Production Finance Director | None Required (Administrative Governance) | Master insurance binder bound (DOC-022); contract vendor roster active; digital COI tracking ledger online. | ACORD 25 Certificate Intake: Ingest all incoming vendor Certificates of Insurance; verify policy effective dates encompass entire load-in, event, and load-out window. | Coverage Limit & Endorsement Audit: Confirm minimum $1M Occurrence / $2M Aggregate GL limits; verify $5M Umbrella, Statutory Workers' Comp, and $1M Commercial Auto. | Additional Insured Endorsement Scrutiny: Verify mandatory endorsement CG 20 26 or equivalent naming GHXSTSHIP, Spotify, and Venue Owner as Additional Insureds with Waiver of Subrogation. | Gate 2 Clearance & Vendor Access Lockout: Mark vendor insurance status 'Approved' in Procurement Catalog; issue digital pass to dock master; lock out unapproved subcontractors. | DOC-022 | Commercial General Liability & $10M Excess Umbrella Insurance Binder | Active | FALSE | Commercial insurance risk underwriting standards & ACORD document verification protocol. | Julian Clarkson | 2026-10-02 09:55 | 2026-10-02
SOP-023 | Aerial Work Platform (AWP) Operation, MEWP Inspection & Fall Arrest Protocols | Fall Protection & High-Altitude Safety | v2.1 |  |  | 5000 Production | 5000.05.02 | Rigging Hardware | 5000.51.02 | Head Arena / Festival Rigger | TAG-002 OSHA · ANSI A92.20 Full-Body Fall Arrest Harness, Shock-Absorbing Lanyard, Hard Hat with Chinstrap | Fall protection plan active (DOC-023); certified MEWP operators rostered; ground drop-zone barricades staged. | Pre-Operation MEWP Walkaround: Perform daily pre-start inspection on scissor lift and articulating boom lift; test ground/basket emergency stop controls and hydraulic lines. | Fall Restraint Lanyard Anchorage: Prior to raising platform, attach harness lanyard to designated engineered anchor point inside basket; confirm 100% tie-off compliance. | Ground Perimeter Drop-Zone Lockout: Establish physical stanchions and red warning tape directly below elevated work basket; position ground spotter with whistle. | Elevated Maneuver & Overhead Clearance: Operate platform smoothly at crawl speed; maintain minimum 10-ft clearance from overhead building utilities, beams, and HVAC ducts. | DOC-023 | OSHA Fall Protection & Aerial Work Platform (AWP) Safety Protocol | Active | FALSE | OSHA 1926.453 & ANSI/SAIA A92.22 safe use of mobile elevating work platforms (MEWPs). | Julian Clarkson | 2026-10-02 09:55 | 2026-10-02
SOP-024 | Structural Rigging Hardware Proof-Testing & Beam Clamp Installation | Structural & Rigging Safety | v1.0 |  |  | 5000 Production | 5000.05.02 | Rigging Hardware | 5000.51.03 | Lead System Rigger | TAG-002 OSHA · TAG-022 ETCP · Hard Hat, Steel-Toe Boots, Heavy Leather Rigging Gloves, Fall Harness | Structural proof pull-test cert on file (DOC-024); stamped rigging plot DOC-004 approved; torque wrench calibrated. | Visual Hardware Grade Inspection: Inspect all 5/8-in Crosby shackles, G-100 master links, wire rope slings, and polyester Spansets; verify zero elongation, cuts, or heat damage. | Engineered Beam Clamp Placement: Mount forged steel beam clamps to approved structural I-beams per stamped plot; torque clamp locking nuts to manufacturer specified foot-pounds. | Secondary Safety Choker Rigging: Rig independent wire rope safety secondary choker around building structural beam node; mouse all shackle pins with stainless safety wire. | Test Pull & Load Cell Zeroing: Hang calibrated digital wireless load cell from hook; perform test pull; zero load cell before pinning truss bridles; log static tare weights. | DOC-024 | ANSI ES1.9 Rigging Point Inspection & Proof Test Certification | Active | FALSE | ANSI ES1.6 & OSHA 1910.184 entertainment rigging hardware inspection and proof-testing. | Julian Clarkson | 2026-10-02 09:55 | 2026-10-02
SOP-025 | Live Show Stage Management, SMPTE Timecode Sync & Performer Handover | Stage Management & Live Production Control | v4.0 |  |  | 9000 Technology | 9000.50.01 | Show Control & Playback | 9000.50.01 | Production Stage Manager | Clear-Com Headset, Production Flashlight with Red Filter, Run of Show Binder | Master cue schedule active (DOC-025); SMPTE timecode sync generator locked (29.97 fps); artist green room escort in place. | Master Timecode Clock Lock: Verify SMPTE linear timecode lock across playback DAWs, grandMA3 lighting desks, and disguise d3 media servers; confirm zero frame drift. | Talent Escort & Mic Sanitization (T-00:20): Escort headline artist from dressing room to stage left; fit sanitized wireless handheld mic and test custom IEM mix with A2. | Standby Call Sequence (T-00:02): Issue verbal countdown on Comms Ch A & B: 'Standby Top of Show, Standby Lighting Look 01, Standby Video Blade 01, Standby Audio Playback'. | Show Trigger GO & Live Changeover: Call crisp 'GO' trigger precisely at 20:00:00; monitor live performance telemetry; oversee seamless 8-minute DJ to live band changeover. | DOC-025 | Master Run of Show & SMPTE Timecode Production Cue Sheet | Active | FALSE | Production stage management and SMPTE timecode synchronization live execution protocol. | Julian Clarkson | 2026-10-02 09:55 | 2026-10-02
SOP-026 | Solid Waste Diversion, Compost Sorting & Post-Event Site Sanitation | Environmental Sustainability & Waste Operations | v1.0 |  |  | 6000 Operations | 6000.09.01 | Waste Management | 6000.51.01 | Janitorial & Waste Operations Lead | TAG-002 OSHA · Heavy-Duty Nitrile Cleaning Gloves, Steel-Toe Boots, High-Vis Vest, Safety Glasses | Waste diversion plan active (DOC-026); dual-stream recycling/trash pairs staged; compost dumpster spotted in yard. | Pre-Event Waste Station Deployment: Position co-located 3-stream waste stations (Compost, Clean Recycling, Landfill) every 25 ft across sanctuary and patio with visual signage. | Live Shift Monitoring & Bin Turnaround: Rove public areas; empty bins before reaching 75% capacity; replace with color-coded biodegradable liners; haul bags to rear compactor. | Post-Event Floor Magnetic & Mechanical Sweep: Following patron egress, execute rolling magnet sweep across lawn/patio for metal fasteners; complete wet mop of polished concrete floors. | Waste Stream Weighing & Diversion Reporting: Record weights of compost, single-stream recyclables, and landfill haul; compute event diversion percentage for sustainability report. | DOC-026 | Solid Waste Diversion, Composting & Site Sanitation Log | Active | FALSE | Zero-waste event certification & LEED temporary event waste diversion protocol. | Julian Clarkson | 2026-10-02 09:55 | 2026-10-02
SOP-027 | Temporary Potable Water Plumbing, Backflow Prevention & Disinfection | Water Distribution & Plumbing Hygiene | v1.0 |  |  | 6000 Operations | 6000.06.04 | Water & Plumbing | 4000.51.01 | HVAC & Site Climate Tech | TAG-002 OSHA · NSF Food-Grade Rubber Gloves, Safety Glasses, Pipe Wrenches | Backflow inspection cert active (DOC-027); certified reduced pressure backflow preventer (RPBP) mounted; potable NSF-61 hoses sanitized. | Source Tie-In & Backflow Assembly Installation: Connect primary water supply to municipal spigot; install tested RPBP backflow preventer; verify zero cross-contamination. | Distribution Line Chlorination & Flush: Flush temporary potable distribution lines with 50 ppm chlorine solution for 24 hours; flush with fresh water until residual chlorine <0.5 ppm. | Potable Water Distribution & Pressure Regulation: Connect NSF-61 certified food-grade hoses to catering prep trailers, beverage carts, and handwash sinks; regulate pressure to 45 PSI. | Daily Water Quality Sampling & Drain Inspection: Conduct daily chlorine and bacterial dip test; inspect gray water collection tanks; schedule pump-out truck before tanks reach 80%. | DOC-027 | Temporary Potable Water System Disinfection & Backflow Certification | Active | FALSE | IPC Section 608 & Miami-Dade WASD temporary potable water distribution protocol. | Julian Clarkson | 2026-10-02 09:55 | 2026-10-02
SOP-028 | RFID / NFC Credential Issuance, Zone Access Encoding & Anti-Passback Validation | Credentialing Systems & Access Security | v2.0 |  |  | 7000 Experience | 7000.50.02 | Credentials | 7000.50.02 | Credential Operations Coordinator | None Required (Administrative / Tech) | Credential security matrix approved (DOC-028); encrypted RFID wristbands in vault; Zebra RFID badge printers online. | Master Credential Database Sync: Ingest approved personnel roster and VIP guest list into access management server; assign unique encrypted UID per record. | RFID Wristband Encoding & Physical Verification: Encode 13.56 MHz NFC wristband chips with tier permissions (All-Access, VIP, Production, GA); visually inspect tamper-evident clasp. | Turnstile Validation & Anti-Passback Enforcement: Configure optical turnstiles and handheld scanners with 15-minute anti-passback rule; verify sub-second scan validation latency. | Real-Time Attendance Headcount Monitoring: Track live scan feeds to maintain real-time occupant counts per zone; alert security if sanctuary approaches 350 occupant cap. | DOC-028 | RFID Credentialing Architecture & Zone Security Matrix | Active | FALSE | ISO/IEC 14443 & PCI compliance event access credentialing protocol. | Julian Clarkson | 2026-10-02 09:55 | 2026-10-02
SOP-029 | Marshalling Yard Loading Dock Traffic Management, Forklift & Rig Staging | Logistics Operations & Loading Dock Safety | v2.2 |  |  | 6000 Operations | 6000.02.01 | Forklifts & Loaders | 6000.51.02 | Marshalling Yard & Dock Master | TAG-002 OSHA · TAG-018 ANSI · Steel-Toe Boots, High-Vis Vest, Hard Hat, Work Gloves, Radio (Channel 3) | Dock booking schedule locked (DOC-029); certified forklift operators on call; yellow jacket cable ramps installed across traffic lane. | Carrier Arrival Check-In & Yard Spotting: Check in carrier trucks at marshalling gate; verify seal numbers against manifest; assign designated trailer staging bay. | Loading Dock Safety Sequence: Position trailer at Dock 1; engage tractor spring brakes; set dual rubber wheel chocks; lower trailer support stabilizing jacks. | Forklift Unloading & Floor Load Distribution: Unload heavy rigging road cases using 5,000-lb forklift; distribute weight evenly across dock floor; maintain clear 8-ft aisleways. | Dock Clearance & Carrier Release Sign-Off: Clear empty pallets and dunnage; inspect trailer floor for damage; sign carrier Bill of Lading with time stamp; dispatch carrier. | DOC-029 | Marshalling Yard Freight Schedule & Dock Booking Master | Active | FALSE | OSHA 1910.178 powered industrial trucks and loading dock freight safety procedures. | Julian Clarkson | 2026-10-02 09:55 | 2026-10-02
SOP-030 | Temporary HVAC Spot Cooler Deployment, Ducting & Condensate Management | Climate Control & Environmental Engineering | v1.2 |  |  | 4000 Environment | 4000.51.02 | Climate Control | 4000.51.01 | HVAC & Site Climate Tech | TAG-002 OSHA · Safety Glasses, Work Gloves, ANSI Steel-Toe Boots | HVAC load calculation on file (DOC-030); 208V 3-phase power drop verified; spot coolers staged in BOH corridor. | Spot Cooler Placement & Power Verification: Position 5-ton spot coolers in designated cooling nodes; connect 50A twist-lock power cables; verify proper phase rotation. | Flexible Ducting Run & Supply Air Balancing: Route 12-inch insulated flexible supply ducts to audience hot zones and stage wings; secure duct runs with zip ties and aircraft cable. | Condensate Pump & Drainage Routing: Connect automatic condensate sump pumps to drainage tubing; route discharge lines to sanitary sewer drain; test float switch cutoff. | Thermostat Calibration & Thermal Load Monitoring: Set digital thermostats to maintain 72 deg F ambient / 50% relative humidity; monitor server rack and LED wall exhaust zones. | DOC-030 | Temporary HVAC Load Calculation & Psychrometric Cooling Plan | Active | FALSE | ASHRAE Standard 55 & Florida Mechanical Code temporary event cooling protocol. | Julian Clarkson | 2026-10-02 09:55 | 2026-10-02
SOP-031 | Talent Hospitality Advancing, Green Room Security & Rider Execution | Artist Production & Hospitality Management | v1.0 |  |  | 2000 Talent | 2000.03.01 | Advancing | 2000.50.02 | Artist Relations Coordinator | Artist Relations Access Lanyard, Production Radio (Channel 4) | Countersigned talent contract on file (DOC-031); rider fulfillment items procured; green room lockbox combination set. | Green Room Space Preparation & Inspection: Deep clean artist green room; stage requested FF&E (couches, mirrors, garment steamer); verify private restroom stocked and locked. | Rider Food & Beverage Fulfillment: Stock rider-specified beverages, organic snacks, and local specialty provisions; verify strict adherence to dietary restrictions and allergies. | Green Room Access Security Lockout: Post security officer outside artist dressing room suite; enforce strict closed-door policy; permit access only to badge-verified roster. | Artist Settlement & Sign-Off Documentation: Review hospitality receipts with artist road manager; confirm cash per-diems disbursed; obtain countersigned settlement voucher. | DOC-031 | Artist Performance Contract, Music Publishing & Sync Clearances | Active | FALSE | GHXSTSHIP talent advancing standards and artist hospitality execution procedure. | Julian Clarkson | 2026-10-02 09:55 | 2026-10-02
SOP-032 | Incident Command CAD Logging, Mass Notification & AHJ Escalation | Crisis Communications & Incident Command | v2.0 |  |  | 6000 Operations | 6000.05.01 | Incident Management | 6000.50.02 | Site Safety & Security Lead | Clear-Com Headset, Mobile CAD Dispatch Tablet, Radio (Channel 1) | Emergency Action Plan active (DOC-032); multi-channel radio matrix active; direct dispatch link to Miami 911 PSAP. | CAD Incident Ingest & Verification: Receive incident report on Radio Ch 1; record exact timestamp, location code (LOC-xx), reporting party, and severity level in CAD log. | Tactical Resource Dispatch: Dispatch nearest security officer, EMT team, or technical lead based on incident class; maintain active timer on response milestone. | Mass Notification Alert Triggering: In event of major life safety emergency, activate pre-recorded audio/visual evacuation message across all PA clusters and LED displays. | AHJ Briefing & Incident Debrief Closure: Coordinate on-site briefing with responding Miami Fire/Police commanders; document resolution notes and witness statements; close ticket. | DOC-032 | Incident Command Structure (ICS) & Emergency CAD Dispatch Guide | Active | FALSE | FEMA NIMS Incident Command System & NFPA 3000 emergency operations procedure. | Julian Clarkson | 2026-10-02 09:55 | 2026-10-02
SOP-033 | Environmental Scent Diffusion Nebulization & Fragrance Safety Control | Sensory Design & Atmosphere Management | v1.1 |  |  | 7000 Experience | 7000.04.01 | Scent Diffusion | 7000.50.01 | Front of House Lead / Box Office Manager | Nitrile Handling Gloves, Safety Glasses | IFRA compliance safety data sheet active (DOC-033); cold-air nebulizers installed; botanical aroma cartridges stocked. | Cartridge Ingest & IFRA Batch Verification: Inspect aroma oil cartridges; verify IFRA safety certificates and batch numbers; ensure 100% hypoallergenic, phthalate-free oil. | Nebulizer Installation & HVAC Ducted Interface: Install cold-air diffusion units in primary air handler supply plenums; calibrate sub-micron droplet atomization. | Daypart Intensity Programming: Program digital diffusion duty cycles: 20% intensity for daytime arrival, 45% for evening reception, 10% during high-energy performance. | Sensory Air Quality Monitoring: Inspect venue air quality; ensure zero visible haze or oil residue on surfaces; log guest feedback and adjust fragrance concentration. | DOC-033 | Scent Diffusion Formulation & Hypoallergenic Safety Data Sheet (SDS) | Active | FALSE | IFRA Standards & OSHA indoor air quality environmental fragrancing protocol. | Julian Clarkson | 2026-10-02 09:55 | 2026-10-02
SOP-034 | Post-Event Venue Space Handover, Damage Inspection & Landlord Sign-Off | Facility Restoration & Space Handover | v1.0 |  |  | 0000 Executive | 0000.50.04 | Close Activities | 0000.50.01 | Chief Executive Officer | High-Vis Vest, Flashlight, Digital Camera / Tablet | Architectural site CAD on file (DOC-034); pre-lease baseline photographic survey on file; strike completed (SOP-008). | Joint Architectural Walkthrough: Conduct comprehensive physical walk of sanctuary, patio, mezzanine, and parking facilities with building owner / landlord representative. | Photographic Punch List Generation: Photograph all surfaces, doors, glazing, and electrical tie-in panels; document any pre-existing vs event-related wear or marks. | Immediate Restoration Remediation: Deploy facilities maintenance technician to patch minor drywall blemishes, paint scuffs, or replace blown utility light bulbs. | Formal Handover Sign-Off & Security Deposit Release: Execute countersigned space release and condition certificate; submit documentation to finance for security bond return. | DOC-034 | Post-Event Site Restoration & Landlord Handover Inspection Log | Active | FALSE | Commercial lease surrender and post-production venue restoration sign-off procedure. | Julian Clarkson | 2026-10-02 09:55 | 2026-10-02

## Locations
RECORD ID | PROJECT ID | DEPARTMENT | CATEGORY | SUB CATEGORY | LOCATION | DESCRIPTION | STATUS | FLAG | NOTES | CREATED BY | CREATED AT | UPDATED AT
LOC-01 | CSMIA26 | Site Operations | Stage | Main Stage | Zone B - Main Stage | Primary festival performance stage and FOH corridor | Active | FALSE | Safety ramp inspection cleared | Julian Clarkson | 2026-09-30 13:05 | 2026-09-30 13:05
LOC-02 | CSMIA26 | Guest Experience | Gates | Box Office | Gate 1 - North Box Office | Primary attendee entrance and wristband exchange | Active | FALSE | Guest services lockbox compartment on site | Sarah Jenkins | 2026-09-30 13:05 | 2026-09-30 13:05
LOC-03 | CSMIA26 | Technical Production | Production Office | Quartermaster | Production Office / Quartermaster | Central technical asset check-out and production admin | Active | FALSE | Radio depot and surveillance kit hub | Alex Rivera | 2026-09-30 13:05 | 2026-09-30 13:05
LOC-04 | CSMIA26 | Stage Operations | Back of House | Stage Left | Back of House - Stage Left | Stage deck build, crew check-in, and truss staging | Active | FALSE | Overhire stagehand crew muster point | Julian Clarkson | 2026-09-30 13:05 | 2026-09-30 13:05
LOC-05 | CSMIA26 | Logistics / Site Ops | Loading Dock | Freight | Loading Dock B | Heavy freight delivery intake and staging dock | Active | FALSE | BOL filing and crate intake hub | Elena Rostova | 2026-09-30 13:05 | 2026-09-30 13:05
LOC-06 | CSMIA26 | Catering & Hospitality | Hospitality | Artist Village | Artist Village Green Room | Artist hospitality green room suites and compound | Active | FALSE | Hospitality logistics and catering runs | Sarah Jenkins | 2026-09-30 13:05 | 2026-09-30 13:05
LOC-07 | CSMIA26 | Site Operations | Power Compound | Generators | Zone D - Generator Compound 2 | Primary 250kVA generator compound and fuel bank | Active | FALSE | Fuel technician dispatch monitoring | Julian Clarkson | 2026-09-30 13:05 | 2026-09-30 13:05
LOC-08 | CSMIA26 | Security | Perimeter | Gates | Gate 2 - South Gate | Secondary patron ingress and emergency egress | Active | FALSE | Perimeter access point | Julian Clarkson | 2026-09-30 13:05 | 2026-09-30 13:05
LOC-09 | CSMIA26 | Medical | Health & Safety | First Aid | Medical Tent A - Zone A | Primary triage station and emergency EMT center | Active | FALSE | Paramedic team base | Julian Clarkson | 2026-09-30 13:05 | 2026-09-30 13:05
LOC-10 | CSMIA26 | Site Operations | Sanitation | Facilities | Sanitation Compound East | Waste management and greywater pumping depot | Active | FALSE | Scheduled servicing route | Julian Clarkson | 2026-09-30 13:05 | 2026-09-30 13:05
LOC-11 | CSMIA26 | Food & Beverage | Concessions | Bar 1 | Zone A Concessions Row | Main public beverage dispensing stations | Active | FALSE | POS terminals and beverage stock | Julian Clarkson | 2026-09-30 13:05 | 2026-09-30 13:05
LOC-12 | CSMIA26 | Site Operations | Power Compound | Distribution | Zone A - Power Compound 1 | Audio/visual power distro transformers | Active | FALSE | Load balancing regular checks | Julian Clarkson | 2026-09-30 13:05 | 2026-09-30 13:05
LOC-13 | CSMIA26 | Stage Operations | Back of House | Stage Right | Back of House - Stage Right | Secondary artist wing, monitor world, audio distro | Active | FALSE | Monitor engineer staging | Julian Clarkson | 2026-09-30 13:05 | 2026-09-30 13:05
LOC-14 | CSMIA26 | Technical Production | Front of House | Control | Main Stage FOH Control | Sound and lighting console mixing tower | Active | FALSE | FOH riser cleared | Julian Clarkson | 2026-09-30 13:05 | 2026-09-30 13:05
LOC-15 | CSMIA26 | Logistics / Site Ops | Storage | Containers | Zone C - Storage Compound | Production containers and road case storage | Active | FALSE | Secure lockup compound | Julian Clarkson | 2026-09-30 13:05 | 2026-09-30 13:05
LOC-16 | CSMIA26 | Guest Experience | VIP | Lounge | VIP Oasis Lounge | Premium hospitality, viewing deck, and bar | Active | FALSE | Wristband verification scanner | Julian Clarkson | 2026-09-30 13:05 | 2026-09-30 13:05
LOC-17 | CSMIA26 | Security | Command | Dispatch | Joint Operations Center (JOC) | Unified command center for police, fire, ops, medical | Active | FALSE | 24/7 communications monitoring | Julian Clarkson | 2026-09-30 13:05 | 2026-09-30 13:05
LOC-18 | CSMIA26 | Transportation | Parking | Staff | Lot C - Staff & Production Parking | Credentialed crew vehicle parking and check-in | Active | FALSE | Parking pass hangtag required | Julian Clarkson | 2026-09-30 13:05 | 2026-09-30 13:05
LOC-19 | CSMIA26 | Transportation | Shuttle | Dropoff | Rideshare / Shuttle Hub North | Mass transit and rideshare passenger dispatch | Active | FALSE | Traffic management cones active | Julian Clarkson | 2026-09-30 13:05 | 2026-09-30 13:05
LOC-20 | CSMIA26 | Food & Beverage | Catering | Commissary | Crew Catering Commissary | Production and vendor meal service hall | Active | FALSE | Meal pass scanning active | Julian Clarkson | 2026-09-30 13:05 | 2026-09-30 13:05
LOC-21 | CSMIA26 | Stage Operations | Stage | Side Stage | Stage 2 - Tent Deck | Secondary electronic dance music stage | Active | FALSE | Audio rig cleared | Julian Clarkson | 2026-09-30 13:05 | 2026-09-30 13:05
LOC-22 | CSMIA26 | Technical Production | Broadcast | OB Truck | Media Compound / Broadcast Truck | Live stream and archival recording OB unit | Active | FALSE | Fiber run connected | Julian Clarkson | 2026-09-30 13:05 | 2026-09-30 13:05
LOC-23 | CSMIA26 | Guest Experience | Lost & Found | Info | Information Booth & Lost and Found | Central attendee inquiries and lost item drop | Active | FALSE | Lockbox storage system | Julian Clarkson | 2026-09-30 13:05 | 2026-09-30 13:05
LOC-24 | CSMIA26 | Site Operations | Fueling | Compound | Fuel Depot B | Diesel and unleaded reserve fuel tank storage | Active | FALSE | Hazard containment berm verified | Julian Clarkson | 2026-09-30 13:05 | 2026-09-30 13:05
LOC-25 | CSMIA26 | Medical | Health & Safety | First Aid | Medical Tent B - Zone C | Secondary medical post for southern perimeter | Active | FALSE | EMT response team assigned | Julian Clarkson | 2026-09-30 13:05 | 2026-09-30 13:05
LOC-26 | CSMIA26 | Security | K-9 | Post | Security K-9 Screening Post | Explosives and narcotics canine screening post | Active | FALSE | Daily patrol schedule cleared | Julian Clarkson | 2026-09-30 13:05 | 2026-09-30 13:05
LOC-27 | CSMIA26 | Guest Experience | ADA | Viewing | ADA Viewing Platform - Main Stage | Elevated accessible viewing platform | Active | FALSE | Ramp gradient certified compliant | Julian Clarkson | 2026-09-30 13:05 | 2026-09-30 13:05
LOC-28 | CSMIA26 | Site Operations | Water | Station | Hydration Station 1 - Central Lawn | Free patron filtered water refill station | Active | FALSE | Pressure testing cleared | Julian Clarkson | 2026-09-30 13:05 | 2026-09-30 13:05
LOC-29 | CSMIA26 | Site Operations | Heavy Equipment | Yard | Equipment Yard & Heavy Machinery Yard | Forklift, telehandler, and golf cart charging depot | Active | FALSE | Equipment checkout log active | Julian Clarkson | 2026-09-30 13:05 | 2026-09-30 13:05
LOC-30 | CSMIA26 | Stage Operations | Dressing Rooms | Portables | Artist Trailer Compound B | Headliner dressing trailers and rehearsal spaces | Active | FALSE | Private security checkpoint on site | Julian Clarkson | 2026-09-30 13:05 | 2026-09-30 13:05
LOC-31 | CSMIA26 | Logistics / Site Ops | Loading Dock | Freight | Loading Dock A | Primary heavy freight intake dock | Active | FALSE | Primary dock for production semi-trailers | Julian Clarkson | 2026-09-30 13:05 | 2026-09-30 13:05
LOC-32 | CSMIA26 | Site Operations | Venue | Main Property | The Sanctuary MiMo | Historic sanctuary venue in MiMo district | Active | FALSE | Primary venue property | Julian Clarkson | 2026-09-30 13:05 | 2026-09-30 13:05

## Shipping Manifest
RECORD ID | PROJECT ID | DEPARTMENT | CATEGORY | SUB CATEGORY | VENDOR ID | ITEM | DESCRIPTION | CONTAINER | PALLET COUNT | PIECE COUNT | LENGTH (FT) | WIDTH (FT) | HEIGHT (FT) | VOLUME (CU FT) | DIMENSIONS | WEIGHT | SHIPMENT DATE | SENDER | ORIGIN | PERSONNEL ID | LOCATION ID | CARRIER | CARRIER PHONE | TRAILER LICENSE | SEAL NUMBER | FREIGHT TYPE | TRACKING NUMBER | BILL OF LADING (BOL) | STATUS | FLAG | NOTES | CREATED BY | CREATED AT | UPDATED AT
SHP-001 | CSMIA26 | 5000 Production | 5000.52.01 | Freight Inbound | VEN-001 | Main Stage Line Array & Truss Rig | Heavy staging & line array dispatch | 53ft Semi | 26 | 84 | 53 | 8.5 | 13.5 | 6081.75 | 53 ft x 8.5 ft x 13.5 ft | 45,000 lbs | 2026-10-02 | PRG Logistics | Orlando, FL | P-021 | LOC-31 | PRG Freight | (800) 555-0191 | FL-TL-8821 | SL-990142 | Ground Freight | TRK-88219 | BOL-IIIP-01 | Scheduled | FALSE | Priority load-in delivery; calltime 08:00 EDT | Julian Clarkson | 2026-10-01 | 2026-10-01
SHP-002 | CSMIA26 | 5000 Production | 5000.03.01 | Video Inbound | VEN-014 | LED Video Tiles & Processors | High-res outdoor wall panels | 26ft Box Truck | 12 | 48 | 26 | 8 | 12.5 | 2600 | 26 ft x 8 ft x 12.5 ft | 10,000 lbs | 2026-10-06 | NEP Screenworks | Miami, FL | P-021 | LOC-05 | NEP Logistics | (305) 555-0182 | FL-BX-4410 | SL-990143 | Ground Freight | TRK-99301 | BOL-IIIP-02 | Scheduled | FALSE | Indoor & outdoor LED walls; calltime 10:00 EDT | Julian Clarkson | 2026-10-01 | 2026-10-01
SHP-003 | CSMIA26 | 5000 Production | 5000.52.01 | Freight Outbound | VEN-001 | Full Production Strike & Return | Post-event outbound return freight | 53ft Semi | 26 | 84 | 53 | 8.5 | 13.5 | 6081.75 | 53 ft x 8.5 ft x 13.5 ft | 45,000 lbs | 2026-10-19 | Mana Wynwood | Miami, FL | P-021 | LOC-31 | PRG Freight | (800) 555-0191 | FL-TL-8822 | SL-990144 | Ground Freight | TRK-88220 | BOL-IIIP-03 | Scheduled | FALSE | Strike and venue return; calltime 06:00 EDT | Julian Clarkson | 2026-10-01 | 2026-10-01

## Marshalling Yard Log
RECORD ID | PROJECT ID | DEPARTMENT | CATEGORY | SUB CATEGORY | VEHICLE CALLSIGN | CARRIER / VENDOR ID | SHIPMENT ID | VEHICLE TYPE | DRIVER NAME | CARRIER PHONE | TRAILER LICENSE | SEAL NUMBER | DIMENSIONS | WEIGHT | STAGING BAY | TARGET DOCK ID | CHECK-IN TIME | DOCK CALL TIME | DOCK RELEASE TIME | STATUS | FLAG | NOTES | CREATED BY | CREATED AT | UPDATED AT
MYL-001 | CSMIA26 | 6000 Operations | 6000.02.07 | Freight Staging | TRUCK-01 | VEN-001 | SHP-001 | 53ft Tractor-Trailer | Carlos Gomez | (407) 555-0142 | FL-TL-8821 | SL-990142 | 53ft x 8.5ft x 13.5ft | 45,000 lbs | BAY-01 | LOC-31 | 2026-10-02 07:30 | 2026-10-02 08:00 | 2026-10-02 11:30 | Staged | FALSE | Arrived on schedule; holding for dock A clearance | Julian Clarkson | 2026-10-01 | 2026-10-01
MYL-002 | CSMIA26 | 6000 Operations | 6000.02.07 | Video Staging | TRUCK-02 | VEN-014 | SHP-002 | 26ft Box Truck | Marcus Vance | (305) 555-0178 | FL-BX-4410 | SL-990143 | 26ft x 8.0ft x 12.5ft | 10,000 lbs | BAY-02 | LOC-05 | 2026-10-06 09:30 | 2026-10-06 10:00 | 2026-10-06 13:00 | Staged | FALSE | LED wall freight queued for unload | Julian Clarkson | 2026-10-01 | 2026-10-01

## Advance Requests
RECORD ID | ORGANIZATION | PROJECT ID | DEPARTMENT | CATEGORY | SUB CATEGORY | VENDOR ID | ITEM | DESCRIPTION | URID | QUANTITY | UNIT BASIS | ESTIMATE RATE | TOTAL ESTIMATE | LOCATION ID | NEEDED BY DATE | REQUESTED BY | APPROVER ROLE | APPROVAL DATE | PO NUMBER | STATUS | FLAG | NOTES | CREATED BY | CREATED AT | UPDATED AT

## Hospitality Fulfillment
RECORD ID | ORGANIZATION | PROJECT ID | DEPARTMENT | CATEGORY | SUB CATEGORY | ARTIST NAME | LOCATION ID | LIAISON ID | RIDER CONTRACT REF | CATERING PACKAGE | DIETARY REQUIREMENTS | HEADCOUNT | DELIVERY DEADLINE | DELIVERY POINT | SERVICE STYLE | STATUS | FLAG | NOTES | CREATED BY | CREATED AT | UPDATED AT

## Asset Inventory
RECORD ID | PROJECT ID | ITEM ID | ITEM | DESCRIPTION | SPECIFICATIONS | COLOR | MAKE & MODEL | SERIAL NUMBER | LABEL | QUANTITY | CONDITION | LOCATION ID | VENDOR ID | UNIT COST | STATUS | FLAG | NOTES | CREATED BY | CREATED AT | UPDATED AT
AST-0001 | CSMIA26 | 9000.03.01-XPMS-004 | Radio - Two-Way - Standard | UHF or VHF handheld two-way radio for event operations. |  | Black |  | SN-CP200-001 | Radio 01 | 1 | Good | LOC-03 | VEN-021 | 15 | Active | FALSE | Standard comms allocation | Julian Clarkson | 2026-09-15 | 2026-09-15
AST-0002 | CSMIA26 | 5000.05.01-XPMS-001 | Chain Motor - Half Ton | Half-ton (1,000 lb) electric chain hoist for lighting and scenic rigging. | 1/2 ton capacity ¦ 60ft chain ¦ Variable speed. | Black |  | SN-MOTR-0881 | Motor 01 | 1 | Excellent | LOC-01 | VEN-012 | 48.5 | Active | FALSE | Overhead hoist point | Julian Clarkson | 2026-09-15 | 2026-09-15
AST-0003 | CSMIA26 | 9000.03.02-XPMS-002 | Intercom - Wireless | Digital wireless intercom for mobile production staff. |  | Black |  | SN-BOLERO-014 | Beltpack 01 | 1 | Good | LOC-04 | VEN-015 | 100 | Active | FALSE | Roaming stage intercom | Julian Clarkson | 2026-09-15 | 2026-09-15
FALSE

## Asset Assignments
RECORD ID | ORGANIZATION | PROJECT ID | DEPARTMENT | CATEGORY | SUB CATEGORY | ASSET ID | PERSONNEL ID | ALL CALL | STATUS | FLAG | NOTES | CREATED BY | CREATED AT | UPDATED AT

## Personnel Roster
PERSONNEL ID | ORGANIZATION | PROJECT ID | FIRST NAME | LAST NAME | PREFERRED NAME | EMAIL | PHONE | COMPANY | ROLE CODE | POSITION | DEPARTMENT | CATEGORY | SUB CATEGORY | CLEARANCE TIER | ZONE ACCESS | CREDENTIAL | CREDENTIAL RECORD ID | ON SITE START | ON SITE END | DIETARY RESTRICTIONS | SHIRT SIZE | SPECIAL ACCOMMODATIONS | EMERGENCY CONTACT NAME | EMERGENCY CONTACT PHONE | STATUS | FLAG | NOTES | CREATED BY | CREATED AT | UPDATED AT
P-001 | GHXSTSHIP | CSMIA26 | Ashley | Sumner | Ashley | ashley@tigresoundsystem.com | (305) 555-0101 | Tigre Studio | 0000.50.01 | Chief Executive Officer | 0000 Executive | 0.5 | Governance and Client Relations | Tier 1 - Executive Master | All Zones | All Access | CRD-001 | 2026-09-01 | 2026-12-31 | None | M | None | Tigre Emergency | (305) 555-0199 | Active | FALSE | Commercial owner | Julian Clarkson | 2026-09-15 | 2026-09-15
P-005 | GHXSTSHIP | CSMIA26 | Isabella | Acker | Izzy | isabella@spotify.com | (305) 555-0105 | Spotify | 1000.50.01 | Creative Director | 1000 Creative | 1000.5 | Programming and Creative Direction | Tier 1 - Executive Master | All Zones | All Access | CRD-002 | 2026-09-01 | 2026-12-31 | Vegetarian | S | None | Spotify Emergency | (305) 555-0195 | Active | FALSE | Creative and talent lead | Julian Clarkson | 2026-09-15 | 2026-09-15
P-016 | GHXSTSHIP | CSMIA26 | Mary | Christianson | Mary | mary@tigresoundsystem.com | (305) 555-0116 | Tigre Studio | 6000.50.01 | House Manager | 6000 Operations | 6000.5 | House Management | Tier 1 - Executive Master | All Zones | All Access | CRD-003 | 2026-10-26 | 2026-12-31 | None | M | None | Emergency Contact | (305) 555-0188 | Active | FALSE | House operations lead | Julian Clarkson | 2026-09-15 | 2026-09-15
P-021 | GHXSTSHIP | CSMIA26 | Julian | Clarkson | Julian | julian.clarkson@ghxstship.pro | (305) 555-0121 | Tigre Studio | 5000.50.01 | Production & Operations Director | 5000 Production | 5000.5 | Production Leadership | Tier 1 - Executive Master | All Zones | All Access | CRD-004 | 2026-09-01 | 2026-12-31 | None | L | None | GHXSTSHIP HQ | (305) 555-0100 | Active | FALSE | Senior production lead | Julian Clarkson | 2026-09-15 | 2026-09-15
P-024 | GHXSTSHIP | CSMIA26 | David | Miller | Dave | dave@unreal-systems.com | (305) 555-0124 | Unreal-Systems | 9000.50.02 | Audio Engineer - A1/FOH | 5000 Production | 9000.5 | Audio Systems | Tier 2 - Technical Lead | Stage & FOH | Production | CRD-005 | 2026-11-16 | 2026-12-31 | None | XL | None | Unreal HQ | (305) 555-0155 | Active | FALSE | FOH audio engineer | Julian Clarkson | 2026-09-15 | 2026-09-15
P-006 | GHXSTSHIP | CSMIA26 | Rebecca | Bex | Bex | bex@tigresoundsystem.com | (305) 555-0106 | Tigre Studio | 1000.50.02 | Event & Programming Director | 1000 Creative | 1000.5 | Programming and Creative Direction | Tier 1 - Executive Master | All Zones | All Access | CRD-006 | 2026-08-01 | 2026-12-31 | None | M | None | Tigre Emergency | (305) 555-0199 | Active | FALSE | Creative and programming lead | Julian Clarkson | 2026-09-15 | 2026-09-15

## Staffing Requisition
REQ ID | EVENT PHASE | ROLE CODE | RATE CARD ID | JOB TITLE | HEADCOUNT | DURATION (DAYS) | STANDARD RATE | TOTAL ESTIMATED COST | STATUS | FLAG | NOTES | CREATED BY | CREATED AT | UPDATED AT
REQ-001 | Pre-Production | 0000.50.01 | LRC-001 | Chief Executive Officer | 1 | 30 | 1800 | 54000 | Approved | FALSE |  | Julian Clarkson | 2026-10-01 | 2026-10-01
REQ-002 | Creative Conception | 1000.50.01 | LRC-002 | Creative Director | 1 | 25 | 1250 | 31250 | Approved | FALSE |  | Julian Clarkson | 2026-10-01 | 2026-10-01
REQ-003 | Site Build & Load-In | 5000.50.01 | LRC-004 | Production & Operations Director | 1 | 20 | 1350 | 27000 | Approved | FALSE |  | Julian Clarkson | 2026-10-01 | 2026-10-01
REQ-004 | Site Power Install | 5000.50.02 | LRC-005 | Master Electrician / Power Lead | 2 | 12 | 850 | 20400 | Approved | FALSE |  | Julian Clarkson | 2026-10-01 | 2026-10-01
REQ-005 | Venue Operations | 6000.50.01 | LRC-006 | House Manager | 1 | 10 | 750 | 7500 | Approved | FALSE |  | Julian Clarkson | 2026-10-01 | 2026-10-01
REQ-006 | Security Grid Deployment | 6000.50.02 | LRC-007 | Site Safety & Security Lead | 2 | 8 | 700 | 11200 | Approved | FALSE |  | Julian Clarkson | 2026-10-01 | 2026-10-01
REQ-007 | Stage Deck Execution | 9000.50.01 | LRC-008 | Production Stage Manager | 1 | 6 | 950 | 5700 | Approved | FALSE |  | Julian Clarkson | 2026-10-01 | 2026-10-01
REQ-008 | FOH Sound Tuning & Show | 9000.50.02 | LRC-009 | Audio Engineer - A1/FOH | 2 | 6 | 850 | 10200 | Approved | FALSE |  | Julian Clarkson | 2026-10-01 | 2026-10-01
REQ-009 | Lighting Rig & Show Cues | 9000.50.03 | LRC-010 | Lighting Designer / LD | 2 | 6 | 800 | 9600 | Approved | FALSE |  | Julian Clarkson | 2026-10-01 | 2026-10-01

## Crew Shifts
SHIFT ID | PROJECT ID | SHIFT DATE | DEPARTMENT | LOCATION NAME | PERSONNEL ID | CREW NAME | ROLE CODE | RATE CARD ID | JOB TITLE | SCHEDULED CALL TIME | SCHEDULED WRAP TIME | SCHEDULED MEAL BREAK (HRS) | NET SCHEDULED HOURS | PAY BASIS | STANDARD RATE | HOURLY BASE RATE | SCHEDULED PAY | STATUS | FLAG | NOTES | CREATED BY | CREATED AT | UPDATED AT
SHF-001 | CSMIA26 | 2026-11-20 | 5000 Production | Main Stage & Bar | P-021 | Julian Clarkson | 5000.50.01 | LRC-004 | Production & Operations Director | 8:00 | 19:00 | 1 | 10 | Day Rate | 1350 | 135 | 1350 | Confirmed | FALSE |  | Julian Clarkson | 2026-10-01 | 2026-10-01
SHF-002 | CSMIA26 | 2026-11-20 | 5000 Production | Main Stage & Bar | P-024 | David Miller | 9000.50.02 | LRC-009 | Audio Engineer - A1/FOH | 8:00 | 19:00 | 1 | 10 | Day Rate | 850 | 85 | 850 | Confirmed | FALSE |  | Julian Clarkson | 2026-10-01 | 2026-10-01
SHF-003 | CSMIA26 | 2026-11-20 | 6000 Operations | All Zones | P-016 | Mary Christianson | 6000.50.01 | LRC-006 | House Manager | 9:00 | 19:00 | 1 | 9 | Day Rate | 750 | 75 | 750 | Confirmed | FALSE |  | Julian Clarkson | 2026-10-01 | 2026-10-01
SHF-004 | CSMIA26 | 2026-11-20 | 1000 Creative | All Zones | P-005 | Isabella Acker | 1000.50.01 | LRC-002 | Creative Director | 9:00 | 19:00 | 1 | 9 | Day Rate | 1250 | 125 | 1250 | Confirmed | FALSE |  | Julian Clarkson | 2026-10-01 | 2026-10-01
SHF-005 | CSMIA26 | 2026-11-20 | 1000 Creative | All Zones | P-006 | Rebecca Bex | 1000.50.02 | LRC-003 | Event & Programming Director | 9:00 | 19:00 | 1 | 9 | Day Rate | 1100 | 110 | 1100 | Confirmed | FALSE |  | Julian Clarkson | 2026-10-01 | 2026-10-01
SHF-006 | CSMIA26 | 2026-11-20 | 0000 Executive | All Zones | P-001 | Ashley Sumner | 0000.50.01 | LRC-001 | Chief Executive Officer | 10:00 | 18:00 | 1 | 7 | Day Rate | 1800 | 180 | 1800 | Confirmed | FALSE |  | Julian Clarkson | 2026-10-01 | 2026-10-01
SHF-007 | CSMIA26 | 2026-11-21 | 5000 Production | Main Stage & Bar | P-021 | Julian Clarkson | 5000.50.01 | LRC-004 | Production & Operations Director | 8:00 | 20:00 | 1 | 11 | Day Rate | 1350 | 135 | 1350 | Confirmed | FALSE |  | Julian Clarkson | 2026-10-01 | 2026-10-01
SHF-008 | CSMIA26 | 2026-11-21 | 5000 Production | Main Stage & Bar | P-024 | David Miller | 9000.50.02 | LRC-009 | Audio Engineer - A1/FOH | 8:00 | 20:00 | 1 | 11 | Day Rate | 850 | 85 | 850 | Confirmed | FALSE |  | Julian Clarkson | 2026-10-01 | 2026-10-01

## Crew Timesheets
TIMESHEET ID | PROJECT ID | SHIFT ID | WORK DATE | PERSONNEL ID | CREW NAME | ROLE CODE | RATE CARD ID | JOB TITLE | ACTUAL IN TIME | MEAL OUT TIME | MEAL IN TIME | ACTUAL OUT TIME | MEAL DURATION (HRS) | TOTAL ELAPSED HOURS | NET WORKED HOURS | REGULAR HOURS (1.0x) | OVERTIME HOURS (1.5x) | DOUBLE TIME HOURS (2.0x) | HOURLY BASE RATE | REGULAR PAY | OVERTIME PAY | DOUBLE TIME PAY | MEAL PENALTY PAY | PER DIEM PAY | GROSS EARNINGS | EXPENSE GL ACCOUNT | EXPENSE GL NAME | STATUS | FLAG | NOTES | CREATED BY | CREATED AT | UPDATED AT
TS-001 | CSMIA26 | SHF-001 | 2026-11-20 | P-021 | Julian Clarkson | 5000.50.01 | LRC-004 | Production & Operations Director | 7:45 | 13:00 | 14:00 | 19:15 | 1 | 11.5 | 10.5 | 8 | 2.5 | 0 | 135 | 1080 | 506.25 | 0 | 0 | 75 | 1661.25 | 5500 | Expense · Production | Approved | FALSE |  | Julian Clarkson | 2026-11-20 | 2026-11-20
TS-002 | CSMIA26 | SHF-002 | 2026-11-20 | P-024 | David Miller | 9000.50.02 | LRC-009 | Audio Engineer - A1/FOH | 8:00 | 14:30 | 15:30 | 21:00 | 1 | 13 | 12 | 8 | 4 | 0 | 85 | 680 | 510 | 0 | 50 | 75 | 1315 | 5500 | Expense · Production | Approved | FALSE |  | Julian Clarkson | 2026-11-20 | 2026-11-20
TS-003 | CSMIA26 | SHF-003 | 2026-11-20 | P-016 | Mary Christianson | 6000.50.01 | LRC-006 | House Manager | 8:45 | 13:30 | 14:30 | 18:45 | 1 | 10 | 9 | 8 | 1 | 0 | 75 | 600 | 112.5 | 0 | 0 | 75 | 787.5 | 5600 | Expense · Operations | Approved | FALSE |  | Julian Clarkson | 2026-11-20 | 2026-11-20
TS-004 | CSMIA26 | SHF-004 | 2026-11-20 | P-005 | Isabella Acker | 1000.50.01 | LRC-002 | Creative Director | 9:00 | 14:00 | 15:00 | 19:00 | 1 | 10 | 9 | 8 | 1 | 0 | 125 | 1000 | 187.5 | 0 | 0 | 75 | 1262.5 | 5100 | Expense · Creative | Approved | FALSE |  | Julian Clarkson | 2026-11-20 | 2026-11-20
TS-005 | CSMIA26 | SHF-005 | 2026-11-20 | P-006 | Rebecca Bex | 1000.50.02 | LRC-003 | Event & Programming Director | 9:00 | 13:45 | 14:45 | 19:30 | 1 | 10.5 | 9.5 | 8 | 1.5 | 0 | 110 | 880 | 247.5 | 0 | 0 | 75 | 1202.5 | 5100 | Expense · Creative | Approved | FALSE |  | Julian Clarkson | 2026-11-20 | 2026-11-20
TS-006 | CSMIA26 | SHF-006 | 2026-11-20 | P-001 | Ashley Sumner | 0000.50.01 | LRC-001 | Chief Executive Officer | 10:00 | 14:00 | 15:00 | 18:00 | 1 | 8 | 7 | 7 | 0 | 0 | 180 | 1260 | 0 | 0 | 0 | 75 | 1335 | 5000 | Expense · Executive | Approved | FALSE |  | Julian Clarkson | 2026-11-20 | 2026-11-20
TS-007 | CSMIA26 | SHF-007 | 2026-11-21 | P-021 | Julian Clarkson | 5000.50.01 | LRC-004 | Production & Operations Director | 7:30 | 14:00 | 15:00 | 22:30 | 1 | 15 | 14 | 8 | 4 | 2 | 135 | 1080 | 810 | 540 | 50 | 75 | 2555 | 5500 | Expense · Production | Approved | FALSE |  | Julian Clarkson | 2026-11-21 | 2026-11-21
TS-008 | CSMIA26 | SHF-008 | 2026-11-21 | P-024 | David Miller | 9000.50.02 | LRC-009 | Audio Engineer - A1/FOH | 7:30 | 13:00 | 14:00 | 22:00 | 1 | 14.5 | 13.5 | 8 | 4 | 1.5 | 85 | 680 | 510 | 255 | 0 | 75 | 1520 | 5500 | Expense · Production | Approved | FALSE |  | Julian Clarkson | 2026-11-21 | 2026-11-21

## Labor Rate Cards
RATE CARD ID | ROLE CODE | JOB TITLE | ENGAGEMENT TYPE | PAY BASIS | STANDARD RATE | MIN GRADE RATE | MAX GRADE RATE | OT MULTIPLIER | DT MULTIPLIER | PER DIEM RATE | DEFAULT GL ACCOUNT | DEFAULT GL NAME | STATUS | FLAG | NOTES | CREATED BY | CREATED AT | UPDATED AT
LRC-001 | 0000.50.01 | Chief Executive Officer | Retainer | Day Rate | 1800 | 1500 | 2200 | 1 | 1 | 75 | 5000 | Expense · Executive | Active | FALSE | Canonical Executive Lead | Julian Clarkson | 2026-09-15 | 2026-09-15
LRC-002 | 1000.50.01 | Creative Director | Contractor 1099 | Day Rate | 1250 | 1000 | 1500 | 1.5 | 2 | 75 | 5100 | Expense · Creative | Active | FALSE | Canonical Creative Lead | Julian Clarkson | 2026-09-15 | 2026-09-15
LRC-003 | 1000.50.02 | Event & Programming Director | Contractor 1099 | Day Rate | 1100 | 900 | 1350 | 1.5 | 2 | 75 | 5100 | Expense · Creative | Active | FALSE | Canonical Programming Lead | Julian Clarkson | 2026-09-15 | 2026-09-15
LRC-004 | 5000.50.01 | Production & Operations Director | Retainer | Day Rate | 1350 | 1100 | 1600 | 1.5 | 2 | 75 | 5500 | Expense · Production | Active | FALSE | Canonical Senior Production Lead | Julian Clarkson | 2026-09-15 | 2026-09-15
LRC-005 | 5000.50.02 | Master Electrician / Power Lead | W2 Daily | Day Rate | 850 | 700 | 1000 | 1.5 | 2 | 75 | 5500 | Expense · Production | Active | FALSE | Master Power Systems Lead | Julian Clarkson | 2026-09-15 | 2026-09-15
LRC-006 | 6000.50.01 | House Manager | Contractor 1099 | Day Rate | 750 | 600 | 900 | 1.5 | 2 | 75 | 5600 | Expense · Operations | Active | FALSE | Canonical House Ops Lead | Julian Clarkson | 2026-09-15 | 2026-09-15
LRC-007 | 6000.50.02 | Site Safety & Security Lead | Contractor 1099 | Day Rate | 700 | 550 | 850 | 1.5 | 2 | 75 | 5600 | Expense · Operations | Active | FALSE | Perimeter & Incident Security | Julian Clarkson | 2026-09-15 | 2026-09-15
LRC-008 | 9000.50.01 | Production Stage Manager | W2 Daily | Day Rate | 950 | 800 | 1150 | 1.5 | 2 | 75 | 5500 | Expense · Production | Active | FALSE | Lead Deck Stage Manager | Julian Clarkson | 2026-09-15 | 2026-09-15
LRC-009 | 9000.50.02 | Audio Engineer - A1/FOH | Vendor Master | Day Rate | 850 | 700 | 1000 | 1.5 | 2 | 75 | 5500 | Expense · Production | Active | FALSE | Lead Audio Engineer FOH | Julian Clarkson | 2026-09-15 | 2026-09-15
LRC-010 | 9000.50.03 | Lighting Designer / LD | Contractor 1099 | Day Rate | 800 | 650 | 950 | 1.5 | 2 | 75 | 5500 | Expense · Production | Active | FALSE | Lead Lighting Programmer | Julian Clarkson | 2026-09-15 | 2026-09-15
LRC-011 | 9000.50.04 | Video Director / V1 | Contractor 1099 | Day Rate | 800 | 650 | 950 | 1.5 | 2 | 75 | 5500 | Expense · Production | Active | FALSE | Lead Video & Media Engineer | Julian Clarkson | 2026-09-15 | 2026-09-15
LRC-012 | 0000.51.01 | Production Finance Director | Contractor 1099 | Day Rate | 1200 | 1000 | 1450 | 1.0x | 1.0x | 75 | 5000 | Expense · Executive | Active | FALSE | Fiscal Governance Lead | Julian Clarkson | 2026-09-15 | 2026-09-15
LRC-013 | 1000.51.01 | Scenic Art Director | Contractor 1099 | Day Rate | 900 | 750 | 1100 | 1.5x | 2.0x | 75 | 5100 | Expense · Creative | Active | FALSE | Scenic & Environment Lead | Julian Clarkson | 2026-09-15 | 2026-09-15
LRC-014 | 2000.50.01 | Backline Tech / Instrument Specialist | W2 Daily | Day Rate | 650 | 550 | 800 | 1.5x | 2.0x | 75 | 5200 | Expense · Talent | Active | FALSE | Stage Backline Lead | Julian Clarkson | 2026-09-15 | 2026-09-15
LRC-015 | 2000.50.02 | Artist Relations Coordinator | Contractor 1099 | Day Rate | 550 | 450 | 700 | 1.5x | 2.0x | 75 | 5200 | Expense · Talent | Active | FALSE | Backstage Artist Care Lead | Julian Clarkson | 2026-09-15 | 2026-09-15
LRC-016 | 3000.50.01 | Principal Event Photographer | Contractor 1099 | Day Rate | 800 | 650 | 1000 | 1.5x | 2.0x | 75 | 5300 | Expense · Marketing | Active | FALSE | Lead Stills Photographer | Julian Clarkson | 2026-09-15 | 2026-09-15
LRC-017 | 3000.50.02 | Lead Cinematographer / Video Shooter | Contractor 1099 | Day Rate | 900 | 750 | 1150 | 1.5x | 2.0x | 75 | 5300 | Expense · Marketing | Active | FALSE | Lead Live Video Capture | Julian Clarkson | 2026-09-15 | 2026-09-15
LRC-018 | 3000.50.03 | Real-Time Social Content Producer | Contractor 1099 | Day Rate | 600 | 500 | 750 | 1.5x | 2.0x | 75 | 5300 | Expense · Marketing | Active | FALSE | Live Social Channel Producer | Julian Clarkson | 2026-09-15 | 2026-09-15
LRC-019 | 4000.50.01 | Structural Carpenter / Build Lead | W2 Daily | Day Rate | 700 | 600 | 850 | 1.5x | 2.0x | 75 | 5400 | Expense · Environment | Active | FALSE | Master Scenic Build Lead | Julian Clarkson | 2026-09-15 | 2026-09-15
LRC-020 | 4000.51.01 | HVAC & Site Climate Tech | Vendor Master | Day Rate | 650 | 550 | 800 | 1.5x | 2.0x | 75 | 5400 | Expense · Environment | Active | FALSE | Site Environmental Climate Tech | Julian Clarkson | 2026-09-15 | 2026-09-15
LRC-021 | 5000.50.03 | Production Coordinator | Contractor 1099 | Day Rate | 600 | 500 | 750 | 1.5x | 2.0x | 75 | 5500 | Expense · Production | Active | FALSE | Central Production Office Coordinator | Julian Clarkson | 2026-09-15 | 2026-09-15
LRC-022 | 5000.51.01 | Lead Stagehand / Deck Crew Chief | W2 Daily | Day Rate | 550 | 450 | 700 | 1.5x | 2.0x | 75 | 5500 | Expense · Production | Active | FALSE | Lead Stage Deck Crew Chief | Julian Clarkson | 2026-09-15 | 2026-09-15
LRC-023 | 5000.51.02 | Head Arena / Festival Rigger | Contractor 1099 | Day Rate | 950 | 800 | 1150 | 1.5x | 2.0x | 75 | 5500 | Expense · Production | Active | FALSE | Head Overhead Rigging Specialist | Julian Clarkson | 2026-09-15 | 2026-09-15
LRC-024 | 5000.51.03 | Lead System Rigger | W2 Daily | Day Rate | 750 | 650 | 900 | 1.5x | 2.0x | 75 | 5500 | Expense · Production | Active | FALSE | High Steel Rigger | Julian Clarkson | 2026-09-15 | 2026-09-15
LRC-025 | 5000.52.01 | Special Effects / Pyro Lead | Vendor Master | Day Rate | 800 | 650 | 1000 | 1.5x | 2.0x | 75 | 5500 | Expense · Production | Active | FALSE | Lead SFX & Atmospherics Operator | Julian Clarkson | 2026-09-15 | 2026-09-15
LRC-026 | 6000.50.03 | VIP Experience Manager | Contractor 1099 | Day Rate | 700 | 550 | 850 | 1.5x | 2.0x | 75 | 5600 | Expense · Operations | Active | FALSE | Lead VIP Guest Experience Manager | Julian Clarkson | 2026-09-15 | 2026-09-15
LRC-027 | 6000.51.01 | Janitorial & Waste Operations Lead | W2 Daily | Day Rate | 450 | 380 | 550 | 1.5x | 2.0x | 50 | 5600 | Expense · Operations | Active | FALSE | Site Cleanliness & Environmental Lead | Julian Clarkson | 2026-09-15 | 2026-09-15
LRC-028 | 6000.51.02 | Marshalling Yard & Dock Master | Contractor 1099 | Day Rate | 700 | 600 | 850 | 1.5x | 2.0x | 75 | 5600 | Expense · Operations | Active | FALSE | Freight Dispatch & Dock Master | Julian Clarkson | 2026-09-15 | 2026-09-15
LRC-029 | 6000.52.01 | Security Supervisor | Vendor Master | Day Rate | 600 | 500 | 750 | 1.5x | 2.0x | 75 | 5600 | Expense · Operations | Active | FALSE | Perimeter & Ingress Security Supervisor | Julian Clarkson | 2026-09-15 | 2026-09-15
LRC-030 | 7000.50.01 | Front of House Lead / Box Office Manager | Contractor 1099 | Day Rate | 650 | 500 | 800 | 1.5x | 2.0x | 75 | 5700 | Expense · Experience | Active | FALSE | Ingress & Box Office Lead | Julian Clarkson | 2026-09-15 | 2026-09-15
LRC-031 | 7000.50.02 | Credential Operations Coordinator | Contractor 1099 | Day Rate | 550 | 450 | 700 | 1.5x | 2.0x | 75 | 5700 | Expense · Experience | Active | FALSE | Master Credential & RFID Lead | Julian Clarkson | 2026-09-15 | 2026-09-15
LRC-032 | 7000.51.01 | Lead Event Paramedic / EMT | Vendor Master | Day Rate | 650 | 550 | 800 | 1.5x | 2.0x | 75 | 5700 | Expense · Experience | Active | FALSE | On-Site Medical & Triage Lead | Julian Clarkson | 2026-09-15 | 2026-09-15
LRC-033 | 8000.50.01 | Head Beverage Director / Bar Manager | Contractor 1099 | Day Rate | 700 | 550 | 850 | 1.5x | 2.0x | 75 | 5800 | Expense · Hospitality | Active | FALSE | Master Bar & Beverage Lead | Julian Clarkson | 2026-09-15 | 2026-09-15
LRC-034 | 8000.51.01 | Executive Catering Captain | Contractor 1099 | Day Rate | 650 | 500 | 800 | 1.5x | 2.0x | 75 | 5800 | Expense · Hospitality | Active | FALSE | Artist & Crew Catering Lead | Julian Clarkson | 2026-09-15 | 2026-09-15
LRC-035 | 9000.52.01 | Lead Network & Comms Engineer | Vendor Master | Day Rate | 850 | 700 | 1050 | 1.5x | 2.0x | 75 | 5900 | Expense · Technology | Active | FALSE | Core IT Network & RF Systems Lead | Julian Clarkson | 2026-09-15 | 2026-09-15

## Roles Library
ROLE CODE | JOB TITLE | DEPARTMENT | DISCIPLINE | RANK | JOB SUMMARY | KEY RESPONSIBILITIES | QUALIFICATIONS | PHYSICAL REQUIREMENTS | REQUIRED CERTIFICATIONS | DEFAULT CLEARANCE TIER | DEFAULT RADIO CHANNEL | STATUS | FLAG | NOTES | CREATED BY | CREATED AT | UPDATED AT
0000.50.01 | Chief Executive Officer | 0000 Executive | Governance & Client Relations | Executive | Overall executive leadership, commercial governance, and client stakeholder management. | Direct executive strategy; authorize major expenditures; represent production to partners. | 10+ years executive leadership in large-scale live productions. | Standard office & site walkthroughs. | Executive Leadership Certification | Tier 1 - Executive Master | Channel 1 (Emergency) | Active | FALSE | Canonical Executive Lead | Julian Clarkson | 2026-09-15 | 2026-09-15
1000.50.01 | Creative Director | 1000 Creative | Programming & Creative Direction | Director | Visionary oversight for artistic programming, scenic design, and guest creative experience. | Lead creative concepts, guide scenic aesthetics, curate artist programming cadence. | 8+ years creative direction in experiential entertainment. | Standard site walks across creative zones. | Creative Arts Degree or equivalent experience | Tier 1 - Executive Master | Channel 3 (Site Ops) | Active | FALSE | Canonical Creative Lead | Julian Clarkson | 2026-09-15 | 2026-09-15
1000.50.02 | Event & Programming Director | 1000 Creative | Programming & Creative Direction | Director | Curates talent lineup, schedules performance blocks, and coordinates talent logistics. | Manage talent booking, run-of-show synchronization, artist relations alignment. | 7+ years music industry and festival talent management. | Prolonged site presence during show run. | Talent Logistics & Artist Relations Certification | Tier 1 - Executive Master | Channel 3 (Site Ops) | Active | FALSE | Canonical Programming Lead | Julian Clarkson | 2026-09-15 | 2026-09-15
5000.50.01 | Production & Operations Director | 5000 Production | Production Leadership | Director | Senior technical director overseeing stage, site ops, logistics, and vendor integration. | Oversee multi-stage build, enforce master production schedule, direct site leads. | 10+ years festival technical direction and venue buildout. | Able to walk active construction grounds 10+ hrs/day. | OSHA 30, Rigging Inspection Certified | Tier 1 - Executive Master | Channel 3 (Site Ops) | Active | FALSE | Canonical Senior Production Lead | Julian Clarkson | 2026-09-15 | 2026-09-15
5000.50.02 | Master Electrician / Power Lead | 5000 Production | Power & Utilities | Lead Technician | Directs site power distribution, generator synchronization, and technical power safety. | Calculate load schedules, manage temporary generator banks, balance distribution panels. | 6+ years temporary power distribution for live events. | Able to lift 50 lbs, climb ladders, and work outdoors. | Licensed Master Electrician, NFPA 70E | Tier 2 - Technical Lead | Channel 5 (Power & IT) | Active | FALSE | Master Power Systems Lead | Julian Clarkson | 2026-09-15 | 2026-09-15
6000.50.01 | House Manager | 6000 Operations | House Management | Manager | Manages front of house operations, guest circulation, hospitality, and crowd services. | Supervise ushering, coordinate box office and access control, oversee ingress/egress. | 5+ years venue operations and public assembly management. | Continuous walking and standing during operating hours. | Crowd Management Certification, First Aid / CPR | Tier 1 - Executive Master | Channel 4 (Exterior Ops) | Active | FALSE | Canonical House Ops Lead | Julian Clarkson | 2026-09-15 | 2026-09-15
6000.50.02 | Site Safety & Security Lead | 6000 Operations | Safety & Security | Lead | Leads perimeter integrity, crowd safety protocols, emergency egress, and liaison with AHJ. | Direct private security deployment, coordinate with local fire/police, enforce security grid. | 7+ years event security management and law enforcement coordination. | High mobility across perimeter and venue grounds. | OSHA 30, Crowd Control Specialist, CPR/AED | Tier 2 - Technical Lead | Channel 2 (Security) | Active | FALSE | Perimeter & Incident Security | Julian Clarkson | 2026-09-15 | 2026-09-15
9000.50.01 | Production Stage Manager | 5000 Production | Stage Operations | Manager | Executes live run-of-show cues, stage deck turnover, and backline technical transitions. | Call stage cues, coordinate artist deck arrivals, enforce show schedule timing. | 6+ years calling major festival stages or theatrical productions. | Standing and moving backstage during full event duration. | Stage Management Association / OSHA 10 | Tier 2 - Technical Lead | Channel 7 (Stage Ops) | Active | FALSE | Lead Deck Stage Manager | Julian Clarkson | 2026-09-15 | 2026-09-15
9000.50.02 | Audio Engineer - A1/FOH | 5000 Production | Audio Systems | Lead Technician | Front-of-house engineer in charge of acoustic tuning, console mixing, and PA safety. | Mix FOH sound, optimize line array dispersion, oversee Dante audio networking. | 7+ years live concert audio engineering and system design. | Prolonged standing at mixing console, lifting 40 lbs. | Dante Level 3, SMAART Certification | Tier 2 - Technical Lead | Channel 8 (Audio) | Active | FALSE | Lead Audio Engineer FOH | Julian Clarkson | 2026-09-15 | 2026-09-15
9000.50.03 | Lighting Designer / LD | 5000 Production | Lighting Systems | Lead Technician | Programs dynamic visual show cues, operates GrandMA console, and supervises lighting rig. | Program show files, oversee fixture focus and truss hanging, execute show lighting. | 5+ years moving light programming and concert lighting design. | Prolonged console operation, comfortable with heights. | GrandMA3 Programmer Certified, ETCP Preferred | Tier 2 - Technical Lead | Channel 9 (Lighting) | Active | FALSE | Lead Lighting Programmer | Julian Clarkson | 2026-09-15 | 2026-09-15
9000.50.04 | Video Director / V1 | 5000 Production | Video Systems | Lead Technician | Supervises LED wall processors, live video switching, media server playback, and camera feeds. | Manage video switching, synchronize media servers, calibrate LED panels. | 5+ years live video playback and LED video wall engineering. | Sedentary video control position with rapid deck response. | Barco Certified, Disguise D3 Workflow Certified | Tier 2 - Technical Lead | Channel 7 (Stage Ops) | Active | FALSE | Lead Video & Media Engineer | Julian Clarkson | 2026-09-15 | 2026-09-15
0000.51.01 | Production Finance Director | 0000 Executive | Commercial and Finance | Director | Directs overall event fiscal governance, purchase commitments, payroll, and financial closeout. | Manage event pro forma, authorize vendor purchase orders, reconcile master production budget. | 8+ years live event production finance and commercial management. | Standard office & production trailer environment. | CPA or Master in Finance Preferred | Tier 1 - Executive Master | Channel 1 (Emergency) | Active | FALSE | Fiscal Governance Lead | Julian Clarkson | 2026-09-15 | 2026-09-15
1000.51.01 | Scenic Art Director | 1000 Creative | Scenic and Graphics Production | Lead | Oversees spatial styling, environmental scenic fabrication, and artistic installation fidelity. | Manage scenic fabrication vendors, direct scenic dressing, approve finish materials. | 6+ years theatrical or experiential scenic design and fabrication. | Active walking across build environments and scenic shops. | OSHA 10, Scenic Design Degree or equivalent | Tier 2 - Technical Lead | Channel 3 (Site Ops) | Active | FALSE | Scenic & Environment Lead | Julian Clarkson | 2026-09-15 | 2026-09-15
2000.50.01 | Backline Tech / Instrument Specialist | 2000 Talent | Talent Operations | Technician | Manages backline musical instruments, amplifier rigs, stage tuning, and artist rider fulfillment. | Set up drum kits, tune instrument rigs, execute stage changeovers, manage stage backline. | 5+ years concert touring and festival backline technical experience. | Able to lift 60 lbs, bend, crouch, and move heavy flight cases. | Backline Specialist Certification | Tier 2 - Technical Lead | Channel 7 (Stage Ops) | Active | FALSE | Stage Backline Lead | Julian Clarkson | 2026-09-15 | 2026-09-15
2000.50.02 | Artist Relations Coordinator | 2000 Talent | Talent Operations | Coordinator | Coordinates artist on-site arrivals, dressing room hospitality, green room protocol, and escort. | Advance rider hospitality, escort talent from transport to green rooms, oversee green room amenities. | 3+ years talent hospitality or artist relations at live events. | High mobility across backstage and dressing room corridors. | First Aid / CPR, Hospitality Management Degree | Tier 2 - Technical Lead | Channel 7 (Stage Ops) | Active | FALSE | Backstage Artist Care Lead | Julian Clarkson | 2026-09-15 | 2026-09-15
3000.50.01 | Principal Event Photographer | 3000 Marketing | Content Capture | Specialist | Leads on-site stills photography, red carpet documentation, and real-time social photo delivery. | Capture high-resolution show stills, edit daily hero photo packs, coordinate with social team. | 5+ years concert, festival, and live event production photography. | Continuous mobility across pit, stage wings, and crowd areas with heavy camera gear. | Professional Media Accreditation | Tier 2 - Technical Lead | Channel 6 (Media & Capture) | Active | FALSE | Lead Stills Photographer | Julian Clarkson | 2026-09-15 | 2026-09-15
3000.50.02 | Lead Cinematographer / Video Shooter | 3000 Marketing | Content Capture | Specialist | Captures 4K cinema footage of live performances, activations, and crowd atmosphere for marketing. | Operate gimbal and handheld camera rigs, direct B-roll capture, offload media to DIT. | 5+ years concert documentary and commercial video production. | High mobility carrying camera and stabilizer rigs up to 25 lbs. | FAA Part 107 (if drone), Cinema Camera Operator Certified | Tier 2 - Technical Lead | Channel 6 (Media & Capture) | Active | FALSE | Lead Live Video Capture | Julian Clarkson | 2026-09-15 | 2026-09-15
3000.50.03 | Real-Time Social Content Producer | 3000 Marketing | Content Capture | Coordinator | Produces real-time social cutdowns, story coverage, and live stream clips during event run. | Edit same-day social reels, publish scheduled story drops, coordinate artist social tags. | 3+ years live event social media publishing and mobile content editing. | High mobility throughout audience and VIP activations. | Social Content Specialist Certification | Tier 2 - Technical Lead | Channel 6 (Media & Capture) | Active | FALSE | Live Social Channel Producer | Julian Clarkson | 2026-09-15 | 2026-09-15
4000.50.01 | Structural Carpenter / Build Lead | 4000 Environment | Base Build Delivery | Lead Technician | Directs modular staging construction, custom scenic carpentry, and timber load-in builds. | Lead carpentry build crews, interpret technical CAD elevations, enforce shop safety standards. | 6+ years commercial carpentry or theatrical master carpentry. | Able to lift 75 lbs, operate heavy power tools, work at height. | OSHA 30, Master Carpenter Certification | Tier 2 - Technical Lead | Channel 3 (Site Ops) | Active | FALSE | Master Scenic Build Lead | Julian Clarkson | 2026-09-15 | 2026-09-15
4000.51.01 | HVAC & Site Climate Tech | 4000 Environment | Building Systems Maintenance | Technician | Maintains temporary AC units, tent spot coolers, ductwork runs, and venue air circulation. | Monitor cooling loads, fuel portable AC units, troubleshoot duct transitions, balance room temps. | 4+ years temporary climate control and HVAC equipment service. | Able to lift 50 lbs, crawl into mechanical plenum spaces, outdoor exposure. | EPA Universal HVAC, OSHA 10 | Tier 2 - Technical Lead | Channel 5 (Power & IT) | Active | FALSE | Site Environmental Climate Tech | Julian Clarkson | 2026-09-15 | 2026-09-15
5000.50.03 | Production Coordinator | 5000 Production | Production Leadership | Coordinator | Manages production office logistics, daily crew call sheets, vendor credentials, and radios. | Issue daily call sheets, log equipment deliveries, distribute radios and production expendables. | 3+ years live event or festival production office operations. | Active walking between production trailers and stage decks. | OSHA 10, Event Management Degree | Tier 2 - Technical Lead | Channel 3 (Site Ops) | Active | FALSE | Central Production Office Coordinator | Julian Clarkson | 2026-09-15 | 2026-09-15
5000.51.01 | Lead Stagehand / Deck Crew Chief | 5000 Production | Stage Crew | Crew Chief | Supervises stagehands during equipment load-in, stage turnover, changeovers, and load-out. | Direct push crews, organize truck pack loading, enforce deck safety, expedite gear turns. | 5+ years live stage crewing and union/non-union deck supervision. | Able to lift 75 lbs, prolonged standing and brisk walking across stage decks. | OSHA 10, Forklift Operator Certified | Tier 2 - Technical Lead | Channel 7 (Stage Ops) | Active | FALSE | Lead Stage Deck Crew Chief | Julian Clarkson | 2026-09-15 | 2026-09-15
5000.51.02 | Head Arena / Festival Rigger | 5000 Production | Stage Crew | Lead Technician | Calculates overhead rig loads, supervises motor hangs, truss pinning, and aerial safety. | Review engineered rigging plots, inspect wire rope and hardware, supervise high riggers. | 7+ years arena, festival, or theatrical overhead rigging leadership. | Comfortable working at extreme heights (60+ ft), full harness mobility, lifting 50 lbs. | ETCP Arena Rigging Certified, SPRAT/IRATA Rope Access | Tier 2 - Technical Lead | Channel 3 (Site Ops) | Active | FALSE | Head Overhead Rigging Specialist | Julian Clarkson | 2026-09-15 | 2026-09-15
5000.51.03 | Lead System Rigger | 5000 Production | Stage Crew | Technician | Executes high rigging hangs, bridle points, motor cable runs, and secondary safety tie-offs. | Climb steel structures, pull motor chains, attach beam clamps and spansets to engineered points. | 4+ years commercial entertainment high rigging. | Working at height, climbing truss and steel beams, heavy physical exertion. | ETCP Rigging Apprentice / ETCP Certified, OSHA 10 | Tier 2 - Technical Lead | Channel 3 (Site Ops) | Active | FALSE | High Steel Rigger | Julian Clarkson | 2026-09-15 | 2026-09-15
5000.52.01 | Special Effects / Pyro Lead | 5000 Production | Production Supply | Lead Technician | Operates CO2 cryo jets, cold spark machines, atmospheric hazers, and low-lying fog units. | Program SFX cue triggers, manage pressurized gas cylinders, enforce fire safety perimeter. | 5+ years theatrical special effects and atmospheric systems operation. | Handling heavy gas cylinders (100 lbs with dolly), outdoor and stage exposure. | State Pyrotechnic Operator License, NFPA 1126/160 Certified | Tier 2 - Technical Lead | Channel 7 (Stage Ops) | Active | FALSE | Lead SFX & Atmospherics Operator | Julian Clarkson | 2026-09-15 | 2026-09-15
6000.50.03 | VIP Experience Manager | 6000 Operations | House Management | Manager | Oversees VIP check-in lounge, bottle service coordination, luxury amenities, and guest escorts. | Manage VIP host team, coordinate private table allocations, supervise VIP credential gates. | 5+ years luxury hospitality or festival VIP lounge management. | Continuous standing and walking across VIP spaces. | TIPS / ServSafe Certified, Hospitality Leadership Degree | Tier 2 - Technical Lead | Channel 4 (Exterior Ops) | Active | FALSE | Lead VIP Guest Experience Manager | Julian Clarkson | 2026-09-15 | 2026-09-15
6000.51.01 | Janitorial & Waste Operations Lead | 6000 Operations | Venue Services | Lead | Directs ongoing venue cleanliness, restroom maintenance schedules, trash sorting, and recycling. | Supervise custodial crews, manage compactor cycles, maintain sanitation supply inventories. | 4+ years large venue or public assembly custodial operations. | Continuous physical movement, lifting 50 lbs waste containers. | OSHA 10, HazCom Sanitation Certified | Tier 3 - Staff / Crew | Channel 4 (Exterior Ops) | Active | FALSE | Site Cleanliness & Environmental Lead | Julian Clarkson | 2026-09-15 | 2026-09-15
6000.51.02 | Marshalling Yard & Dock Master | 6000 Operations | Venue Services | Manager | Controls semi-truck holding yard, freight check-in, load-in dock call times, and traffic flow. | Schedule truck dock calls, log bill of lading seals, coordinate forklift unloading sequence. | 6+ years freight logistics, festival marshalling, and transport dispatch. | High mobility across trucking yards, concrete staging aprons, all weather conditions. | DOT Compliance, CDL Class A Preferred | Tier 2 - Technical Lead | Channel 4 (Exterior Ops) | Active | FALSE | Freight Dispatch & Dock Master | Julian Clarkson | 2026-09-15 | 2026-09-15
6000.52.01 | Security Supervisor | 6000 Operations | Event Security | Supervisor | Supervises licensed guard posts, metal detector magnetometers, bag check lanes, and ejections. | Deploy security officers, de-escalate patron disturbances, maintain incident dispatch logs. | 5+ years crowd control security supervision and emergency de-escalation. | Prolonged standing, high physical readiness in crowd environments. | State Security D/G License, First Aid / CPR / AED | Tier 2 - Technical Lead | Channel 2 (Security) | Active | FALSE | Perimeter & Ingress Security Supervisor | Julian Clarkson | 2026-09-15 | 2026-09-15
7000.50.01 | Front of House Lead / Box Office Manager | 7000 Experience | Front of House | Manager | Manages main entrance turnstiles, ticket resolution booths, guest service info desks, and ADA access. | Supervise ticket scanning teams, resolve ticketing exceptions, enforce ADA accessible routes. | 5+ years venue box office management and guest service leadership. | Prolonged standing at entrance gates and patron ingress corridors. | Box Office System Certified, Crowd Management Certified | Tier 2 - Technical Lead | Channel 4 (Exterior Ops) | Active | FALSE | Ingress & Box Office Lead | Julian Clarkson | 2026-09-15 | 2026-09-15
7000.50.02 | Credential Operations Coordinator | 7000 Experience | Front of House | Coordinator | Issues RFID wristbands, crew badges, vehicle passes, and enforces zone access permissions. | Program RFID credentials, audit zone permissions against roster, verify daily photo IDs. | 3+ years event accreditation and access credentialing administration. | Prolonged desk and check-in window operations. | Access Control System Administrator Certified | Tier 2 - Technical Lead | Channel 4 (Exterior Ops) | Active | FALSE | Master Credential & RFID Lead | Julian Clarkson | 2026-09-15 | 2026-09-15
7000.51.01 | Lead Event Paramedic / EMT | 7000 Experience | Guest Safety | Specialist | Manages on-site medical tent, triage protocols, minor injury care, and ambulance dispatch liaison. | Deliver immediate emergency life support, record patient triage logs, liaise with local EMS. | 5+ years emergency medical services and mass gathering event medicine. | Rapid response mobility, ability to carry medical trauma kits (40 lbs). | Licensed Paramedic / EMT-P, ACLS, PALS, CPR/AED | Tier 2 - Technical Lead | Channel 2 (Security) | Active | FALSE | On-Site Medical & Triage Lead | Julian Clarkson | 2026-09-15 | 2026-09-15
8000.50.01 | Head Beverage Director / Bar Manager | 8000 Hospitality | Beverage Service | Manager | Directs multi-station bar operations, draft beer lines, POS reconciliation, and liquor inventory. | Manage bar staff, track spirits depletion against cash/card receipts, oversee ice and garnish prep. | 6+ years high-volume festival or nightlife beverage management. | Continuous standing, lifting kegs (160 lbs with dolly) and liquor cases (45 lbs). | ServSafe Alcohol, TIPS Certified, FL Responsible Vendor | Tier 2 - Technical Lead | Channel 4 (Exterior Ops) | Active | FALSE | Master Bar & Beverage Lead | Julian Clarkson | 2026-09-15 | 2026-09-15
8000.51.01 | Executive Catering Captain | 8000 Hospitality | Catering Service | Manager | Supervises artist dressing room food service, crew meal buffets, dietary accommodations, and chafers. | Coordinate hot meal timing with show stage schedule, monitor buffet sanitation, manage servers. | 5+ years concert touring, festival, or corporate executive catering. | Continuous standing, walking between catering kitchens and green rooms, lifting 35 lbs. | ServSafe Food Manager Certified, Allergen Awareness Certified | Tier 2 - Technical Lead | Channel 4 (Exterior Ops) | Active | FALSE | Artist & Crew Catering Lead | Julian Clarkson | 2026-09-15 | 2026-09-15
9000.52.01 | Lead Network & Comms Engineer | 9000 Technology | Venue IT | Lead Technician | Deploys event core routers, managed switches, fiber optic trunks, high-density guest WiFi, and RF radios. | Configure VLAN segmentation, manage wireless access points, coordinate radio frequencies. | 6+ years temporary live event IT network infrastructure and RF coordination. | Able to lift 50 lbs, climb ladders, pull fiber runs through cable ramps. | Cisco CCNA / Network+, Shure RF Coordinator Certified | Tier 2 - Technical Lead | Channel 5 (Power & IT) | Active | FALSE | Core IT Network & RF Systems Lead | Julian Clarkson | 2026-09-15 | 2026-09-15

## Credential Issuance
RECORD ID | ORGANIZATION | PROJECT ID | DEPARTMENT | CATEGORY | SUB CATEGORY | CREDENTIAL SERIAL | PERSONNEL ID | VENDOR ID | CLEARANCE TIER | CREDENTIAL TYPE | ZONE ACCESS | ISSUED DATE | RETURN STATUS | STATUS | FLAG | NOTES | CREATED BY | CREATED AT | UPDATED AT
CRD-001 | GHXSTSHIP | CSMIA26 | 0000 Executive | 0.5 | Credentials | SER-001 | P-001 | VEN-016 | Tier 1 - Executive Master | All Access | All Zones | 2026-09-01 | Issued | Active | FALSE | Master executive badge | Julian Clarkson | 2026-09-15 | 2026-09-15
CRD-002 | GHXSTSHIP | CSMIA26 | 1000 Creative | 1000.5 | Credentials | SER-002 | P-005 | VEN-017 | Tier 1 - Executive Master | All Access | All Zones | 2026-09-01 | Issued | Active | FALSE | Creative director badge | Julian Clarkson | 2026-09-15 | 2026-09-15
CRD-003 | GHXSTSHIP | CSMIA26 | 6000 Operations | 6000.5 | Credentials | SER-003 | P-016 | VEN-016 | Tier 1 - Executive Master | All Access | All Zones | 2026-09-01 | Issued | Active | FALSE | House manager badge | Julian Clarkson | 2026-09-15 | 2026-09-15
CRD-004 | GHXSTSHIP | CSMIA26 | 5000 Production | 5000.5 | Credentials | SER-004 | P-021 | VEN-016 | Tier 1 - Executive Master | All Access | All Zones | 2026-09-01 | Issued | Active | FALSE | Production director badge | Julian Clarkson | 2026-09-15 | 2026-09-15
CRD-005 | GHXSTSHIP | CSMIA26 | 5000 Production | 5000.5 | Credentials | SER-005 | P-024 | VEN-015 | Tier 2 - Technical Lead | Production | Stage & FOH | 2026-10-01 | Issued | Active | FALSE | FOH audio engineer badge | Julian Clarkson | 2026-09-15 | 2026-09-15
CRD-006 | GHXSTSHIP | CSMIA26 | 1000 Creative | 1000.5 | Credentials | SER-006 | P-006 | VEN-016 | Tier 1 - Executive Master | All Access | All Zones | 2026-08-01 | Issued | Active | FALSE | Event & programming director badge | Julian Clarkson | 2026-09-15 | 2026-09-15

## Access Grid
RECORD ID | ORGANIZATION | PROJECT ID | DEPARTMENT | CATEGORY | SUB CATEGORY | CREDENTIAL | ACCESS POINT | ACCESS LEVEL | CAPACITY | STATUS | FLAG | NOTES | CREATED BY | CREATED AT | UPDATED AT

## Budget Expenses
RECORD ID | PROJECT ID | EVENT | LOCATION | ZONE | SPACE | ACTIVATION | DEPARTMENT | DISCIPLINE | CATEGORY | SUB CATEGORY | ITEM | DESCRIPTION | URID | PHASE | TIER | XYZ | LINE TYPE | QUANTITY | RATE | UNIT BASIS | ESTIMATE | BUDGET | COMMITTED | FORECAST | ACTUAL | VARIANCE | VENDOR | STATUS | FLAG | EXTERNAL NOTES | INTERNAL NOTES | ACCOUNT CODE | ACCOUNT NAME | COST CENTER | URID DIMENSION | TAX TYPE | CURRENCY | CREATED BY | CREATED AT | UPDATED AT
BUD-0001 | CSMIA26 | Event 00 · Venue Startup | The Sanctuary MiMo |  |  |  | 0000 Executive | 0000.01 Executive Leadership & Strategy | Production Leadership | N/A |  |  | 0000.01.01 | Advance | 04 Physical | X | Scope |  | 0 |  |  |  | 0 | 0 |  | 0 |  | Open | FALSE |  |  | 5000 | Expense · Executive | CC-CORP | 0000.01.01 | Tax on Purchases | USD | Julian Clarkson | 2026-09-30 13:05:00 | 2026-09-30 13:05:00
BUD-0002 | CSMIA26 | Event 00 · Venue Startup | The Sanctuary MiMo |  |  |  | 0000 Executive | 0000.02 Finance & Accounting | Production Accounting | N/A |  |  | 0000.02.01 | Advance | 04 Physical | X | Scope |  | 0 |  |  |  | 0 | 0 |  | 0 |  | Open | FALSE |  |  | 5000 | Expense · Executive | CC-VENUE | 0000.02.01 | Tax on Purchases | USD | Julian Clarkson | 2026-09-30 13:05:00 | 2026-09-30 13:05:00
BUD-0003 | CSMIA26 | Event 00 · Venue Startup | The Sanctuary MiMo |  |  |  | 0000 Executive | 0000.03 Legal & Risk | Legal Services | N/A |  |  | 0000.03.01 | Advance | 04 Physical | X | Scope |  | 0 |  |  |  | 0 | 0 |  | 0 |  | Open | FALSE |  |  | 5000 | Expense · Executive | CC-VENUE | 0000.03.01 | Tax on Purchases | USD | Julian Clarkson | 2026-09-30 13:05:00 | 2026-09-30 13:05:00
BUD-0004 | CSMIA26 | Event 00 · Venue Startup | The Sanctuary MiMo |  |  |  | 0000 Executive | 0000.04 Human Resources & People | People Operations | N/A |  |  | 0000.04.01 | Advance | 04 Physical | X | Scope |  | 0 |  |  |  | 0 | 0 |  | 0 |  | Open | FALSE |  |  | 5000 | Expense · Executive | CC-VENUE | 0000.04.01 | Tax on Purchases | USD | Julian Clarkson | 2026-09-30 13:05:00 | 2026-09-30 13:05:00
BUD-0005 | CSMIA26 | Event 00 · Venue Startup | The Sanctuary MiMo |  |  |  | 0000 Executive | 0000.05 Business Development & Partnerships | Business Development | N/A |  |  | 0000.05.01 | Advance | 04 Physical | X | Scope |  | 0 |  |  |  | 0 | 0 |  | 0 |  | Open | FALSE |  |  | 5000 | Expense · Executive | CC-VENUE | 0000.05.01 | Tax on Purchases | USD | Julian Clarkson | 2026-09-30 13:05:00 | 2026-09-30 13:05:00
BUD-0006 | CSMIA26 | Event 00 · Venue Startup | The Sanctuary MiMo |  |  |  | 0000 Executive | 0000.06 Insurance & Permitting | Insurance | N/A |  |  | 0000.06.01 | Advance | 04 Physical | X | Scope |  | 0 |  |  |  | 0 | 0 |  | 0 |  | Open | FALSE |  |  | 5000 | Expense · Executive | CC-VENUE | 0000.06.01 | Tax on Purchases | USD | Julian Clarkson | 2026-09-30 13:05:00 | 2026-09-30 13:05:00
BUD-0007 | CSMIA26 | Event 00 · Venue Startup | The Sanctuary MiMo |  |  |  | 0000 Executive | 0000.06 Insurance & Permitting | Permitting | N/A |  |  | 0000.06.02 | Advance | 04 Physical | X | Scope |  | 0 |  |  |  | 0 | 0 |  | 0 |  | Open | FALSE |  |  | 5000 | Expense · Executive | CC-VENUE | 0000.06.02 | Tax on Purchases | USD | Julian Clarkson | 2026-09-30 13:05:00 | 2026-09-30 13:05:00
BUD-0008 | CSMIA26 | Event 00 · Venue Startup | The Sanctuary MiMo |  |  |  | 0000 Executive | 0000.50 Governance and Client Relations | Client Sponsorship | N/A |  |  | 0000.50.01 | Advance | 04 Physical | Y | Scope |  | 0 |  |  |  | 0 | 0 |  | 0 |  | Open | FALSE |  |  | 5000 | Expense · Executive | CC-VENUE | 0000.50.01 | Tax on Purchases | USD | Julian Clarkson | 2026-09-30 13:05:00 | 2026-09-30 13:05:00
BUD-0009 | CSMIA26 | Event 00 · Venue Startup | The Sanctuary MiMo |  |  |  | 0000 Executive | 0000.50 Governance and Client Relations | Operator Leadership | N/A |  |  | 0000.50.02 | Advance | 04 Physical | Y | Scope |  | 0 |  |  |  | 0 | 0 |  | 0 |  | Open | FALSE |  |  | 5000 | Expense · Executive | CC-VENUE | 0000.50.02 | Tax on Purchases | USD | Julian Clarkson | 2026-09-30 13:05:00 | 2026-09-30 13:05:00
BUD-0010 | CSMIA26 | Event 00 · Venue Startup | The Sanctuary MiMo |  |  |  | 0000 Executive | 0000.50 Governance and Client Relations | Approval Authority | N/A |  |  | 0000.50.03 | Advance | 04 Physical | Y | Scope |  | 0 |  |  |  | 0 | 0 |  | 0 |  | Open | FALSE |  |  | 5000 | Expense · Executive | CC-VENUE | 0000.50.03 | Tax on Purchases | USD | Julian Clarkson | 2026-09-30 13:05:00 | 2026-09-30 13:05:00
BUD-0011 | CSMIA26 | Event 00 · Venue Startup | The Sanctuary MiMo |  |  |  | 0000 Executive | 0000.51 Commercial and Finance | Financial Control | N/A |  |  | 0000.51.01 | Advance | 04 Physical | Y | Scope |  | 0 |  |  |  | 0 | 0 |  | 0 |  | Open | FALSE |  |  | 5000 | Expense · Executive | CC-CORP | 0000.51.01 | Tax on Purchases | USD | Julian Clarkson | 2026-09-30 13:05:00 | 2026-09-30 13:05:00
BUD-0012 | CSMIA26 | Event 00 · Venue Startup | The Sanctuary MiMo |  |  |  | 0000 Executive | 0000.51 Commercial and Finance | Insurance and Risk | N/A |  |  | 0000.51.02 | Advance | 04 Physical | Y | Scope |  | 0 |  |  |  | 0 | 0 |  | 0 |  | Open | FALSE |  |  | 5000 | Expense · Executive | CC-CORP | 0000.51.02 | Tax on Purchases | USD | Julian Clarkson | 2026-09-30 13:05:00 | 2026-09-30 13:05:00
BUD-0013 | CSMIA26 | Event 00 · Venue Startup | The Sanctuary MiMo |  |  |  | 0000 Executive | 0000.51 Commercial and Finance | Legal Counsel | N/A |  |  | 0000.51.03 | Advance | 04 Physical | Y | Scope |  | 0 |  |  |  | 0 | 0 |  | 0 |  | Open | FALSE |  |  | 5000 | Expense · Executive | CC-CORP | 0000.51.03 | Tax on Purchases | USD | Julian Clarkson | 2026-09-30 13:05:00 | 2026-09-30 13:05:00
BUD-0014 | CSMIA26 | Event 00 · Venue Startup | The Sanctuary MiMo |  |  |  | 1000 Creative | 1000.01 Creative Direction | Creative Direction | N/A |  |  | 1000.01.01 | Advance | 04 Physical | X | Scope |  | 0 |  |  |  | 0 | 0 |  | 0 |  | Open | FALSE |  |  | 5100 | Expense · Creative | CC-VENUE | 1000.01.01 | Tax on Purchases | USD | Julian Clarkson | 2026-09-30 13:05:00 | 2026-09-30 13:05:00
BUD-0015 | CSMIA26 | Event 00 · Venue Startup | The Sanctuary MiMo |  |  |  | 1000 Creative | 1000.02 Experiential & Environment Design | Environment Design | N/A |  |  | 1000.02.01 | Advance | 04 Physical | X | Scope |  | 0 |  |  |  | 0 | 0 |  | 0 |  | Open | FALSE |  |  | 5100 | Expense · Creative | CC-VENUE | 1000.02.01 | Tax on Purchases | USD | Julian Clarkson | 2026-09-30 13:05:00 | 2026-09-30 13:05:00
BUD-0016 | CSMIA26 | Event 00 · Venue Startup | The Sanctuary MiMo |  |  |  | 1000 Creative | 1000.03 Brand & Identity Design | Brand Design | N/A |  |  | 1000.03.01 | Advance | 04 Physical | X | Scope |  | 0 |  |  |  | 0 | 0 |  | 0 |  | Open | FALSE |  |  | 5100 | Expense · Creative | CC-VENUE | 1000.03.01 | Tax on Purchases | USD | Julian Clarkson | 2026-09-30 13:05:00 | 2026-09-30 13:05:00
BUD-0017 | CSMIA26 | Event 00 · Venue Startup | The Sanctuary MiMo |  |  |  | 1000 Creative | 1000.04 Graphic & 2D Design | Graphic Design | N/A |  |  | 1000.04.01 | Advance | 04 Physical | X | Scope |  | 0 |  |  |  | 0 | 0 |  | 0 |  | Open | FALSE |  |  | 5100 | Expense · Creative | CC-VENUE | 1000.04.01 | Tax on Purchases | USD | Julian Clarkson | 2026-09-30 13:05:00 | 2026-09-30 13:05:00
BUD-0018 | CSMIA26 | Event 00 · Venue Startup | The Sanctuary MiMo |  |  |  | 1000 Creative | 1000.04 Graphic & 2D Design | Print Collateral | N/A |  |  | 1000.04.02 | Advance | 04 Physical | X | Scope |  | 0 |  |  |  | 0 | 0 |  | 0 |  | Open | FALSE |  |  | 5100 | Expense · Creative | CC-VENUE | 1000.04.02 | Tax on Purchases | USD | Julian Clarkson | 2026-09-30 13:05:00 | 2026-09-30 13:05:00
BUD-0019 | CSMIA26 | Event 00 · Venue Startup | The Sanctuary MiMo |  |  |  | 1000 Creative | 1000.05 Content Production | Content Production | N/A |  |  | 1000.05.01 | Advance | 04 Physical | X | Scope |  | 0 |  |  |  | 0 | 0 |  | 0 |  | Open | FALSE |  |  | 5100 | Expense · Creative | CC-VENUE | 1000.05.01 | Tax on Purchases | USD | Julian Clarkson | 2026-09-30 13:05:00 | 2026-09-30 13:05:00
BUD-0020 | CSMIA26 | Event 00 · Venue Startup | The Sanctuary MiMo |  |  |  | 1000 Creative | 1000.05 Content Production | Sonic Branding | N/A |  |  | 1000.05.02 | Advance | 04 Physical | X | Scope |  | 0 |  |  |  | 0 | 0 |  | 0 |  | Open | FALSE |  |  | 5100 | Expense · Creative | CC-VENUE | 1000.05.02 | Tax on Purchases | USD | Julian Clarkson | 2026-09-30 13:05:00 | 2026-09-30 13:05:00
BUD-0021 | CSMIA26 | Event 00 · Venue Startup | The Sanctuary MiMo |  |  |  | 1000 Creative | 1000.06 Copywriting & Verbal Identity | Verbal Identity | N/A |  |  | 1000.06.01 | Advance | 04 Physical | X | Scope |  | 0 |  |  |  | 0 | 0 |  | 0 |  | Open | FALSE |  |  | 5100 | Expense · Creative | CC-VENUE | 1000.06.01 | Tax on Purchases | USD | Julian Clarkson | 2026-09-30 13:05:00 | 2026-09-30 13:05:00
BUD-0022 | CSMIA26 | Event 00 · Venue Startup | The Sanctuary MiMo |  |  |  | 1000 Creative | 1000.07 Digital & Interactive Design | Digital Design | N/A |  |  | 1000.07.01 | Advance | 04 Physical | X | Scope |  | 0 |  |  |  | 0 | 0 |  | 0 |  | Open | FALSE |  |  | 5100 | Expense · Creative | CC-VENUE | 1000.07.01 | Tax on Purchases | USD | Julian Clarkson | 2026-09-30 13:05:00 | 2026-09-30 13:05:00
BUD-0023 | CSMIA26 | Event 00 · Venue Startup | The Sanctuary MiMo |  |  |  | 1000 Creative | 1000.08 Intellectual Property & Licensing | Intellectual Property & Licensing | N/A |  |  | 1000.08.01 | Advance | 04 Physical | X | Scope |  | 0 |  |  |  | 0 | 0 |  | 0 |  | Open | FALSE |  |  | 5100 | Expense · Creative | CC-VENUE | 1000.08.01 | Tax on Purchases | USD | Julian Clarkson | 2026-09-30 13:05:00 | 2026-09-30 13:05:00
BUD-0024 | CSMIA26 | Event 00 · Venue Startup | The Sanctuary MiMo |  |  |  | 1000 Creative | 1000.50 Programming and Creative Direction | Creative Direction | N/A |  |  | 1000.50.01 | Advance | 04 Physical | Y | Scope |  | 0 |  |  |  | 0 | 0 |  | 0 |  | Open | FALSE |  |  | 5100 | Expense · Creative | CC-VENUE | 1000.50.01 | Tax on Purchases | USD | Julian Clarkson | 2026-09-30 13:05:00 | 2026-09-30 13:05:00
BUD-0025 | CSMIA26 | Event 00 · Venue Startup | The Sanctuary MiMo |  |  |  | 1000 Creative | 1000.50 Programming and Creative Direction | Programming Lead | N/A |  |  | 1000.50.02 | Advance | 04 Physical | Y | Scope |  | 0 |  |  |  | 0 | 0 |  | 0 |  | Open | FALSE |  |  | 5100 | Expense · Creative | CC-VENUE | 1000.50.02 | Tax on Purchases | USD | Julian Clarkson | 2026-09-30 13:05:00 | 2026-09-30 13:05:00
BUD-0026 | CSMIA26 | Event 00 · Venue Startup | The Sanctuary MiMo |  |  |  | 1000 Creative | 1000.51 Scenic and Graphics Production | Signage Fabrication | N/A |  |  | 1000.51.01 | Advance | 04 Physical | Y | Scope |  | 5200 |  |  |  | 5200 | 5200 |  | 0 |  | Open | FALSE |  |  | 5100 | Expense · Creative | CC-VENUE | 1000.51.01 | Tax on Purchases | USD | Julian Clarkson | 2026-09-30 13:05:00 | 2026-09-30 13:05:00
BUD-0027 | CSMIA26 | Event 00 · Venue Startup | The Sanctuary MiMo |  |  |  | 1000 Creative | 1000.51 Scenic and Graphics Production | Scenic Fabrication | N/A |  |  | 1000.51.02 | Advance | 04 Physical | Y | Scope |  | 0 |  |  |  | 0 | 0 |  | 0 |  | Open | FALSE |  |  | 5100 | Expense · Creative | CC-VENUE | 1000.51.02 | Tax on Purchases | USD | Julian Clarkson | 2026-09-30 13:05:00 | 2026-09-30 13:05:00
BUD-0028 | CSMIA26 | Event 00 · Venue Startup | The Sanctuary MiMo |  |  |  | 2000 Talent | 2000.01 Artist Booking & Programming | Booking | N/A |  |  | 2000.01.01 | Engage | 04 Physical | X | Scope |  | 0 |  |  |  | 0 | 0 |  | 0 |  | Open | FALSE |  |  | 5200 | Expense · Talent | CC-VENUE | 2000.01.01 | Tax on Purchases | USD | Julian Clarkson | 2026-09-30 13:05:00 | 2026-09-30 13:05:00
BUD-0029 | CSMIA26 | Event 00 · Venue Startup | The Sanctuary MiMo |  |  |  | 2000 Talent | 2000.02 Music Programming & Curation | Curation | N/A |  |  | 2000.02.01 | Engage | 04 Physical | X | Scope |  | 0 |  |  |  | 0 | 0 |  | 0 |  | Open | FALSE |  |  | 5200 | Expense · Talent | CC-VENUE | 2000.02.01 | Tax on Purchases | USD | Julian Clarkson | 2026-09-30 13:05:00 | 2026-09-30 13:05:00
BUD-0030 | CSMIA26 | Event 00 · Venue Startup | The Sanctuary MiMo |  |  |  | 2000 Talent | 2000.02 Music Programming & Curation | Set Programming | N/A |  |  | 2000.02.02 | Engage | 04 Physical | X | Scope |  | 0 |  |  |  | 0 | 0 |  | 0 |  | Open | FALSE |  |  | 5200 | Expense · Talent | CC-VENUE | 2000.02.02 | Tax on Purchases | USD | Julian Clarkson | 2026-09-30 13:05:00 | 2026-09-30 13:05:00
BUD-0031 | CSMIA26 | Event 00 · Venue Startup | The Sanctuary MiMo |  |  |  | 2000 Talent | 2000.03 Talent Advancing & Riders | Advancing | N/A |  |  | 2000.03.01 | Engage | 04 Physical | X | Scope |  | 0 |  |  |  | 0 | 0 |  | 0 |  | Open | FALSE |  |  | 5200 | Expense · Talent | CC-VENUE | 2000.03.01 | Tax on Purchases | USD | Julian Clarkson | 2026-09-30 13:05:00 | 2026-09-30 13:05:00
BUD-0032 | CSMIA26 | Event 00 · Venue Startup | The Sanctuary MiMo |  |  |  | 2000 Talent | 2000.04 Casting (Performers & Ambassadors) | Casting | N/A |  |  | 2000.04.01 | Engage | 04 Physical | X | Scope |  | 0 |  |  |  | 0 | 0 |  | 0 |  | Open | FALSE |  |  | 5200 | Expense · Talent | CC-VENUE | 2000.04.01 | Tax on Purchases | USD | Julian Clarkson | 2026-09-30 13:05:00 | 2026-09-30 13:05:00
BUD-0033 | CSMIA26 | Event 00 · Venue Startup | The Sanctuary MiMo |  |  |  | 2000 Talent | 2000.05 Speakers, Hosts & MC | Hosts | N/A |  |  | 2000.05.01 | Engage | 04 Physical | X | Scope |  | 0 |  |  |  | 0 | 0 |  | 0 |  | Open | FALSE |  |  | 5200 | Expense · Talent | CC-VENUE | 2000.05.01 | Tax on Purchases | USD | Julian Clarkson | 2026-09-30 13:05:00 | 2026-09-30 13:05:00
BUD-0034 | CSMIA26 | Event 00 · Venue Startup | The Sanctuary MiMo |  |  |  | 2000 Talent | 2000.06 Talent Settlement & Payments | Settlement | N/A |  |  | 2000.06.01 | Engage | 04 Physical | X | Scope |  | 0 |  |  |  | 0 | 0 |  | 0 |  | Open | FALSE |  |  | 5200 | Expense · Talent | CC-VENUE | 2000.06.01 | Tax on Purchases | USD | Julian Clarkson | 2026-09-30 13:05:00 | 2026-09-30 13:05:00
BUD-0035 | CSMIA26 | Event 00 · Venue Startup | The Sanctuary MiMo |  |  |  | 2000 Talent | 2000.07 Talent Travel & Hospitality Coordination | Talent Travel & Hospitality Coordination | N/A |  |  | 2000.07.01 | Engage | 04 Physical | X | Scope |  | 0 |  |  |  | 0 | 0 |  | 0 |  | Open | FALSE |  |  | 5200 | Expense · Talent | CC-VENUE | 2000.07.01 | Tax on Purchases | USD | Julian Clarkson | 2026-09-30 13:05:00 | 2026-09-30 13:05:00
BUD-0036 | CSMIA26 | Event 00 · Venue Startup | The Sanctuary MiMo |  |  |  | 2000 Talent | 2000.50 Talent Operations | Backline Technical | N/A |  |  | 2000.50.01 | Engage | 04 Physical | Y | Scope |  | 0 |  |  |  | 0 | 0 |  | 0 |  | Open | FALSE |  |  | 5200 | Expense · Talent | CC-VENUE | 2000.50.01 | Tax on Purchases | USD | Julian Clarkson | 2026-09-30 13:05:00 | 2026-09-30 13:05:00
BUD-0037 | CSMIA26 | Event 00 · Venue Startup | The Sanctuary MiMo |  |  |  | 3000 Marketing | 3000.01 Brand Marketing & Campaign | Campaign | N/A |  |  | 3000.01.01 | Advance | 04 Physical | X | Scope |  | 0 |  |  |  | 0 | 0 |  | 0 |  | Open | FALSE |  |  | 5300 | Expense · Marketing | CC-VENUE | 3000.01.01 | Tax on Purchases | USD | Julian Clarkson | 2026-09-30 13:05:00 | 2026-09-30 13:05:00
BUD-0038 | CSMIA26 | Event 00 · Venue Startup | The Sanctuary MiMo |  |  |  | 3000 Marketing | 3000.02 Social Media & Community | Social | N/A |  |  | 3000.02.01 | Advance | 04 Physical | X | Scope |  | 0 |  |  |  | 0 | 0 |  | 0 |  | Open | FALSE |  |  | 5300 | Expense · Marketing | CC-VENUE | 3000.02.01 | Tax on Purchases | USD | Julian Clarkson | 2026-09-30 13:05:00 | 2026-09-30 13:05:00
BUD-0039 | CSMIA26 | Event 00 · Venue Startup | The Sanctuary MiMo |  |  |  | 3000 Marketing | 3000.03 Public Relations & Press | Public Relations | N/A |  |  | 3000.03.01 | Advance | 04 Physical | X | Scope |  | 0 |  |  |  | 0 | 0 |  | 0 |  | Open | FALSE |  |  | 5300 | Expense · Marketing | CC-VENUE | 3000.03.01 | Tax on Purchases | USD | Julian Clarkson | 2026-09-30 13:05:00 | 2026-09-30 13:05:00
BUD-0040 | CSMIA26 | Event 00 · Venue Startup | The Sanctuary MiMo |  |  |  | 3000 Marketing | 3000.04 Sponsorship Sales | Sponsorship | N/A |  |  | 3000.04.01 | Advance | 04 Physical | X | Scope |  | 0 |  |  |  | 0 | 0 |  | 0 |  | Open | FALSE |  |  | 5300 | Expense · Marketing | CC-VENUE | 3000.04.01 | Tax on Purchases | USD | Julian Clarkson | 2026-09-30 13:05:00 | 2026-09-30 13:05:00
BUD-0041 | CSMIA26 | Event 00 · Venue Startup | The Sanctuary MiMo |  |  |  | 3000 Marketing | 3000.05 CRM & Audience Data | CRM | N/A |  |  | 3000.05.01 | Advance | 04 Physical | X | Scope |  | 0 |  |  |  | 0 | 0 |  | 0 |  | Open | FALSE |  |  | 5300 | Expense · Marketing | CC-VENUE | 3000.05.01 | Tax on Purchases | USD | Julian Clarkson | 2026-09-30 13:05:00 | 2026-09-30 13:05:00
BUD-0042 | CSMIA26 | Event 00 · Venue Startup | The Sanctuary MiMo |  |  |  | 3000 Marketing | 3000.06 Advertising & Media Buying | Media | N/A |  |  | 3000.06.01 | Advance | 04 Physical | X | Scope |  | 0 |  |  |  | 0 | 0 |  | 0 |  | Open | FALSE |  |  | 5300 | Expense · Marketing | CC-VENUE | 3000.06.01 | Tax on Purchases | USD | Julian Clarkson | 2026-09-30 13:05:00 | 2026-09-30 13:05:00
BUD-0043 | CSMIA26 | Event 00 · Venue Startup | The Sanctuary MiMo |  |  |  | 3000 Marketing | 3000.07 Influencer & Creator Relations | Influencer | N/A |  |  | 3000.07.01 | Advance | 04 Physical | X | Scope |  | 0 |  |  |  | 0 | 0 |  | 0 |  | Open | FALSE |  |  | 5300 | Expense · Marketing | CC-VENUE | 3000.07.01 | Tax on Purchases | USD | Julian Clarkson | 2026-09-30 13:05:00 | 2026-09-30 13:05:00
BUD-0044 | CSMIA26 | Event 00 · Venue Startup | The Sanctuary MiMo |  |  |  | 3000 Marketing | 3000.50 Content Capture | Stills Capture | N/A |  |  | 3000.50.01 | Advance | 04 Physical | Y | Scope |  | 0 |  |  |  | 0 | 0 |  | 0 |  | Open | FALSE |  |  | 5300 | Expense · Marketing | CC-VENUE | 3000.50.01 | Tax on Purchases | USD | Julian Clarkson | 2026-09-30 13:05:00 | 2026-09-30 13:05:00
BUD-0045 | CSMIA26 | Event 00 · Venue Startup | The Sanctuary MiMo |  |  |  | 3000 Marketing | 3000.50 Content Capture | Motion Capture | N/A |  |  | 3000.50.02 | Advance | 04 Physical | Y | Scope |  | 0 |  |  |  | 0 | 0 |  | 0 |  | Open | FALSE |  |  | 5300 | Expense · Marketing | CC-VENUE | 3000.50.02 | Tax on Purchases | USD | Julian Clarkson | 2026-09-30 13:05:00 | 2026-09-30 13:05:00
BUD-0046 | CSMIA26 | Event 00 · Venue Startup | The Sanctuary MiMo |  |  |  | 3000 Marketing | 3000.50 Content Capture | Content Direction | N/A |  |  | 3000.50.03 | Advance | 04 Physical | Y | Scope |  | 0 |  |  |  | 0 | 0 |  | 0 |  | Open | FALSE |  |  | 5300 | Expense · Marketing | CC-VENUE | 3000.50.03 | Tax on Purchases | USD | Julian Clarkson | 2026-09-30 13:05:00 | 2026-09-30 13:05:00
BUD-0047 | CSMIA26 | Event 00 · Venue Startup | The Sanctuary MiMo |  |  |  | 3000 Marketing | 3000.51 Audience Platforms | Guest List and RSVP Platform | N/A |  |  | 3000.51.01 | Advance | 04 Physical | Y | Scope |  | 0 |  |  |  | 0 | 0 |  | 0 |  | Open | FALSE |  |  | 5300 | Expense · Marketing | CC-VENUE | 3000.51.01 | Tax on Purchases | USD | Julian Clarkson | 2026-09-30 13:05:00 | 2026-09-30 13:05:00
BUD-0048 | CSMIA26 | Event 00 · Venue Startup | The Sanctuary MiMo |  |  |  | 4000 Environment | 4000.01 Construction & Carpentry | General Tools & Hardware | N/A |  |  | 4000.01.01 | Install | 04 Physical | X | Scope |  | 0 |  |  |  | 0 | 0 |  | 0 |  | Open | FALSE |  |  | 5400 | Expense · Environment | CC-VENUE | 4000.01.01 | Tax on Purchases | USD | Julian Clarkson | 2026-09-30 13:05:00 | 2026-09-30 13:05:00
BUD-0049 | CSMIA26 | Event 00 · Venue Startup | The Sanctuary MiMo |  |  |  | 4000 Environment | 4000.02 Custom Fabrication | Modular Build Components | N/A |  |  | 4000.02.01 | Install | 04 Physical | X | Scope |  | 0 |  |  |  | 0 | 0 |  | 0 |  | Open | FALSE |  |  | 5400 | Expense · Environment | CC-VENUE | 4000.02.01 | Tax on Purchases | USD | Julian Clarkson | 2026-09-30 13:05:00 | 2026-09-30 13:05:00
BUD-0050 | CSMIA26 | Event 00 · Venue Startup | The Sanctuary MiMo |  |  |  | 4000 Environment | 4000.03 Scenic & Set Fabrication | Scenic & Decorative | N/A |  |  | 4000.03.01 | Install | 04 Physical | X | Scope |  | 0 |  |  |  | 0 | 0 |  | 0 |  | Open | FALSE |  |  | 5400 | Expense · Environment | CC-VENUE | 4000.03.01 | Tax on Purchases | USD | Julian Clarkson | 2026-09-30 13:05:00 | 2026-09-30 13:05:00
BUD-0051 | CSMIA26 | Event 00 · Venue Startup | The Sanctuary MiMo |  |  |  | 4000 Environment | 4000.04 Metalwork & Welding | Metalwork & Welding | N/A |  |  | 4000.04.01 | Install | 04 Physical | X | Scope |  | 0 |  |  |  | 0 | 0 |  | 0 |  | Open | FALSE |  |  | 5400 | Expense · Environment | CC-VENUE | 4000.04.01 | Tax on Purchases | USD | Julian Clarkson | 2026-09-30 13:05:00 | 2026-09-30 13:05:00
BUD-0052 | CSMIA26 | Event 00 · Venue Startup | The Sanctuary MiMo |  |  |  | 4000 Environment | 4000.05 Signage & Environmental Graphics Fabrication | Signage Panels | N/A |  |  | 4000.05.01 | Install | 04 Physical | X | Scope |  | 0 |  |  |  | 0 | 0 |  | 0 |  | Open | FALSE |  |  | 5400 | Expense · Environment | CC-VENUE | 4000.05.01 | Tax on Purchases | USD | Julian Clarkson | 2026-09-30 13:05:00 | 2026-09-30 13:05:00
BUD-0053 | CSMIA26 | Event 00 · Venue Startup | The Sanctuary MiMo |  |  |  | 4000 Environment | 4000.05 Signage & Environmental Graphics Fabrication | Directional Signage | N/A |  |  | 4000.05.02 | Install | 04 Physical | X | Scope |  | 0 |  |  |  | 0 | 0 |  | 0 |  | Open | FALSE |  |  | 5400 | Expense · Environment | CC-VENUE | 4000.05.02 | Tax on Purchases | USD | Julian Clarkson | 2026-09-30 13:05:00 | 2026-09-30 13:05:00
BUD-0054 | CSMIA26 | Event 00 · Venue Startup | The Sanctuary MiMo |  |  |  | 4000 Environment | 4000.06 FF&E (Furniture, Fixtures & Equipment) | FF&E (Furniture, Fixtures & Equipment) | N/A |  |  | 4000.06.01 | Install | 04 Physical | X | Scope |  | 0 |  |  |  | 0 | 0 |  | 0 |  | Open | FALSE |  |  | 5400 | Expense · Environment | CC-VENUE | 4000.06.01 | Tax on Purchases | USD | Julian Clarkson | 2026-09-30 13:05:00 | 2026-09-30 13:05:00
BUD-0055 | CSMIA26 | Event 00 · Venue Startup | The Sanctuary MiMo |  |  |  | 4000 Environment | 4000.07 Surfaces & Finishes | Flooring & Surfaces | N/A |  |  | 4000.07.01 | Install | 04 Physical | X | Scope |  | 0 |  |  |  | 0 | 0 |  | 0 |  | Open | FALSE |  |  | 5400 | Expense · Environment | CC-VENUE | 4000.07.01 | Tax on Purchases | USD | Julian Clarkson | 2026-09-30 13:05:00 | 2026-09-30 13:05:00
BUD-0056 | CSMIA26 | Event 00 · Venue Startup | The Sanctuary MiMo |  |  |  | 4000 Environment | 4000.08 Site Infrastructure & Temporary Structures | Fencing & Barriers | N/A |  |  | 4000.08.01 | Install | 04 Physical | X | Scope |  | 0 |  |  |  | 0 | 0 |  | 0 |  | Open | FALSE |  |  | 5400 | Expense · Environment | CC-VENUE | 4000.08.01 | Tax on Purchases | USD | Julian Clarkson | 2026-09-30 13:05:00 | 2026-09-30 13:05:00
BUD-0057 | CSMIA26 | Event 00 · Venue Startup | The Sanctuary MiMo |  |  |  | 4000 Environment | 4000.08 Site Infrastructure & Temporary Structures | Tents & Structures | N/A |  |  | 4000.08.02 | Install | 04 Physical | X | Scope |  | 0 |  |  |  | 0 | 0 |  | 0 |  | Open | FALSE |  |  | 5400 | Expense · Environment | CC-VENUE | 4000.08.02 | Tax on Purchases | USD | Julian Clarkson | 2026-09-30 13:05:00 | 2026-09-30 13:05:00
BUD-0058 | CSMIA26 | Event 00 · Venue Startup | The Sanctuary MiMo |  |  |  | 4000 Environment | 4000.09 Install & De-Install | Aerial Lifts | N/A |  |  | 4000.09.01 | Install | 04 Physical | X | Scope |  | 0 |  |  |  | 0 | 0 |  | 0 |  | Open | FALSE |  |  | 5400 | Expense · Environment | CC-VENUE | 4000.09.01 | Tax on Purchases | USD | Julian Clarkson | 2026-09-30 13:05:00 | 2026-09-30 13:05:00
BUD-0059 | CSMIA26 | Event 00 · Venue Startup | The Sanctuary MiMo |  |  |  | 4000 Environment | 4000.09 Install & De-Install | Cranes | N/A |  |  | 4000.09.02 | Install | 04 Physical | X | Scope |  | 0 |  |  |  | 0 | 0 |  | 0 |  | Open | FALSE |  |  | 5400 | Expense · Environment | CC-VENUE | 4000.09.02 | Tax on Purchases | USD | Julian Clarkson | 2026-09-30 13:05:00 | 2026-09-30 13:05:00
BUD-0060 | CSMIA26 | Event 00 · Venue Startup | The Sanctuary MiMo |  |  |  | 4000 Environment | 4000.50 Base Build Delivery | Base Build Delivery | N/A |  |  | 4000.50.01 | Install | 04 Physical | Y | Scope |  | 0 |  |  |  | 0 | 0 |  | 0 |  | Open | FALSE |  |  | 5400 | Expense · Environment | CC-VENUE | 4000.50.01 | Tax on Purchases | USD | Julian Clarkson | 2026-09-30 13:05:00 | 2026-09-30 13:05:00
BUD-0061 | CSMIA26 | Event 00 · Venue Startup | The Sanctuary MiMo |  |  |  | 4000 Environment | 4000.51 Building Systems Maintenance | House Technical | N/A |  |  | 4000.51.01 | Install | 04 Physical | Y | Scope |  | 0 |  |  |  | 0 | 0 |  | 0 |  | Open | FALSE |  |  | 5400 | Expense · Environment | CC-VENUE | 4000.51.01 | Tax on Purchases | USD | Julian Clarkson | 2026-09-30 13:05:00 | 2026-09-30 13:05:00
BUD-0062 | CSMIA26 | Event 00 · Venue Startup | The Sanctuary MiMo |  |  |  | 4000 Environment | 4000.51 Building Systems Maintenance | Mechanical Services | N/A |  |  | 4000.51.02 | Install | 04 Physical | Y | Scope |  | 0 |  |  |  | 0 | 0 |  | 0 |  | Open | FALSE |  |  | 5400 | Expense · Environment | CC-VENUE | 4000.51.02 | Tax on Purchases | USD | Julian Clarkson | 2026-09-30 13:05:00 | 2026-09-30 13:05:00
BUD-0063 | CSMIA26 | Event 00 · Venue Startup | The Sanctuary MiMo |  |  |  | 4000 Environment | 4000.51 Building Systems Maintenance | Electrical Services | N/A |  |  | 4000.51.03 | Install | 04 Physical | Y | Scope |  | 0 |  |  |  | 0 | 0 |  | 0 |  | Open | FALSE |  |  | 5400 | Expense · Environment | CC-VENUE | 4000.51.03 | Tax on Purchases | USD | Julian Clarkson | 2026-09-30 13:05:00 | 2026-09-30 13:05:00
BUD-0064 | CSMIA26 | Event 00 · Venue Startup | The Sanctuary MiMo |  |  |  | 4000 Environment | 4000.51 Building Systems Maintenance | Plumbing Services | N/A |  |  | 4000.51.04 | Install | 04 Physical | Y | Scope |  | 0 |  |  |  | 0 | 0 |  | 0 |  | Open | FALSE |  |  | 5400 | Expense · Environment | CC-VENUE | 4000.51.04 | Tax on Purchases | USD | Julian Clarkson | 2026-09-30 13:05:00 | 2026-09-30 13:05:00
BUD-0065 | CSMIA26 | Event 00 · Venue Startup | The Sanctuary MiMo |  |  |  | 5000 Production | 5000.01 Audio | Audio Infrastructure | N/A |  |  | 5000.01.01 | Install | 04 Physical | X | Scope |  | 0 |  |  |  | 0 | 0 |  | 0 |  | Open | FALSE |  |  | 5500 | Expense · Production | CC-VENUE | 5000.01.01 | Tax on Purchases | USD | Julian Clarkson | 2026-09-30 13:05:00 | 2026-09-30 13:05:00
BUD-0066 | CSMIA26 | Event 00 · Venue Startup | The Sanctuary MiMo |  |  |  | 5000 Production | 5000.01 Audio | PA Systems | N/A |  |  | 5000.01.02 | Install | 04 Physical | X | Scope |  | 0 |  |  |  | 0 | 0 |  | 0 |  | Open | FALSE |  |  | 5500 | Expense · Production | CC-VENUE | 5000.01.02 | Tax on Purchases | USD | Julian Clarkson | 2026-09-30 13:05:00 | 2026-09-30 13:05:00
BUD-0067 | CSMIA26 | Event 00 · Venue Startup | The Sanctuary MiMo |  |  |  | 5000 Production | 5000.01 Audio | Microphones & DI | N/A |  |  | 5000.01.03 | Install | 04 Physical | X | Scope |  | 13100 |  |  |  | 13100 | 13100 |  | 0 |  | Open | FALSE |  |  | 5500 | Expense · Production | CC-VENUE | 5000.01.03 | Tax on Purchases | USD | Julian Clarkson | 2026-09-30 13:05:00 | 2026-09-30 13:05:00
BUD-0068 | CSMIA26 | Event 00 · Venue Startup | The Sanctuary MiMo |  |  |  | 5000 Production | 5000.01 Audio | Mixing Consoles | N/A |  |  | 5000.01.04 | Install | 04 Physical | X | Scope |  | 0 |  |  |  | 0 | 0 |  | 0 |  | Open | FALSE |  |  | 5500 | Expense · Production | CC-VENUE | 5000.01.04 | Tax on Purchases | USD | Julian Clarkson | 2026-09-30 13:05:00 | 2026-09-30 13:05:00
BUD-0069 | CSMIA26 | Event 00 · Venue Startup | The Sanctuary MiMo |  |  |  | 5000 Production | 5000.01 Audio | Playback & Processing | N/A |  |  | 5000.01.05 | Install | 04 Physical | X | Scope |  | 0 |  |  |  | 0 | 0 |  | 0 |  | Open | FALSE |  |  | 5500 | Expense · Production | CC-VENUE | 5000.01.05 | Tax on Purchases | USD | Julian Clarkson | 2026-09-30 13:05:00 | 2026-09-30 13:05:00
BUD-0070 | CSMIA26 | Event 00 · Venue Startup | The Sanctuary MiMo |  |  |  | 5000 Production | 5000.01 Audio | Spatial Audio | N/A |  |  | 5000.01.06 | Install | 04 Physical | X | Scope |  | 0 |  |  |  | 0 | 0 |  | 0 |  | Open | FALSE |  |  | 5500 | Expense · Production | CC-VENUE | 5000.01.06 | Tax on Purchases | USD | Julian Clarkson | 2026-09-30 13:05:00 | 2026-09-30 13:05:00
BUD-0071 | CSMIA26 | Event 00 · Venue Startup | The Sanctuary MiMo |  |  |  | 5000 Production | 5000.02 Lighting | Lighting Control | N/A |  |  | 5000.02.01 | Install | 04 Physical | X | Scope |  | 8400 |  |  |  | 8400 | 8400 |  | 0 |  | Open | FALSE |  |  | 5500 | Expense · Production | CC-VENUE | 5000.02.01 | Tax on Purchases | USD | Julian Clarkson | 2026-09-30 13:05:00 | 2026-09-30 13:05:00
BUD-0072 | CSMIA26 | Event 00 · Venue Startup | The Sanctuary MiMo |  |  |  | 5000 Production | 5000.02 Lighting | Automated Fixtures | N/A |  |  | 5000.02.02 | Install | 04 Physical | X | Scope |  | 0 |  |  |  | 0 | 0 |  | 0 |  | Open | FALSE |  |  | 5500 | Expense · Production | CC-VENUE | 5000.02.02 | Tax on Purchases | USD | Julian Clarkson | 2026-09-30 13:05:00 | 2026-09-30 13:05:00
BUD-0073 | CSMIA26 | Event 00 · Venue Startup | The Sanctuary MiMo |  |  |  | 5000 Production | 5000.03 Video & LED | LED Walls & Displays | N/A |  |  | 5000.03.01 | Install | 04 Physical | X | Scope |  | 0 |  |  |  | 0 | 0 |  | 0 |  | Open | FALSE |  |  | 5500 | Expense · Production | CC-VENUE | 5000.03.01 | Tax on Purchases | USD | Julian Clarkson | 2026-09-30 13:05:00 | 2026-09-30 13:05:00
BUD-0074 | CSMIA26 | Event 00 · Venue Startup | The Sanctuary MiMo |  |  |  | 5000 Production | 5000.03 Video & LED | Projection | N/A |  |  | 5000.03.02 | Install | 04 Physical | X | Scope |  | 0 |  |  |  | 0 | 0 |  | 0 |  | Open | FALSE |  |  | 5500 | Expense · Production | CC-VENUE | 5000.03.02 | Tax on Purchases | USD | Julian Clarkson | 2026-09-30 13:05:00 | 2026-09-30 13:05:00
BUD-0075 | CSMIA26 | Event 00 · Venue Startup | The Sanctuary MiMo |  |  |  | 5000 Production | 5000.04 Staging & Decks | Stage Infrastructure | N/A |  |  | 5000.04.01 | Install | 04 Physical | X | Scope |  | 0 |  |  |  | 0 | 0 |  | 0 |  | Open | FALSE |  |  | 5500 | Expense · Production | CC-VENUE | 5000.04.01 | Tax on Purchases | USD | Julian Clarkson | 2026-09-30 13:05:00 | 2026-09-30 13:05:00
BUD-0076 | CSMIA26 | Event 00 · Venue Startup | The Sanctuary MiMo |  |  |  | 5000 Production | 5000.04 Staging & Decks | Stage Decks & Risers | N/A |  |  | 5000.04.02 | Install | 04 Physical | X | Scope |  | 0 |  |  |  | 0 | 0 |  | 0 |  | Open | FALSE |  |  | 5500 | Expense · Production | CC-VENUE | 5000.04.02 | Tax on Purchases | USD | Julian Clarkson | 2026-09-30 13:05:00 | 2026-09-30 13:05:00
BUD-0077 | CSMIA26 | Event 00 · Venue Startup | The Sanctuary MiMo |  |  |  | 5000 Production | 5000.05 Rigging & Motors | Motors & Chain Hoists | N/A |  |  | 5000.05.01 | Install | 04 Physical | X | Scope |  | 0 |  |  |  | 0 | 0 |  | 0 |  | Open | FALSE |  |  | 5500 | Expense · Production | CC-VENUE | 5000.05.01 | Tax on Purchases | USD | Julian Clarkson | 2026-09-30 13:05:00 | 2026-09-30 13:05:00
BUD-0078 | CSMIA26 | Event 00 · Venue Startup | The Sanctuary MiMo |  |  |  | 5000 Production | 5000.05 Rigging & Motors | Rigging Hardware | N/A |  |  | 5000.05.02 | Install | 04 Physical | X | Scope |  | 0 |  |  |  | 0 | 0 |  | 0 |  | Open | FALSE |  |  | 5500 | Expense · Production | CC-VENUE | 5000.05.02 | Tax on Purchases | USD | Julian Clarkson | 2026-09-30 13:05:00 | 2026-09-30 13:05:00
BUD-0079 | CSMIA26 | Event 00 · Venue Startup | The Sanctuary MiMo |  |  |  | 5000 Production | 5000.05 Rigging & Motors | Truss | N/A |  |  | 5000.05.03 | Install | 04 Physical | X | Scope |  | 0 |  |  |  | 0 | 0 |  | 0 |  | Open | FALSE |  |  | 5500 | Expense · Production | CC-VENUE | 5000.05.03 | Tax on Purchases | USD | Julian Clarkson | 2026-09-30 13:05:00 | 2026-09-30 13:05:00
BUD-0080 | CSMIA26 | Event 00 · Venue Startup | The Sanctuary MiMo |  |  |  | 5000 Production | 5000.06 Power & Distribution | Power & Electrical | N/A |  |  | 5000.06.01 | Install | 04 Physical | X | Scope |  | 0 |  |  |  | 0 | 0 |  | 0 |  | Open | FALSE |  |  | 5500 | Expense · Production | CC-VENUE | 5000.06.01 | Tax on Purchases | USD | Julian Clarkson | 2026-09-30 13:05:00 | 2026-09-30 13:05:00
BUD-0081 | CSMIA26 | Event 00 · Venue Startup | The Sanctuary MiMo |  |  |  | 5000 Production | 5000.07 Special Effects & Atmospherics | Atmospheric Effects | N/A |  |  | 5000.07.01 | Install | 04 Physical | X | Scope |  | 0 |  |  |  | 0 | 0 |  | 0 |  | Open | FALSE |  |  | 5500 | Expense · Production | CC-VENUE | 5000.07.01 | Tax on Purchases | USD | Julian Clarkson | 2026-09-30 13:05:00 | 2026-09-30 13:05:00
BUD-0082 | CSMIA26 | Event 00 · Venue Startup | The Sanctuary MiMo |  |  |  | 5000 Production | 5000.08 Broadcast, Capture & Streaming | Cameras & Capture | N/A |  |  | 5000.08.01 | Install | 04 Physical | X | Scope |  | 0 |  |  |  | 0 | 0 |  | 0 |  | Open | FALSE |  |  | 5500 | Expense · Production | CC-VENUE | 5000.08.01 | Tax on Purchases | USD | Julian Clarkson | 2026-09-30 13:05:00 | 2026-09-30 13:05:00
BUD-0083 | CSMIA26 | Event 00 · Venue Startup | The Sanctuary MiMo |  |  |  | 5000 Production | 5000.09 Show Control & Playback | Show Control & Playback | N/A |  |  | 5000.09.01 | Install | 04 Physical | X | Scope |  | 0 |  |  |  | 0 | 0 |  | 0 |  | Open | FALSE |  |  | 5500 | Expense · Production | CC-VENUE | 5000.09.01 | Tax on Purchases | USD | Julian Clarkson | 2026-09-30 13:05:00 | 2026-09-30 13:05:00
BUD-0084 | CSMIA26 | Event 00 · Venue Startup | The Sanctuary MiMo |  |  |  | 5000 Production | 5000.10 Backline & Instruments | DJ Equipment | N/A |  |  | 5000.10.01 | Install | 04 Physical | X | Scope |  | 0 |  |  |  | 0 | 0 |  | 0 |  | Open | FALSE |  |  | 5500 | Expense · Production | CC-VENUE | 5000.10.01 | Tax on Purchases | USD | Julian Clarkson | 2026-09-30 13:05:00 | 2026-09-30 13:05:00
BUD-0085 | CSMIA26 | Event 00 · Venue Startup | The Sanctuary MiMo |  |  |  | 5000 Production | 5000.10 Backline & Instruments | Amplifiers & Cabinets | N/A |  |  | 5000.10.02 | Install | 04 Physical | X | Scope |  | 0 |  |  |  | 0 | 0 |  | 0 |  | Open | FALSE |  |  | 5500 | Expense · Production | CC-VENUE | 5000.10.02 | Tax on Purchases | USD | Julian Clarkson | 2026-09-30 13:05:00 | 2026-09-30 13:05:00
BUD-0086 | CSMIA26 | Event 00 · Venue Startup | The Sanctuary MiMo |  |  |  | 5000 Production | 5000.10 Backline & Instruments | Drum Kits | N/A |  |  | 5000.10.03 | Install | 04 Physical | X | Scope |  | 0 |  |  |  | 0 | 0 |  | 0 |  | Open | FALSE |  |  | 5500 | Expense · Production | CC-VENUE | 5000.10.03 | Tax on Purchases | USD | Julian Clarkson | 2026-09-30 13:05:00 | 2026-09-30 13:05:00
BUD-0087 | CSMIA26 | Event 00 · Venue Startup | The Sanctuary MiMo |  |  |  | 5000 Production | 5000.10 Backline & Instruments | Miscellaneous Backline | N/A |  |  | 5000.10.04 | Install | 04 Physical | X | Scope |  | 0 |  |  |  | 0 | 0 |  | 0 |  | Open | FALSE |  |  | 5500 | Expense · Production | CC-VENUE | 5000.10.04 | Tax on Purchases | USD | Julian Clarkson | 2026-09-30 13:05:00 | 2026-09-30 13:05:00
BUD-0088 | CSMIA26 | Event 00 · Venue Startup | The Sanctuary MiMo |  |  |  | 5000 Production | 5000.10 Backline & Instruments | Keyboards & Controllers | N/A |  |  | 5000.10.05 | Install | 04 Physical | X | Scope |  | 0 |  |  |  | 0 | 0 |  | 0 |  | Open | FALSE |  |  | 5500 | Expense · Production | CC-VENUE | 5000.10.05 | Tax on Purchases | USD | Julian Clarkson | 2026-09-30 13:05:00 | 2026-09-30 13:05:00
BUD-0089 | CSMIA26 | Event 00 · Venue Startup | The Sanctuary MiMo |  |  |  | 5000 Production | 5000.50 Production Leadership | Venue Production Management | N/A |  |  | 5000.50.01 | Install | 04 Physical | Y | Scope |  | 0 |  |  |  | 0 | 0 |  | 0 |  | Open | FALSE |  |  | 5500 | Expense · Production | CC-VENUE | 5000.50.01 | Tax on Purchases | USD | Julian Clarkson | 2026-09-30 13:05:00 | 2026-09-30 13:05:00
BUD-0090 | CSMIA26 | Event 00 · Venue Startup | The Sanctuary MiMo |  |  |  | 5000 Production | 5000.50 Production Leadership | Event Production Management | N/A |  |  | 5000.50.02 | Install | 04 Physical | Y | Scope |  | 0 |  |  |  | 0 | 0 |  | 0 |  | Open | FALSE |  |  | 5500 | Expense · Production | CC-VENUE | 5000.50.02 | Tax on Purchases | USD | Julian Clarkson | 2026-09-30 13:05:00 | 2026-09-30 13:05:00
BUD-0091 | CSMIA26 | Event 00 · Venue Startup | The Sanctuary MiMo |  |  |  | 5000 Production | 5000.51 Stage Crew | Stagehand | N/A |  |  | 5000.51.01 | Install | 04 Physical | Y | Scope |  | 0 |  |  |  | 0 | 0 |  | 0 |  | Open | FALSE |  |  | 5500 | Expense · Production | CC-VENUE | 5000.51.01 | Tax on Purchases | USD | Julian Clarkson | 2026-09-30 13:05:00 | 2026-09-30 13:05:00
BUD-0092 | CSMIA26 | Event 00 · Venue Startup | The Sanctuary MiMo |  |  |  | 5000 Production | 5000.51 Stage Crew | Rigging | N/A |  |  | 5000.51.02 | Install | 04 Physical | Y | Scope |  | 0 |  |  |  | 0 | 0 |  | 0 |  | Open | FALSE |  |  | 5500 | Expense · Production | CC-VENUE | 5000.51.02 | Tax on Purchases | USD | Julian Clarkson | 2026-09-30 13:05:00 | 2026-09-30 13:05:00
BUD-0093 | CSMIA26 | Event 00 · Venue Startup | The Sanctuary MiMo |  |  |  | 5000 Production | 5000.52 Production Supply | Equipment Rental | N/A |  |  | 5000.52.01 | Install | 04 Physical | Y | Scope |  | 0 |  |  |  | 0 | 0 |  | 0 |  | Open | FALSE |  |  | 5500 | Expense · Production | CC-VENUE | 5000.52.01 | Tax on Purchases | USD | Julian Clarkson | 2026-09-30 13:05:00 | 2026-09-30 13:05:00
BUD-0094 | CSMIA26 | Event 00 · Venue Startup | The Sanctuary MiMo |  |  |  | 5000 Production | 5000.52 Production Supply | Trucking and Logistics | N/A |  |  | 5000.52.02 | Install | 04 Physical | Y | Scope |  | 0 |  |  |  | 0 | 0 |  | 0 |  | Open | FALSE |  |  | 5500 | Expense · Production | CC-VENUE | 5000.52.02 | Tax on Purchases | USD | Julian Clarkson | 2026-09-30 13:05:00 | 2026-09-30 13:05:00
BUD-0095 | CSMIA26 | Event 00 · Venue Startup | The Sanctuary MiMo |  |  |  | 5000 Production | 5000.52 Production Supply | Rigging Engineering | N/A |  |  | 5000.52.03 | Install | 04 Physical | Y | Scope |  | 0 |  |  |  | 0 | 0 |  | 0 |  | Open | FALSE |  |  | 5500 | Expense · Production | CC-VENUE | 5000.52.03 | Tax on Purchases | USD | Julian Clarkson | 2026-09-30 13:05:00 | 2026-09-30 13:05:00
BUD-0096 | CSMIA26 | Event 00 · Venue Startup | The Sanctuary MiMo |  |  |  | 6000 Operations | 6000.01 Event Operations & Production Management | Production Management | N/A |  |  | 6000.01.01 | Operate | 04 Physical | X | Scope |  | 0 |  |  |  | 0 | 0 |  | 0 |  | Open | FALSE |  |  | 5600 | Expense · Operations | CC-VENUE | 6000.01.01 | Tax on Purchases | USD | Julian Clarkson | 2026-09-30 13:05:00 | 2026-09-30 13:05:00
BUD-0097 | CSMIA26 | Event 00 · Venue Startup | The Sanctuary MiMo |  |  |  | 6000 Operations | 6000.02 Logistics & Transport | Forklifts & Loaders | N/A |  |  | 6000.02.01 | Operate | 04 Physical | X | Scope |  | 0 |  |  |  | 0 | 0 |  | 0 |  | Open | FALSE |  |  | 5600 | Expense · Operations | CC-VENUE | 6000.02.01 | Tax on Purchases | USD | Julian Clarkson | 2026-09-30 13:05:00 | 2026-09-30 13:05:00
BUD-0098 | CSMIA26 | Event 00 · Venue Startup | The Sanctuary MiMo |  |  |  | 6000 Operations | 6000.02 Logistics & Transport | Flights | N/A |  |  | 6000.02.02 | Operate | 04 Physical | X | Scope |  | 0 |  |  |  | 0 | 0 |  | 0 |  | Open | FALSE |  |  | 5600 | Expense · Operations | CC-VENUE | 6000.02.02 | Tax on Purchases | USD | Julian Clarkson | 2026-09-30 13:05:00 | 2026-09-30 13:05:00
BUD-0099 | CSMIA26 | Event 00 · Venue Startup | The Sanctuary MiMo |  |  |  | 6000 Operations | 6000.02 Logistics & Transport | Water Transport | N/A |  |  | 6000.02.03 | Operate | 04 Physical | X | Scope |  | 0 |  |  |  | 0 | 0 |  | 0 |  | Open | FALSE |  |  | 5600 | Expense · Operations | CC-VENUE | 6000.02.03 | Tax on Purchases | USD | Julian Clarkson | 2026-09-30 13:05:00 | 2026-09-30 13:05:00
BUD-0100 | CSMIA26 | Event 00 · Venue Startup | The Sanctuary MiMo |  |  |  | 6000 Operations | 6000.02 Logistics & Transport | Ground Transport | N/A |  |  | 6000.02.04 | Operate | 04 Physical | X | Scope |  | 0 |  |  |  | 0 | 0 |  | 0 |  | Open | FALSE |  |  | 5600 | Expense · Operations | CC-VENUE | 6000.02.04 | Tax on Purchases | USD | Julian Clarkson | 2026-09-30 13:05:00 | 2026-09-30 13:05:00
BUD-0101 | CSMIA26 | Event 00 · Venue Startup | The Sanctuary MiMo |  |  |  | 6000 Operations | 6000.02 Logistics & Transport | Cars & Trucks | N/A |  |  | 6000.02.05 | Operate | 04 Physical | X | Scope |  | 0 |  |  |  | 0 | 0 |  | 0 |  | Open | FALSE |  |  | 5600 | Expense · Operations | CC-VENUE | 6000.02.05 | Tax on Purchases | USD | Julian Clarkson | 2026-09-30 13:05:00 | 2026-09-30 13:05:00
BUD-0102 | CSMIA26 | Event 00 · Venue Startup | The Sanctuary MiMo |  |  |  | 6000 Operations | 6000.02 Logistics & Transport | Utility Vehicles | N/A |  |  | 6000.02.06 | Operate | 04 Physical | X | Scope |  | 0 |  |  |  | 0 | 0 |  | 0 |  | Open | FALSE |  |  | 5600 | Expense · Operations | CC-VENUE | 6000.02.06 | Tax on Purchases | USD | Julian Clarkson | 2026-09-30 13:05:00 | 2026-09-30 13:05:00
BUD-0103 | CSMIA26 | Event 00 · Venue Startup | The Sanctuary MiMo |  |  |  | 6000 Operations | 6000.02 Logistics & Transport | Trucks & Transport | N/A |  |  | 6000.02.07 | Operate | 04 Physical | X | Scope |  | 0 |  |  |  | 0 | 0 |  | 0 |  | Open | FALSE |  |  | 5600 | Expense · Operations | CC-VENUE | 6000.02.07 | Tax on Purchases | USD | Julian Clarkson | 2026-09-30 13:05:00 | 2026-09-30 13:05:00
BUD-0104 | CSMIA26 | Event 00 · Venue Startup | The Sanctuary MiMo |  |  |  | 6000 Operations | 6000.02 Logistics & Transport | Specialty Vehicles | N/A |  |  | 6000.02.08 | Operate | 04 Physical | X | Scope |  | 0 |  |  |  | 0 | 0 |  | 0 |  | Open | FALSE |  |  | 5600 | Expense · Operations | CC-VENUE | 6000.02.08 | Tax on Purchases | USD | Julian Clarkson | 2026-09-30 13:05:00 | 2026-09-30 13:05:00
BUD-0105 | CSMIA26 | Event 00 · Venue Startup | The Sanctuary MiMo |  |  |  | 6000 Operations | 6000.03 Labor & Crewing | Department Heads | N/A |  |  | 6000.03.01 | Operate | 04 Physical | X | Scope |  | 0 |  |  |  | 0 | 0 |  | 0 |  | Open | FALSE |  |  | 5600 | Expense · Operations | CC-VENUE | 6000.03.01 | Tax on Purchases | USD | Julian Clarkson | 2026-09-30 13:05:00 | 2026-09-30 13:05:00
BUD-0106 | CSMIA26 | Event 00 · Venue Startup | The Sanctuary MiMo |  |  |  | 6000 Operations | 6000.03 Labor & Crewing | Certified Operators | N/A |  |  | 6000.03.02 | Operate | 04 Physical | X | Scope |  | 0 |  |  |  | 0 | 0 |  | 0 |  | Open | FALSE |  |  | 5600 | Expense · Operations | CC-VENUE | 6000.03.02 | Tax on Purchases | USD | Julian Clarkson | 2026-09-30 13:05:00 | 2026-09-30 13:05:00
BUD-0107 | CSMIA26 | Event 00 · Venue Startup | The Sanctuary MiMo |  |  |  | 6000 Operations | 6000.03 Labor & Crewing | Event Staff | N/A |  |  | 6000.03.03 | Operate | 04 Physical | X | Scope |  | 0 |  |  |  | 0 | 0 |  | 0 |  | Open | FALSE |  |  | 5600 | Expense · Operations | CC-VENUE | 6000.03.03 | Tax on Purchases | USD | Julian Clarkson | 2026-09-30 13:05:00 | 2026-09-30 13:05:00
BUD-0108 | CSMIA26 | Event 00 · Venue Startup | The Sanctuary MiMo |  |  |  | 6000 Operations | 6000.03 Labor & Crewing | Specialty Staff | N/A |  |  | 6000.03.04 | Operate | 04 Physical | X | Scope |  | 0 |  |  |  | 0 | 0 |  | 0 |  | Open | FALSE |  |  | 5600 | Expense · Operations | CC-VENUE | 6000.03.04 | Tax on Purchases | USD | Julian Clarkson | 2026-09-30 13:05:00 | 2026-09-30 13:05:00
BUD-0109 | CSMIA26 | Event 00 · Venue Startup | The Sanctuary MiMo |  |  |  | 6000 Operations | 6000.03 Labor & Crewing | Technical Crew | N/A |  |  | 6000.03.05 | Operate | 04 Physical | X | Scope |  | 0 |  |  |  | 0 | 0 |  | 0 |  | Open | FALSE |  |  | 5600 | Expense · Operations | CC-VENUE | 6000.03.05 | Tax on Purchases | USD | Julian Clarkson | 2026-09-30 13:05:00 | 2026-09-30 13:05:00
BUD-0110 | CSMIA26 | Event 00 · Venue Startup | The Sanctuary MiMo |  |  |  | 6000 Operations | 6000.03 Labor & Crewing | Staff Apparel | N/A |  |  | 6000.03.06 | Operate | 04 Physical | X | Scope |  | 0 |  |  |  | 0 | 0 |  | 0 |  | Open | FALSE |  |  | 5600 | Expense · Operations | CC-VENUE | 6000.03.06 | Tax on Purchases | USD | Julian Clarkson | 2026-09-30 13:05:00 | 2026-09-30 13:05:00
BUD-0111 | CSMIA26 | Event 00 · Venue Startup | The Sanctuary MiMo |  |  |  | 6000 Operations | 6000.03 Labor & Crewing | Stagehands | N/A |  |  | 6000.03.07 | Operate | 04 Physical | X | Scope |  | 0 |  |  |  | 0 | 0 |  | 0 |  | Open | FALSE |  |  | 5600 | Expense · Operations | CC-VENUE | 6000.03.07 | Tax on Purchases | USD | Julian Clarkson | 2026-09-30 13:05:00 | 2026-09-30 13:05:00
BUD-0112 | CSMIA26 | Event 00 · Venue Startup | The Sanctuary MiMo |  |  |  | 6000 Operations | 6000.04 Security & Access Control | Security & Access Control | N/A |  |  | 6000.04.01 | Operate | 04 Physical | X | Scope |  | 0 |  |  |  | 0 | 0 |  | 0 |  | Open | FALSE |  |  | 5600 | Expense · Operations | CC-VENUE | 6000.04.01 | Tax on Purchases | USD | Julian Clarkson | 2026-09-30 13:05:00 | 2026-09-30 13:05:00
BUD-0113 | CSMIA26 | Event 00 · Venue Startup | The Sanctuary MiMo |  |  |  | 6000 Operations | 6000.05 Medical, Safety & EMS | Safety Equipment | N/A |  |  | 6000.05.01 | Operate | 04 Physical | X | Scope |  | 0 |  |  |  | 0 | 0 |  | 0 |  | Open | FALSE |  |  | 5600 | Expense · Operations | CC-VENUE | 6000.05.01 | Tax on Purchases | USD | Julian Clarkson | 2026-09-30 13:05:00 | 2026-09-30 13:05:00
BUD-0114 | CSMIA26 | Event 00 · Venue Startup | The Sanctuary MiMo |  |  |  | 6000 Operations | 6000.05 Medical, Safety & EMS | Medical | N/A |  |  | 6000.05.02 | Operate | 04 Physical | X | Scope |  | 0 |  |  |  | 0 | 0 |  | 0 |  | Open | FALSE |  |  | 5600 | Expense · Operations | CC-VENUE | 6000.05.02 | Tax on Purchases | USD | Julian Clarkson | 2026-09-30 13:05:00 | 2026-09-30 13:05:00
BUD-0115 | CSMIA26 | Event 00 · Venue Startup | The Sanctuary MiMo |  |  |  | 6000 Operations | 6000.05 Medical, Safety & EMS | PPE | N/A |  |  | 6000.05.03 | Operate | 04 Physical | X | Scope |  | 0 |  |  |  | 0 | 0 |  | 0 |  | Open | FALSE |  |  | 5600 | Expense · Operations | CC-VENUE | 6000.05.03 | Tax on Purchases | USD | Julian Clarkson | 2026-09-30 13:05:00 | 2026-09-30 13:05:00
BUD-0116 | CSMIA26 | Event 00 · Venue Startup | The Sanctuary MiMo |  |  |  | 6000 Operations | 6000.06 Site Operations & Facilities | Specialty Rentals | N/A |  |  | 6000.06.01 | Operate | 04 Physical | X | Scope |  | 0 |  |  |  | 0 | 0 |  | 0 | Landlord proposal dated 27 May 2026. |  | FALSE | Landlord proposal dated 27 May 2026. |  | 5600 | Expense · Operations | CC-VENUE | 6000.06.01 | Tax on Purchases | USD | Julian Clarkson | 2026-09-30 13:05:00 | 2026-09-30 13:05:00
BUD-0117 | CSMIA26 | Event 00 · Venue Startup | The Sanctuary MiMo |  |  |  | 6000 Operations | 6000.06 Site Operations & Facilities | Portable Facilities | N/A |  |  | 6000.06.02 | Operate | 04 Physical | X | Scope |  | 0 |  |  |  | 0 | 0 |  | 0 |  | Open | FALSE |  |  | 5600 | Expense · Operations | CC-VENUE | 6000.06.02 | Tax on Purchases | USD | Julian Clarkson | 2026-09-30 13:05:00 | 2026-09-30 13:05:00
BUD-0118 | CSMIA26 | Event 00 · Venue Startup | The Sanctuary MiMo |  |  |  | 6000 Operations | 6000.06 Site Operations & Facilities | Climate Control | N/A |  |  | 6000.06.03 | Operate | 04 Physical | X | Scope |  | 0 |  |  |  | 0 | 0 |  | 0 |  | Open | FALSE |  |  | 5600 | Expense · Operations | CC-VENUE | 6000.06.03 | Tax on Purchases | USD | Julian Clarkson | 2026-09-30 13:05:00 | 2026-09-30 13:05:00
BUD-0119 | CSMIA26 | Event 00 · Venue Startup | The Sanctuary MiMo |  |  |  | 6000 Operations | 6000.06 Site Operations & Facilities | Water & Plumbing | N/A |  |  | 6000.06.04 | Operate | 04 Physical | X | Scope |  | 0 |  |  |  | 0 | 0 |  | 0 |  | Open | FALSE |  |  | 5600 | Expense · Operations | CC-VENUE | 6000.06.04 | Tax on Purchases | USD | Julian Clarkson | 2026-09-30 13:05:00 | 2026-09-30 13:05:00
BUD-0120 | CSMIA26 | Event 00 · Venue Startup | The Sanctuary MiMo |  |  |  | 6000 Operations | 6000.07 Credentialing & Accreditation | Credentials | N/A |  |  | 6000.07.01 | Operate | 04 Physical | X | Scope |  | 0 |  |  |  | 0 | 0 |  | 0 |  | Open | FALSE |  |  | 5600 | Expense · Operations | CC-VENUE | 6000.07.01 | Tax on Purchases | USD | Julian Clarkson | 2026-09-30 13:05:00 | 2026-09-30 13:05:00
BUD-0121 | CSMIA26 | Event 00 · Venue Startup | The Sanctuary MiMo |  |  |  | 6000 Operations | 6000.08 Production Office & Workplace | Expendables & Consumables | N/A |  |  | 6000.08.01 | Operate | 04 Physical | X | Scope |  | 0 |  |  |  | 0 | 0 |  | 0 |  | Open | FALSE |  |  | 5600 | Expense · Operations | CC-VENUE | 6000.08.01 | Tax on Purchases | USD | Julian Clarkson | 2026-09-30 13:05:00 | 2026-09-30 13:05:00
BUD-0122 | CSMIA26 | Event 00 · Venue Startup | The Sanctuary MiMo |  |  |  | 6000 Operations | 6000.08 Production Office & Workplace | Office & Production | N/A |  |  | 6000.08.02 | Operate | 04 Physical | X | Scope |  | 0 |  |  |  | 0 | 0 |  | 0 |  | Open | FALSE |  |  | 5600 | Expense · Operations | CC-VENUE | 6000.08.02 | Tax on Purchases | USD | Julian Clarkson | 2026-09-30 13:05:00 | 2026-09-30 13:05:00
BUD-0123 | CSMIA26 | Event 00 · Venue Startup | The Sanctuary MiMo |  |  |  | 6000 Operations | 6000.09 Waste & Environmental Services | Waste Management | N/A |  |  | 6000.09.01 | Operate | 04 Physical | X | Scope |  | 0 |  |  |  | 0 | 0 |  | 0 |  | Open | FALSE |  |  | 5600 | Expense · Operations | CC-VENUE | 6000.09.01 | Tax on Purchases | USD | Julian Clarkson | 2026-09-30 13:05:00 | 2026-09-30 13:05:00
BUD-0124 | CSMIA26 | Event 00 · Venue Startup | The Sanctuary MiMo |  |  |  | 6000 Operations | 6000.50 House Management | House Management | N/A |  |  | 6000.50.01 | Operate | 04 Physical | Y | Scope |  | 0 |  |  |  | 0 | 0 |  | 0 |  | Open | FALSE |  |  | 5600 | Expense · Operations | CC-VENUE | 6000.50.01 | Tax on Purchases | USD | Julian Clarkson | 2026-09-30 13:05:00 | 2026-09-30 13:05:00
BUD-0125 | CSMIA26 | Event 00 · Venue Startup | The Sanctuary MiMo |  |  |  | 6000 Operations | 6000.50 House Management | Deputy House Management | N/A |  |  | 6000.50.02 | Operate | 04 Physical | Y | Scope |  | 0 |  |  |  | 0 | 0 |  | 0 |  | Open | FALSE |  |  | 5600 | Expense · Operations | CC-VENUE | 6000.50.02 | Tax on Purchases | USD | Julian Clarkson | 2026-09-30 13:05:00 | 2026-09-30 13:05:00
BUD-0126 | CSMIA26 | Event 00 · Venue Startup | The Sanctuary MiMo |  |  |  | 6000 Operations | 6000.51 Venue Services | Janitorial | N/A |  | $2.25 per rentable square foot on 14,139 sq ft; 3% annual escalation. | 6000.51.01 | Operate | 04 Physical | Z | Overhead | 14139 | 0 | sq ft per year | 0 | 0 | 0 | 0 |  | 0 | Landlord | Open | FALSE |  |  | 5600 | Expense · Operations | CC-VENUE | 6000.51.01 | Tax on Purchases | USD | Julian Clarkson | 2026-09-30 13:05:00 | 2026-09-30 13:05:00
BUD-0127 | CSMIA26 | Event 00 · Venue Startup | The Sanctuary MiMo |  |  |  | 6000 Operations | 6000.51 Venue Services | Waste and Recycling | N/A |  |  | 6000.51.02 | Operate | 04 Physical | Y | Scope |  | 0 |  |  |  | 0 | 0 |  | 0 |  | Open | FALSE |  |  | 5600 | Expense · Operations | CC-VENUE | 6000.51.02 | Tax on Purchases | USD | Julian Clarkson | 2026-09-30 13:05:00 | 2026-09-30 13:05:00
BUD-0128 | CSMIA26 | Event 00 · Venue Startup | The Sanctuary MiMo |  |  |  | 6000 Operations | 6000.51 Venue Services | Pest Control | N/A |  |  | 6000.51.03 | Operate | 04 Physical | Y | Scope |  | 0 |  |  |  | 0 | 0 |  | 0 |  | Open | FALSE |  |  | 5600 | Expense · Operations | CC-VENUE | 6000.51.03 | Tax on Purchases | USD | Julian Clarkson | 2026-09-30 13:05:00 | 2026-09-30 13:05:00
BUD-0129 | CSMIA26 | Event 00 · Venue Startup | The Sanctuary MiMo |  |  |  | 6000 Operations | 6000.51 Venue Services | Fire and Life Safety | N/A |  |  | 6000.51.04 | Operate | 04 Physical | Y | Scope |  | 0 |  |  |  | 0 | 0 |  | 0 |  | Open | FALSE |  |  | 5600 | Expense · Operations | CC-VENUE | 6000.51.04 | Tax on Purchases | USD | Julian Clarkson | 2026-09-30 13:05:00 | 2026-09-30 13:05:00
BUD-0130 | CSMIA26 | Event 00 · Venue Startup | The Sanctuary MiMo |  |  |  | 6000 Operations | 6000.51 Venue Services | Key and Access Control | N/A |  |  | 6000.51.05 | Operate | 04 Physical | Y | Scope |  | 0 |  |  |  | 0 | 0 |  | 0 |  | Open | FALSE |  |  | 5600 | Expense · Operations | CC-VENUE | 6000.51.05 | Tax on Purchases | USD | Julian Clarkson | 2026-09-30 13:05:00 | 2026-09-30 13:05:00
BUD-0131 | CSMIA26 | Event 00 · Venue Startup | The Sanctuary MiMo |  |  |  | 6000 Operations | 6000.52 Event Security | Security Supervision | N/A |  |  | 6000.52.01 | Operate | 04 Physical | Y | Scope |  | 0 |  |  |  | 0 | 0 |  | 0 |  | Open | FALSE |  |  | 5600 | Expense · Operations | CC-VENUE | 6000.52.01 | Tax on Purchases | USD | Julian Clarkson | 2026-09-30 13:05:00 | 2026-09-30 13:05:00
BUD-0132 | CSMIA26 | Event 00 · Venue Startup | The Sanctuary MiMo |  |  |  | 6000 Operations | 6000.52 Event Security | Security Officer | N/A |  |  | 6000.52.02 | Operate | 04 Physical | Y | Scope |  | 0 |  |  |  | 0 | 0 |  | 0 |  | Open | FALSE |  |  | 5600 | Expense · Operations | CC-VENUE | 6000.52.02 | Tax on Purchases | USD | Julian Clarkson | 2026-09-30 13:05:00 | 2026-09-30 13:05:00
BUD-0133 | CSMIA26 | Event 00 · Venue Startup | The Sanctuary MiMo | Whole Venue |  | Standing Operations | 6000 Operations | 6000.53 Occupancy & Utilities | Base Rent | N/A |  | $60.00 per rentable square foot on 14,139 sq ft; 3% annual escalation. | 6000.53.01 | Operate | 04 Physical | Z | Overhead | 14139 | 0 | sq ft per year | 0 | 0 | 0 | 0 |  | 0 | Landlord | Estimated | FALSE | Landlord proposal dated 27 May 2026. |  | 5600 | Expense · Operations | CC-VENUE | 6000.53.01 | Tax on Purchases | USD | Julian Clarkson | 2026-09-30 13:05:00 | 2026-09-30 13:05:00
BUD-0134 | CSMIA26 | Event 00 · Venue Startup | The Sanctuary MiMo | Whole Venue |  | Standing Operations | 6000 Operations | 6000.53 Occupancy & Utilities | Base Rent (Credit) | N/A |  | $5.00 per rentable square foot on 14,139 sq ft; 3% annual escalation. | 6000.53.01 | Operate | 04 Physical | Z | Overhead | 14139 | 0 | sq ft per year | 0 | 0 | 0 | 0 |  | 0 | Landlord | Estimated | FALSE | Landlord proposal dated 27 May 2026. |  | 5600 | Expense · Operations | CC-VENUE | 6000.53.01 | Tax on Purchases | USD | Julian Clarkson | 2026-09-30 13:05:00 | 2026-09-30 13:05:00
BUD-0135 | CSMIA26 | Event 00 · Venue Startup | The Sanctuary MiMo | Whole Venue |  | Standing Operations | 6000 Operations | 6000.53 Occupancy & Utilities | Operating Expense Recovery | N/A |  | $9.13 per rentable square foot on 14,139 sq ft; 3% annual escalation. | 6000.53.02 | Operate | 04 Physical | Z | Overhead | 14139 | 0 | sq ft per year | 0 | 0 | 0 | 0 |  | 0 | Landlord | Estimated | FALSE | Landlord proposal dated 27 May 2026. |  | 5600 | Expense · Operations | CC-VENUE | 6000.53.02 | Tax on Purchases | USD | Julian Clarkson | 2026-09-30 13:05:00 | 2026-09-30 13:05:00
BUD-0136 | CSMIA26 | Event 00 · Venue Startup | The Sanctuary MiMo | Whole Venue |  | Standing Operations | 6000 Operations | 6000.53 Occupancy & Utilities | Real Estate Taxes | N/A |  | $2.57 per rentable square foot on 14,139 sq ft; 3% annual escalation. | 6000.53.03 | Operate | 04 Physical | Z | Overhead | 14139 | 0 | sq ft per year | 0 | 0 | 0 | 0 |  | 0 | Landlord | Estimated | FALSE | Landlord proposal dated 27 May 2026. |  | 5600 | Expense · Operations | CC-VENUE | 6000.53.03 | Tax on Purchases | USD | Julian Clarkson | 2026-09-30 13:05:00 | 2026-09-30 13:05:00
BUD-0137 | CSMIA26 | Event 00 · Venue Startup | The Sanctuary MiMo | Whole Venue |  | Standing Operations | 6000 Operations | 6000.53 Occupancy & Utilities | Electricity | N/A |  | $2.50 per rentable square foot on 14,139 sq ft; 3% annual escalation. | 6000.53.04 | Operate | 04 Physical | Z | Overhead | 14139 | 0 | sq ft per year | 0 | 0 | 0 | 0 |  | 0 | Landlord | Estimated | FALSE | Landlord proposal dated 27 May 2026. |  | 5600 | Expense · Operations | CC-VENUE | 6000.53.04 | Tax on Purchases | USD | Julian Clarkson | 2026-09-30 13:05:00 | 2026-09-30 13:05:00
BUD-0138 | CSMIA26 | Event 00 · Venue Startup | The Sanctuary MiMo | Whole Venue |  | Standing Operations | 6000 Operations | 6000.53 Occupancy & Utilities | Water & Sewer | N/A |  | $0.50 per rentable square foot on 14,139 sq ft; 3% annual escalation. | 6000.53.05 | Operate | 04 Physical | Z | Overhead | 14139 | 0 | sq ft per year | 0 | 0 | 0 | 0 |  | 0 | Landlord | Estimated | FALSE | Landlord proposal dated 27 May 2026. |  | 5600 | Expense · Operations | CC-VENUE | 6000.53.05 | Tax on Purchases | USD | Julian Clarkson | 2026-09-30 13:05:00 | 2026-09-30 13:05:00
BUD-0139 | CSMIA26 | Event 00 · Venue Startup | The Sanctuary MiMo |  |  |  | 7000 Experience | 7000.01 Guest Experience & Journey | Guest Experience & Journey | N/A |  |  | 7000.01.01 | Operate | 04 Physical | X | Scope |  | 0 |  |  |  | 0 | 0 |  | 0 |  | Open | FALSE |  |  | 5700 | Expense · Experience | CC-VENUE | 7000.01.01 | Tax on Purchases | USD | Julian Clarkson | 2026-09-30 13:05:00 | 2026-09-30 13:05:00
BUD-0140 | CSMIA26 | Event 00 · Venue Startup | The Sanctuary MiMo |  |  |  | 7000 Experience | 7000.02 Activations & Brand Experiences | Creative & Specialty | N/A |  |  | 7000.02.01 | Operate | 04 Physical | X | Scope |  | 0 |  |  |  | 0 | 0 |  | 0 |  | Open | FALSE |  |  | 5700 | Expense · Experience | CC-VENUE | 7000.02.01 | Tax on Purchases | USD | Julian Clarkson | 2026-09-30 13:05:00 | 2026-09-30 13:05:00
BUD-0141 | CSMIA26 | Event 00 · Venue Startup | The Sanctuary MiMo |  |  |  | 7000 Experience | 7000.02 Activations & Brand Experiences | Props | N/A |  |  | 7000.02.02 | Operate | 04 Physical | X | Scope |  | 0 |  |  |  | 0 | 0 |  | 0 |  | Open | FALSE |  |  | 5700 | Expense · Experience | CC-VENUE | 7000.02.02 | Tax on Purchases | USD | Julian Clarkson | 2026-09-30 13:05:00 | 2026-09-30 13:05:00
BUD-0142 | CSMIA26 | Event 00 · Venue Startup | The Sanctuary MiMo |  |  |  | 7000 Experience | 7000.02 Activations & Brand Experiences | Verbal Identity | N/A |  |  | 7000.02.03 | Operate | 04 Physical | X | Scope |  | 0 |  |  |  | 0 | 0 |  | 0 |  | Open | FALSE |  |  | 5700 | Expense · Experience | CC-VENUE | 7000.02.03 | Tax on Purchases | USD | Julian Clarkson | 2026-09-30 13:05:00 | 2026-09-30 13:05:00
BUD-0143 | CSMIA26 | Event 00 · Venue Startup | The Sanctuary MiMo |  |  |  | 7000 Experience | 7000.03 Retail & Merchandise | Vendor Infrastructure | N/A |  |  | 7000.03.01 | Operate | 04 Physical | X | Scope |  | 0 |  |  |  | 0 | 0 |  | 0 |  | Open | FALSE |  |  | 5700 | Expense · Experience | CC-VENUE | 7000.03.01 | Tax on Purchases | USD | Julian Clarkson | 2026-09-30 13:05:00 | 2026-09-30 13:05:00
BUD-0144 | CSMIA26 | Event 00 · Venue Startup | The Sanctuary MiMo |  |  |  | 7000 Experience | 7000.03 Retail & Merchandise | Packaging & Supplies | N/A |  |  | 7000.03.02 | Operate | 04 Physical | X | Scope |  | 0 |  |  |  | 0 | 0 |  | 0 |  | Open | FALSE |  |  | 5700 | Expense · Experience | CC-VENUE | 7000.03.02 | Tax on Purchases | USD | Julian Clarkson | 2026-09-30 13:05:00 | 2026-09-30 13:05:00
BUD-0145 | CSMIA26 | Event 00 · Venue Startup | The Sanctuary MiMo |  |  |  | 7000 Experience | 7000.03 Retail & Merchandise | Display & Fixtures | N/A |  |  | 7000.03.03 | Operate | 04 Physical | X | Scope |  | 0 |  |  |  | 0 | 0 |  | 0 |  | Open | FALSE |  |  | 5700 | Expense · Experience | CC-VENUE | 7000.03.03 | Tax on Purchases | USD | Julian Clarkson | 2026-09-30 13:05:00 | 2026-09-30 13:05:00
BUD-0146 | CSMIA26 | Event 00 · Venue Startup | The Sanctuary MiMo |  |  |  | 7000 Experience | 7000.03 Retail & Merchandise | Static Fixtures | N/A |  |  | 7000.03.04 | Operate | 04 Physical | X | Scope |  | 0 |  |  |  | 0 | 0 |  | 0 |  | Open | FALSE |  |  | 5700 | Expense · Experience | CC-VENUE | 7000.03.04 | Tax on Purchases | USD | Julian Clarkson | 2026-09-30 13:05:00 | 2026-09-30 13:05:00
BUD-0147 | CSMIA26 | Event 00 · Venue Startup | The Sanctuary MiMo |  |  |  | 7000 Experience | 7000.03 Retail & Merchandise | Merchandise | N/A |  |  | 7000.03.05 | Operate | 04 Physical | X | Scope |  | 0 |  |  |  | 0 | 0 |  | 0 |  | Open | FALSE |  |  | 5700 | Expense · Experience | CC-VENUE | 7000.03.05 | Tax on Purchases | USD | Julian Clarkson | 2026-09-30 13:05:00 | 2026-09-30 13:05:00
BUD-0148 | CSMIA26 | Event 00 · Venue Startup | The Sanctuary MiMo |  |  |  | 7000 Experience | 7000.04 Sensory & Atmosphere | Scent Diffusion | N/A |  |  | 7000.04.01 | Operate | 04 Physical | X | Scope |  | 0 |  |  |  | 0 | 0 |  | 0 |  | Open | FALSE |  |  | 5700 | Expense · Experience | CC-VENUE | 7000.04.01 | Tax on Purchases | USD | Julian Clarkson | 2026-09-30 13:05:00 | 2026-09-30 13:05:00
BUD-0149 | CSMIA26 | Event 00 · Venue Startup | The Sanctuary MiMo |  |  |  | 7000 Experience | 7000.04 Sensory & Atmosphere | Aromatics | N/A |  |  | 7000.04.02 | Operate | 04 Physical | X | Scope |  | 0 |  |  |  | 0 | 0 |  | 0 |  | Open | FALSE |  |  | 5700 | Expense · Experience | CC-VENUE | 7000.04.02 | Tax on Purchases | USD | Julian Clarkson | 2026-09-30 13:05:00 | 2026-09-30 13:05:00
BUD-0150 | CSMIA26 | Event 00 · Venue Startup | The Sanctuary MiMo |  |  |  | 7000 Experience | 7000.04 Sensory & Atmosphere | Scent Design | N/A |  |  | 7000.04.03 | Operate | 04 Physical | X | Scope |  | 0 |  |  |  | 0 | 0 |  | 0 |  | Open | FALSE |  |  | 5700 | Expense · Experience | CC-VENUE | 7000.04.03 | Tax on Purchases | USD | Julian Clarkson | 2026-09-30 13:05:00 | 2026-09-30 13:05:00
BUD-0151 | CSMIA26 | Event 00 · Venue Startup | The Sanctuary MiMo |  |  |  | 7000 Experience | 7000.04 Sensory & Atmosphere | Scent Service | N/A |  |  | 7000.04.04 | Operate | 04 Physical | X | Scope |  | 0 |  |  |  | 0 | 0 |  | 0 |  | Open | FALSE |  |  | 5700 | Expense · Experience | CC-VENUE | 7000.04.04 | Tax on Purchases | USD | Julian Clarkson | 2026-09-30 13:05:00 | 2026-09-30 13:05:00
BUD-0152 | CSMIA26 | Event 00 · Venue Startup | The Sanctuary MiMo |  |  |  | 7000 Experience | 7000.04 Sensory & Atmosphere | Soundscape | N/A |  |  | 7000.04.05 | Operate | 04 Physical | X | Scope |  | 0 |  |  |  | 0 | 0 |  | 0 |  | Open | FALSE |  |  | 5700 | Expense · Experience | CC-VENUE | 7000.04.05 | Tax on Purchases | USD | Julian Clarkson | 2026-09-30 13:05:00 | 2026-09-30 13:05:00
BUD-0153 | CSMIA26 | Event 00 · Venue Startup | The Sanctuary MiMo |  |  |  | 7000 Experience | 7000.05 Photo & Shareable Moments | Photo Moments | N/A |  |  | 7000.05.01 | Operate | 04 Physical | X | Scope |  | 0 |  |  |  | 0 | 0 |  | 0 |  | Open | FALSE |  |  | 5700 | Expense · Experience | CC-VENUE | 7000.05.01 | Tax on Purchases | USD | Julian Clarkson | 2026-09-30 13:05:00 | 2026-09-30 13:05:00
BUD-0154 | CSMIA26 | Event 00 · Venue Startup | The Sanctuary MiMo |  |  |  | 7000 Experience | 7000.06 Gifting & Premiums | Gifting | N/A |  |  | 7000.06.01 | Operate | 04 Physical | X | Scope |  | 0 |  |  |  | 0 | 0 |  | 0 |  | Open | FALSE |  |  | 5700 | Expense · Experience | CC-VENUE | 7000.06.01 | Tax on Purchases | USD | Julian Clarkson | 2026-09-30 13:05:00 | 2026-09-30 13:05:00
BUD-0155 | CSMIA26 | Event 00 · Venue Startup | The Sanctuary MiMo |  |  |  | 7000 Experience | 7000.06 Gifting & Premiums | Premiums | N/A |  |  | 7000.06.02 | Operate | 04 Physical | X | Scope |  | 0 |  |  |  | 0 | 0 |  | 0 |  | Open | FALSE |  |  | 5700 | Expense · Experience | CC-VENUE | 7000.06.02 | Tax on Purchases | USD | Julian Clarkson | 2026-09-30 13:05:00 | 2026-09-30 13:05:00
BUD-0156 | CSMIA26 | Event 00 · Venue Startup | The Sanctuary MiMo |  |  |  | 7000 Experience | 7000.07 Sponsorship Fulfillment | Sponsorship Fulfillment | N/A |  |  | 7000.07.01 | Operate | 04 Physical | X | Scope |  | 0 |  |  |  | 0 | 0 |  | 0 |  | Open | FALSE |  |  | 5700 | Expense · Experience | CC-VENUE | 7000.07.01 | Tax on Purchases | USD | Julian Clarkson | 2026-09-30 13:05:00 | 2026-09-30 13:05:00
BUD-0157 | CSMIA26 | Event 00 · Venue Startup | The Sanctuary MiMo |  |  |  | 7000 Experience | 7000.08 Interactive & Immersive Experiences | Interactive & Immersive Experiences | N/A |  |  | 7000.08.01 | Operate | 04 Physical | X | Scope |  | 0 |  |  |  | 0 | 0 |  | 0 |  | Open | FALSE |  |  | 5700 | Expense · Experience | CC-VENUE | 7000.08.01 | Tax on Purchases | USD | Julian Clarkson | 2026-09-30 13:05:00 | 2026-09-30 13:05:00
BUD-0158 | CSMIA26 | Event 00 · Venue Startup | The Sanctuary MiMo |  |  |  | 7000 Experience | 7000.50 Front of House | Front of House Leadership | N/A |  |  | 7000.50.01 | Operate | 04 Physical | Y | Scope |  | 0 |  |  |  | 0 | 0 |  | 0 |  | Open | FALSE |  |  | 5700 | Expense · Experience | CC-VENUE | 7000.50.01 | Tax on Purchases | USD | Julian Clarkson | 2026-09-30 13:05:00 | 2026-09-30 13:05:00
BUD-0159 | CSMIA26 | Event 00 · Venue Startup | The Sanctuary MiMo |  |  |  | 7000 Experience | 7000.50 Front of House | Credential Check | N/A |  |  | 7000.50.02 | Operate | 04 Physical | Y | Scope |  | 0 |  |  |  | 0 | 0 |  | 0 |  | Open | FALSE |  |  | 5700 | Expense · Experience | CC-VENUE | 7000.50.02 | Tax on Purchases | USD | Julian Clarkson | 2026-09-30 13:05:00 | 2026-09-30 13:05:00
BUD-0160 | CSMIA26 | Event 00 · Venue Startup | The Sanctuary MiMo |  |  |  | 7000 Experience | 7000.50 Front of House | Guest Services | N/A |  |  | 7000.50.03 | Operate | 04 Physical | Y | Scope |  | 0 |  |  |  | 0 | 0 |  | 0 |  | Open | FALSE |  |  | 5700 | Expense · Experience | CC-VENUE | 7000.50.03 | Tax on Purchases | USD | Julian Clarkson | 2026-09-30 13:05:00 | 2026-09-30 13:05:00
BUD-0161 | CSMIA26 | Event 00 · Venue Startup | The Sanctuary MiMo |  |  |  | 7000 Experience | 7000.50 Front of House | Coat Check | N/A |  |  | 7000.50.04 | Operate | 04 Physical | Y | Scope |  | 0 |  |  |  | 0 | 0 |  | 0 |  | Open | FALSE |  |  | 5700 | Expense · Experience | CC-VENUE | 7000.50.04 | Tax on Purchases | USD | Julian Clarkson | 2026-09-30 13:05:00 | 2026-09-30 13:05:00
BUD-0162 | CSMIA26 | Event 00 · Venue Startup | The Sanctuary MiMo |  |  |  | 7000 Experience | 7000.51 Guest Safety | Event Medical | N/A |  |  | 7000.51.01 | Operate | 04 Physical | Y | Scope |  | 0 |  |  |  | 0 | 0 |  | 0 |  | Open | FALSE |  |  | 5700 | Expense · Experience | CC-VENUE | 7000.51.01 | Tax on Purchases | USD | Julian Clarkson | 2026-09-30 13:05:00 | 2026-09-30 13:05:00
BUD-0163 | CSMIA26 | Event 00 · Venue Startup | The Sanctuary MiMo |  |  |  | 8000 Hospitality | 8000.01 Catering & Culinary | Guest & VIP Catering | N/A |  |  | 8000.01.01 | Procure | 04 Physical | X | Scope |  | 16500 |  |  |  | 16500 | 16500 |  | 0 |  | Open | FALSE |  |  | 5800 | Expense · Hospitality | CC-VENUE | 8000.01.01 | Tax on Purchases | USD | Julian Clarkson | 2026-09-30 13:05:00 | 2026-09-30 13:05:00
BUD-0164 | CSMIA26 | Event 00 · Venue Startup | The Sanctuary MiMo |  |  |  | 8000 Hospitality | 8000.01 Catering & Culinary | Artist & Crew Catering | N/A |  |  | 8000.01.02 | Procure | 04 Physical | X | Scope |  | 0 |  |  |  | 0 | 0 |  | 0 |  | Open | FALSE |  |  | 5800 | Expense · Hospitality | CC-VENUE | 8000.01.02 | Tax on Purchases | USD | Julian Clarkson | 2026-09-30 13:05:00 | 2026-09-30 13:05:00
BUD-0165 | CSMIA26 | Event 00 · Venue Startup | The Sanctuary MiMo |  |  |  | 8000 Hospitality | 8000.01 Catering & Culinary | Service Equipment | N/A |  |  | 8000.01.03 | Procure | 04 Physical | X | Scope |  | 0 |  |  |  | 0 | 0 |  | 0 |  | Open | FALSE |  |  | 5800 | Expense · Hospitality | CC-VENUE | 8000.01.03 | Tax on Purchases | USD | Julian Clarkson | 2026-09-30 13:05:00 | 2026-09-30 13:05:00
BUD-0166 | CSMIA26 | Event 00 · Venue Startup | The Sanctuary MiMo |  |  |  | 8000 Hospitality | 8000.01 Catering & Culinary | Kitchen Equipment | N/A |  |  | 8000.01.04 | Procure | 04 Physical | X | Scope |  | 0 |  |  |  | 0 | 0 |  | 0 |  | Open | FALSE |  |  | 5800 | Expense · Hospitality | CC-VENUE | 8000.01.04 | Tax on Purchases | USD | Julian Clarkson | 2026-09-30 13:05:00 | 2026-09-30 13:05:00
BUD-0167 | CSMIA26 | Event 00 · Venue Startup | The Sanctuary MiMo |  |  |  | 8000 Hospitality | 8000.02 Bar & Beverage | Bar Equipment | N/A |  |  | 8000.02.01 | Procure | 04 Physical | X | Scope |  | 0 |  |  |  | 0 | 0 |  | 0 |  | Open | FALSE |  |  | 5800 | Expense · Hospitality | CC-VENUE | 8000.02.01 | Tax on Purchases | USD | Julian Clarkson | 2026-09-30 13:05:00 | 2026-09-30 13:05:00
BUD-0168 | CSMIA26 | Event 00 · Venue Startup | The Sanctuary MiMo |  |  |  | 8000 Hospitality | 8000.02 Bar & Beverage | Bar Consumables | N/A |  |  | 8000.02.02 | Procure | 04 Physical | X | Scope |  | 0 |  |  |  | 0 | 0 |  | 0 |  | Open | FALSE |  |  | 5800 | Expense · Hospitality | CC-VENUE | 8000.02.02 | Tax on Purchases | USD | Julian Clarkson | 2026-09-30 13:05:00 | 2026-09-30 13:05:00
BUD-0169 | CSMIA26 | Event 00 · Venue Startup | The Sanctuary MiMo |  |  |  | 8000 Hospitality | 8000.03 Concessions & Vending | Concessions & Carts | N/A |  |  | 8000.03.01 | Procure | 04 Physical | X | Scope |  | 0 |  |  |  | 0 | 0 |  | 0 |  | Open | FALSE |  |  | 5800 | Expense · Hospitality | CC-VENUE | 8000.03.01 | Tax on Purchases | USD | Julian Clarkson | 2026-09-30 13:05:00 | 2026-09-30 13:05:00
BUD-0170 | CSMIA26 | Event 00 · Venue Startup | The Sanctuary MiMo |  |  |  | 8000 Hospitality | 8000.04 VIP & Hospitality Services | Amenities & Services | N/A |  |  | 8000.04.01 | Procure | 04 Physical | X | Scope |  | 0 |  |  |  | 0 | 0 |  | 0 |  | Open | FALSE |  |  | 5800 | Expense · Hospitality | CC-VENUE | 8000.04.01 | Tax on Purchases | USD | Julian Clarkson | 2026-09-30 13:05:00 | 2026-09-30 13:05:00
BUD-0171 | CSMIA26 | Event 00 · Venue Startup | The Sanctuary MiMo |  |  |  | 8000 Hospitality | 8000.04 VIP & Hospitality Services | VIP & Lounge | N/A |  |  | 8000.04.02 | Procure | 04 Physical | X | Scope |  | 0 |  |  |  | 0 | 0 |  | 0 |  | Open | FALSE |  |  | 5800 | Expense · Hospitality | CC-VENUE | 8000.04.02 | Tax on Purchases | USD | Julian Clarkson | 2026-09-30 13:05:00 | 2026-09-30 13:05:00
BUD-0172 | CSMIA26 | Event 00 · Venue Startup | The Sanctuary MiMo |  |  |  | 8000 Hospitality | 8000.04 VIP & Hospitality Services | Artist Hospitality | N/A |  |  | 8000.04.03 | Procure | 04 Physical | X | Scope |  | 0 |  |  |  | 0 | 0 |  | 0 |  | Open | FALSE |  |  | 5800 | Expense · Hospitality | CC-VENUE | 8000.04.03 | Tax on Purchases | USD | Julian Clarkson | 2026-09-30 13:05:00 | 2026-09-30 13:05:00
BUD-0173 | CSMIA26 | Event 00 · Venue Startup | The Sanctuary MiMo |  |  |  | 8000 Hospitality | 8000.04 VIP & Hospitality Services | Lounge & VIP | N/A |  |  | 8000.04.04 | Procure | 04 Physical | X | Scope |  | 0 |  |  |  | 0 | 0 |  | 0 |  | Open | FALSE |  |  | 5800 | Expense · Hospitality | CC-VENUE | 8000.04.04 | Tax on Purchases | USD | Julian Clarkson | 2026-09-30 13:05:00 | 2026-09-30 13:05:00
BUD-0174 | CSMIA26 | Event 00 · Venue Startup | The Sanctuary MiMo |  |  |  | 8000 Hospitality | 8000.05 Lodging & Accommodation | Hotels | N/A |  |  | 8000.05.01 | Procure | 04 Physical | X | Scope |  | 0 |  |  |  | 0 | 0 |  | 0 |  | Open | FALSE |  |  | 5800 | Expense · Hospitality | CC-VENUE | 8000.05.01 | Tax on Purchases | USD | Julian Clarkson | 2026-09-30 13:05:00 | 2026-09-30 13:05:00
BUD-0175 | CSMIA26 | Event 00 · Venue Startup | The Sanctuary MiMo |  |  |  | 8000 Hospitality | 8000.05 Lodging & Accommodation | Alternative Lodging | N/A |  |  | 8000.05.02 | Procure | 04 Physical | X | Scope |  | 0 |  |  |  | 0 | 0 |  | 0 |  | Open | FALSE |  |  | 5800 | Expense · Hospitality | CC-VENUE | 8000.05.02 | Tax on Purchases | USD | Julian Clarkson | 2026-09-30 13:05:00 | 2026-09-30 13:05:00
BUD-0176 | CSMIA26 | Event 00 · Venue Startup | The Sanctuary MiMo |  |  |  | 8000 Hospitality | 8000.06 Front of House & Guest Services | Front of House & Guest Services | N/A |  |  | 8000.06.01 | Procure | 04 Physical | X | Scope |  | 0 |  |  |  | 0 | 0 |  | 0 |  | Open | FALSE |  |  | 5800 | Expense · Hospitality | CC-VENUE | 8000.06.01 | Tax on Purchases | USD | Julian Clarkson | 2026-09-30 13:05:00 | 2026-09-30 13:05:00
BUD-0177 | CSMIA26 | Event 00 · Venue Startup | The Sanctuary MiMo |  |  |  | 8000 Hospitality | 8000.50 Beverage Service | Bartending | N/A |  |  | 8000.50.01 | Procure | 04 Physical | Y | Scope |  | 0 |  |  |  | 0 | 0 |  | 0 |  | Open | FALSE |  |  | 5800 | Expense · Hospitality | CC-VENUE | 8000.50.01 | Tax on Purchases | USD | Julian Clarkson | 2026-09-30 13:05:00 | 2026-09-30 13:05:00
BUD-0178 | CSMIA26 | Event 00 · Venue Startup | The Sanctuary MiMo |  |  |  | 8000 Hospitality | 8000.50 Beverage Service | Bar Support | N/A |  |  | 8000.50.02 | Procure | 04 Physical | Y | Scope |  | 0 |  |  |  | 0 | 0 |  | 0 |  | Open | FALSE |  |  | 5800 | Expense · Hospitality | CC-VENUE | 8000.50.02 | Tax on Purchases | USD | Julian Clarkson | 2026-09-30 13:05:00 | 2026-09-30 13:05:00
BUD-0179 | CSMIA26 | Event 00 · Venue Startup | The Sanctuary MiMo |  |  |  | 8000 Hospitality | 8000.51 Catering Service | Catering Supervision | N/A |  |  | 8000.51.01 | Procure | 04 Physical | Y | Scope |  | 0 |  |  |  | 0 | 0 |  | 0 |  | Open | FALSE |  |  | 5800 | Expense · Hospitality | CC-VENUE | 8000.51.01 | Tax on Purchases | USD | Julian Clarkson | 2026-09-30 13:05:00 | 2026-09-30 13:05:00
BUD-0180 | CSMIA26 | Event 00 · Venue Startup | The Sanctuary MiMo |  |  |  | 8000 Hospitality | 8000.51 Catering Service | Catering Service | N/A |  |  | 8000.51.02 | Procure | 04 Physical | Y | Scope |  | 0 |  |  |  | 0 | 0 |  | 0 |  | Open | FALSE |  |  | 5800 | Expense · Hospitality | CC-VENUE | 8000.51.02 | Tax on Purchases | USD | Julian Clarkson | 2026-09-30 13:05:00 | 2026-09-30 13:05:00
BUD-0181 | CSMIA26 | Event 00 · Venue Startup | The Sanctuary MiMo |  |  |  | 8000 Hospitality | 8000.51 Catering Service | Food and Beverage Provision | N/A |  |  | 8000.51.03 | Procure | 04 Physical | Y | Scope |  | 0 |  |  |  | 0 | 0 |  | 0 |  | Open | FALSE |  |  | 5800 | Expense · Hospitality | CC-VENUE | 8000.51.03 | Tax on Purchases | USD | Julian Clarkson | 2026-09-30 13:05:00 | 2026-09-30 13:05:00
BUD-0182 | CSMIA26 | Event 00 · Venue Startup | The Sanctuary MiMo |  |  |  | 8000 Hospitality | 8000.52 Event Rentals | Linen and Furniture Rental | N/A |  |  | 8000.52.01 | Procure | 04 Physical | Y | Scope |  | 0 |  |  |  | 0 | 0 |  | 0 |  | Open | FALSE |  |  | 5800 | Expense · Hospitality | CC-VENUE | 8000.52.01 | Tax on Purchases | USD | Julian Clarkson | 2026-09-30 13:05:00 | 2026-09-30 13:05:00
BUD-0183 | CSMIA26 | Event 00 · Venue Startup | The Sanctuary MiMo |  |  |  | 9000 Technology | 9000.01 IT & Networking | IT & Networking | N/A |  |  | 9000.01.01 | Procure | 04 Physical | X | Scope |  | 0 |  |  |  | 0 | 0 |  | 0 |  | Open | FALSE |  |  | 5900 | Expense · Technology | CC-VENUE | 9000.01.01 | Tax on Purchases | USD | Julian Clarkson | 2026-09-30 13:05:00 | 2026-09-30 13:05:00
BUD-0184 | CSMIA26 | Event 00 · Venue Startup | The Sanctuary MiMo |  |  |  | 9000 Technology | 9000.02 Connectivity & Internet | Internet & Connectivity | N/A |  |  | 9000.02.01 | Procure | 04 Physical | X | Scope |  | 0 |  |  |  | 0 | 0 |  | 0 |  | Open | FALSE |  |  | 5900 | Expense · Technology | CC-VENUE | 9000.02.01 | Tax on Purchases | USD | Julian Clarkson | 2026-09-30 13:05:00 | 2026-09-30 13:05:00
BUD-0185 | CSMIA26 | Event 00 · Venue Startup | The Sanctuary MiMo |  |  |  | 9000 Technology | 9000.03 RF & Communications | Two-Way Radios | N/A |  |  | 9000.03.01 | Procure | 04 Physical | X | Scope |  | 3400 |  |  |  | 3400 | 3400 |  | 0 |  | Open | FALSE |  |  | 5900 | Expense · Technology | CC-VENUE | 9000.03.01 | Tax on Purchases | USD | Julian Clarkson | 2026-09-30 13:05:00 | 2026-09-30 13:05:00
BUD-0186 | CSMIA26 | Event 00 · Venue Startup | The Sanctuary MiMo |  |  |  | 9000 Technology | 9000.03 RF & Communications | Intercoms | N/A |  |  | 9000.03.02 | Procure | 04 Physical | X | Scope |  | 0 |  |  |  | 0 | 0 |  | 0 |  | Open | FALSE |  |  | 5900 | Expense · Technology | CC-VENUE | 9000.03.02 | Tax on Purchases | USD | Julian Clarkson | 2026-09-30 13:05:00 | 2026-09-30 13:05:00
BUD-0187 | CSMIA26 | Event 00 · Venue Startup | The Sanctuary MiMo |  |  |  | 9000 Technology | 9000.04 Ticketing & Access Technology | Access Control | N/A |  |  | 9000.04.01 | Procure | 04 Physical | X | Scope |  | 0 |  |  |  | 0 | 0 |  | 0 |  | Open | FALSE |  |  | 5900 | Expense · Technology | CC-VENUE | 9000.04.01 | Tax on Purchases | USD | Julian Clarkson | 2026-09-30 13:05:00 | 2026-09-30 13:05:00
BUD-0188 | CSMIA26 | Event 00 · Venue Startup | The Sanctuary MiMo |  |  |  | 9000 Technology | 9000.05 Point of Sale & Payments | POS & Technology | N/A |  |  | 9000.05.01 | Procure | 04 Physical | X | Scope |  | 0 |  |  |  | 0 | 0 |  | 0 |  | Open | FALSE |  |  | 5900 | Expense · Technology | CC-VENUE | 9000.05.01 | Tax on Purchases | USD | Julian Clarkson | 2026-09-30 13:05:00 | 2026-09-30 13:05:00
BUD-0189 | CSMIA26 | Event 00 · Venue Startup | The Sanctuary MiMo |  |  |  | 9000 Technology | 9000.06 Data & Analytics | Data & Analytics | N/A |  |  | 9000.06.01 | Procure | 04 Physical | X | Scope |  | 0 |  |  |  | 0 | 0 |  | 0 |  | Open | FALSE |  |  | 5900 | Expense · Technology | CC-VENUE | 9000.06.01 | Tax on Purchases | USD | Julian Clarkson | 2026-09-30 13:05:00 | 2026-09-30 13:05:00
BUD-0190 | CSMIA26 | Event 00 · Venue Startup | The Sanctuary MiMo |  |  |  | 9000 Technology | 9000.07 AR / VR / XR & Immersive Tech | AR / VR / XR & Immersive Tech | N/A |  |  | 9000.07.01 | Procure | 04 Physical | X | Scope |  | 0 |  |  |  | 0 | 0 |  | 0 |  | Open | FALSE |  |  | 5900 | Expense · Technology | CC-VENUE | 9000.07.01 | Tax on Purchases | USD | Julian Clarkson | 2026-09-30 13:05:00 | 2026-09-30 13:05:00
BUD-0191 | CSMIA26 | Event 00 · Venue Startup | The Sanctuary MiMo |  |  |  | 9000 Technology | 9000.08 Cybersecurity & Systems | Security Systems | N/A |  |  | 9000.08.01 | Procure | 04 Physical | X | Scope |  | 0 |  |  |  | 0 | 0 |  | 0 |  | Open | FALSE |  |  | 5900 | Expense · Technology | CC-VENUE | 9000.08.01 | Tax on Purchases | USD | Julian Clarkson | 2026-09-30 13:05:00 | 2026-09-30 13:05:00
BUD-0192 | CSMIA26 | Event 00 · Venue Startup | The Sanctuary MiMo |  |  |  | 9000 Technology | 9000.09 Digital Signage & CMS | Digital Signage | N/A |  |  | 9000.09.01 | Procure | 04 Physical | X | Scope |  | 0 |  |  |  | 0 | 0 |  | 0 |  | Open | FALSE |  |  | 5900 | Expense · Technology | CC-VENUE | 9000.09.01 | Tax on Purchases | USD | Julian Clarkson | 2026-09-30 13:05:00 | 2026-09-30 13:05:00
BUD-0193 | CSMIA26 | Event 00 · Venue Startup | The Sanctuary MiMo |  |  |  | 9000 Technology | 9000.50 Audio Systems | Audio System Design | N/A |  |  | 9000.50.01 | Procure | 04 Physical | Y | Scope |  | 0 |  |  |  | 0 | 0 |  | 0 |  | Open | FALSE |  |  | 5900 | Expense · Technology | CC-VENUE | 9000.50.01 | Tax on Purchases | USD | Julian Clarkson | 2026-09-30 13:05:00 | 2026-09-30 13:05:00
BUD-0194 | CSMIA26 | Event 00 · Venue Startup | The Sanctuary MiMo |  |  |  | 9000 Technology | 9000.50 Audio Systems | Front of House Audio | N/A |  |  | 9000.50.02 | Procure | 04 Physical | Y | Scope |  | 0 |  |  |  | 0 | 0 |  | 0 |  | Open | FALSE |  |  | 5900 | Expense · Technology | CC-VENUE | 9000.50.02 | Tax on Purchases | USD | Julian Clarkson | 2026-09-30 13:05:00 | 2026-09-30 13:05:00
BUD-0195 | CSMIA26 | Event 00 · Venue Startup | The Sanctuary MiMo |  |  |  | 9000 Technology | 9000.50 Audio Systems | Stage Audio | N/A |  |  | 9000.50.03 | Procure | 04 Physical | Y | Scope |  | 0 |  |  |  | 0 | 0 |  | 0 |  | Open | FALSE |  |  | 5900 | Expense · Technology | CC-VENUE | 9000.50.03 | Tax on Purchases | USD | Julian Clarkson | 2026-09-30 13:05:00 | 2026-09-30 13:05:00
BUD-0196 | CSMIA26 | Event 00 · Venue Startup | The Sanctuary MiMo |  |  |  | 9000 Technology | 9000.50 Audio Systems | Loudspeaker Supply | N/A |  |  | 9000.50.04 | Procure | 04 Physical | Y | Scope |  | 0 |  |  |  | 0 | 0 |  | 0 |  | Open | FALSE |  |  | 5900 | Expense · Technology | CC-VENUE | 9000.50.04 | Tax on Purchases | USD | Julian Clarkson | 2026-09-30 13:05:00 | 2026-09-30 13:05:00
BUD-0197 | CSMIA26 | Event 00 · Venue Startup | The Sanctuary MiMo |  |  |  | 9000 Technology | 9000.51 Lighting and Video | Lighting Operation | N/A |  |  | 9000.51.01 | Procure | 04 Physical | Y | Scope |  | 0 |  |  |  | 0 | 0 |  | 0 |  | Open | FALSE |  |  | 5900 | Expense · Technology | CC-VENUE | 9000.51.01 | Tax on Purchases | USD | Julian Clarkson | 2026-09-30 13:05:00 | 2026-09-30 13:05:00
BUD-0198 | CSMIA26 | Event 00 · Venue Startup | The Sanctuary MiMo |  |  |  | 9000 Technology | 9000.51 Lighting and Video | Video Operation | N/A |  |  | 9000.51.02 | Procure | 04 Physical | Y | Scope |  | 0 |  |  |  | 0 | 0 |  | 0 |  | Open | FALSE |  |  | 5900 | Expense · Technology | CC-VENUE | 9000.51.02 | Tax on Purchases | USD | Julian Clarkson | 2026-09-30 13:05:00 | 2026-09-30 13:05:00
BUD-0199 | CSMIA26 | Event 00 · Venue Startup | The Sanctuary MiMo |  |  |  | 9000 Technology | 9000.52 Venue IT | Network Provision | N/A |  |  | 9000.52.01 | Procure | 04 Physical | Y | Scope |  | 0 |  |  |  | 0 | 0 |  | 0 |  | Open | FALSE |  |  | 5900 | Expense · Technology | CC-VENUE | 9000.52.01 | Tax on Purchases | USD | Julian Clarkson | 2026-09-30 13:05:00 | 2026-09-30 13:05:00
BUD-0200 | CSMIA26 | Event 00 · Venue Startup | The Sanctuary MiMo |  |  |  | 9000 Technology | 9000.52 Venue IT | Access Control and CCTV | N/A |  |  | 9000.52.02 | Procure | 04 Physical | Y | Scope |  | 0 |  |  |  | 0 | 0 |  | 0 |  | Open | FALSE |  |  | 5900 | Expense · Technology | CC-VENUE | 9000.52.02 | Tax on Purchases | USD | Julian Clarkson | 2026-09-30 13:05:00 | 2026-09-30 13:05:00
BUD-0201 | CSMIA26 | Event 00 · Venue Startup | The Sanctuary MiMo |  |  |  | 9000 Technology | 9000.52 Venue IT | Point of Sale | N/A |  |  | 9000.52.03 | Procure | 04 Physical | Y | Scope |  | 0 |  |  |  | 0 | 0 |  | 0 |  | Open | FALSE |  |  | 5900 | Expense · Technology | CC-VENUE | 9000.52.03 | Tax on Purchases | USD | Julian Clarkson | 2026-09-30 13:05:00 | 2026-09-30 13:05:00
BUD-0202 | CSMIA26 | Event 00 · Venue Startup | The Sanctuary MiMo |  |  |  | 9000 Technology | 9000.53 Systems Integration | Audiovisual Integration | N/A |  |  | 9000.53.01 | Procure | 04 Physical | Y | Scope |  | 0 |  |  |  | 0 | 0 |  | 0 |  | Open | FALSE |  |  | 5900 | Expense · Technology | CC-VENUE | 9000.53.01 | Tax on Purchases | USD | Julian Clarkson | 2026-09-30 13:05:00 | 2026-09-30 13:05:00
CON-001 | CSMIA26 | Contract Duration | The Sanctuary MiMo |  |  |  | 0000 Executive | 0000.01 Executive Leadership & Strategy | Production Leadership | N/A | Contingency | Five percent of Grade 2 scope, added on top. | 0000.01.01 | Scope | 04 Physical | Z | Contingency | 1 | 0 | lump sum | 0 | 0 | 0 | 0 |  | 0 | Tigre | Open | FALSE |  |  | 5000 | Expense · Executive | CC-CORP | 0000.01.01 | Tax on Purchases | USD | Julian Clarkson | 2026-09-30 13:05:00 | 2026-09-30 13:05:00
FEE-001 | CSMIA26 | Contract Duration | The Sanctuary MiMo |  |  |  | 0000 Executive | 0000.01 Executive Leadership & Strategy | Production Leadership | N/A | Producer Fee | Per the engagement agreement. | 0000.01.01 | Scope | 04 Physical | Z | Fee | 1 | 0 | lump sum | 0 | 0 | 0 | 0 |  | 0 | Tigre | Open | FALSE |  |  | 5000 | Expense · Executive | CC-CORP | 0000.01.01 | Tax on Purchases | USD | Julian Clarkson | 2026-09-30 13:05:00 | 2026-09-30 13:05:00
RET-001 | CSMIA26 | Contract Duration | The Sanctuary MiMo |  |  |  | 0000 Executive | 0000.01 Executive Leadership & Strategy | Production Leadership | N/A | Management Retainer | Fixed monthly retainer for the term; overhead, not a per-event fee. | 0000.01.01 | Scope | 04 Physical | Z | Retainer | 1 | 0 | lump sum | 0 | 0 | 0 | 0 |  | 0 | Tigre | Open | FALSE |  |  | 5000 | Expense · Executive | CC-CORP | 0000.01.01 | Tax on Purchases | USD | Julian Clarkson | 2026-09-30 13:05:00 | 2026-09-30 13:05:00

## Change Orders
RECORD ID | PROJECT ID | PARENT PO NUMBER | PO LINE ID | EXPENSE REF ID | ITEM ID | VENDOR ID | CHANGE ORDER TYPE | REASON CODE | DESCRIPTION | QUANTITY | UNIT RATE | TOTAL AMOUNT | GL ACCOUNT | COST CENTER | CURRENCY | SCHEDULE IMPACT (DAYS) | CLIENT IMPACT | JUSTIFICATION | REQUESTED BY | APPROVED BY | APPROVAL DATE | STATUS | FLAG | NOTES | CREATED BY | CREATED AT | UPDATED AT
CO-001 | CSMIA26 | PO-2026-001 | POL-001-02 | BUD-0067 | 5000.01.03-XPMS-004 | VEN-012 | Scope Addition | RC-SCOPE | Additional wireless handheld units for surprise guest artists | 4 | 150 | 600 | 5500 | CC-VENUE | USD | 0 | None | Additional wireless handheld units for surprise guest artists. | Julian Clarkson | Isabella Acker | 2026-10-15 | Approved | FALSE | Approved via email authorization per SOW | Julian Clarkson | 2026-10-15 | 2026-10-15
CO-002 | CSMIA26 | PO-2026-002 | POL-002-01 | BUD-0026 | 4000.03.01-XPMS-001 | VEN-013 | Material Upgrade | RC-UPGRADE | Dimensional entrance archway branding upgrade | 1 | 400 | 400 | 5100 | CC-VENUE | USD | 0 | Positive | Dimensional entrance archway branding upgrade. | Rebecca (Bex) | Isabella Acker | 2026-10-18 | Approved | FALSE | Approved per creative brief addendum | Julian Clarkson | 2026-10-18 | 2026-10-18
CO-003 | CSMIA26 | PO-2026-003 | POL-003-01 | BUD-0071 | 5000.02.01-GHXST-002 | VEN-005 | Scope Addition | RC-SCOPE | Additional audience blinder lighting fixtures | 4 | 50 | 200 | 5500 | CC-VENUE | USD | 0 | None | Additional audience blinders for headliner moment | Julian Clarkson | Isabella Acker | 2026-10-20 | Approved | FALSE | Approved per lighting designer addendum | Julian Clarkson | 2026-10-20 | 2026-10-20

## Purchase Orders
PO NUMBER | PROJECT ID | VENDOR ID | VENDOR NAME | ISSUE DATE | DELIVERY DATE | PAYMENT TERMS | SUBTOTAL AMOUNT | TAX AMOUNT | SHIPPING AMOUNT | TOTAL AMOUNT | COMMITTED AMOUNT | INVOICED AMOUNT | PAID AMOUNT | CURRENCY | STATUS | FLAG | NOTES | CREATED BY | CREATED AT | UPDATED AT
PO-2026-001 | CSMIA26 | VEN-012 | LPS Production | 2026-10-01 | 2026-10-15 | Net 30 | 12500 | 875 | 500 | 13875 | 13875 | 6937.5 | 6937.5 | USD | Approved | FALSE |  | Julian Clarkson | 2026-10-01 | 2026-10-01
PO-2026-002 | CSMIA26 | VEN-013 | RIOT Color | 2026-10-05 | 2026-10-18 | Net 30 | 4800 | 336 | 250 | 5386 | 5386 | 5386 | 2693 | USD | Approved | FALSE |  | Julian Clarkson | 2026-10-05 | 2026-10-05
PO-2026-003 | CSMIA26 | VEN-005 | Design Oasis | 2026-10-08 | 2026-10-22 | Net 30 | 8200 | 574 | 350 | 9124 | 9124 | 4562 | 0 | USD | Approved | FALSE |  | Julian Clarkson | 2026-10-08 | 2026-10-08
PO-2026-004 | CSMIA26 | VEN-008 | Motorola Solutions / BearCom | 2026-10-10 | 2026-10-24 | Net 30 | 3400 | 238 | 150 | 3788 | 3788 | 3788 | 3788 | USD | Approved | FALSE |  | Julian Clarkson | 2026-10-10 | 2026-10-10
PO-2026-005 | CSMIA26 | VEN-007 | Artisan Hospitality Services | 2026-10-12 | 2026-10-28 | Net 30 | 16500 | 1155 | 0 | 17655 | 17655 | 8827.5 | 8827.5 | USD | Approved | FALSE |  | Julian Clarkson | 2026-10-12 | 2026-10-12

## PO Line Items
PO LINE ID | PO NUMBER | EXPENSE REF ID | ITEM ID | USER LINE DESCRIPTION | QUANTITY | UNIT RATE | TOTAL AMOUNT | GL ACCOUNT | COST CENTER | LINE STATE
POL-001-01 | PO-2026-001 | BUD-0067 | 5000.01.01-XPMS-006 | Main Room PA + Subs + DSP installed sound system | 1 | 10000 | 10000 | 5500 | CC-VENUE | Committed
POL-001-02 | PO-2026-001 | BUD-0067 | 5000.01.03-XPMS-004 | Professional wireless handheld microphone systems | 16 | 156.25 | 2500 | 5500 | CC-VENUE | Committed
POL-002-01 | PO-2026-002 | BUD-0026 | 1000.51.01-XOS-001 | Signage fabrication and exterior wayfinding packages | 1 | 4800 | 4800 | 5100 | CC-VENUE | Committed
POL-003-01 | PO-2026-003 | BUD-0071 | 5000.02.01-XPMS-004 | Main stage automated lighting rig and atmospheric hazers | 1 | 8200 | 8200 | 5500 | CC-VENUE | Committed
POL-004-01 | PO-2026-004 | BUD-0185 | 9000.03.01-XPMS-003 | Digital two-way radios with belt clips and surveillance earpieces | 50 | 30 | 1500 | 5900 | CC-VENUE | Committed
POL-004-02 | PO-2026-004 | BUD-0185 | 9000.03.01-XPMS-001 | Multi-bay gang chargers for digital two-way radios | 8 | 25 | 200 | 5900 | CC-VENUE | Committed
POL-004-03 | PO-2026-004 | BUD-0185 | 9000.03.01-XPMS-005 | Digital UHF radio signal repeater with duplexer and antenna mast | 1 | 1700 | 1700 | 5900 | CC-VENUE | Committed
POL-005-01 | PO-2026-005 | BUD-0163 | 8000.01.01-XPMS-002 | VIP catering package with chef-designed passed canapés and grazing stations | 150 | 100 | 15000 | 5800 | CC-VENUE | Committed
POL-005-02 | PO-2026-005 | BUD-0163 | 8000.02.01-XPMS-001 | Portable custom bar stations with ice wells and speed rails | 4 | 375 | 1500 | 5800 | CC-VENUE | Committed

## Universal Posting Line
DATE | ACCOUNT CODE | COST CENTER CODE | URID | VENDOR ID | ITEM ID | DESCRIPTION | QUANTITY | UNIT BASIS | AMOUNT | TAX TYPE | CURRENCY | EXTERNAL REF | LINE STATE
2026-09-01 | 5600 | CC-VENUE | 6000.53.01 | VEN-022 | 6000.53.01-XOS-001 | Base rent monthly installment per lease agreement. | 1 | month | 70695 | Tax on Purchases | USD | BUD-0133 | Committed
2026-09-01 | 5600 | CC-VENUE | 6000.53.02 | VEN-022 | 6000.53.02-XOS-001 | Operating expense recovery monthly allocation. | 1 | month | 10757.25 | Tax on Purchases | USD | BUD-0135 | Committed
2026-09-01 | 5600 | CC-VENUE | 6000.51.01 | VEN-023 | 6000.51.01-XOS-001 | Standing janitorial and cleaning service monthly retainer. | 1 | month | 2651.06 | Tax on Purchases | USD | BUD-0126 | Committed
2026-09-01 | 5000 | CC-CORP | 0000.01.01 | VEN-016 | 0000.01.01-XPMS-004 | Management retainer monthly allocation for executive governance. | 1 | month | 15000 | Tax on Purchases | USD | RET-001 | Committed

## Procurement Catalog
ITEM ID | URID | ITEM NAME | RESOURCE KIND | SCHEMA FAMILY (XYZ) | DEFAULT GL ACCOUNT | DEFAULT GL NAME | DEFAULT COST CENTER | UNIT OF MEASURE | GRADE 1 BASIC ($ LOW) | GRADE 2 STANDARD ($ COST) | GRADE 3 PREMIUM ($ HIGH) | DESCRIPTION | SPECIFICATIONS | LEAD TIME (HRS) | TIER | DEFAULT PHASE | EXTERNAL REF
0000.51.01-XOS-004 | 0000.51.01 | Lease Security Deposit | asset | X | 1500 | Fixed Assets | CC-CORP | each | 35000 | 45000 | 60000 | Refundable deposit held by the landlord. |  |  | 04 Physical | Scope | 0000.51.01-XOS-1600-1472
0000.51.01-XOS-005 | 0000.51.01 | Vendor Deposit | asset | X | 1500 | Fixed Assets | CC-CORP | each | 15000 | 20000 | 28000 | Refundable deposit held by a vendor. |  |  | 04 Physical | Scope | 0000.51.01-XOS-1600-1473
0000.51.01-XOS-001 | 0000.51.01 | Accrued Event Cost | liability | X | 2200 | Deferred Revenue | CC-CORP | each | 5000 | 7500 | 10000 | Cost incurred and not yet invoiced. |  |  | 04 Physical | Scope | 0000.51.01-XOS-2200-1474
0000.51.01-XOS-002 | 0000.51.01 | Deferred Hire Revenue | liability | X | 2300 | Sales Tax Payable | CC-CORP | each | 15000 | 25000 | 40000 | Hire revenue received before the event. |  |  | 04 Physical | Scope | 0000.51.01-XOS-2300-1476
0000.51.01-XOS-003 | 0000.51.01 | Deferred Sponsorship Revenue | liability | X | 2300 | Sales Tax Payable | CC-CORP | each | 35000 | 50000 | 75000 | Sponsor revenue received before the event. |  |  | 04 Physical | Scope | 0000.51.01-XOS-2300-1475
0000.01.01-XOS-001 | 0000.01.01 | Private Hire · Full Venue | revenue | Y | 4000 | Revenue · Executive | CC-CORP | day | 3500 | 5000 | 7500 | Full venue hire for a private event, per day. |  |  | 04 Physical | Scope | 0000.01.01-XOS-4100-1443
0000.01.01-XOS-002 | 0000.01.01 | Private Hire · Single Zone | revenue | Y | 4000 | Revenue · Executive | CC-CORP | day | 1500 | 2500 | 4000 | Single zone hire, per day. |  |  | 04 Physical | Scope | 0000.01.01-XOS-4100-1444
0000.01.01-XOS-003 | 0000.01.01 | Production Fee | revenue | Y | 4000 | Revenue · Executive | CC-CORP | event | 3500 | 5000 | 7500 | Production management fee invoiced to the brand house, per event. |  |  | 04 Physical | Scope | 0000.01.01-XOS-4100-1445
0000.01.01-XOS-004 | 0000.01.01 | Sponsorship · Presenting | revenue | Y | 4000 | Revenue · Executive | CC-CORP | package | 25000 | 35000 | 50000 | Presenting sponsorship package. |  |  | 04 Physical | Scope | 0000.01.01-XOS-4300-1451
0000.01.01-XOS-005 | 0000.01.01 | Sponsorship · Title | revenue | Y | 4000 | Revenue · Executive | CC-CORP | package | 50000 | 75000 | 120000 | Title sponsorship package against evidenced deliverables. |  |  | 04 Physical | Scope | 0000.01.01-XOS-4300-1450
0000.01.01-XOS-006 | 0000.01.01 | Ticket · General Admission | revenue | Y | 4000 | Revenue · Executive | CC-CORP | each | 45 | 65 | 95 | General admission ticket. |  |  | 04 Physical | Scope | 0000.01.01-XOS-4100-1446
0000.01.01-XOS-007 | 0000.01.01 | Ticket · VIP | revenue | Y | 4000 | Revenue · Executive | CC-CORP | each | 125 | 185 | 275 | VIP ticket with premium access. |  |  | 04 Physical | Scope | 0000.01.01-XOS-4100-1447
0000.01.01-XOS-008 | 0000.01.01 | Value in Kind | revenue | Y | 4000 | Revenue · Executive | CC-CORP | each | 10000 | 15000 | 25000 | Sponsor-provided goods or services at agreed value. |  |  | 04 Physical | Scope | 0000.01.01-XOS-4300-1452
7000.01.01-XOS-022 | 7000.01.01 | Coat Check Fee | revenue | Y | 4700 | Revenue · Experience | CC-VENUE | each | 5 | 7.5 | 10 | Coat and bag check, per item. |  |  | 04 Physical | Scope | 7000.01.01-XOS-4400-1454
7000.01.01-XOS-023 | 7000.01.01 | Merchandise Sales | revenue | Y | 4700 | Revenue · Experience | CC-VENUE | each | 25 | 35 | 55 | Merchandise at the point of sale. |  |  | 04 Physical | Scope | 7000.01.01-XOS-4400-1453
7000.01.01-XOS-024 | 7000.01.01 | Parking and Valet Fee | revenue | Y | 4700 | Revenue · Experience | CC-VENUE | each | 20 | 30 | 45 | Parking or valet, per vehicle. |  |  | 04 Physical | Scope | 7000.01.01-XOS-4400-1455
8000.01.01-XOS-031 | 8000.01.01 | Bar Sales | revenue | Y | 4800 | Revenue · Hospitality | CC-VENUE | each | 12 | 16 | 22 | Bar revenue at the point of sale. |  |  | 04 Physical | Scope | 8000.01.01-XOS-4200-1448
8000.01.01-XOS-032 | 8000.01.01 | Catering Sales | revenue | Y | 4800 | Revenue · Hospitality | CC-VENUE | cover | 45 | 65 | 95 | Food revenue at the point of sale or per cover. |  |  | 04 Physical | Scope | 8000.01.01-XOS-4200-1449
0000.01.01-XPMS-011 | 0000.01.01 | Budget Envelope Development | service | Y | 5000 | Expense · Executive | CC-CORP | each | 6500 | 8500 | 12000 | Order-of-magnitude cost model built from comparable engagements, establishing the envelope a design is constrained by. Carries its own confidence and is superseded by the gate 3 baseline, never merged into it. |  |  | 05 Experiential | Scope
0000.01.01-XPMS-001 | 0000.01.01 | Executive Producer or Project Lead | service | Y | 5000 | Expense · Executive | CC-CORP | each | 1500 | 1800 | 2200 | Senior producer accountable for the engagement. |  |  | 05 Experiential | Operate
0000.01.01-XPMS-009 | 0000.01.01 | Feasibility Study | service | Y | 5000 | Expense · Executive | CC-CORP | each | 7500 | 10000 | 15000 | Structured assessment of whether a proposed event can be delivered at the stated scope, budget and date in a named jurisdiction. Covers venue capacity, code constraints, labour availability, seasonality and permit lead times. Produces a go / no-go recommendation with the constraints that drove it. |  |  | 05 Experiential | Scope
0000.01.01-XPMS-008 | 0000.01.01 | Insurance or Permits | package | Y | 5000 | Expense · Executive | CC-CORP | each | 4500 | 6500 | 9500 | Executive · Insurance / permits. |  |  | 04 Physical | Operate
0000.01.01-XPMS-006 | 0000.01.01 | Insurance · GL, Property, Liquor | opex | Y | 5000 | Expense · Executive | CC-CORP | each | 6500 | 8500 | 12000 | Executive · Insurance; GL, Property, Liquor. |  |  | 04 Physical | Operate
0000.01.01-XPMS-005 | 0000.01.01 | Legal & Compliance | opex | X | 5000 | Expense · Executive | CC-CORP | each | 3500 | 5000 | 7500 | Executive · Legal and Compliance. |  |  | 04 Physical | Operate
0000.01.01-XPMS-004 | 0000.01.01 | Management Retainer | opex | Y | 5000 | Expense · Executive | CC-CORP | each | 7500 | 10000 | 15000 | Executive · Management Retainer. |  |  | 04 Physical | Operate
0000.01.01-XPMS-007 | 0000.01.01 | Permits & Licenses (amortized) | opex | Y | 5000 | Expense · Executive | CC-CORP | each | 2500 | 3500 | 5000 | Executive · Permits and Licenses (amortized). |  |  | 04 Physical | Operate
0000.01.01-XPMS-010 | 0000.01.01 | Project Charter & Objectives Definition | service | Y | 5000 | Expense · Executive | CC-CORP | each | 4500 | 6500 | 9500 | Facilitated definition of measurable objectives, success criteria, scope boundaries and named decision authority. Gate 8 measures against these, so a project without them can report activity but not success. |  |  | 05 Experiential | Scope
0000.01.01-XPMS-002 | 0000.01.01 | Project Controls or ATLVS Instance | service | Y | 5000 | Expense · Executive | CC-CORP | each | 5000 | 7500 | 12000 | Controls, reporting, software setup. |  |  | 04 Physical | Build
0000.01.01-XPMS-003 | 0000.01.01 | Waste Diversion + Sustainable Materials | service | Y | 5000 | Expense · Executive | CC-CORP | each | 3500 | 5000 | 7500 | Diversion plan + materials premium. |  |  | 04 Physical | Build
0000.02.01-XPMS-003 | 0000.02.01 | Bookkeeping & Job-Costing | opex | X | 5000 | Expense · Executive | CC-VENUE | each | 1800 | 2500 | 3500 | Dedicated job-cost ledger. |  |  | 04 Physical | Operate
0000.02.01-XPMS-004 | 0000.02.01 | Pro Forma & Scenario Modelling | service | Y | 5000 | Expense · Executive | CC-VENUE | each | 4500 | 6500 | 9500 | Revenue and cost scenarios across attendance, pricing and scope variants, showing where the engagement breaks even and where it fails. Scenario modelling, not a forecast. |  |  | 05 Experiential | Scope
0000.02.01-XPMS-001 | 0000.02.01 | Production Accounting & Budget Management | service | Y | 5000 | Expense · Executive | CC-VENUE | each | 3500 | 5000 | 7500 | Budgeting, cost tracking, reconciliation. |  |  | 05 Experiential | Operate
0000.02.01-XPMS-002 | 0000.02.01 | Project Bookkeeping & Job-Costing | service | Y | 5000 | Expense · Executive | CC-VENUE | each | 2500 | 3500 | 5000 | Dedicated job-cost ledger. |  |  | 04 Physical | Build
0000.03.01-XPMS-001 | 0000.03.01 | Contract & Legal Review | service | Y | 5000 | Expense · Executive | CC-VENUE | each | 2500 | 3500 | 5000 | Contracts, releases, risk review. |  |  | 05 Experiential | Operate
0000.03.01-XPMS-002 | 0000.03.01 | Legal or Vendor Contracting | service | Y | 5000 | Expense · Executive | CC-VENUE | each | 4500 | 6500 | 9500 | MSAs, SOWs, vendor agreements. |  |  | 04 Physical | Build
0000.03.01-XPMS-003 | 0000.03.01 | Risk Register Development | service | Y | 5000 | Expense · Executive | CC-VENUE | each | 3500 | 5000 | 7500 | Initial identification, likelihood and impact scoring of project risks, with named owners. Maintained through the lifecycle; the register, not the memory of it, is the deliverable. |  |  | 05 Experiential | Scope
0000.04.01-XPMS-001 | 0000.04.01 | Staffing & HR Coordination | service | Y | 5000 | Expense · Executive | CC-VENUE | each | 750 | 950 | 1250 | Crew HR, onboarding, labor coordination. |  |  | 05 Experiential | Operate
0000.05.01-XPMS-001 | 0000.05.01 | Partnership Development | service | Y | 5000 | Expense · Executive | CC-VENUE | each | 3500 | 5000 | 7500 | Partner sourcing and deal development. |  |  | 05 Experiential | Operate
0000.05.01-XPMS-002 | 0000.05.01 | Sponsorship Prospecting & Valuation | service | Y | 5000 | Expense · Executive | CC-VENUE | each | 6500 | 9500 | 14000 | Identification of sponsorship prospects and valuation of available inventory against comparable engagements. Establishes what may be contracted, which gate 8 must later evidence. |  |  | 05 Experiential | Scope
0000.06.01-XPMS-001 | 0000.06.01 | General Liability & Builders-Risk Insurance | service | Y | 5000 | Expense · Executive | CC-VENUE | each | 5500 | 7500 | 11000 | Event GL and builders-risk coverage. |  |  | 05 Experiential | Operate
0000.06.01-XPMS-003 | 0000.06.01 | Jurisdiction & Permit Feasibility Review | service | Y | 5000 | Expense · Executive | CC-VENUE | each | 3500 | 5000 | 7500 | Determination of which authority has jurisdiction, which permits the concept triggers, and what the lead times are. Where the jurisdiction carries no loaded rule set, this review states that no answer is available rather than applying another jurisdiction's code. |  |  | 05 Experiential | Scope
0000.06.01-XPMS-002 | 0000.06.01 | Permit Coordination Liaison | service | Y | 5000 | Expense · Executive | CC-VENUE | each | 2500 | 3500 | 5000 | Liaison; permitting led by Spotify. |  |  | 04 Physical | Build
0000.06.02-XPMS-001 | 0000.06.02 | Event Permits & Licensing | service | Y | 5000 | Expense · Executive | CC-VENUE | each | 3500 | 5000 | 7500 | Permit filing, licensing, expediting. |  |  | 05 Experiential | Operate
0000.50.01-XOS-001 | 0000.50.01 | Client Sponsorship | service | Y | 5000 | Expense · Executive | CC-VENUE | lump sum | 15000 | 25000 | 40000 | Representative line for client sponsorship so the category can carry cost. Replace with the specific item on award. |  |  | 04 Physical | Procure | 0000.50.01-XOS-001
0000.50.02-XOS-001 | 0000.50.02 | Operator Leadership | service | Y | 5000 | Expense · Executive | CC-VENUE | lump sum | 10000 | 15000 | 25000 | Representative line for operator leadership so the category can carry cost. Replace with the specific item on award. |  |  | 04 Physical | Procure | 0000.50.02-XOS-001
0000.50.03-XOS-001 | 0000.50.03 | Approval Authority | service | Y | 5000 | Expense · Executive | CC-VENUE | lump sum | 5000 | 7500 | 12000 | Representative line for approval authority so the category can carry cost. Replace with the specific item on award. |  |  | 04 Physical | Procure | 0000.50.03-XOS-001
0000.51.01-XOS-006 | 0000.51.01 | Financial Control | service | Y | 5000 | Expense · Executive | CC-CORP | lump sum | 4500 | 6500 | 9500 | Representative line for financial control so the category can carry cost. Replace with the specific item on award. |  |  | 04 Physical | Procure | 0000.51.01-XOS-001
0000.51.02-XOS-001 | 0000.51.02 | General Liability Policy | insurance | Y | 5000 | Expense · Executive | CC-CORP | year | 6500 | 9500 | 14000 | Annual general liability policy. |  |  | 04 Physical | Procure | 0000.51.02-XOS-6020-1456
0000.51.02-XOS-005 | 0000.51.02 | Insurance and Risk | service | Y | 5000 | Expense · Executive | CC-CORP | lump sum | 5000 | 7500 | 12000 | Representative line for insurance and risk so the category can carry cost. Replace with the specific item on award. |  |  | 04 Physical | Procure | 0000.51.02-XOS-001
0000.51.02-XOS-002 | 0000.51.02 | Liquor Liability Policy | insurance | Y | 5000 | Expense · Executive | CC-CORP | year | 4500 | 6500 | 9500 | Annual liquor liability policy. |  |  | 04 Physical | Procure | 0000.51.02-XOS-6020-1457
0000.51.02-XOS-003 | 0000.51.02 | Property Policy | insurance | Y | 5000 | Expense · Executive | CC-CORP | year | 3500 | 5000 | 7500 | Annual property and contents policy. |  |  | 04 Physical | Procure | 0000.51.02-XOS-6020-1459
0000.51.02-XOS-004 | 0000.51.02 | Umbrella Policy | insurance | Y | 5000 | Expense · Executive | CC-CORP | year | 5500 | 7500 | 11000 | Annual umbrella policy. |  |  | 04 Physical | Procure | 0000.51.02-XOS-6020-1458
0000.51.03-XOS-001 | 0000.51.03 | Business Tax Receipt | license | Y | 5000 | Expense · Executive | CC-CORP | year | 650 | 950 | 1500 | City and county business license. |  |  | 04 Physical | Procure | 0000.51.03-XOS-6030-1464
0000.51.03-XOS-007 | 0000.51.03 | Legal Counsel | service | Y | 5000 | Expense · Executive | CC-CORP | lump sum | 5000 | 7500 | 12000 | Representative line for legal counsel so the category can carry cost. Replace with the specific item on award. |  |  | 04 Physical | Procure | 0000.51.03-XOS-001
0000.51.03-XOS-002 | 0000.51.03 | Performance Rights License · ASCAP | license | Y | 5000 | Expense · Executive | CC-CORP | year | 1500 | 2200 | 3200 | Annual public performance license. |  |  | 04 Physical | Procure | 0000.51.03-XOS-6030-1460
0000.51.03-XOS-003 | 0000.51.03 | Performance Rights License · BMI | license | Y | 5000 | Expense · Executive | CC-CORP | year | 1500 | 2200 | 3200 | Annual public performance license. |  |  | 04 Physical | Procure | 0000.51.03-XOS-6030-1461
0000.51.03-XOS-004 | 0000.51.03 | Performance Rights License · GMR | license | Y | 5000 | Expense · Executive | CC-CORP | year | 1200 | 1800 | 2600 | Annual public performance license. |  |  | 04 Physical | Procure | 0000.51.03-XOS-6030-1463
0000.51.03-XOS-005 | 0000.51.03 | Performance Rights License · SESAC | license | Y | 5000 | Expense · Executive | CC-CORP | year | 1200 | 1800 | 2600 | Annual public performance license. |  |  | 04 Physical | Procure | 0000.51.03-XOS-6030-1462
0000.51.03-XOS-006 | 0000.51.03 | Special Event Permit | license | Y | 5000 | Expense · Executive | CC-CORP | event | 1500 | 2500 | 4000 | Per-event permit where triggered by occupancy, hours or street use. |  |  | 04 Physical | Procure | 0000.51.03-XOS-6030-1465
0000.60.01-XOS-001 | 0000.60.01 | Scope Activities · Executive | service | Y | 5000 | Expense · Executive | CC-E00 | lump sum | 3500 | 5000 | 7500 | Representative line for scope activities so the category can carry cost. Replace with the specific item on award. |  |  | 04 Physical | Scope | 0000.60.01-XOS-001
0000.60.02-XOS-001 | 0000.60.02 | Engage Activities · Executive | service | Y | 5000 | Expense · Executive | CC-E00 | lump sum | 5000 | 7500 | 12000 | Representative line for engage activities so the category can carry cost. Replace with the specific item on award. |  |  | 04 Physical | Engage | 0000.60.02-XOS-001
0000.60.03-XOS-001 | 0000.60.03 | Advance Activities · Executive | service | Y | 5000 | Expense · Executive | CC-E00 | lump sum | 5000 | 7500 | 12000 | Representative line for advance activities so the category can carry cost. Replace with the specific item on award. |  |  | 04 Physical | Advance | 0000.60.03-XOS-001
0000.60.04-XOS-001 | 0000.60.04 | Procure Activities · Executive | service | Y | 5000 | Expense · Executive | CC-E00 | lump sum | 6500 | 9500 | 15000 | Representative line for procure activities so the category can carry cost. Replace with the specific item on award. |  |  | 04 Physical | Procure | 0000.60.04-XOS-001
0000.60.05-XOS-001 | 0000.60.05 | Build Activities · Executive | service | Y | 5000 | Expense · Executive | CC-E00 | lump sum | 10000 | 15000 | 25000 | Representative line for build activities so the category can carry cost. Replace with the specific item on award. |  |  | 04 Physical | Build | 0000.60.05-XOS-001
0000.60.06-XOS-001 | 0000.60.06 | Install Activities · Executive | service | Y | 5000 | Expense · Executive | CC-E00 | lump sum | 10000 | 15000 | 25000 | Representative line for install activities so the category can carry cost. Replace with the specific item on award. |  |  | 04 Physical | Install | 0000.60.06-XOS-001
0000.60.07-XOS-001 | 0000.60.07 | Operate Activities · Executive | service | Y | 5000 | Expense · Executive | CC-E00 | lump sum | 7500 | 10000 | 15000 | Representative line for operate activities so the category can carry cost. Replace with the specific item on award. |  |  | 04 Physical | Operate | 0000.60.07-XOS-001
0000.60.08-XOS-001 | 0000.60.08 | Amplify Activities · Executive | service | Y | 5000 | Expense · Executive | CC-E00 | lump sum | 4500 | 6500 | 9500 | Representative line for amplify activities so the category can carry cost. Replace with the specific item on award. |  |  | 04 Physical | Amplify | 0000.60.08-XOS-001
0000.60.09-XOS-001 | 0000.60.09 | Close Activities · Executive | service | Y | 5000 | Expense · Executive | CC-E00 | lump sum | 3500 | 5000 | 7500 | Representative line for close activities so the category can carry cost. Replace with the specific item on award. |  |  | 04 Physical | Close | 0000.60.09-XOS-001
1000.01.01-XPMS-002 | 1000.01.01 | 3D Renderings · 5 Key Spaces | service | Y | 5100 | Expense · Creative | CC-VENUE | each | 2500 | 3500 | 5000 | Photoreal renderings. |  |  | 04 Physical | Build
1000.01.01-XOS-031 | 1000.01.01 | Arrival or Ambient Soundscape · Base | experience | Y | 5100 | Expense · Creative | CC-VENUE | each | 750 | 1100 | 1600 | Background playlist at arrival and lounge zones. | Zone: Entrance / Lobby. Tier fit: T1; T4. Upgrades: Custom-composed ambient score. Add-ons: Spatial zone audio. Substitutions: Standard playlist only. |  | 05 Experiential | Scope | SND-03
1000.01.01-XOS-032 | 1000.01.01 | Arrival or Ambient Soundscape · Elevated | experience | Y | 5100 | Expense · Creative | CC-VENUE | each | 950 | 1350 | 1950 | Designed arrival soundscape with zone-specific moods. | Zone: Entrance / Lobby. Tier fit: T1; T4. Upgrades: Custom-composed ambient score. Add-ons: Spatial zone audio. Substitutions: Standard playlist only. |  | 05 Experiential | Scope | SND-03
1000.01.01-XOS-033 | 1000.01.01 | Arrival or Ambient Soundscape · Premium | experience | Y | 5100 | Expense · Creative | CC-VENUE | each | 1450 | 2100 | 3100 | Composed ambient score that evolves across the guest journey and zones. | Zone: Entrance / Lobby. Tier fit: T1; T4. Upgrades: Custom-composed ambient score. Add-ons: Spatial zone audio. Substitutions: Standard playlist only. |  | 05 Experiential | Scope | SND-03
1000.01.01-XOS-001 | 1000.01.01 | Bar & Menu Boards · Base | experience | Y | 5100 | Expense · Creative | CC-VENUE | each | 35 | 55 | 85 | Printed bar menu cards at each station. | Zone: Main Stage and Bar. Tier fit: T1; T4. Upgrades: Backlit menu wall; chalk mural. Add-ons: Digital menu screen. Substitutions: Tabletop menu cards only. |  | 04 Physical | Build | SGT-19
1000.01.01-XOS-002 | 1000.01.01 | Bar & Menu Boards · Elevated | experience | Y | 5100 | Expense · Creative | CC-VENUE | each | 75 | 115 | 175 | A-frame or easel menu boards with branded layout. | Zone: Main Stage and Bar. Tier fit: T1; T4. Upgrades: Backlit menu wall; chalk mural. Add-ons: Digital menu screen. Substitutions: Tabletop menu cards only. |  | 04 Physical | Build | SGT-19
1000.01.01-XOS-003 | 1000.01.01 | Bar & Menu Boards · Premium | experience | Y | 5100 | Expense · Creative | CC-VENUE | each | 145 | 210 | 320 | Backlit menu walls or chalk-art murals matched to the F&B story. | Zone: Main Stage and Bar. Tier fit: T1; T4. Upgrades: Backlit menu wall; chalk mural. Add-ons: Digital menu screen. Substitutions: Tabletop menu cards only. |  | 04 Physical | Build | SGT-19
1000.01.01-XOS-004 | 1000.01.01 | Bar or Zone Neon · Base | experience | Y | 5100 | Expense · Creative | CC-VENUE | each | 250 | 380 | 550 | Small neon zone label (e.g., bar name) per station. | Zone: Main Stage and Bar. Tier fit: T1; T4. Upgrades: Multi-zone neon set. Add-ons: Spanish-language variant. Substitutions: Printed zone signage. |  | 04 Physical | Build | SGT-50
1000.01.01-XOS-005 | 1000.01.01 | Bar or Zone Neon · Elevated | experience | Y | 5100 | Expense · Creative | CC-VENUE | each | 450 | 650 | 950 | Set of zone-name neons matched to sub-branding. | Zone: Main Stage and Bar. Tier fit: T1; T4. Upgrades: Multi-zone neon set. Add-ons: Spanish-language variant. Substitutions: Printed zone signage. |  | 04 Physical | Build | SGT-50
1000.01.01-XOS-006 | 1000.01.01 | Bar or Zone Neon · Premium | experience | Y | 5100 | Expense · Creative | CC-VENUE | each | 750 | 1100 | 1600 | Custom illuminated zone identities with layered lighting. | Zone: Main Stage and Bar. Tier fit: T1; T4. Upgrades: Multi-zone neon set. Add-ons: Spanish-language variant. Substitutions: Printed zone signage. |  | 04 Physical | Build | SGT-50
1000.01.01-XOS-007 | 1000.01.01 | Catchphrase Neon (Custom) · Base | experience | Y | 5100 | Expense · Creative | CC-VENUE | each | 450 | 650 | 950 | Single-color LED-neon phrase, up to 3ft, on a painted backer. | Zone: Exhibition Room. Tier fit: T1; T4. Upgrades: Glass-neon upgrade; oversized. Add-ons: Animated / sequenced neon. Substitutions: Backlit acrylic sign. |  | 04 Physical | Build | SGT-48
1000.01.01-XOS-008 | 1000.01.01 | Catchphrase Neon (Custom) · Elevated | experience | Y | 5100 | Expense · Creative | CC-VENUE | each | 750 | 1100 | 1600 | Two-tone LED-neon phrase on a finished backer with mounting. | Zone: Exhibition Room. Tier fit: T1; T4. Upgrades: Glass-neon upgrade; oversized. Add-ons: Animated / sequenced neon. Substitutions: Backlit acrylic sign. |  | 04 Physical | Build | SGT-48
1000.01.01-XOS-009 | 1000.01.01 | Catchphrase Neon (Custom) · Premium | experience | Y | 5100 | Expense · Creative | CC-VENUE | each | 1250 | 1850 | 2650 | Large custom glass-neon or premium LED phrase as a hero sign. | Zone: Exhibition Room. Tier fit: T1; T4. Upgrades: Glass-neon upgrade; oversized. Add-ons: Animated / sequenced neon. Substitutions: Backlit acrylic sign. |  | 04 Physical | Build | SGT-48
1000.01.01-XPMS-008 | 1000.01.01 | Concept Development & Creative Direction | service | Y | 5100 | Expense · Creative | CC-VENUE | each | 7500 | 11000 | 16500 | Development of the creative concept from brief to approved direction: narrative, visual language and experiential intent, with the reference material that justifies it. |  |  | 05 Experiential | Scope
1000.01.01-XPMS-001 | 1000.01.01 | Creative Direction | service | Y | 5100 | Expense · Creative | CC-VENUE | each | 1000 | 1250 | 1500 | Overall creative vision and art direction. |  |  | 05 Experiential | Operate
1000.01.01-XOS-019 | 1000.01.01 | Custom Packaging · Base | experience | Y | 5100 | Expense · Creative | CC-VENUE | each | 18 | 28 | 42 | Branded bag or tissue for merch/gifts. | Zone: Entrance / Lobby. Tier fit: T2; T4. Upgrades: Rigid box; foil; insert tray. Add-ons: Reusable / keepsake packaging. Substitutions: Plain bag only. |  | 04 Physical | Advance | TCH-12
1000.01.01-XOS-020 | 1000.01.01 | Custom Packaging · Elevated | experience | Y | 5100 | Expense · Creative | CC-VENUE | each | 35 | 52 | 78 | Custom-printed boxes and bags with tissue and sticker seal. | Zone: Entrance / Lobby. Tier fit: T2; T4. Upgrades: Rigid box; foil; insert tray. Add-ons: Reusable / keepsake packaging. Substitutions: Plain bag only. |  | 04 Physical | Advance | TCH-12
1000.01.01-XOS-021 | 1000.01.01 | Custom Packaging · Premium | experience | Y | 5100 | Expense · Creative | CC-VENUE | each | 65 | 95 | 145 | Bespoke rigid packaging with magnetic closure, foil, and insert tray. | Zone: Entrance / Lobby. Tier fit: T2; T4. Upgrades: Rigid box; foil; insert tray. Add-ons: Reusable / keepsake packaging. Substitutions: Plain bag only. |  | 04 Physical | Advance | TCH-12
1000.01.01-XPMS-004 | 1000.01.01 | Décor or Theming or Scenic Dressing | package | X | 5100 | Expense · Creative | CC-VENUE | each | 4500 | 6500 | 9500 | Creative · Décor / theming / scenic dressing. |  |  | 04 Physical | Operate
1000.01.01-XPMS-005 | 1000.01.01 | Environmental Graphics & Branding | service | Y | 5100 | Expense · Creative | CC-VENUE | each | 3500 | 5000 | 7500 | Creative · Environmental graphics and branding. |  |  | 04 Physical | Operate
1000.01.01-XPMS-003 | 1000.01.01 | Exhibition Content Curation & Layout | service | Y | 5100 | Expense · Creative | CC-VENUE | each | 4500 | 6500 | 9500 | Rotating artist content. |  |  | 04 Physical | Build
1000.01.01-XOS-022 | 1000.01.01 | Invitations · Base | experience | Y | 5100 | Expense · Creative | CC-VENUE | each | 12 | 18 | 28 | Digital invite with branded template. | Zone: Back of House. Tier fit: T1; T4. Upgrades: Letterpress / foil; wax seal. Add-ons: Bilingual invite suite. Substitutions: Digital invite only. |  | 04 Physical | Advance | TCH-07
1000.01.01-XOS-023 | 1000.01.01 | Invitations · Elevated | experience | Y | 5100 | Expense · Creative | CC-VENUE | each | 22 | 32 | 48 | Printed invite on quality stock with envelope. | Zone: Back of House. Tier fit: T1; T4. Upgrades: Letterpress / foil; wax seal. Add-ons: Bilingual invite suite. Substitutions: Digital invite only. |  | 04 Physical | Advance | TCH-07
1000.01.01-XOS-024 | 1000.01.01 | Invitations · Premium | experience | Y | 5100 | Expense · Creative | CC-VENUE | each | 38 | 55 | 85 | Letterpress or foil invitation suite with special finishes and wax seal. | Zone: Back of House. Tier fit: T1; T4. Upgrades: Letterpress / foil; wax seal. Add-ons: Bilingual invite suite. Substitutions: Digital invite only. |  | 04 Physical | Advance | TCH-07
1000.01.01-XPMS-007 | 1000.01.01 | Local Artist or Muralist Collaboration | service | Y | 5100 | Expense · Creative | CC-VENUE | each | 3500 | 5000 | 7500 | Creative · Local artist / muralist collaboration. |  |  | 04 Physical | Operate
1000.01.01-XOS-025 | 1000.01.01 | Menus & Place Cards (Printed) · Base | experience | Y | 5100 | Expense · Creative | CC-VENUE | each | 6.5 | 9.5 | 14.5 | Printed menu card per table. | Zone: El Patio. Tier fit: T1; T4. Upgrades: Foil / edge-paint finishes. Add-ons: Calligraphy place cards. Substitutions: Digital / chalkboard menu. |  | 04 Physical | Advance | TCH-08
1000.01.01-XOS-026 | 1000.01.01 | Menus & Place Cards (Printed) · Elevated | experience | Y | 5100 | Expense · Creative | CC-VENUE | each | 12 | 18 | 26 | Designed menu and place-card set on quality stock. | Zone: El Patio. Tier fit: T1; T4. Upgrades: Foil / edge-paint finishes. Add-ons: Calligraphy place cards. Substitutions: Digital / chalkboard menu. |  | 04 Physical | Advance | TCH-08
1000.01.01-XOS-027 | 1000.01.01 | Menus & Place Cards (Printed) · Premium | experience | Y | 5100 | Expense · Creative | CC-VENUE | each | 22 | 32 | 48 | Specialty-finish menus, place cards, and table numbers as a styled suite. | Zone: El Patio. Tier fit: T1; T4. Upgrades: Foil / edge-paint finishes. Add-ons: Calligraphy place cards. Substitutions: Digital / chalkboard menu. |  | 04 Physical | Advance | TCH-08
1000.01.01-XOS-010 | 1000.01.01 | Mural or Wall Art · Base | experience | Y | 5100 | Expense · Creative | CC-VENUE | each | 450 | 650 | 950 | Vinyl-applied graphic mural in palette. | Zone: All Zones. Tier fit: T1; T4. Upgrades: Live-painting activation. Add-ons: Bilingual artist statement card. Substitutions: Printed backdrop instead. |  | 04 Physical | Build | SGT-33
1000.01.01-XOS-011 | 1000.01.01 | Mural or Wall Art · Elevated | experience | Y | 5100 | Expense · Creative | CC-VENUE | each | 950 | 1450 | 2150 | Hand-painted live or pre-painted mural by a local artist. | Zone: All Zones. Tier fit: T1; T4. Upgrades: Live-painting activation. Add-ons: Bilingual artist statement card. Substitutions: Printed backdrop instead. |  | 04 Physical | Build | SGT-33
1000.01.01-XOS-012 | 1000.01.01 | Mural or Wall Art · Premium | experience | Y | 5100 | Expense · Creative | CC-VENUE | each | 1850 | 2750 | 3950 | Commissioned signature mural with dimensional or mixed-media elements. | Zone: All Zones. Tier fit: T1; T4. Upgrades: Live-painting activation. Add-ons: Bilingual artist statement card. Substitutions: Printed backdrop instead. |  | 04 Physical | Build | SGT-33
1000.01.01-XPMS-006 | 1000.01.01 | OOH or Experiential Installations | package | Y | 5100 | Expense · Creative | CC-VENUE | each | 5500 | 8000 | 12000 | Creative · OOH / experiential installations. |  |  | 04 Physical | Operate
1000.01.01-XOS-028 | 1000.01.01 | Programs & Run Cards · Base | experience | Y | 5100 | Expense · Creative | CC-VENUE | each | 8 | 12 | 18 | Printed one-page program or set times card. | Zone: Entrance / Lobby. Tier fit: T1; T4. Upgrades: Saddle-stitch / bound booklet. Add-ons: QR to digital program. Substitutions: Digital program only. |  | 04 Physical | Advance | TCH-09
1000.01.01-XOS-029 | 1000.01.01 | Programs & Run Cards · Elevated | experience | Y | 5100 | Expense · Creative | CC-VENUE | each | 14 | 20 | 30 | Folded program with lineup, map, and brand story. | Zone: Entrance / Lobby. Tier fit: T1; T4. Upgrades: Saddle-stitch / bound booklet. Add-ons: QR to digital program. Substitutions: Digital program only. |  | 04 Physical | Advance | TCH-09
1000.01.01-XOS-030 | 1000.01.01 | Programs & Run Cards · Premium | experience | Y | 5100 | Expense · Creative | CC-VENUE | each | 24 | 35 | 52 | Keepsake program booklet with artist content and special binding. | Zone: Entrance / Lobby. Tier fit: T1; T4. Upgrades: Saddle-stitch / bound booklet. Add-ons: QR to digital program. Substitutions: Digital program only. |  | 04 Physical | Advance | TCH-09
1000.01.01-XOS-013 | 1000.01.01 | Wayfinding & Directional · Base | experience | Y | 5100 | Expense · Creative | CC-VENUE | each | 120 | 180 | 260 | Foamcore directional signs on easels at decision points. | Zone: All Zones. Tier fit: T1; T4. Upgrades: Backlit / halo-lit lettering. Add-ons: Floor vinyl footpath. Substitutions: Digital wayfinding screen. |  | 04 Physical | Build | SGT-16
1000.01.01-XOS-014 | 1000.01.01 | Wayfinding & Directional · Elevated | experience | Y | 5100 | Expense · Creative | CC-VENUE | each | 250 | 360 | 520 | Printed rigid signs on branded stanchions with arrows and zone names. | Zone: All Zones. Tier fit: T1; T4. Upgrades: Backlit / halo-lit lettering. Add-ons: Floor vinyl footpath. Substitutions: Digital wayfinding screen. |  | 04 Physical | Build | SGT-16
1000.01.01-XOS-015 | 1000.01.01 | Wayfinding & Directional · Premium | experience | Y | 5100 | Expense · Creative | CC-VENUE | each | 450 | 680 | 980 | Dimensional routed wayfinding with standoff lettering and integrated lighting. | Zone: All Zones. Tier fit: T1; T4. Upgrades: Backlit / halo-lit lettering. Add-ons: Floor vinyl footpath. Substitutions: Digital wayfinding screen. |  | 04 Physical | Build | SGT-16
1000.01.01-XOS-016 | 1000.01.01 | Welcome or Entry Identification · Base | experience | Y | 5100 | Expense · Creative | CC-VENUE | each | 350 | 500 | 750 | Printed welcome banner at the entrance. | Zone: Entrance / Lobby. Tier fit: T1; T4. Upgrades: Lit entry portal; archway. Add-ons: Misting / red-carpet runner. Substitutions: Projection welcome gobo. |  | 04 Physical | Build | SGT-17
1000.01.01-XOS-017 | 1000.01.01 | Welcome or Entry Identification · Elevated | experience | Y | 5100 | Expense · Creative | CC-VENUE | each | 750 | 1100 | 1650 | Branded entry header with tensioned fabric and a freestanding ID monument. | Zone: Entrance / Lobby. Tier fit: T1; T4. Upgrades: Lit entry portal; archway. Add-ons: Misting / red-carpet runner. Substitutions: Projection welcome gobo. |  | 04 Physical | Build | SGT-17
1000.01.01-XOS-018 | 1000.01.01 | Welcome or Entry Identification · Premium | experience | Y | 5100 | Expense · Creative | CC-VENUE | each | 1450 | 2150 | 3150 | Sculptural entry portal with dimensional brand lockup and integrated lighting. | Zone: Entrance / Lobby. Tier fit: T1; T4. Upgrades: Lit entry portal; archway. Add-ons: Misting / red-carpet runner. Substitutions: Projection welcome gobo. |  | 04 Physical | Build | SGT-17
1000.02.01-XPMS-005 | 1000.02.01 | Design Development & Specification Package | service | Y | 5100 | Expense · Creative | CC-VENUE | each | 6500 | 9500 | 14000 | Resolution of schematic design into specified assemblies, materials, finishes and interfaces, sufficient to procure against. The document a bid is evaluated on. |  |  | 05 Experiential | Scope
1000.02.01-XPMS-001 | 1000.02.01 | Environment & Scenic Design | service | Y | 5100 | Expense · Creative | CC-VENUE | each | 4500 | 6500 | 9500 | Spatial, scenic, and set design. |  |  | 05 Experiential | Operate
1000.02.01-XPMS-003 | 1000.02.01 | FF&E Specification & Sourcing | service | Y | 5100 | Expense · Creative | CC-VENUE | each | 3500 | 5000 | 7500 | Spec + sourcing fee. |  |  | 04 Physical | Build
1000.02.01-XPMS-002 | 1000.02.01 | Schematic + Design Development | service | Y | 5100 | Expense · Creative | CC-VENUE | each | 6500 | 9500 | 14000 | Full-house schematic and DD. |  |  | 04 Physical | Build
1000.02.01-XPMS-004 | 1000.02.01 | Schematic Design Package | service | Y | 5100 | Expense · Creative | CC-VENUE | each | 4500 | 6500 | 9500 | Plans, elevations and sections establishing spatial arrangement and scale, sufficient for order-of-magnitude costing and stakeholder approval. Precedes any fabrication drawing. |  |  | 05 Experiential | Scope
1000.03.01-XOS-001 | 1000.03.01 | Bar Sub-Brand Identity · Base | experience | Y | 5100 | Expense · Creative | CC-VENUE | each | 350 | 550 | 850 | Bar named with a printed header card. | Zone: Main Stage and Bar. Tier fit: T2; T4. Upgrades: Branded glassware + staff styling. Add-ons: Pop-up partner bar concept. Substitutions: House bar (no sub-brand). |  | 04 Physical | Scope | SGT-52
1000.03.01-XOS-002 | 1000.03.01 | Bar Sub-Brand Identity · Elevated | experience | Y | 5100 | Expense · Creative | CC-VENUE | each | 750 | 1100 | 1650 | Named bar with logo, menu, and matching signage. | Zone: Main Stage and Bar. Tier fit: T2; T4. Upgrades: Branded glassware + staff styling. Add-ons: Pop-up partner bar concept. Substitutions: House bar (no sub-brand). |  | 04 Physical | Scope | SGT-52
1000.03.01-XOS-003 | 1000.03.01 | Bar Sub-Brand Identity · Premium | experience | Y | 5100 | Expense · Creative | CC-VENUE | each | 1450 | 2200 | 3200 | Fully art-directed bar concept: identity, menu, glassware, and staff styling. | Zone: Main Stage and Bar. Tier fit: T2; T4. Upgrades: Branded glassware + staff styling. Add-ons: Pop-up partner bar concept. Substitutions: House bar (no sub-brand). |  | 04 Physical | Scope | SGT-52
1000.03.01-XPMS-001 | 1000.03.01 | Brand & Identity System | service | Y | 5100 | Expense · Creative | CC-VENUE | each | 4500 | 6500 | 9500 | Identity system, sub-brands, guidelines. |  |  | 05 Experiential | Operate
1000.03.01-XOS-004 | 1000.03.01 | Brand Lockup Neon · Base | experience | Y | 5100 | Expense · Creative | CC-VENUE | each | 350 | 550 | 850 | Single-color brand wordmark in LED-neon. | Zone: Entrance / Lobby. Tier fit: T1; T4. Upgrades: Scenic-integrated install. Add-ons: Color-changing control. Substitutions: Lit acrylic lockup. |  | 04 Physical | Build | SGT-49
1000.03.01-XOS-005 | 1000.03.01 | Brand Lockup Neon · Elevated | experience | Y | 5100 | Expense · Creative | CC-VENUE | each | 650 | 950 | 1450 | Brand lockup neon with finished backer and dimmer. | Zone: Entrance / Lobby. Tier fit: T1; T4. Upgrades: Scenic-integrated install. Add-ons: Color-changing control. Substitutions: Lit acrylic lockup. |  | 04 Physical | Build | SGT-49
1000.03.01-XOS-006 | 1000.03.01 | Brand Lockup Neon · Premium | experience | Y | 5100 | Expense · Creative | CC-VENUE | each | 1250 | 1850 | 2650 | Dimensional brand neon integrated into a scenic feature. | Zone: Entrance / Lobby. Tier fit: T1; T4. Upgrades: Scenic-integrated install. Add-ons: Color-changing control. Substitutions: Lit acrylic lockup. |  | 04 Physical | Build | SGT-49
1000.03.01-XPMS-002 | 1000.03.01 | Brand Toolkit Application | service | Y | 5100 | Expense · Creative | CC-VENUE | each | 3500 | 5000 | 7500 | Spotify toolkit + env graphics design. |  |  | 04 Physical | Build
1000.03.01-XOS-007 | 1000.03.01 | Lounge or Activation Sub-Brand · Base | experience | Y | 5100 | Expense · Creative | CC-VENUE | each | 450 | 680 | 980 | Lounge labeled with a simple name sign. | Zone: Exhibition Room. Tier fit: T2; T4. Upgrades: Content hook + hashtag system. Add-ons: Sponsor co-brand layer. Substitutions: Unbranded lounge. |  | 04 Physical | Scope | SGT-53
1000.03.01-XOS-008 | 1000.03.01 | Lounge or Activation Sub-Brand · Elevated | experience | Y | 5100 | Expense · Creative | CC-VENUE | each | 850 | 1250 | 1850 | Lounge concept with name, palette, and applied graphics. | Zone: Exhibition Room. Tier fit: T2; T4. Upgrades: Content hook + hashtag system. Add-ons: Sponsor co-brand layer. Substitutions: Unbranded lounge. |  | 04 Physical | Scope | SGT-53
1000.03.01-XOS-009 | 1000.03.01 | Lounge or Activation Sub-Brand · Premium | experience | Y | 5100 | Expense · Creative | CC-VENUE | each | 1650 | 2450 | 3550 | Signature activation sub-brand with identity, set, and content hook. | Zone: Exhibition Room. Tier fit: T2; T4. Upgrades: Content hook + hashtag system. Add-ons: Sponsor co-brand layer. Substitutions: Unbranded lounge. |  | 04 Physical | Scope | SGT-53
1000.03.01-XOS-010 | 1000.03.01 | Sponsor or Brand Lockups · Base | experience | Y | 5100 | Expense · Creative | CC-VENUE | each | 250 | 380 | 550 | Single printed sponsor banner. | Zone: All Zones. Tier fit: T1; T4. Upgrades: Dimensional lit lockup. Add-ons: Co-brand partner panel. Substitutions: Digital lockup on screens. |  | 04 Physical | Build | SGT-20
1000.03.01-XOS-011 | 1000.03.01 | Sponsor or Brand Lockups · Elevated | experience | Y | 5100 | Expense · Creative | CC-VENUE | each | 450 | 680 | 980 | Tensioned-fabric brand lockups at key sightlines and the stage. | Zone: All Zones. Tier fit: T1; T4. Upgrades: Dimensional lit lockup. Add-ons: Co-brand partner panel. Substitutions: Digital lockup on screens. |  | 04 Physical | Build | SGT-20
1000.03.01-XOS-012 | 1000.03.01 | Sponsor or Brand Lockups · Premium | experience | Y | 5100 | Expense · Creative | CC-VENUE | each | 850 | 1250 | 1850 | Dimensional brand walls and lit lockups integrated into scenic. | Zone: All Zones. Tier fit: T1; T4. Upgrades: Dimensional lit lockup. Add-ons: Co-brand partner panel. Substitutions: Digital lockup on screens. |  | 04 Physical | Build | SGT-20
1000.03.01-XOS-013 | 1000.03.01 | Zone Naming System · Base | experience | Y | 5100 | Expense · Creative | CC-VENUE | each | 250 | 380 | 550 | Functional zone names (Bar, Lounge, Stage) on signage. | Zone: All Zones. Tier fit: T1; T4. Upgrades: Per-zone identity system. Add-ons: Bilingual naming (EN/ES). Substitutions: Generic functional naming. |  | 04 Physical | Scope | SGT-51
1000.03.01-XOS-014 | 1000.03.01 | Zone Naming System · Elevated | experience | Y | 5100 | Expense · Creative | CC-VENUE | each | 480 | 720 | 1050 | Themed zone names tied to the artist story across signage and menus. | Zone: All Zones. Tier fit: T1; T4. Upgrades: Per-zone identity system. Add-ons: Bilingual naming (EN/ES). Substitutions: Generic functional naming. |  | 04 Physical | Scope | SGT-51
1000.03.01-XOS-015 | 1000.03.01 | Zone Naming System · Premium | experience | Y | 5100 | Expense · Creative | CC-VENUE | each | 950 | 1450 | 2150 | Full sub-brand identity per zone: name, mark, copy, and applied graphics. | Zone: All Zones. Tier fit: T1; T4. Upgrades: Per-zone identity system. Add-ons: Bilingual naming (EN/ES). Substitutions: Generic functional naming. |  | 04 Physical | Scope | SGT-51
1000.04.01-XPMS-001 | 1000.04.01 | Graphic & Signage Design | service | Y | 5100 | Expense · Creative | CC-VENUE | each | 550 | 750 | 950 | Graphics, signage, and print design. |  |  | 05 Experiential | Operate
1000.04.01-XPMS-002 | 1000.04.01 | Wayfinding & Signage Design | service | Y | 5100 | Expense · Creative | CC-VENUE | each | 4500 | 6500 | 9500 | Signage schedule, hierarchy, placement and specification, including regulatory and accessibility signage required by the jurisdiction. |  |  | 05 Experiential | Scope
1000.04.02-XPMS-001 | 1000.04.02 | Stationery & Print Collateral Design | service | Y | 5100 | Expense · Creative | CC-VENUE | each | 3500 | 5000 | 7500 | Menus, stationery, invitations, collateral. |  |  | 05 Experiential | Operate
1000.04.02-XOS-001 | 1000.04.02 | Thank-You & Collateral · Base | experience | Y | 5100 | Expense · Creative | CC-VENUE | each | 8 | 12 | 18 | Printed thank-you card at exit. | Zone: Entrance / Lobby. Tier fit: T1; T4. Upgrades: Personalized / hand-signed. Add-ons: Follow-up digital recap link. Substitutions: Digital thank-you only. |  | 04 Physical | Advance | TCH-10
1000.04.02-XOS-002 | 1000.04.02 | Thank-You & Collateral · Elevated | experience | Y | 5100 | Expense · Creative | CC-VENUE | each | 16 | 24 | 35 | Thank-you note plus a branded collateral piece (sticker, card). | Zone: Entrance / Lobby. Tier fit: T1; T4. Upgrades: Personalized / hand-signed. Add-ons: Follow-up digital recap link. Substitutions: Digital thank-you only. |  | 04 Physical | Advance | TCH-10
1000.04.02-XOS-003 | 1000.04.02 | Thank-You & Collateral · Premium | experience | Y | 5100 | Expense · Creative | CC-VENUE | each | 28 | 42 | 62 | Personalized thank-you suite with follow-up gift card and packaging. | Zone: Entrance / Lobby. Tier fit: T1; T4. Upgrades: Personalized / hand-signed. Add-ons: Follow-up digital recap link. Substitutions: Digital thank-you only. |  | 04 Physical | Advance | TCH-10
1000.05.01-XPMS-004 | 1000.05.01 | Content Editing & Post-Production | service | Y | 5100 | Expense · Creative | CC-VENUE | each | 1200 | 1600 | 2200 | Editorial, colour, sound and finishing of captured material into delivered assets. Priced by the edit day rather than the deliverable, since scope is set by footage volume rather than output count. |  |  | 05 Experiential | Amplify
1000.05.01-XPMS-001 | 1000.05.01 | Content Production (Photo or Video) | service | Y | 5100 | Expense · Creative | CC-VENUE | each | 850 | 1100 | 1450 | Photo, video, and motion content. |  |  | 05 Experiential | Operate
1000.05.01-XPMS-005 | 1000.05.01 | Photo Editing & Asset Delivery | service | Y | 5100 | Expense · Creative | CC-VENUE | each | 1450 | 1950 | 2650 | Selection, retouching, captioning and delivery of event photography to a named asset library with usage terms attached. |  |  | 05 Experiential | Amplify
1000.05.01-XPMS-003 | 1000.05.01 | Post-Event Highlight Film | service | Y | 5100 | Expense · Creative | CC-VENUE | each | 4500 | 6500 | 9500 | Edited highlight film cut from event capture and delivered to specified formats and durations. Requires cleared rights for every asset, person and track appearing in it. |  |  | 05 Experiential | Amplify
1000.05.01-XPMS-002 | 1000.05.01 | Same-Day Social Edit Package | service | Y | 5100 | Expense · Creative | CC-VENUE | each | 1200 | 1600 | 2200 | Shooter-editor delivering cut-down social content during the event day. |  |  | 01 Social | Amplify
1000.05.02-XPMS-001 | 1000.05.02 | Sonic Branding & Audio Identity | service | Y | 5100 | Expense · Creative | CC-VENUE | each | 1200 | 1600 | 2200 | Sonic logo, audio identity package. |  |  | 05 Experiential | Operate
1000.05.02-XOS-001 | 1000.05.02 | Sonic Branding or Stings & IDs · Base | experience | Y | 5100 | Expense · Creative | CC-VENUE | each | 1800 | 2400 | 3200 | Brand audio sting at key moments. | Zone: All Zones. Tier fit: T2; T4. Upgrades: Bespoke sonic identity suite. Add-ons: Spanish-language VO ID. Substitutions: No sonic branding. |  | 02 Digital | Scope | SND-04
1000.05.02-XOS-002 | 1000.05.02 | Sonic Branding or Stings & IDs · Elevated | experience | Y | 5100 | Expense · Creative | CC-VENUE | each | 2500 | 3500 | 5000 | Set of sonic IDs for arrival, peak, and reveal moments. | Zone: All Zones. Tier fit: T2; T4. Upgrades: Bespoke sonic identity suite. Add-ons: Spanish-language VO ID. Substitutions: No sonic branding. |  | 02 Digital | Scope | SND-04
1000.05.02-XOS-003 | 1000.05.02 | Sonic Branding or Stings & IDs · Premium | experience | Y | 5100 | Expense · Creative | CC-VENUE | each | 550 | 750 | 1000 | Bespoke sonic identity system woven through the night and content. | Zone: All Zones. Tier fit: T2; T4. Upgrades: Bespoke sonic identity suite. Add-ons: Spanish-language VO ID. Substitutions: No sonic branding. |  | 02 Digital | Scope | SND-04
1000.06.01-XOS-001 | 1000.06.01 | Catchphrase or Copy System · Base | experience | Y | 5100 | Expense · Creative | CC-VENUE | each | 4500 | 6500 | 9500 | One hero catchphrase applied to a sign (e.g., 'Press Play'). | Zone: All Zones. Tier fit: T1; T4. Upgrades: Bilingual (EN/ES) line system. Add-ons: Per-zone copy variants. Substitutions: Single hero line only. |  | 01 Social | Scope | TCH-11
1000.06.01-XOS-002 | 1000.06.01 | Catchphrase or Copy System · Elevated | experience | Y | 5100 | Expense · Creative | CC-VENUE | each | 5500 | 7500 | 10500 | Catchphrase set across signage, menus, and merch ('Made for Listening', 'The Sound Lives Here'). | Zone: All Zones. Tier fit: T1; T4. Upgrades: Bilingual (EN/ES) line system. Add-ons: Per-zone copy variants. Substitutions: Single hero line only. |  | 01 Social | Scope | TCH-11
1000.06.01-XOS-003 | 1000.06.01 | Catchphrase or Copy System · Premium | experience | Y | 5100 | Expense · Creative | CC-VENUE | each | 4500 | 6500 | 9500 | Full verbal-identity system: hero line, zone lines, and bilingual variants ('Donde Suena Todo'). | Zone: All Zones. Tier fit: T1; T4. Upgrades: Bilingual (EN/ES) line system. Add-ons: Per-zone copy variants. Substitutions: Single hero line only. |  | 01 Social | Scope | TCH-11
1000.06.01-XPMS-001 | 1000.06.01 | Copywriting & Verbal Identity | service | Y | 5100 | Expense · Creative | CC-VENUE | each | 6500 | 9500 | 14000 | Copy, naming, scripts, tone of voice. |  |  | 05 Experiential | Operate
1000.07.01-XPMS-001 | 1000.07.01 | Digital & Interactive Design | service | Y | 5100 | Expense · Creative | CC-VENUE | each | 5500 | 7500 | 11000 | Web, app, and interactive design. |  |  | 05 Experiential | Operate
1000.07.01-XPMS-002 | 1000.07.01 | Event Microsite Design & Build | service | Y | 5100 | Expense · Creative | CC-VENUE | each | 4500 | 6500 | 9500 | Branded event microsite with RSVP, schedule, and content modules. |  |  | 02 Digital | Scope
1000.07.01-XPMS-003 | 1000.07.01 | Experience & Interaction Design | service | Y | 5100 | Expense · Creative | CC-VENUE | each | 4500 | 6500 | 9500 | Design of guest interaction: journey, decision points, dwell, throughput and the behaviour of any interactive element. Distinct from visual design; this is what the guest does, not what they see. |  |  | 05 Experiential | Scope
1000.08.01-XPMS-002 | 1000.08.01 | Brand IP Clearance & Trademark Review | service | Y | 5100 | Expense · Creative | CC-VENUE | each | 4500 | 6500 | 9500 | Legal clearance of event marks, activation names, and brand assets against existing registrations. |  |  | 02 Digital | Scope
1000.08.01-XPMS-001 | 1000.08.01 | Music Licensing - PRO Event License | service | Y | 5100 | Expense · Creative | CC-VENUE | each | 3500 | 5000 | 7500 | ASCAP/BMI/SESAC public-performance license for live and recorded music at a ticketed or brand event. |  |  | 02 Digital | Advance
1000.08.01-XPMS-003 | 1000.08.01 | Photo or Film Location Release Package | service | Y | 5100 | Expense · Creative | CC-VENUE | each | 1500 | 2200 | 3200 | Drafted and executed location, appearance, and capture releases for venue and talent. |  |  | 04 Physical | Advance
1000.08.01-XPMS-005 | 1000.08.01 | Rights Clearance & Usage Licensing | service | Y | 5100 | Expense · Creative | CC-VENUE | each | 3500 | 5000 | 7500 | Clearance of talent, music, venue and third-party marks for each intended usage and territory. An asset with unknown clearance is a blocker rather than a risk to accept, because publishing is irreversible. |  |  | 05 Experiential | Amplify
1000.08.01-XPMS-004 | 1000.08.01 | Stock Content & Footage Clearance | service | Y | 5100 | Expense · Creative | CC-VENUE | each | 350 | 500 | 750 | Rights clearance and licensing of third-party stock imagery, footage, and music beds for event content. |  |  | 02 Digital | Scope
1000.50.02-XOS-001 | 1000.50.02 | Programming Lead | service | Y | 5100 | Expense · Creative | CC-VENUE | lump sum | 650 | 950 | 1450 | Representative line for programming lead so the category can carry cost. Replace with the specific item on award. |  |  | 04 Physical | Procure | 1000.50.02-XOS-001
1000.51.01-XOS-001 | 1000.51.01 | Signage Fabrication | service | Y | 5100 | Expense · Creative | CC-VENUE | lump sum | 1250 | 1850 | 2650 | Representative line for signage fabrication so the category can carry cost. Replace with the specific item on award. |  |  | 04 Physical | Procure | 1000.51.01-XOS-001
1000.51.02-XOS-001 | 1000.51.02 | Scenic Fabrication | service | Y | 5100 | Expense · Creative | CC-VENUE | lump sum | 450 | 650 | 950 | Representative line for scenic fabrication so the category can carry cost. Replace with the specific item on award. |  |  | 04 Physical | Procure | 1000.51.02-XOS-001
1000.60.01-XOS-001 | 1000.60.01 | Scope Activities · Creative | service | Y | 5100 | Expense · Creative | CC-E00 | lump sum | 850 | 1250 | 1850 | Representative line for scope activities so the category can carry cost. Replace with the specific item on award. |  |  | 04 Physical | Scope | 1000.60.01-XOS-001
1000.60.02-XOS-001 | 1000.60.02 | Engage Activities · Creative | service | Y | 5100 | Expense · Creative | CC-E00 | lump sum | 1650 | 2450 | 3550 | Representative line for engage activities so the category can carry cost. Replace with the specific item on award. |  |  | 04 Physical | Engage | 1000.60.02-XOS-001
1000.60.03-XOS-001 | 1000.60.03 | Advance Activities · Creative | service | Y | 5100 | Expense · Creative | CC-E00 | lump sum | 3500 | 5000 | 7500 | Representative line for advance activities so the category can carry cost. Replace with the specific item on award. |  |  | 04 Physical | Advance | 1000.60.03-XOS-001
1000.60.04-XOS-001 | 1000.60.04 | Procure Activities · Creative | service | Y | 5100 | Expense · Creative | CC-E00 | lump sum | 2500 | 3500 | 5000 | Representative line for procure activities so the category can carry cost. Replace with the specific item on award. |  |  | 04 Physical | Procure | 1000.60.04-XOS-001
1000.60.05-XOS-001 | 1000.60.05 | Build Activities · Creative | service | Y | 5100 | Expense · Creative | CC-E00 | lump sum | 750 | 1100 | 1600 | Representative line for build activities so the category can carry cost. Replace with the specific item on award. |  |  | 04 Physical | Build | 1000.60.05-XOS-001
1000.60.06-XOS-001 | 1000.60.06 | Install Activities · Creative | service | Y | 5100 | Expense · Creative | CC-E00 | lump sum | 750 | 1100 | 1600 | Representative line for install activities so the category can carry cost. Replace with the specific item on award. |  |  | 04 Physical | Install | 1000.60.06-XOS-001
1000.60.07-XOS-001 | 1000.60.07 | Operate Activities · Creative | service | Y | 5100 | Expense · Creative | CC-E00 | lump sum | 1250 | 1850 | 2650 | Representative line for operate activities so the category can carry cost. Replace with the specific item on award. |  |  | 04 Physical | Operate | 1000.60.07-XOS-001
1000.60.08-XOS-001 | 1000.60.08 | Amplify Activities · Creative | service | Y | 5100 | Expense · Creative | CC-E00 | lump sum | 2800 | 4000 | 5800 | Representative line for amplify activities so the category can carry cost. Replace with the specific item on award. |  |  | 04 Physical | Amplify | 1000.60.08-XOS-001
1000.60.09-XOS-001 | 1000.60.09 | Close Activities · Creative | service | Y | 5100 | Expense · Creative | CC-E00 | lump sum | 450 | 650 | 950 | Representative line for close activities so the category can carry cost. Replace with the specific item on award. |  |  | 04 Physical | Close | 1000.60.09-XOS-001
2000.01.01-XPMS-001 | 2000.01.01 | Artist Booking & Programming | service | Y | 5200 | Expense · Talent | CC-VENUE | each | 850 | 1250 | 1850 | Headliner and support booking. |  |  | 05 Experiential | Operate
2000.01.01-XOS-001 | 2000.01.01 | Listening Session · Base | experience | Y | 5200 | Expense · Talent | CC-VENUE | each | 1650 | 2450 | 3550 | Casual playback listening moment in a lounge. | Zone: Exhibition Room. Tier fit: T1; T3. Upgrades: Hi-fi / vinyl playback salon. Add-ons: Artist Q&A integration. Substitutions: Standard lounge playback. |  | 05 Experiential | Show | SND-07
2000.01.01-XOS-002 | 2000.01.01 | Listening Session · Elevated | experience | Y | 5200 | Expense · Talent | CC-VENUE | each | 2500 | 3500 | 5000 | Hosted album / catalog listening session with the artist's curation. | Zone: Exhibition Room. Tier fit: T1; T3. Upgrades: Hi-fi / vinyl playback salon. Add-ons: Artist Q&A integration. Substitutions: Standard lounge playback. |  | 05 Experiential | Show | SND-07
2000.01.01-XOS-003 | 2000.01.01 | Listening Session · Premium | experience | Y | 5200 | Expense · Talent | CC-VENUE | each | 7500 | 12000 | 18000 | Premium hi-fi listening salon with vinyl, host, and spatial playback. | Zone: Exhibition Room. Tier fit: T1; T3. Upgrades: Hi-fi / vinyl playback salon. Add-ons: Artist Q&A integration. Substitutions: Standard lounge playback. |  | 05 Experiential | Show | SND-07
2000.01.01-XOS-004 | 2000.01.01 | Silent Disco · Base | experience | Y | 5200 | Expense · Talent | CC-VENUE | each | 1800 | 2500 | 3500 | Single-channel silent-disco headphone set for an after-room. | Zone: Exhibition Room. Tier fit: T1; T3. Upgrades: LED headphones; channel battle host. Add-ons: Branded headphone keepsake. Substitutions: No silent disco. |  | 05 Experiential | Show | SND-06
2000.01.01-XOS-005 | 2000.01.01 | Silent Disco · Elevated | experience | Y | 5200 | Expense · Talent | CC-VENUE | each | 650 | 850 | 1150 | Three-channel silent disco with branded headphones. | Zone: Exhibition Room. Tier fit: T1; T3. Upgrades: LED headphones; channel battle host. Add-ons: Branded headphone keepsake. Substitutions: No silent disco. |  | 05 Experiential | Show | SND-06
2000.01.01-XOS-006 | 2000.01.01 | Silent Disco · Premium | experience | Y | 5200 | Expense · Talent | CC-VENUE | each | 650 | 850 | 1150 | Premium silent-disco production with LED headphones and a hosted channel battle. | Zone: Exhibition Room. Tier fit: T1; T3. Upgrades: LED headphones; channel battle host. Add-ons: Branded headphone keepsake. Substitutions: No silent disco. |  | 05 Experiential | Show | SND-06
2000.02.01-XPMS-002 | 2000.02.01 | Event Performing Talent (Placeholder) | service | Y | 5200 | Expense · Talent | CC-VENUE | each | 550 | 750 | 1050 | Phase 2 event-driven. |  |  | 04 Physical | Build
2000.02.01-XPMS-001 | 2000.02.01 | Music Programming & Curation | service | Y | 5200 | Expense · Talent | CC-VENUE | each | 1200 | 1600 | 2200 | Lineup curation and set design. |  |  | 05 Experiential | Operate
2000.02.02-XPMS-001 | 2000.02.02 | DJ or Live Set Programming | service | Y | 5200 | Expense · Talent | CC-VENUE | each | 650 | 850 | 1150 | Set programming and music direction. |  |  | 05 Experiential | Operate
2000.02.02-XOS-001 | 2000.02.02 | DJ or Selector Format · Base | experience | Y | 5200 | Expense · Talent | CC-VENUE | each | 650 | 850 | 1150 | House or local DJ on a single deck for ambiance and transitions. | Zone: Main Stage and Bar. Tier fit: T1; T4. Upgrades: Headline talent; b2b set. Add-ons: Vinyl-only / open-format set. Substitutions: Playlist playback only. |  | 06 Theatrical | Show | SND-01
2000.02.02-XOS-002 | 2000.02.02 | DJ or Selector Format · Elevated | experience | Y | 5200 | Expense · Talent | CC-VENUE | each | 450 | 650 | 950 | Curated DJ with a programmed arc and a featured guest selector. | Zone: Main Stage and Bar. Tier fit: T1; T4. Upgrades: Headline talent; b2b set. Add-ons: Vinyl-only / open-format set. Substitutions: Playlist playback only. |  | 06 Theatrical | Show | SND-01
2000.02.02-XOS-003 | 2000.02.02 | DJ or Selector Format · Premium | experience | Y | 5200 | Expense · Talent | CC-VENUE | each | 1200 | 1600 | 2200 | Headline DJ (e.g., DJ SWVNLVKE) with a full programmed journey and support sets. | Zone: Main Stage and Bar. Tier fit: T1; T4. Upgrades: Headline talent; b2b set. Add-ons: Vinyl-only / open-format set. Substitutions: Playlist playback only. |  | 06 Theatrical | Show | SND-01
2000.02.02-XOS-004 | 2000.02.02 | Live Performance Format · Base | experience | Y | 5200 | Expense · Talent | CC-VENUE | each | 450 | 600 | 800 | Solo acoustic or single artist short set. | Zone: Main Stage and Bar. Tier fit: T2; T4. Upgrades: Multi-act bill; surprise guest. Add-ons: Acoustic / stripped session. Substitutions: DJ-only programming. |  | 06 Theatrical | Show | SND-02
2000.02.02-XOS-005 | 2000.02.02 | Live Performance Format · Elevated | experience | Y | 5200 | Expense · Talent | CC-VENUE | each | 350 | 450 | 600 | Full band or featured artist set with proper backline. | Zone: Main Stage and Bar. Tier fit: T2; T4. Upgrades: Multi-act bill; surprise guest. Add-ons: Acoustic / stripped session. Substitutions: DJ-only programming. |  | 06 Theatrical | Show | SND-02
2000.02.02-XOS-006 | 2000.02.02 | Live Performance Format · Premium | experience | Y | 5200 | Expense · Talent | CC-VENUE | each | 550 | 750 | 1050 | Multi-act bill with a headline performance and curated support. | Zone: Main Stage and Bar. Tier fit: T2; T4. Upgrades: Multi-act bill; surprise guest. Add-ons: Acoustic / stripped session. Substitutions: DJ-only programming. |  | 06 Theatrical | Show | SND-02
2000.03.01-XPMS-003 | 2000.03.01 | Artist Hospitality | service | Y | 5200 | Expense · Talent | CC-VENUE | each | 4500 | 6500 | 9500 | Talent · Artist hospitality. |  |  | 04 Physical | Operate
2000.03.01-XPMS-002 | 2000.03.01 | Artist Performance Fees | service | Y | 5200 | Expense · Talent | CC-VENUE | each | 3500 | 5000 | 7500 | Talent · Artist performance fees. |  |  | 04 Physical | Operate
2000.03.01-XPMS-004 | 2000.03.01 | Backline & Instruments | service | Y | 5200 | Expense · Talent | CC-VENUE | each | 4500 | 6500 | 9500 | Talent · Backline and instruments. |  |  | 04 Physical | Operate
2000.03.01-XPMS-001 | 2000.03.01 | Talent Advancing & Riders | service | Y | 5200 | Expense · Talent | CC-VENUE | each | 4500 | 6500 | 9500 | Technical and hospitality rider advance. |  |  | 05 Experiential | Operate
2000.04.01-XPMS-001 | 2000.04.01 | Performer & Ambassador Casting | service | Y | 5200 | Expense · Talent | CC-VENUE | each | 5500 | 7500 | 11000 | Casting of performers and ambassadors. |  |  | 05 Experiential | Operate
2000.05.01-XPMS-001 | 2000.05.01 | Host or MC Services | service | Y | 5200 | Expense · Talent | CC-VENUE | each | 4500 | 6500 | 9500 | Emcee, host, moderator. |  |  | 05 Experiential | Operate
2000.06.01-XPMS-001 | 2000.06.01 | Talent Settlement & Payments | service | Y | 5200 | Expense · Talent | CC-VENUE | each | 4500 | 6500 | 9500 | Guarantees, per-diems, settlement. |  |  | 05 Experiential | Operate
2000.06.01-XPMS-002 | 2000.06.01 | Talent Usage Settlement | service | Y | 5200 | Expense · Talent | CC-VENUE | each | 3500 | 5000 | 7500 | Reconciliation and payment of usage, residual and buyout obligations arising from published content, distinct from performance fees settled at Close. |  |  | 05 Experiential | Amplify
2000.07.01-XPMS-002 | 2000.07.01 | Artist Ground Transport Package - SUV & Driver | travel | Z | 5200 | Expense · Talent | CC-VENUE | each | 1500 | 2200 | 3200 | Black SUV with vetted driver on artist call, airport-to-venue-to-hotel loop, 10-hr day. |  |  | 05 Experiential | Operate
2000.07.01-XPMS-004 | 2000.07.01 | Artist Hotel Block Management | service | Y | 5200 | Expense · Talent | CC-VENUE | each | 3500 | 5000 | 7500 | Management of artist and crew hotel blocks, rooming lists, and billing reconciliation. |  |  | 05 Experiential | Advance
2000.07.01-XPMS-001 | 2000.07.01 | Artist Travel Coordinator | labor | Y | 5200 | Expense · Talent | CC-VENUE | each | 3500 | 5000 | 7500 | Dedicated coordinator managing artist flights, ground, lodging, and rider logistics through show day. |  |  | 05 Experiential | Advance
2000.07.01-XPMS-003 | 2000.07.01 | VIP Airport Meet & Greet Service | travel | Z | 5200 | Expense · Talent | CC-VENUE | each | 3500 | 5000 | 7500 | Airside or curbside meet, luggage assist, and escort for arriving talent or executives. |  |  | 05 Experiential | Operate
2000.50.01-XOS-001 | 2000.50.01 | Backline Technical | service | Y | 5200 | Expense · Talent | CC-VENUE | lump sum | 3500 | 5000 | 7500 | Representative line for backline technical so the category can carry cost. Replace with the specific item on award. |  |  | 04 Physical | Procure | 2000.50.01-XOS-001
2000.60.01-XOS-001 | 2000.60.01 | Scope Activities · Talent | service | Y | 5200 | Expense · Talent | CC-E00 | lump sum | 2500 | 3500 | 5000 | Representative line for scope activities so the category can carry cost. Replace with the specific item on award. |  |  | 04 Physical | Scope | 2000.60.01-XOS-001
2000.60.02-XOS-001 | 2000.60.02 | Engage Activities · Talent | service | Y | 5200 | Expense · Talent | CC-E00 | lump sum | 3500 | 5000 | 7500 | Representative line for engage activities so the category can carry cost. Replace with the specific item on award. |  |  | 04 Physical | Engage | 2000.60.02-XOS-001
2000.60.03-XOS-001 | 2000.60.03 | Advance Activities · Talent | service | Y | 5200 | Expense · Talent | CC-E00 | lump sum | 6500 | 9500 | 14000 | Representative line for advance activities so the category can carry cost. Replace with the specific item on award. |  |  | 04 Physical | Advance | 2000.60.03-XOS-001
2000.60.04-XOS-001 | 2000.60.04 | Procure Activities · Talent | service | Y | 5200 | Expense · Talent | CC-E00 | lump sum | 450 | 600 | 800 | Representative line for procure activities so the category can carry cost. Replace with the specific item on award. |  |  | 04 Physical | Procure | 2000.60.04-XOS-001
2000.60.05-XOS-001 | 2000.60.05 | Build Activities · Talent | service | Y | 5200 | Expense · Talent | CC-E00 | lump sum | 3500 | 5000 | 7500 | Representative line for build activities so the category can carry cost. Replace with the specific item on award. |  |  | 04 Physical | Build | 2000.60.05-XOS-001
2000.60.06-XOS-001 | 2000.60.06 | Install Activities · Talent | service | Y | 5200 | Expense · Talent | CC-E00 | lump sum | 450 | 650 | 900 | Representative line for install activities so the category can carry cost. Replace with the specific item on award. |  |  | 04 Physical | Install | 2000.60.06-XOS-001
2000.60.07-XOS-001 | 2000.60.07 | Operate Activities · Talent | service | Y | 5200 | Expense · Talent | CC-E00 | lump sum | 950 | 1350 | 1850 | Representative line for operate activities so the category can carry cost. Replace with the specific item on award. |  |  | 04 Physical | Operate | 2000.60.07-XOS-001
2000.60.08-XOS-001 | 2000.60.08 | Amplify Activities · Talent | service | Y | 5200 | Expense · Talent | CC-E00 | lump sum | 2500 | 3500 | 5000 | Representative line for amplify activities so the category can carry cost. Replace with the specific item on award. |  |  | 04 Physical | Amplify | 2000.60.08-XOS-001
2000.60.09-XOS-001 | 2000.60.09 | Close Activities · Talent | service | Y | 5200 | Expense · Talent | CC-E00 | lump sum | 3500 | 5000 | 7500 | Representative line for close activities so the category can carry cost. Replace with the specific item on award. |  |  | 04 Physical | Close | 2000.60.09-XOS-001
3000.01.01-XPMS-004 | 3000.01.01 | Always-On Marketing & Social | opex | X | 5300 | Expense · Marketing | CC-VENUE | each | 1200 | 1600 | 2200 | Marketing · Always-On Marketing and Social. |  |  | 04 Physical | Operate
3000.01.01-XPMS-003 | 3000.01.01 | Build + Launch Photography or Videography | service | Y | 5300 | Expense · Marketing | CC-VENUE | each | 3500 | 5000 | 7500 | Document build and launch. |  |  | 04 Physical | Build
3000.01.01-XPMS-001 | 3000.01.01 | Campaign Strategy & Brand Marketing | service | Y | 5300 | Expense · Marketing | CC-VENUE | each | 2500 | 3500 | 5000 | Go-to-market and campaign strategy. |  |  | 05 Experiential | Operate
3000.01.01-XPMS-007 | 3000.01.01 | Local Partnership or Community Org | package | X | 5300 | Expense · Marketing | CC-VENUE | each | 2500 | 3500 | 5000 | Marketing · Local partnership / community org. |  |  | 04 Physical | Operate
3000.01.01-XPMS-005 | 3000.01.01 | PR & Community Relations | opex | X | 5300 | Expense · Marketing | CC-VENUE | each | 3500 | 5000 | 7500 | Marketing · PR and Community Relations. |  |  | 04 Physical | Operate
3000.01.01-XPMS-006 | 3000.01.01 | PR or Press or Influencer | package | X | 5300 | Expense · Marketing | CC-VENUE | each | 4500 | 6500 | 9500 | Marketing · PR / press / influencer. |  |  | 04 Physical | Operate
3000.01.01-XPMS-008 | 3000.01.01 | Post-Event Campaign Execution | service | Y | 5300 | Expense · Marketing | CC-VENUE | each | 6500 | 9500 | 14000 | Paid and owned campaign activity running after the event against the objectives set at Discover; retargeting, nurture and next-cycle acquisition. |  |  | 05 Experiential | Amplify
3000.01.01-XPMS-002 | 3000.01.01 | Street Team Activation Staff | labor | Y | 5300 | Expense · Marketing | CC-VENUE | each | 3500 | 5000 | 7500 | Brand-trained street team for flyering, sampling, and footprint engagement. |  |  | 01 Social | Operate
3000.02.01-XPMS-003 | 3000.02.01 | Launch Content Capture Kit or Social | service | Y | 5300 | Expense · Marketing | CC-VENUE | each | 5500 | 7500 | 11000 | Social assets at launch. |  |  | 04 Physical | Build
3000.02.01-XPMS-002 | 3000.02.01 | Live Social Media Manager - Event Day | labor | Y | 5300 | Expense · Marketing | CC-VENUE | each | 4500 | 6500 | 9500 | Real-time posting, stories, and community engagement through the event day. |  |  | 01 Social | Operate
3000.02.01-XPMS-004 | 3000.02.01 | Social Cutdown Package | service | Y | 5300 | Expense · Marketing | CC-VENUE | each | 3500 | 5000 | 7500 | Platform-specific short-form edits derived from primary capture, delivered to each platform's aspect ratio, duration and caption requirements. |  |  | 05 Experiential | Amplify
3000.02.01-XPMS-001 | 3000.02.01 | Social Media & Community Management | service | Y | 5300 | Expense · Marketing | CC-VENUE | each | 2500 | 3500 | 5000 | Social channels and community. |  |  | 05 Experiential | Operate
3000.03.01-XPMS-004 | 3000.03.01 | Earned Media & Coverage Report | service | Y | 5300 | Expense · Marketing | CC-VENUE | each | 3500 | 5000 | 7500 | Compilation of resulting coverage with reach and equivalency measures, sourced and dated. Carries its own confidence: a media-equivalency figure is modelled, not quoted, and must not be presented as revenue. |  |  | 05 Experiential | Amplify
3000.03.01-XPMS-003 | 3000.03.01 | Press Release & Media Distribution | service | Y | 5300 | Expense · Marketing | CC-VENUE | each | 3500 | 5000 | 7500 | Drafting, approval and distribution of post-event press material, with a clip report of resulting coverage. |  |  | 05 Experiential | Amplify
3000.03.01-XPMS-002 | 3000.03.01 | Press or PR Launch Support | service | Y | 5300 | Expense · Marketing | CC-VENUE | each | 2500 | 3500 | 5000 | Launch PR. |  |  | 04 Physical | Build
3000.03.01-XPMS-001 | 3000.03.01 | Public Relations & Press | service | Y | 5300 | Expense · Marketing | CC-VENUE | each | 1500 | 2200 | 3200 | Press strategy, releases, media relations. |  |  | 05 Experiential | Operate
3000.04.01-XPMS-001 | 3000.04.01 | Sponsorship Sales & Packaging | service | Y | 5300 | Expense · Marketing | CC-VENUE | each | 2500 | 3500 | 5000 | Sponsor packaging and sales. |  |  | 05 Experiential | Operate
3000.05.01-XPMS-002 | 3000.05.01 | Audience & Market Research | service | Y | 5300 | Expense · Marketing | CC-VENUE | each | 3500 | 5000 | 7500 | Primary or secondary research characterising the intended audience, demand and competitive context. Feeds the objectives that gate 8 measures against. |  |  | 05 Experiential | Scope
3000.05.01-XPMS-001 | 3000.05.01 | CRM & Audience Data | service | Y | 5300 | Expense · Marketing | CC-VENUE | each | 2500 | 3500 | 5000 | CRM, segmentation, lifecycle. |  |  | 05 Experiential | Operate
3000.05.01-GHXST-001 | 3000.05.01 | Camera - IMAG | equipment | X | 5300 | Expense · Marketing | CC-VENUE | each | 675 | 800 | 925 | Broadcast-quality camera for live image magnification. | PTZ, manned tripod, jib, or Steadicam. | 336 | 04 Physical | Procurement | TECH-VIDO-CAMR-001 · 5000.050.00
3000.05.01-GHXST-002 | 3000.05.01 | Charger - Radio - Multi-Bay | radio | X | 5300 | Expense · Marketing | CC-VENUE | each | 21 | 25 | 29 | 6-unit or 12-unit charging station for radios. | 6-bay or 12-bay ¦ With conditioning display. | 168 | 04 Physical | Procurement | WORK-COMM-RDIO-004 · 9000.020.00
3000.05.01-GHXST-003 | 3000.05.01 | Display - Flat Panel | equipment | X | 5300 | Expense · Marketing | CC-VENUE | each | 85 | 100 | 115 | Professional flat panel display on stand or mount. | 42in through 98in ¦ Outdoor-rated available. | 336 | 04 Physical | Procurement | TECH-VIDO-LEDW-005 · 5000.050.00
3000.05.01-GHXST-004 | 3000.05.01 | Intercom - Wired | radio | X | 5300 | Expense · Marketing | CC-VENUE | each | 50 | 60 | 70 | Hard-wired intercom for stage management and production. | Clear-Com MS-702 station ¦ 2-channel or 4-channel ¦ With headset. | 168 | 04 Physical | Procurement | WORK-COMM-INTC-001 · 9000.020.00
3000.05.01-GHXST-005 | 3000.05.01 | Intercom - Wireless | radio | X | 5300 | Expense · Marketing | CC-VENUE | each | 85 | 100 | 115 | Digital wireless intercom for mobile production staff. | Riedel Bolero ¦ Clear-Com FreeSpeak II ¦ Green-GO. | 168 | 04 Physical | Procurement | WORK-COMM-INTC-002 · 9000.020.00
3000.05.01-GHXST-006 | 3000.05.01 | LED Screen - Mobile | equipment | X | 5300 | Expense · Marketing | CC-VENUE | each | 2975 | 3500 | 4025 | Self-contained mobile LED screen on trailer. | 9x16ft through 16x28ft ¦ With audio and generator options. | 336 | 04 Physical | Procurement | TECH-VIDO-LEDW-004 · 5000.050.00
3000.05.01-GHXST-007 | 3000.05.01 | LED Tile - Floor or Ceiling | equipment | X | 5300 | Expense · Marketing | CC-VENUE | each | 130 | 150 | 170 | Walkable or overhead LED panel for immersive installations. | 2.9mm or 3.9mm ¦ Load-rated (floor) or overhead-rated. | 672 | 04 Physical | Procurement | TECH-VIDO-LEDW-003 · 5000.050.00
3000.05.01-GHXST-008 | 3000.05.01 | LED Wall - Indoor | equipment | X | 5300 | Expense · Marketing | CC-VENUE | each | 85 | 100 | 115 | Modular LED video panel wall for stage backdrop or IMAG. | 2.6mm, 2.9mm, or 3.9mm pixel pitch ¦ 500x500mm panels. | 336 | 04 Physical | Procurement | TECH-VIDO-LEDW-001 · 5000.050.00
3000.05.01-GHXST-009 | 3000.05.01 | LED Wall - Outdoor | equipment | X | 5300 | Expense · Marketing | CC-VENUE | each | 105 | 125 | 145 | Weather-rated LED panels for outdoor events. | 3.9mm through 10mm pixel pitch ¦ IP65 rated. | 336 | 04 Physical | Procurement | TECH-VIDO-LEDW-002 · 5000.050.00
3000.05.01-GHXST-010 | 3000.05.01 | Livestream Package | equipment | X | 5300 | Expense · Marketing | CC-VENUE | each | 2550 | 3000 | 3450 | Complete livestream setup with encoding and CDN delivery. | Single camera through multi-cam with graphics and remote guests. | 336 | 04 Physical | Procurement | TECH-VIDO-CAMR-003 · 5000.050.00
3000.05.01-GHXST-011 | 3000.05.01 | Media Server | equipment | X | 5300 | Expense · Marketing | CC-VENUE | each | 1025 | 1200 | 1375 | Professional media server for content playback and processing. | Disguise, Resolume, Watchout, Notch, or Green Hippo. | 336 | 04 Physical | Procurement | TECH-VIDO-PLAY-001 · 5000.050.00
3000.05.01-GHXST-012 | 3000.05.01 | Monitor - Confidence | equipment | X | 5300 | Expense · Marketing | CC-VENUE | each | 85 | 100 | 115 | On-stage confidence monitor for presenters or performers. | 15in through 24in ¦ Teleprompter-style available. | 336 | 04 Physical | Procurement | TECH-VIDO-LEDW-006 · 5000.050.00
3000.05.01-GHXST-013 | 3000.05.01 | Motorola XPR7550 Two-Way Radio | radio | X | 5300 | Expense · Marketing | CC-VENUE | each | 550 | 650 | 750 | UHF digital radio, 5W, 1000 channels. |  |  | 04 Physical | Procurement | moto-xpr7550 · 9000.020.00
3000.05.01-GHXST-014 | 3000.05.01 | Processor - Video | equipment | X | 5300 | Expense · Marketing | CC-VENUE | each | 425 | 500 | 575 | Video processing, scaling, and switching for LED walls and projection. | Novastar, Brompton, Barco E2, or Analog Way. | 336 | 04 Physical | Procurement | TECH-VIDO-PLAY-002 · 5000.050.00
3000.05.01-GHXST-015 | 3000.05.01 | Projector - Large Venue | equipment | X | 5300 | Expense · Marketing | CC-VENUE | each | 2550 | 3000 | 3450 | High-brightness laser projector for large venues and outdoor use. | 20,000 through 60,000 or more lumens. | 168 | 04 Physical | Procurement | TECH-VIDO-PROJ-002 · 5000.050.00
3000.05.01-GHXST-016 | 3000.05.01 | Projector - Standard | equipment | X | 5300 | Expense · Marketing | CC-VENUE | each | 340 | 400 | 460 | LCD or DLP projector for presentations and basic projection. | 5,000 through 15,000 lumens. | 168 | 04 Physical | Procurement | TECH-VIDO-PROJ-001 · 5000.050.00
3000.05.01-GHXST-017 | 3000.05.01 | Radio - Two-Way - Standard | radio | X | 5300 | Expense · Marketing | CC-VENUE | each | 13 | 15 | 17 | UHF or VHF handheld two-way radio for event operations. | Motorola CP200d ¦ CLP1010 ¦ Kenwood NX-P1300. | 168 | 04 Physical | Procurement | WORK-COMM-RDIO-001 · 9000.020.00
3000.05.01-GHXST-018 | 3000.05.01 | Repeater - Radio | radio | X | 5300 | Expense · Marketing | CC-VENUE | each | 105 | 125 | 145 | Signal repeater to extend radio coverage across large sites. | UHF or VHF ¦ Digital DMR ¦ With antenna and duplexer. | 168 | 04 Physical | Procurement | WORK-COMM-RDIO-003 · 9000.020.00
3000.05.01-GHXST-019 | 3000.05.01 | Switcher - Video | equipment | X | 5300 | Expense · Marketing | CC-VENUE | each | 675 | 800 | 925 | Live video switching system for multi-camera production. | 4-input through 16-input and above ¦ With streaming. | 336 | 04 Physical | Procurement | TECH-VIDO-CAMR-002 · 5000.050.00
3000.06.01-XPMS-001 | 3000.06.01 | Advertising & Media Buying | service | Y | 5300 | Expense · Marketing | CC-VENUE | each | 3500 | 5000 | 7500 | Paid media and media buys. |  |  | 05 Experiential | Operate
3000.07.01-XPMS-001 | 3000.07.01 | Influencer & Creator Relations | service | Y | 5300 | Expense · Marketing | CC-VENUE | each | 4500 | 6500 | 9500 | Influencer and creator partnerships. |  |  | 05 Experiential | Operate
3000.50.01-XOS-001 | 3000.50.01 | Stills Capture | service | Y | 5300 | Expense · Marketing | CC-VENUE | lump sum | 1200 | 1600 | 2200 | Representative line for stills capture so the category can carry cost. Replace with the specific item on award. |  |  | 04 Physical | Procure | 3000.50.01-XOS-001
3000.50.02-XOS-001 | 3000.50.02 | Motion Capture | service | Y | 5300 | Expense · Marketing | CC-VENUE | lump sum | 1800 | 2400 | 3200 | Representative line for motion capture so the category can carry cost. Replace with the specific item on award. |  |  | 04 Physical | Procure | 3000.50.02-XOS-001
3000.50.03-XOS-001 | 3000.50.03 | Content Direction | service | Y | 5300 | Expense · Marketing | CC-VENUE | lump sum | 2500 | 3500 | 5000 | Representative line for content direction so the category can carry cost. Replace with the specific item on award. |  |  | 04 Physical | Procure | 3000.50.03-XOS-001
3000.51.01-XOS-001 | 3000.51.01 | Guest List and RSVP Platform | service | Y | 5300 | Expense · Marketing | CC-VENUE | lump sum | 1200 | 1800 | 2600 | Representative line for guest list and rsvp platform so the category can carry cost. Replace with the specific item on award. |  |  | 04 Physical | Procure | 3000.51.01-XOS-001
3000.60.01-XOS-001 | 3000.60.01 | Scope Activities · Marketing | service | Y | 5300 | Expense · Marketing | CC-E00 | lump sum | 3500 | 5000 | 7500 | Representative line for scope activities so the category can carry cost. Replace with the specific item on award. |  |  | 04 Physical | Scope | 3000.60.01-XOS-001
3000.60.02-XOS-001 | 3000.60.02 | Engage Activities · Marketing | service | Y | 5300 | Expense · Marketing | CC-E00 | lump sum | 3500 | 5000 | 7500 | Representative line for engage activities so the category can carry cost. Replace with the specific item on award. |  |  | 04 Physical | Engage | 3000.60.02-XOS-001
3000.60.03-XOS-001 | 3000.60.03 | Advance Activities · Marketing | service | Y | 5300 | Expense · Marketing | CC-E00 | lump sum | 2500 | 3500 | 5000 | Representative line for advance activities so the category can carry cost. Replace with the specific item on award. |  |  | 04 Physical | Advance | 3000.60.03-XOS-001
3000.60.04-XOS-001 | 3000.60.04 | Procure Activities · Marketing | service | Y | 5300 | Expense · Marketing | CC-E00 | lump sum | 2500 | 3500 | 5000 | Representative line for procure activities so the category can carry cost. Replace with the specific item on award. |  |  | 04 Physical | Procure | 3000.60.04-XOS-001
3000.60.05-XOS-001 | 3000.60.05 | Build Activities · Marketing | service | Y | 5300 | Expense · Marketing | CC-E00 | lump sum | 3500 | 5000 | 7500 | Representative line for build activities so the category can carry cost. Replace with the specific item on award. |  |  | 04 Physical | Build | 3000.60.05-XOS-001
3000.60.06-XOS-001 | 3000.60.06 | Install Activities · Marketing | service | Y | 5300 | Expense · Marketing | CC-E00 | lump sum | 4500 | 6500 | 9500 | Representative line for install activities so the category can carry cost. Replace with the specific item on award. |  |  | 04 Physical | Install | 3000.60.06-XOS-001
3000.60.07-XOS-001 | 3000.60.07 | Operate Activities · Marketing | service | Y | 5300 | Expense · Marketing | CC-E00 | lump sum | 6500 | 9500 | 14000 | Representative line for operate activities so the category can carry cost. Replace with the specific item on award. |  |  | 04 Physical | Operate | 3000.60.07-XOS-001
3000.60.08-XOS-001 | 3000.60.08 | Amplify Activities · Marketing | service | Y | 5300 | Expense · Marketing | CC-E00 | lump sum | 3500 | 5000 | 7500 | Representative line for amplify activities so the category can carry cost. Replace with the specific item on award. |  |  | 04 Physical | Amplify | 3000.60.08-XOS-001
3000.60.09-XOS-001 | 3000.60.09 | Close Activities · Marketing | service | Y | 5300 | Expense · Marketing | CC-E00 | lump sum | 5500 | 7500 | 11000 | Representative line for close activities so the category can carry cost. Replace with the specific item on award. |  |  | 04 Physical | Close | 3000.60.09-XOS-001
4000.01.01-GHXST-001 | 4000.01.01 | Air Conditioner - Portable | equipment | X | 5400 | Expense · Environment | CC-VENUE | each | 340 | 400 | 460 | Spot cooler or portable AC unit for tents and structures. | 1 through 50 ton. | 168 | 04 Physical | Install | SITE-SERV-CLIM-001 · 5000.130.00
4000.01.01-GHXST-002 | 4000.01.01 | Battery Pack - Portable | equipment | X | 5400 | Expense · Environment | CC-VENUE | each | 65 | 75 | 85 | Battery backup or solar power pack for off-grid areas. | 1kWh through 10kWh ¦ Solar and battery combo available. | 168 | 04 Physical | Install | SITE-SERV-POWR-005 · 5000.130.00
4000.01.01-GHXST-003 | 4000.01.01 | Booth - Guard | equipment | X | 5400 | Expense · Environment | CC-VENUE | each | 130 | 150 | 170 | Small portable booth for security checkpoints or ticketing. | 4x4 through 4x8 ¦ With window, counter, and lighting. | 48 | 04 Physical | Build | SITE-INFR-PORT-006 · 6000.020.00
4000.01.01-GHXST-004 | 4000.01.01 | Cable Run - Feeder | equipment | X | 5400 | Expense · Environment | CC-VENUE | each | 65 | 75 | 85 | Temporary power cable from generator or utility to distribution point. | 2/0 or 4/0 AWG ¦ Single or 5-wire sets ¦ Various lengths. | 48 | 04 Physical | Install | SITE-SERV-POWR-003 · 5000.130.00
4000.01.01-GHXST-005 | 4000.01.01 | Compactor - Portable | equipment | X | 5400 | Expense · Environment | CC-VENUE | each | 210 | 250 | 290 | On-site waste compactor to reduce haul frequency. | 2 through 6 cubic yard compactor. | 48 | 04 Physical | Install | SITE-SERV-WAST-004 · 5000.130.00
4000.01.01-XPMS-007 | 4000.01.01 | Demo or Surface Prep or Paint | service | Y | 5400 | Expense · Environment | CC-VENUE | each | 2500 | 3500 | 5000 | Cosmetic, non-structural prep. |  |  | 04 Physical | Build
4000.01.01-GHXST-006 | 4000.01.01 | Driver - CDL | labor | Y | 5400 | Expense · Environment | CC-VENUE | each | 340 | 400 | 460 | Commercial driver for trucks over 26,001 GVWR. | Full-day or per-trip ¦ CDL Class A or B ¦ DOT compliant. | 72 | 04 Physical | Build | LABR-OPER-CERT-004 · 6000.020.00
4000.01.01-GHXST-007 | 4000.01.01 | Dumpster - Roll-Off | equipment | X | 5400 | Expense · Environment | CC-VENUE | each | 425 | 500 | 575 | Open-top roll-off dumpster for construction and event waste. | 10 through 40 cubic yard. | 48 | 04 Physical | Install | SITE-SERV-WAST-001 · 5000.130.00
4000.01.01-GHXST-008 | 4000.01.01 | Fan - Industrial | equipment | X | 5400 | Expense · Environment | CC-VENUE | each | 42 | 48.5 | 55 | High-volume air mover for ventilation and cooling. | 18in through 48in diameter. | 168 | 04 Physical | Install | SITE-SERV-CLIM-003 · 5000.130.00
4000.01.01-XPMS-006 | 4000.01.01 | Flex Room Build + Modular Partitions | service | Y | 5400 | Expense · Environment | CC-VENUE | each | 4500 | 6500 | 9500 | Minimal build + partitions. |  |  | 04 Physical | Build
4000.01.01-GHXST-009 | 4000.01.01 | Forklift - Standard | equipment | X | 5400 | Expense · Environment | CC-VENUE | each | 300 | 350 | 400 | Warehouse or event forklift for loading and placement. | 5,000 through 15,000 lb capacity. | 48 | 04 Physical | Build | SITE-HEQP-FORK-001 · 4000.150.00
4000.01.01-GHXST-010 | 4000.01.01 | Generator - Towable | equipment | X | 5400 | Expense · Environment | CC-VENUE | each | 675 | 800 | 925 | Towable diesel generator for temporary event power. | 20kW through 2MW. | 168 | 04 Physical | Install | SITE-SERV-POWR-001 · 5000.130.00
4000.01.01-XPMS-001 | 4000.01.01 | Hand Truck | tool | X | 5400 | Expense · Environment | CC-VENUE | each | 13 | 15 | 18 | Two-wheel hand truck or platform dolly for moving equipment. |  |  | 04 Physical | Procure
4000.01.01-GHXST-011 | 4000.01.01 | Heater - Portable | equipment | X | 5400 | Expense · Environment | CC-VENUE | each | 150 | 175 | 200 | Forced air or radiant heater for cold-weather events. | 40K through 400K BTU. | 168 | 04 Physical | Install | SITE-SERV-CLIM-002 · 5000.130.00
4000.01.01-XPMS-002 | 4000.01.01 | Ladder - A-Frame | tool | X | 5400 | Expense · Environment | CC-VENUE | each | 21 | 25 | 30 | Aluminum A-frame step ladder for general site work. |  |  | 04 Physical | Procure
4000.01.01-XPMS-003 | 4000.01.01 | Ladder - Extension | tool | X | 5400 | Expense · Environment | CC-VENUE | each | 30 | 35 | 42 | Aluminum extension ladder for elevated access. |  |  | 04 Physical | Procure
4000.01.01-GHXST-012 | 4000.01.01 | Light Tower - Portable | equipment | X | 5400 | Expense · Environment | CC-VENUE | each | 130 | 150 | 170 | Towable light tower for site illumination and safety. | 4-head or 6-head ¦ LED or metal halide ¦ 20 to 30ft mast. | 168 | 04 Physical | Install | SITE-SERV-POWR-006 · 5000.130.00
4000.01.01-GHXST-013 | 4000.01.01 | Loader - Skid Steer | equipment | X | 5400 | Expense · Environment | CC-VENUE | each | 300 | 350 | 400 | Compact loader for grading, moving material, and site prep. | 1,500 to 3,000 lb rated capacity ¦ Various attachments. | 48 | 04 Physical | Build | SITE-HEQP-FORK-003 · 4000.150.00
4000.01.01-XPMS-008 | 4000.01.01 | MEP Rough-In | service | Y | 5400 | Expense · Environment | CC-VENUE | each | 6500 | 8500 | 12000 | BY OWNER (Spotify). |  |  | 04 Physical | Build
4000.01.01-GHXST-014 | 4000.01.01 | Network - Ethernet - Temp | equipment | X | 5400 | Expense · Environment | CC-VENUE | each | 30 | 35 | 40 | Temporary ethernet infrastructure for production and POS. | Cat6 or Cat6a or Fiber ¦ Managed switch ¦ Patch panel. | 672 | 04 Physical | Install | SITE-SERV-INET-003 · 5000.130.00
4000.01.01-GHXST-015 | 4000.01.01 | Operator - Aerial Lift | labor | Y | 5400 | Expense · Environment | CC-VENUE | each | 320 | 375 | 430 | Certified aerial lift operator for elevated work. | 8 to 12hr shift ¦ ANSI and OSHA certified. | 72 | 04 Physical | Build | LABR-OPER-CERT-002 · 6000.020.00
4000.01.01-GHXST-016 | 4000.01.01 | Operator - Crane | labor | Y | 5400 | Expense · Environment | CC-VENUE | each | 675 | 800 | 925 | Certified crane operator for heavy lifts. | 8 to 12hr shift ¦ NCCCO certified ¦ With oiler and signal person. | 72 | 04 Physical | Build | LABR-OPER-CERT-003 · 6000.020.00
4000.01.01-GHXST-017 | 4000.01.01 | Operator - Forklift | labor | Y | 5400 | Expense · Environment | CC-VENUE | each | 300 | 350 | 400 | Certified forklift operator for loading, unloading, and placement. | 8 to 12hr shift ¦ OSHA 1910.178 certified. | 72 | 04 Physical | Build | LABR-OPER-CERT-001 · 6000.020.00
4000.01.01-XPMS-004 | 4000.01.01 | Pallet Jack - Manual | tool | X | 5400 | Expense · Environment | CC-VENUE | each | 30 | 35 | 42 | Manual hydraulic pallet jack for moving loaded pallets. |  |  | 04 Physical | Procure
4000.01.01-GHXST-018 | 4000.01.01 | Receptacle - Trash and Recycling | equipment | X | 5400 | Expense · Environment | CC-VENUE | each | 8 | 10 | 12 | Event-grade waste receptacle with liner and signage. | 32 gal or 44 gal ¦ Slim Jim ¦ Custom branded. | 48 | 04 Physical | Install | SITE-SERV-WAST-002 · 5000.130.00
4000.01.01-GHXST-019 | 4000.01.01 | Restroom Trailer - Luxury | equipment | X | 5400 | Expense · Environment | CC-VENUE | each | 1025 | 1200 | 1375 | Multi-stall climate-controlled restroom trailer with running water and flushing toilets. | 2-stall through 10-stall ¦ Climate controlled ¦ Running water. | 336 | 04 Physical | Build | SITE-INFR-PORT-002 · 6000.020.00
4000.01.01-GHXST-020 | 4000.01.01 | Service - Waste Removal | equipment | X | 5400 | Expense · Environment | CC-VENUE | each | 1025 | 1200 | 1375 | Scheduled waste collection and disposal during multi-day events. | Daily, twice daily, or on-call. | 48 | 04 Physical | Install | SITE-SERV-WAST-003 · 5000.130.00
4000.01.01-XPMS-009 | 4000.01.01 | Set or Scenic or Stage Fabrication | service | Y | 5400 | Expense · Environment | CC-VENUE | each | 5500 | 8000 | 12000 | Build · Set / scenic / stage fabrication. |  |  | 04 Physical | Operate
4000.01.01-GHXST-021 | 4000.01.01 | Signal Booster - Cellular | equipment | X | 5400 | Expense · Environment | CC-VENUE | each | 2500 | 3500 | 5000 | Temporary distributed antenna system or cellular booster. | Single carrier through full DAS. | 672 | 04 Physical | Install | SITE-SERV-INET-002 · 5000.130.00
4000.01.01-XPMS-010 | 4000.01.01 | Signature Installation Fabrication | service | Y | 5400 | Expense · Environment | CC-VENUE | each | 7500 | 12000 | 18000 | Build · Signature installation fabrication. |  |  | 04 Physical | Operate
4000.01.01-XPMS-011 | 4000.01.01 | Structural Engineering & Stamped Drawings | service | Y | 5400 | Expense · Environment | CC-VENUE | each | 3500 | 5000 | 7500 | Engineering analysis and stamped drawings for load-bearing or occupied structures, valid for a named jurisdiction. An unstamped structure is not a structure of unknown capacity; it is one no engineer will stand behind, and gate 5 blocks on it. |  |  | 05 Experiential | Scope
4000.01.01-GHXST-022 | 4000.01.01 | Tank - Gray Water | equipment | X | 5400 | Expense · Environment | CC-VENUE | each | 130 | 150 | 170 | Gray water collection tank for sink and shower drainage. | 250 through 1,000 gallon ¦ Pump-out service. | 168 | 04 Physical | Install | SITE-SERV-WATR-002 · 5000.130.00
4000.01.01-GHXST-023 | 4000.01.01 | Telehandler | equipment | X | 5400 | Expense · Environment | CC-VENUE | each | 500 | 600 | 700 | Telescopic handler for high-reach material placement. | 6,000 to 12,000 lb capacity ¦ 42 to 55ft reach. | 48 | 04 Physical | Build | SITE-HEQP-FORK-002 · 4000.150.00
4000.01.01-XPMS-005 | 4000.01.01 | Tool Kit - Production | tool | X | 5400 | Expense · Environment | CC-VENUE | each | 50 | 60 | 70 | Comprehensive tool kit for on-site production work. |  |  | 04 Physical | Procure
4000.01.01-GHXST-024 | 4000.01.01 | Water Tank - Potable | equipment | X | 5400 | Expense · Environment | CC-VENUE | each | 210 | 250 | 290 | Mobile potable water storage for events without municipal access. | 250 through 5,000 gallon. | 168 | 04 Physical | Install | SITE-SERV-WATR-001 · 5000.130.00
4000.01.01-GHXST-025 | 4000.01.01 | WiFi Network - Temporary | equipment | X | 5400 | Expense · Environment | CC-VENUE | each | 1700 | 2000 | 2300 | Managed WiFi network for event operations and guest access. | 50 through 1,000 or more users. | 672 | 04 Physical | Install | SITE-SERV-INET-001 · 5000.130.00
4000.02.01-GHXST-001 | 4000.02.01 | Artist - Hair and Makeup | labor | Y | 5400 | Expense · Environment | CC-VENUE | each | 130 | 150 | 170 | Professional hair and makeup for talent or branding. | Per person ¦ Bridal or editorial level ¦ With kit. | 672 | 04 Physical | Build | LABR-SKIL-CREA-005 · 6000.100.00
4000.02.01-XPMS-008 | 4000.02.01 | Bar Millwork + Back-Bar Build | service | Y | 5400 | Expense · Environment | CC-VENUE | each | 4500 | 6500 | 9500 | Cocktail/coffee/juice bar. |  |  | 04 Physical | Build
4000.02.01-GHXST-002 | 4000.02.01 | Carpenter - Scenic | labor | Y | 5400 | Expense · Environment | CC-VENUE | each | 340 | 400 | 460 | Skilled carpenter for scenic construction and stage builds. | 8 to 12hr shift ¦ Build plus strike. | 672 | 04 Physical | Build | LABR-SKIL-TCRE-006 · 6000.100.00
4000.02.01-XPMS-001 | 4000.02.01 | Counter or Desk · Plywood Counter W or Graphic Skin (3 Ft×3 Ft2 In) | equipment | X | 5400 | Expense · Environment | CC-VENUE | each | 120 | 150 | 190 | Host station / DJ table / merch counter. |  |  | 04 Physical | Build
4000.02.01-GHXST-003 | 4000.02.01 | Designer - Graphic | labor | Y | 5400 | Expense · Environment | CC-VENUE | each | 425 | 500 | 575 | On-site graphic designer for day-of signage and changes. | Full-day ¦ Laptop plus design software ¦ Quick turnaround. | 672 | 04 Physical | Build | LABR-SKIL-CREA-004 · 6000.100.00
4000.02.01-GHXST-004 | 4000.02.01 | Drone Pilot - Licensed | labor | Y | 5400 | Expense · Environment | CC-VENUE | each | 850 | 1000 | 1150 | FAA Part 107 licensed drone pilot for aerial capture. | Photography, videography, mapping, or FPV. | 672 | 04 Physical | Build | LABR-SKIL-CREA-003 · 6000.100.00
4000.02.01-GHXST-005 | 4000.02.01 | Electrician - Licensed | labor | Y | 5400 | Expense · Environment | CC-VENUE | each | 470 | 547.5 | 625 | Licensed electrician for temporary power installation. | 8 to 12hr shift ¦ Power distribution, tie-ins, and troubleshooting. | 672 | 04 Physical | Build | LABR-SKIL-TCRE-005 · 6000.100.00
4000.02.01-XPMS-002 | 4000.02.01 | Fence or Rail · Plywood Frame W or Mesh Infill (4 Ft×2 Ft6 In) | equipment | X | 5400 | Expense · Environment | CC-VENUE | each | 65 | 85 | 115 | Perimeter fence / rail; defines the arena footprint. |  |  | 04 Physical | Build
4000.02.01-XPMS-003 | 4000.02.01 | Frame Module · Plywood Frame W or Mesh Infill (3 Ft×7 Ft) | equipment | X | 5400 | Expense · Environment | CC-VENUE | each | 110 | 140 | 180 | See-through mesh module; sight-lines into showcase. |  |  | 04 Physical | Build
4000.02.01-GHXST-006 | 4000.02.01 | Kiosk - Digital | equipment | X | 5400 | Expense · Environment | CC-VENUE | each | 400 | 500 | 650 | Freestanding digital display kiosk for wayfinding or information. | 43in or 55in ¦ Touch-enabled and outdoor-rated available. | 336 | 04 Physical | Install | SITE-SIGN-DGTL-002 · 6000.190.00
4000.02.01-GHXST-007 | 4000.02.01 | Message Board - LED | equipment | X | 5400 | Expense · Environment | CC-VENUE | each | 200 | 250 | 320 | Programmable LED message display for announcements. | Single-line through full color ¦ Solar available. | 336 | 04 Physical | Install | SITE-SIGN-DGTL-001 · 6000.190.00
4000.02.01-XPMS-007 | 4000.02.01 | Reception or Check-in Desk Millwork | service | Y | 5400 | Expense · Environment | CC-VENUE | each | 2500 | 3500 | 5000 | Custom reception desk. |  |  | 04 Physical | Build
4000.02.01-XPMS-004 | 4000.02.01 | Shelf or Display · Plywood Shelving W or Pegboard Back (3 Ft×6 Ft6 In) | equipment | X | 5400 | Expense · Environment | CC-VENUE | each | 120 | 160 | 210 | Product showcase shelving; pegboard back for flexibility. |  |  | 04 Physical | Build
4000.02.01-GHXST-008 | 4000.02.01 | Stylist - Wardrobe | labor | Y | 5400 | Expense · Environment | CC-VENUE | each | 425 | 500 | 575 | Wardrobe management and costume coordination for talent. | Full-day ¦ Steaming, fitting, and quick changes. | 672 | 04 Physical | Build | LABR-SKIL-CREA-006 · 6000.100.00
4000.02.01-GHXST-009 | 4000.02.01 | Technician - Audio | labor | Y | 5400 | Expense · Environment | CC-VENUE | each | 380 | 452.5 | 525 | Audio system tech, patch, RF coordination, and stage tech support. | 8 to 12hr shift ¦ System deployment plus show support. | 672 | 04 Physical | Build | LABR-SKIL-TCRE-001 · 6000.100.00
4000.02.01-GHXST-010 | 4000.02.01 | Technician - Lighting | labor | Y | 5400 | Expense · Environment | CC-VENUE | each | 340 | 400 | 460 | Lighting focus, programming support, and fixture maintenance. | 8 to 12hr shift ¦ Hang plus focus plus show support. | 672 | 04 Physical | Build | LABR-SKIL-TCRE-002 · 6000.100.00
4000.02.01-GHXST-011 | 4000.02.01 | Technician - Video | labor | Y | 5400 | Expense · Environment | CC-VENUE | each | 360 | 425 | 490 | LED wall build, camera operation, and cable management. | 8 to 12hr shift ¦ Build plus show support. | 672 | 04 Physical | Build | LABR-SKIL-TCRE-003 · 6000.100.00
4000.02.01-XPMS-005 | 4000.02.01 | Tower Panel · Plywood Framed Identity Tower (2 Ft×8 Ft) | equipment | X | 5400 | Expense · Environment | CC-VENUE | each | 120 | 150 | 190 | Vertical identity tower; adidas + Foot Locker lockup. |  |  | 04 Physical | Build
4000.02.01-XPMS-006 | 4000.02.01 | Wall Panel · Plywood Frame W or Graphic Skin (3 Ft×7 Ft) | equipment | X | 5400 | Expense · Environment | CC-VENUE | each | 95 | 120 | 155 | Modular wall panel; graphic-skinned activation wall. |  |  | 04 Physical | Build
4000.03.01-XPMS-001 | 4000.03.01 | Archway - Inflatable | equipment | X | 5400 | Expense · Environment | CC-VENUE | each | 350 | 400 | 460 | Custom inflatable entrance arch or branded structure. | 10ft through 25ft wide ¦ LED-lit available. | 336 | 04 Physical | Install
4000.03.01-XPMS-002 | 4000.03.01 | Balloon Installation | equipment | X | 5400 | Expense · Environment | CC-VENUE | each | 170 | 200 | 230 | Decorative balloon installation for entrances or photo ops. | 8ft through 12ft arch ¦ 6 to 8ft column ¦ Custom. | 336 | 04 Physical | Install
4000.03.01-XPMS-005 | 4000.03.01 | Branded Entry Mural | service | Y | 5400 | Expense · Environment | CC-VENUE | each | 1500 | 2200 | 3200 | Hand-painted mural. |  |  | 04 Physical | Build
4000.03.01-XPMS-004 | 4000.03.01 | Facade Treatment + Entrance Moment | service | Y | 5400 | Expense · Environment | CC-VENUE | each | 4500 | 6500 | 9500 | Custom facade + entrance fab. |  |  | 04 Physical | Build
4000.03.01-XPMS-003 | 4000.03.01 | Neon Sign - LED Custom | equipment | X | 5400 | Expense · Environment | CC-VENUE | each | 255 | 300 | 345 | Custom neon or LED flex neon sign for branding or decor. | Custom text or logo ¦ 12 to 72in ¦ RGB or single color. | 336 | 04 Physical | Install
4000.03.01-XPMS-007 | 4000.03.01 | Patio Shade or Pergola + Courtyard Scenic | service | Y | 5400 | Expense · Environment | CC-VENUE | each | 3500 | 5000 | 7500 | Shade structure + scenic; turf and palms exist. |  |  | 04 Physical | Build
4000.03.01-XPMS-006 | 4000.03.01 | Podcast Studio Set Build | service | Y | 5400 | Expense · Environment | CC-VENUE | each | 6500 | 9500 | 14000 | Set build + acoustic. |  |  | 04 Physical | Build
4000.03.01-XPMS-008 | 4000.03.01 | Window Treatments · Blackout & Solar Control | service | Y | 5400 | Expense · Environment | CC-VENUE | each | 2500 | 3500 | 5000 | Motorized shades / blackout for storefront + clerestory glazing. |  |  | 04 Physical | Build
4000.04.01-XPMS-004 | 4000.04.01 | Custom Metal Railing - Fabricated | equipment | X | 5400 | Expense · Environment | CC-VENUE | each | 75 | 110 | 160 | Custom steel or aluminum guardrail and handrail fabricated to code for stages, ramps, and platforms. |  |  | 04 Physical | Build
4000.04.01-XPMS-002 | 4000.04.01 | Custom Steel Base Plates - Fabricated | equipment | X | 5400 | Expense · Environment | CC-VENUE | each | 45 | 65 | 95 | Custom-fabricated steel base and ballast plates to engineered spec. |  |  | 04 Physical | Procure
4000.04.01-XPMS-001 | 4000.04.01 | Mobile Welding Rig with Operator | equipment | X | 5400 | Expense · Environment | CC-VENUE | each | 650 | 850 | 1150 | Truck-mounted MIG/stick welding rig with certified operator for on-site fabrication. |  |  | 04 Physical | Build
4000.04.01-XPMS-005 | 4000.04.01 | Structural Construction & Shell | service | Y | 5400 | Expense · Environment | CC-VENUE | each | 15000 | 25000 | 40000 | BY OWNER (Spotify). |  |  | 04 Physical | Build
4000.04.01-XPMS-003 | 4000.04.01 | Truss Repair & Recertification Service | service | Y | 5400 | Expense · Environment | CC-VENUE | each | 450 | 650 | 950 | Inspection, weld repair, and load recertification of aluminum truss sections. |  |  | 04 Physical | Build
4000.05.01-XPMS-002 | 4000.05.01 | Environmental Graphics or Wayfinding Fab & Install | service | Y | 5400 | Expense · Environment | CC-VENUE | each | 2500 | 3500 | 5000 | Guest-facing wayfinding fab. |  |  | 04 Physical | Build
4000.05.01-XPMS-001 | 4000.05.01 | Sign Panel · Plywood Sign W or Base (2 Ft×6 Ft) | equipment | X | 5400 | Expense · Environment | CC-VENUE | each | 65 | 85 | 115 | Free-standing sign panel; wayfinding + brand mark. |  |  | 04 Physical | Build
4000.05.02-XPMS-001 | 4000.05.02 | Banner - Vinyl | equipment | X | 5400 | Expense · Environment | CC-VENUE | each | 50 | 60 | 70 | Large format vinyl banner with grommets. | 3x6 through custom size. | 336 | 04 Physical | Install
4000.05.02-XPMS-002 | 4000.05.02 | Banner Stand - Retractable | equipment | X | 5400 | Expense · Environment | CC-VENUE | each | 85 | 100 | 115 | Portable pull-up banner for registration, info, or branding. | 33x80 through 47x80 ¦ Double-sided available. | 336 | 04 Physical | Install
4000.05.02-XPMS-003 | 4000.05.02 | Flag - Feather | equipment | X | 5400 | Expense · Environment | CC-VENUE | each | 70 | 80 | 90 | Tall fabric flag banner on flexible pole. | 8ft through 18ft ¦ Single or double-sided. | 336 | 04 Physical | Install
4000.05.02-XPMS-004 | 4000.05.02 | Sign - A-Frame | equipment | X | 5400 | Expense · Environment | CC-VENUE | each | 26 | 30 | 34 | Double-sided A-frame sign for ground-level wayfinding. | 24x36 or 28x44 ¦ Chalkboard and dry-erase options. | 336 | 04 Physical | Install
4000.05.02-XPMS-005 | 4000.05.02 | Sign - Coroplast | equipment | X | 5400 | Expense · Environment | CC-VENUE | each | 13 | 15 | 17 | 4mm corrugated plastic sign, single or double-sided print. | 18x24 through custom size. | 336 | 04 Physical | Install
4000.05.02-XPMS-006 | 4000.05.02 | Sign - Foam Board | equipment | X | 5400 | Expense · Environment | CC-VENUE | each | 21 | 25 | 29 | Rigid foam board sign for indoor or sheltered display. | 18x24 through custom ¦ 3/16in or 1/2in thickness. | 336 | 04 Physical | Install
4000.05.02-XPMS-007 | 4000.05.02 | Sign - Truss-Mounted | equipment | X | 5400 | Expense · Environment | CC-VENUE | each | 500 | 600 | 700 | Large signage mounted to truss archway or tower. | 4x8 through custom size ¦ Printed or LED options. | 336 | 04 Physical | Install
4000.06.01-XPMS-002 | 4000.06.01 | Accent Lounge Chair Rental | equipment | X | 5400 | Expense · Environment | CC-VENUE | each | 65 | 85 | 115 | Single accent chair for lounge vignettes and VIP seating groups. |  |  | 04 Physical | Install
4000.06.01-GHXST-001 | 4000.06.01 | Chair - Folding | equipment | X | 5400 | Expense · Environment | CC-VENUE | each | 3.4 | 4 | 4.6 | Standard folding event chair. | Metal or plastic ¦ Padded or unpadded ¦ Indoor and outdoor. | 48 | 04 Physical | Procurement | WORK-FURN-OFFC-003 · 6000.040.00
4000.06.01-XPMS-007 | 4000.06.01 | Coat Check Rack with Hangers | equipment | X | 5400 | Expense · Environment | CC-VENUE | each | 25 | 35 | 48 | Rolling garment rack with numbered hangers and tag set, 50-coat capacity. |  |  | 04 Physical | Install
4000.06.01-XPMS-004 | 4000.06.01 | Conference Table - 8 to 10 Person | equipment | X | 5400 | Expense · Environment | CC-VENUE | each | 95 | 125 | 165 | Production-office or boardroom-style conference table rental. |  |  | 04 Physical | Install
4000.06.01-XPMS-005 | 4000.06.01 | Director Fts Chair - Tall | equipment | X | 5400 | Expense · Environment | CC-VENUE | each | 35 | 45 | 60 | Tall director's chair for panels, green rooms, and video village. |  |  | 04 Physical | Install
4000.06.01-GHXST-002 | 4000.06.01 | Furniture Set - Lounge | equipment | X | 5400 | Expense · Environment | CC-VENUE | each | 300 | 350 | 400 | Styled lounge seating group with sofa, chairs, and coffee table. | Sofa plus 2 chairs plus coffee table plus side table ¦ Various styles. | 336 | 04 Physical | Procurement | WORK-FURN-LNGE-001 · 6000.040.00
4000.06.01-XPMS-003 | 4000.06.01 | LED Glow Cocktail Table | equipment | X | 5400 | Expense · Environment | CC-VENUE | each | 55 | 75 | 105 | Illuminated cocktail table with app or remote color control. |  |  | 04 Physical | Install
4000.06.01-XPMS-010 | 4000.06.01 | LED Vanity Mirror - Full Length | equipment | X | 5400 | Expense · Environment | CC-VENUE | each | 45 | 65 | 90 | Full-length lighted mirror for styling suites and photo-adjacent moments. |  |  | 04 Physical | Install
4000.06.01-XPMS-008 | 4000.06.01 | Lectern - Acrylic | equipment | X | 5400 | Expense · Environment | CC-VENUE | each | 65 | 85 | 115 | Clear acrylic lectern for speakers and program moments. |  |  | 04 Physical | Install
4000.06.01-XPMS-009 | 4000.06.01 | Lounge Area Rug - 8x10 | equipment | X | 5400 | Expense · Environment | CC-VENUE | each | 65 | 90 | 125 | Area rug anchoring lounge vignettes and softening hard floors. |  |  | 04 Physical | Install
4000.06.01-XPMS-001 | 4000.06.01 | Lounge Sofa - 3-Seat Rental | equipment | X | 5400 | Expense · Environment | CC-VENUE | each | 180 | 250 | 340 | Three-seat contemporary lounge sofa, white or black, event rental grade. |  |  | 04 Physical | Install
4000.06.01-GHXST-003 | 4000.06.01 | Ottoman | equipment | X | 5400 | Expense · Environment | CC-VENUE | each | 26 | 30 | 34 | Accent seating ottoman or pouf for lounge areas. | Round, square, or cube ¦ Various fabrics. | 168 | 04 Physical | Procurement | WORK-FURN-LNGE-002 · 6000.040.00
4000.06.01-XPMS-006 | 4000.06.01 | Outdoor Patio Furniture Set | equipment | X | 5400 | Expense · Environment | CC-VENUE | each | 250 | 350 | 480 | Weather-rated outdoor seating group: sofa or sectional, chairs, and table. |  |  | 04 Physical | Install
4000.06.01-GHXST-004 | 4000.06.01 | Stool - Bar | equipment | X | 5400 | Expense · Environment | CC-VENUE | each | 8 | 10 | 12 | Tall seating for bars and high-top tables. | 30in (bar height) or 26in (counter height) ¦ With or without back. | 168 | 04 Physical | Procurement | WORK-FURN-LNGE-003 · 6000.040.00
4000.06.01-GHXST-005 | 4000.06.01 | Table - Cocktail | equipment | X | 5400 | Expense · Environment | CC-VENUE | each | 13 | 15 | 17 | Cocktail-height round table for standing events. | 30in round x 42in tall ¦ With spandex cover options. | 48 | 04 Physical | Procurement | WORK-FURN-OFFC-004 · 6000.040.00
4000.06.01-GHXST-006 | 4000.06.01 | Table - Folding - 6ft | equipment | X | 5400 | Expense · Environment | CC-VENUE | each | 10 | 12 | 14 | Standard 6ft rectangular folding banquet table. | 6ft x 30in ¦ Plastic or wood top ¦ 30in height. | 48 | 04 Physical | Procurement | WORK-FURN-OFFC-001 · 6000.040.00
4000.06.01-GHXST-007 | 4000.06.01 | Table - Folding - 8ft | equipment | X | 5400 | Expense · Environment | CC-VENUE | each | 13 | 15 | 17 | Standard 8ft rectangular folding banquet table. | 8ft x 30in ¦ Plastic or wood top ¦ 30in height. | 48 | 04 Physical | Procurement | WORK-FURN-OFFC-002 · 6000.040.00
4000.06.01-GHXST-008 | 4000.06.01 | Table - Round - 60in or 72in | equipment | X | 5400 | Expense · Environment | CC-VENUE | each | 15 | 18 | 21 | Standard 60 or 72 inch round banquet table for dining or meetings. | 60in (seats 8) or 72in (seats 10) ¦ Plastic or wood. | 48 | 04 Physical | Procurement | WORK-FURN-OFFC-008 · 6000.040.00
4000.06.01-GHXST-009 | 4000.06.01 | Whiteboard - Freestanding | equipment | X | 5400 | Expense · Environment | CC-VENUE | each | 17 | 20 | 23 | Freestanding whiteboard or corkboard for production office. | 24x36 through 48x72 ¦ Double-sided and mobile options. | 48 | 04 Physical | Procurement | WORK-FURN-OFFC-006 · 6000.040.00
4000.07.01-XPMS-008 | 4000.07.01 | Acoustic Wall Treatment or Panels | service | Y | 5400 | Expense · Environment | CC-VENUE | each | 3500 | 4800 | 6500 | ~1,200 sf acoustic treatment. |  |  | 04 Physical | Build
4000.07.01-XPMS-001 | 4000.07.01 | Carpet - Event | equipment | X | 5400 | Expense · Environment | CC-VENUE | each | 2.55 | 3 | 3.45 | Event carpet for aisles, entrances, and VIP areas. |  |  | 04 Physical | Build
4000.07.01-XPMS-002 | 4000.07.01 | Dance Floor - Marley | equipment | X | 5400 | Expense · Environment | CC-VENUE | each | 1.7 | 2 | 2.3 | Professional vinyl dance surface for performance stages. | 5.25ft wide rolls ¦ 1.5mm thickness ¦ Matte finish. | 168 | 04 Physical | Build
4000.07.01-XPMS-003 | 4000.07.01 | Dance Floor - Portable | equipment | X | 5400 | Expense · Environment | CC-VENUE | each | 3.4 | 4 | 4.6 | Modular interlocking dance floor panels, indoor and outdoor rated. |  |  | 04 Physical | Build
4000.07.01-XPMS-004 | 4000.07.01 | Floor - Raised Access | equipment | X | 5400 | Expense · Environment | CC-VENUE | each | 7 | 8 | 9 | Modular raised floor system for leveling or cable management. |  |  | 04 Physical | Build
4000.07.01-XPMS-005 | 4000.07.01 | Mat - Ground Protection | equipment | X | 5400 | Expense · Environment | CC-VENUE | each | 21 | 25 | 29 | Heavy-duty composite ground protection mat for vehicles and pedestrians. |  |  | 04 Physical | Build
4000.07.01-XPMS-006 | 4000.07.01 | Mat - Rubber - Anti-Fatigue | equipment | X | 5400 | Expense · Environment | CC-VENUE | each | 5 | 6 | 7 | Heavy-duty interlocking rubber floor tile for BOH and utility areas. | 3ft x 3ft ¦ 3/4in thick ¦ Anti-fatigue ¦ Non-slip. | 168 | 04 Physical | Build
4000.07.01-XPMS-007 | 4000.07.01 | Turf - Synthetic | equipment | X | 5400 | Expense · Environment | CC-VENUE | each | 1.7 | 2 | 2.3 | Artificial turf for temporary ground cover and aesthetics. | 12ft or 15ft wide rolls ¦ 1.5in pile height ¦ UV stabilized. | 168 | 04 Physical | Build
4000.08.01-XPMS-001 | 4000.08.01 | Barricade - Bike Rack - 8ft | equipment | X | 5400 | Expense · Environment | CC-VENUE | each | 10 | 12 | 14 | Steel interlocking crowd control barricade, 8ft sections, hot-dip galvanized. | 8ft x 43in ¦ Steel ¦ 38 lbs per section ¦ Interlocking feet. | 48 | 04 Physical | Build
4000.08.01-XPMS-002 | 4000.08.01 | Barrier - Front of Stage | equipment | X | 5400 | Expense · Environment | CC-VENUE | each | 34 | 40 | 46 | Front-of-stage crowd safety barrier with integrated cable trough. | Mojo Barrier style ¦ Stabilizer legs ¦ Expandable corners. | 48 | 04 Physical | Build
4000.08.01-XPMS-003 | 4000.08.01 | Barrier - Jersey - Concrete | equipment | X | 5400 | Expense · Environment | CC-VENUE | each | 47 | 56 | 65 | Precast concrete traffic barrier for high-security vehicle mitigation. | 10ft L x 24in W x 32in H ¦ 4,000 lbs ¦ Reinforced concrete. | 168 | 04 Physical | Build
4000.08.01-XPMS-004 | 4000.08.01 | Barrier - Jersey - Water-Filled | equipment | X | 5400 | Expense · Environment | CC-VENUE | each | 34 | 40 | 46 | Polyethylene water-filled traffic barrier for vehicle mitigation and perimeter control. |  |  | 04 Physical | Build
4000.08.01-XPMS-005 | 4000.08.01 | Barrier - Median - Concrete DOT | equipment | X | 5400 | Expense · Environment | CC-VENUE | each | 60 | 70 | 80 | DOT-rated concrete median barrier for road closures and perimeter security. | 12ft section ¦ 6,000 lbs ¦ MASH TL-3 rated. | 48 | 04 Physical | Build
4000.08.01-XPMS-006 | 4000.08.01 | Bollard - Removable | equipment | X | 5400 | Expense · Environment | CC-VENUE | each | 210 | 250 | 290 | Anti-vehicle bollard for pedestrian zone protection. | 36in H ¦ Steel pipe filled ¦ Removable or permanent ¦ Crash-rated options. | 48 | 04 Physical | Build
4000.08.01-XPMS-007 | 4000.08.01 | Cone - Traffic | equipment | X | 5400 | Expense · Environment | CC-VENUE | each | 1.7 | 2 | 2.3 | Standard traffic cone for channelizing and delineation. | 18in ¦ 28in ¦ 36in ¦ Reflective collar ¦ Weighted base. | 48 | 04 Physical | Build
4000.08.01-XPMS-008 | 4000.08.01 | Fence Panel - Chain Link - 6ft Temp | equipment | X | 5400 | Expense · Environment | CC-VENUE | each | 13 | 15 | 17 | Temporary 6ft chain link fence panel with stands and clamps. | 6ft H x 10ft W ¦ 11.5 gauge galvanized steel ¦ Wind screen compatible. | 48 | 04 Physical | Build
4000.08.01-XPMS-009 | 4000.08.01 | Stanchion - Retractable Belt | equipment | X | 5400 | Expense · Environment | CC-VENUE | each | 7 | 8 | 9 | Chrome or black retractable belt stanchion for queue management. | 40in H ¦ 8ft retractable belt ¦ Weighted base. | 24 | 04 Physical | Build
4000.08.02-XPMS-001 | 4000.08.02 | Canopy - Pop-Up - 10x10 | equipment | X | 5400 | Expense · Environment | CC-VENUE | each | 425 | 500 | 575 | Portable instant canopy with aluminum frame, event grade. | 10ft x 10ft ¦ 40 lbs ¦ 150 sq ft coverage. | 24 | 04 Physical | Build
4000.08.02-XPMS-002 | 4000.08.02 | Shade Sail - Tension | equipment | X | 5400 | Expense · Environment | CC-VENUE | each | 380 | 452.5 | 525 | Fabric tension shade structure, custom shapes, UV-resistant. | Triangle ¦ Square ¦ Rectangle ¦ Custom shapes ¦ UV-resistant fabric. | 336 | 04 Physical | Build
4000.08.02-XPMS-003 | 4000.08.02 | Shipping Container - Office | equipment | X | 5400 | Expense · Environment | CC-VENUE | each |  |  |  | Modified ISO container for bar, retail, greenroom, or storage use. |  |  | 04 Physical | Build
4000.08.02-XPMS-004 | 4000.08.02 | Shipping Container - Storage | equipment | X | 5400 | Expense · Environment | CC-VENUE | each | 105 | 125 | 145 | Unmodified ISO shipping container for secure on-site storage. | 20ft or 40ft ¦ Lock box ¦ Ventilated options. | 336 | 04 Physical | Build
4000.08.02-XPMS-005 | 4000.08.02 | Structure - Clear Span | equipment | X | 5400 | Expense · Environment | CC-VENUE | each | 5 | 6 | 7 | Engineered clear span temporary structure for large-scale events. | 40ft to 150ft wide, unlimited length in 15ft bays ¦ Aluminum frame. | 672 | 04 Physical | Build
4000.08.02-XPMS-006 | 4000.08.02 | Tent - Frame | equipment | X | 5400 | Expense · Environment | CC-VENUE | each | 1275 | 1500 | 1725 | Commercial aluminum frame tent, no center poles, clear span interior. | 20x20 through 40x80 ¦ Aluminum frame ¦ Modular. | 336 | 04 Physical | Build
4000.08.02-XPMS-007 | 4000.08.02 | Tent - Pole - High Peak | equipment | X | 5400 | Expense · Environment | CC-VENUE | each | 1025 | 1200 | 1375 | Traditional high-peak pole tent with center and side poles. | 20x20 through 60x120 ¦ Center poles ¦ Sailcloth or vinyl. | 336 | 04 Physical | Build
4000.09.01-XPMS-001 | 4000.09.01 | Boom Lift - Articulating | equipment | X | 5400 | Expense · Environment | CC-VENUE | each | 4500 | 6500 | 9500 | Articulating boom lift for reaching over obstacles. | 40ft through 135ft platform height. | 48 | 04 Physical | Build
4000.09.01-XPMS-002 | 4000.09.01 | Boom Lift - Telescopic | equipment | X | 5400 | Expense · Environment | CC-VENUE | each | 500 | 600 | 700 | Straight telescopic boom lift for maximum height and reach. | 60ft through 185ft platform height. | 48 | 04 Physical | Build
4000.09.01-XPMS-005 | 4000.09.01 | General Install Labor + Scenic Finishes | service | Y | 5400 | Expense · Environment | CC-VENUE | each |  |  |  | Full Venue install and finish labor. |  |  | 04 Physical | Build
4000.09.01-XPMS-003 | 4000.09.01 | Lift - Vertical - Push-Around | equipment | X | 5400 | Expense · Environment | CC-VENUE | each | 105 | 125 | 145 | Manually positioned vertical personnel lift for light-duty tasks. | 12ft through 25ft platform height ¦ 300 to 500 lb capacity. | 48 | 04 Physical | Build
4000.09.01-XPMS-004 | 4000.09.01 | Scissor Lift - Electric | equipment | X | 5400 | Expense · Environment | CC-VENUE | each | 235 | 275 | 315 | Electric scissor lift for indoor and outdoor elevated work. | 26ft through 46ft platform height ¦ 500 to 1,000 lb capacity. | 48 | 04 Physical | Build
4000.09.02-XPMS-001 | 4000.09.02 | Crane - Mobile | equipment | X | 5400 | Expense · Environment | CC-VENUE | each | 4500 | 6500 | 9500 | Hydraulic truck-mounted crane for heavy lifts. | 25-ton through 300-ton and above. | 672 | 04 Physical | Build
4000.09.02-XPMS-002 | 4000.09.02 | Crane - Tower | equipment | X | 5400 | Expense · Environment | CC-VENUE | each | 2500 | 3500 | 5000 | Fixed tower crane for multi-day heavy construction and installation. | 100 to 300ft height ¦ 1 to 20 ton tip load. | 672 | 04 Physical | Build
4000.50.01-XOS-001 | 4000.50.01 | Base Build Delivery | service | Y | 5400 | Expense · Environment | CC-VENUE | lump sum | 3500 | 5000 | 7500 | Representative line for base build delivery so the category can carry cost. Replace with the specific item on award. |  |  | 04 Physical | Procure | 4000.50.01-XOS-001
4000.51.01-XOS-001 | 4000.51.01 | House Technical | service | Y | 5400 | Expense · Environment | CC-VENUE | lump sum | 3500 | 5000 | 7500 | Representative line for house technical so the category can carry cost. Replace with the specific item on award. |  |  | 04 Physical | Procure | 4000.51.01-XOS-001
4000.51.02-XOS-001 | 4000.51.02 | Mechanical Services | service | Y | 5400 | Expense · Environment | CC-VENUE | lump sum | 2500 | 3500 | 5000 | Representative line for mechanical services so the category can carry cost. Replace with the specific item on award. |  |  | 04 Physical | Procure | 4000.51.02-XOS-001
4000.51.03-XOS-001 | 4000.51.03 | Electrical Services | service | Y | 5400 | Expense · Environment | CC-VENUE | lump sum | 3500 | 5000 | 7500 | Representative line for electrical services so the category can carry cost. Replace with the specific item on award. |  |  | 04 Physical | Procure | 4000.51.03-XOS-001
4000.51.04-XOS-001 | 4000.51.04 | Plumbing Services | service | Y | 5400 | Expense · Environment | CC-VENUE | lump sum | 3500 | 5000 | 7500 | Representative line for plumbing services so the category can carry cost. Replace with the specific item on award. |  |  | 04 Physical | Procure | 4000.51.04-XOS-001
4000.60.01-XOS-001 | 4000.60.01 | Scope Activities · Environment | service | Y | 5400 | Expense · Environment | CC-E00 | lump sum | 2500 | 3500 | 5000 | Representative line for scope activities so the category can carry cost. Replace with the specific item on award. |  |  | 04 Physical | Scope | 4000.60.01-XOS-001
4000.60.02-XOS-001 | 4000.60.02 | Engage Activities · Environment | service | Y | 5400 | Expense · Environment | CC-E00 | lump sum | 2500 | 3500 | 5000 | Representative line for engage activities so the category can carry cost. Replace with the specific item on award. |  |  | 04 Physical | Engage | 4000.60.02-XOS-001
4000.60.03-XOS-001 | 4000.60.03 | Advance Activities · Environment | service | Y | 5400 | Expense · Environment | CC-E00 | lump sum | 3500 | 5000 | 7500 | Representative line for advance activities so the category can carry cost. Replace with the specific item on award. |  |  | 04 Physical | Advance | 4000.60.03-XOS-001
4000.60.04-XOS-001 | 4000.60.04 | Procure Activities · Environment | service | Y | 5400 | Expense · Environment | CC-E00 | lump sum | 4500 | 6500 | 9500 | Representative line for procure activities so the category can carry cost. Replace with the specific item on award. |  |  | 04 Physical | Procure | 4000.60.04-XOS-001
4000.60.05-XOS-001 | 4000.60.05 | Build Activities · Environment | service | Y | 5400 | Expense · Environment | CC-E00 | lump sum | 6500 | 9500 | 14000 | Representative line for build activities so the category can carry cost. Replace with the specific item on award. |  |  | 04 Physical | Build | 4000.60.05-XOS-001
4000.60.06-XOS-001 | 4000.60.06 | Install Activities · Environment | service | Y | 5400 | Expense · Environment | CC-E00 | lump sum | 3500 | 5000 | 7500 | Representative line for install activities so the category can carry cost. Replace with the specific item on award. |  |  | 04 Physical | Install | 4000.60.06-XOS-001
4000.60.07-XOS-001 | 4000.60.07 | Operate Activities · Environment | service | Y | 5400 | Expense · Environment | CC-E00 | lump sum | 5500 | 7500 | 11000 | Representative line for operate activities so the category can carry cost. Replace with the specific item on award. |  |  | 04 Physical | Operate | 4000.60.07-XOS-001
4000.60.08-XOS-001 | 4000.60.08 | Amplify Activities · Environment | service | Y | 5400 | Expense · Environment | CC-E00 | lump sum | 4500 | 6500 | 9500 | Representative line for amplify activities so the category can carry cost. Replace with the specific item on award. |  |  | 04 Physical | Amplify | 4000.60.08-XOS-001
4000.60.09-XOS-001 | 4000.60.09 | Close Activities · Environment | service | Y | 5400 | Expense · Environment | CC-E00 | lump sum | 2500 | 3500 | 5000 | Representative line for close activities so the category can carry cost. Replace with the specific item on award. |  |  | 04 Physical | Close | 4000.60.09-XOS-001
5000.01.01-XPMS-021 | 5000.01.01 | AV or Stage Labor | package | Y | 5500 | Expense · Production | CC-VENUE | each | 210 | 250 | 290 | Production · AV / stage labor. |  |  | 04 Physical | Operate
5000.01.01-XPMS-001 | 5000.01.01 | Amplifier Rack - Audio | equipment | X | 5500 | Expense · Production | CC-VENUE | each | 170 | 200 | 250 | Power amplifier rack for passive speaker systems. | 2-channel through rack configurations ¦ DSP-integrated options. | 336 | 04 Physical | Procure
5000.01.01-XPMS-015 | 5000.01.01 | Backline · Bass (head or Cab or DI) | equipment | X | 5500 | Expense · Production | CC-VENUE | each | 85 | 100 | 125 | Production · Backline; Bass (head/cab/DI). |  |  | 04 Physical | Build
5000.01.01-XPMS-019 | 5000.01.01 | Backline · Common (stands or Snakes or DI or Road Cases) | equipment | X | 5500 | Expense · Production | CC-VENUE | each | 450 | 550 | 650 | Production · Backline; Common (stands/snakes/DI/road cases). |  |  | 04 Physical | Build
5000.01.01-XPMS-012 | 5000.01.01 | Backline · DJ: 4× Turntables (Technics SL-1200MK7) | equipment | X | 5500 | Expense · Production | CC-VENUE | each | 850 | 1000 | 1200 | Production · Backline; DJ: 4× Turntables (Technics SL-1200MK7). |  |  | 04 Physical | Build
5000.01.01-XPMS-008 | 5000.01.01 | Backline · DJ: 8× CDJ-3000X Media Players | equipment | X | 5500 | Expense · Production | CC-VENUE | each | 150 | 175 | 220 | Production · Backline; DJ: 8× CDJ-3000X media players. |  |  | 04 Physical | Build
5000.01.01-XPMS-011 | 5000.01.01 | Backline · DJ: DJM-A9 (4-ch Flagship) | equipment | X | 5500 | Expense · Production | CC-VENUE | each | 200 | 240 | 290 | Production · Backline; DJ: DJM-A9 (4-ch flagship). |  |  | 04 Physical | Build
5000.01.01-XPMS-009 | 5000.01.01 | Backline · DJ: DJM-V10 (6-ch Mixer) | equipment | X | 5500 | Expense · Production | CC-VENUE | each | 200 | 240 | 290 | Production · Backline; DJ: DJM-V10 (6-ch mixer). |  |  | 04 Physical | Build
5000.01.01-XPMS-010 | 5000.01.01 | Backline · DJ: DJM-V10-LF (6-ch Long-fader) | equipment | X | 5500 | Expense · Production | CC-VENUE | each | 300 | 350 | 420 | Production · Backline; DJ: DJM-V10-LF (6-ch long-fader). |  |  | 04 Physical | Build
5000.01.01-XPMS-016 | 5000.01.01 | Backline · Drums (pro Kit + Drum Mics) | equipment | X | 5500 | Expense · Production | CC-VENUE | each | 180 | 220 | 270 | Production · Backline; Drums (pro kit + drum mics). |  |  | 04 Physical | Build
5000.01.01-XPMS-014 | 5000.01.01 | Backline · Guitar (amp or Cab or DI or Stands) | equipment | X | 5500 | Expense · Production | CC-VENUE | each | 120 | 150 | 190 | Production · Backline; Guitar (amp/cab/DI/stands). |  |  | 04 Physical | Build
5000.01.01-XPMS-017 | 5000.01.01 | Backline · Horns (4× Horn Mics + DI) | equipment | X | 5500 | Expense · Production | CC-VENUE | each | 140 | 175 | 220 | Production · Backline; Horns (4× horn mics + DI). |  |  | 04 Physical | Build
5000.01.01-XPMS-018 | 5000.01.01 | Backline · Latin or World Percussion + Mics | equipment | X | 5500 | Expense · Production | CC-VENUE | each | 250 | 300 | 380 | Production · Backline; Latin/World Percussion + mics. |  |  | 04 Physical | Build
5000.01.01-XPMS-020 | 5000.01.01 | Backline · Rehearsal or Backup Kit (full Coverage, Value Spec) | equipment | X | 5500 | Expense · Production | CC-VENUE | each | 220 | 260 | 320 | Production · Backline; Rehearsal/Backup Kit (full coverage, value spec). |  |  | 04 Physical | Build
5000.01.01-XPMS-013 | 5000.01.01 | Backline · Vocals (4× Wireless HH + 4× IEM) | equipment | X | 5500 | Expense · Production | CC-VENUE | each | 3500 | 4500 | 6000 | Production · Backline; Vocals (4× wireless HH + 4× IEM). |  |  | 04 Physical | Build
5000.01.01-XPMS-006 | 5000.01.01 | Main Room PA + Subs + DSP | package | X | 5500 | Expense · Production | CC-VENUE | each | 130 | 150 | 170 | Installed main room system. |  |  | 04 Physical | Build
5000.01.01-XPMS-002 | 5000.01.01 | Monitor - In-Ear | equipment | X | 5500 | Expense · Production | CC-VENUE | each | 85 | 100 | 115 | Personal in-ear monitoring system for performers. | Shure PSM1000 ¦ Sennheiser EW IEM G4 ¦ Shure PSM900. | 336 | 04 Physical | Procure
5000.01.01-XPMS-003 | 5000.01.01 | Monitor - Stage Wedge | equipment | X | 5500 | Expense · Production | CC-VENUE | each | 85 | 100 | 115 | Floor monitor wedge for performer monitoring. | 12in or 15in ¦ Bi-amp ¦ Active or passive. | 336 | 04 Physical | Procure
5000.01.01-XOS-001 | 5000.01.01 | PA or Sound System · Base | experience | Y | 5500 | Expense · Production | CC-VENUE | each | 850 | 1200 | 1600 | Powered point-source mains plus subs sized for 100; one mix position. | Zone: Main Stage and Bar. Tier fit: T1; T4. Upgrades: Cardioid sub array; delay towers. Add-ons: Stage monitor package; IEM. Substitutions: House PA passthrough only. |  | 04 Physical | Build | SGT-11
5000.01.01-XOS-002 | 5000.01.01 | PA or Sound System · Elevated | experience | Y | 5500 | Expense · Production | CC-VENUE | each | 1800 | 2500 | 3500 | Compact line-array hang with subs and front-fills, tuned for music playback and live sets. | Zone: Main Stage and Bar. Tier fit: T1; T4. Upgrades: Cardioid sub array; delay towers. Add-ons: Stage monitor package; IEM. Substitutions: House PA passthrough only. |  | 04 Physical | Build | SGT-11
5000.01.01-XOS-003 | 5000.01.01 | PA or Sound System · Premium | experience | Y | 5500 | Expense · Production | CC-VENUE | each | 3500 | 5000 | 7500 | Full line-array system with cardioid subs, delay fills, and a tuned, measured room for 350+. | Zone: Main Stage and Bar. Tier fit: T1; T4. Upgrades: Cardioid sub array; delay towers. Add-ons: Stage monitor package; IEM. Substitutions: House PA passthrough only. |  | 04 Physical | Build | SGT-11
5000.01.01-XPMS-007 | 5000.01.01 | Patio DJ Audio + Booth Lighting | package | X | 5500 | Expense · Production | CC-VENUE | each | 1800 | 2500 | 3500 | Patio audio + DJ booth. |  |  | 04 Physical | Build
5000.01.01-XPMS-024 | 5000.01.01 | Power or Distro or Generators | package | X | 5500 | Expense · Production | CC-VENUE | each | 3500 | 5000 | 7500 | Production · Power / distro / generators. |  |  | 04 Physical | Operate
5000.01.01-XPMS-004 | 5000.01.01 | Recording System - Live | equipment | X | 5500 | Expense · Production | CC-VENUE | each | 340 | 400 | 460 | Multi-track recording or playback rig for live audio capture. | Multi-track recorder or laptop with interface ¦ Redundant backup. | 336 | 04 Physical | Procure
5000.01.01-XPMS-022 | 5000.01.01 | SFX or Atmospherics | package | X | 5500 | Expense · Production | CC-VENUE | each | 2500 | 3500 | 5000 | Production · SFX / atmospherics. |  |  | 04 Physical | Operate
5000.01.01-XPMS-005 | 5000.01.01 | Snake - Audio | equipment | X | 5500 | Expense · Production | CC-VENUE | each | 130 | 150 | 170 | Multi-channel analog or digital audio snake. | 16 through 64 channels ¦ Analog or Dante or MADI. | 336 | 04 Physical | Procure
5000.01.01-XPMS-023 | 5000.01.01 | Staging or Decking or Barricade | package | X | 5500 | Expense · Production | CC-VENUE | each | 3500 | 5000 | 7500 | Production · Staging / decking / barricade. |  |  | 04 Physical | Operate
5000.01.01-XPMS-025 | 5000.01.01 | Technical Design & System Drawings | service | Y | 5500 | Expense · Production | CC-VENUE | each | 4500 | 6500 | 9500 | Signal flow, plots, patch and power distribution drawings for audio, lighting and video systems. The document install is verified against. |  |  | 05 Experiential | Scope
5000.01.01-XOS-004 | 5000.01.01 | Video or LED Wall · Base | experience | Y | 5500 | Expense · Production | CC-VENUE | each | 1200 | 1800 | 2600 | Single 4x3 LED panel wall as stage backdrop; static content playback. | Zone: Main Stage and Bar. Tier fit: T2; T4. Upgrades: Media server + content design. Add-ons: IMAG camera package. Substitutions: Projection / projection mapping. |  | 04 Physical | Build | SGT-13
5000.01.01-XOS-005 | 5000.01.01 | Video or LED Wall · Elevated | experience | Y | 5500 | Expense · Production | CC-VENUE | each | 2800 | 4000 | 5800 | Wide stage-width LED backdrop with content switching and IMAG capability. | Zone: Main Stage and Bar. Tier fit: T2; T4. Upgrades: Media server + content design. Add-ons: IMAG camera package. Substitutions: Projection / projection mapping. |  | 04 Physical | Build | SGT-13
5000.01.01-XOS-006 | 5000.01.01 | Video or LED Wall · Premium | experience | Y | 5500 | Expense · Production | CC-VENUE | each | 5500 | 8000 | 12000 | Wraparound LED scenic system with floor, walls, and side blades on a media server. | Zone: Main Stage and Bar. Tier fit: T2; T4. Upgrades: Media server + content design. Add-ons: IMAG camera package. Substitutions: Projection / projection mapping. |  | 04 Physical | Build | SGT-13
5000.01.02-XPMS-001 | 5000.01.02 | Audio System - Distributed | equipment | X | 5500 | Expense · Production | CC-VENUE | each | 425 | 500 | 575 | Zone-based speaker system for ambient audio across large sites. | Ceiling, pendant, or surface mount ¦ Weather-rated ¦ Multi-zone. | 672 | 04 Physical | Procure
5000.01.02-XPMS-002 | 5000.01.02 | Delay System - Tower | equipment | X | 5500 | Expense · Production | CC-VENUE | each | 1025 | 1200 | 1375 | Auxiliary delay or fill speaker system for large venues. | 2 to 4 boxes per tower ¦ Processing ¦ Cabling. | 336 | 04 Physical | Procure
5000.01.02-XPMS-003 | 5000.01.02 | Line Array - Large | equipment | X | 5500 | Expense · Production | CC-VENUE | each | 34000 | 40000 | 46000 | Concert and festival-grade line array for 10,000 or more capacity. | 16 to 24 boxes per side ¦ 16 to 32 subs ¦ Multiple delay rings. | 672 | 04 Physical | Procure
5000.01.02-XPMS-004 | 5000.01.02 | Line Array - Medium | equipment | X | 5500 | Expense · Production | CC-VENUE | each | 12800 | 15000 | 17200 | Professional line array for 2,000 to 10,000 capacity. | 12 to 16 boxes per side ¦ 8 to 16 subs ¦ Delay fills. | 336 | 04 Physical | Procure
5000.01.02-XPMS-005 | 5000.01.02 | Line Array - Small | equipment | X | 5500 | Expense · Production | CC-VENUE | each | 4250 | 5025 | 5800 | Compact line array system for venues up to 2,000 capacity. | 8 to 12 boxes per side ¦ 4 to 8 subwoofers ¦ Processing and cabling. | 168 | 04 Physical | Procure
5000.01.02-XPMS-006 | 5000.01.02 | Speaker System - Point Source | equipment | X | 5500 | Expense · Production | CC-VENUE | each | 675 | 800 | 925 | Self-powered or passive point-source speakers for small to medium rooms. | 2 to 4 tops ¦ 1 to 2 subs ¦ Processor ¦ Cabling. | 168 | 04 Physical | Procure
5000.01.03-XPMS-001 | 5000.01.03 | Direct Box - DI | equipment | X | 5500 | Expense · Production | CC-VENUE | each | 13 | 15 | 17 | Active or passive direct injection box for instruments and playback. | Radial JDI ¦ Radial J48 ¦ Countryman Type 85 ¦ BSS AR-133. | 48 | 04 Physical | Procure
5000.01.03-XPMS-002 | 5000.01.03 | Microphone - Instrument | equipment | X | 5500 | Expense · Production | CC-VENUE | each | 30 | 35 | 40 | Specialized microphone for amps, acoustic instruments, and overheads. | Shure SM57 ¦ Sennheiser e906 ¦ AKG C414 ¦ Neumann KM184. | 48 | 04 Physical | Procure
5000.01.03-XPMS-003 | 5000.01.03 | Microphone - Vocal - Wired | equipment | X | 5500 | Expense · Production | CC-VENUE | each | 26 | 30 | 34 | Professional dynamic or condenser vocal microphone. | Shure SM58 ¦ Sennheiser e935 ¦ Neumann KMS 105. | 48 | 04 Physical | Procure
5000.01.03-XPMS-004 | 5000.01.03 | Microphone - Wireless System | equipment | X | 5500 | Expense · Production | CC-VENUE | each | 130 | 150 | 170 | Professional wireless handheld or bodypack system. | Shure ULXD ¦ Sennheiser EW-DX ¦ Shure Axient. | 48 | 04 Physical | Procure
5000.01.03-XPMS-005 | 5000.01.03 | Microphone Kit - Drum | equipment | X | 5500 | Expense · Production | CC-VENUE | each | 150 | 175 | 200 | Complete drum mic package for live performance. | Shure DMK57-52 ¦ Audix DP7 ¦ Sennheiser e600. | 48 | 04 Physical | Procure
5000.01.04-XPMS-001 | 5000.01.04 | Mixing Console - Large | equipment | X | 5500 | Expense · Production | CC-VENUE | each | 1700 | 2000 | 2300 | Full-scale digital mixer for concerts and festivals. | 48 to 96 or more input channels ¦ Multiple mix buses ¦ Redundancy. | 336 | 04 Physical | Procure
5000.01.04-XPMS-002 | 5000.01.04 | Mixing Console - Small | equipment | X | 5500 | Expense · Production | CC-VENUE | each | 425 | 500 | 575 | Compact digital mixer for corporate and small events. | 16 to 32 input channels ¦ Built-in effects ¦ Dante optional. | 336 | 04 Physical | Procure
5000.01.05-XPMS-001 | 5000.01.05 | Media Server | equipment | X | 5500 | Expense · Production | CC-VENUE | each | 1025 | 1200 | 1375 | Professional media server for content playback and processing. |  |  | 04 Physical | Procure
5000.01.05-XPMS-002 | 5000.01.05 | Processor - Video | equipment | X | 5500 | Expense · Production | CC-VENUE | each | 425 | 500 | 575 | Video processing, scaling, and switching for LED walls and projection. |  |  | 04 Physical | Procure
5000.01.06-XOS-001 | 5000.01.06 | Immersive or Spatial Audio · Base | experience | Y | 5500 | Expense · Production | CC-VENUE | each | 650 | 950 | 1450 | Stereo zone audio for lounge listening. | Zone: Exhibition Room. Tier fit: T3; T4. Upgrades: Object-based content design. Add-ons: Headphone spatial mix. Substitutions: Standard stereo zones. |  | 05 Experiential | Build | SND-05
5000.01.06-XOS-002 | 5000.01.06 | Immersive or Spatial Audio · Elevated | experience | Y | 5500 | Expense · Production | CC-VENUE | each | 1250 | 1850 | 2650 | Multi-speaker spatial audio in a feature zone. | Zone: Exhibition Room. Tier fit: T3; T4. Upgrades: Object-based content design. Add-ons: Headphone spatial mix. Substitutions: Standard stereo zones. |  | 05 Experiential | Build | SND-05
5000.01.06-XOS-003 | 5000.01.06 | Immersive or Spatial Audio · Premium | experience | Y | 5500 | Expense · Production | CC-VENUE | each | 2500 | 3500 | 5000 | Full immersive spatial-audio room with object-based content design. | Zone: Exhibition Room. Tier fit: T3; T4. Upgrades: Object-based content design. Add-ons: Headphone spatial mix. Substitutions: Standard stereo zones. |  | 05 Experiential | Build | SND-05
5000.01.06-XPMS-001 | 5000.01.06 | Spatial or Immersive Audio System | equipment | X | 5500 | Expense · Production | CC-VENUE | each | 2500 | 3500 | 5000 | Object-based / immersive audio system. |  |  | 05 Experiential | Operate
5000.02.01-XOS-001 | 5000.02.01 | Artist-Themed Palette · Base | experience | Y | 5500 | Expense · Production | CC-VENUE | each | 450 | 650 | 950 | Static color wash drawn from the artist's brand palette. | Zone: Main Stage and Bar. Tier fit: T1; T4. Upgrades: Set-synced color choreography. Add-ons: Custom gobo set. Substitutions: Brand green/black wash. |  | 04 Physical | Build | SGT-40
5000.02.01-XOS-002 | 5000.02.01 | Artist-Themed Palette · Elevated | experience | Y | 5500 | Expense · Production | CC-VENUE | each | 850 | 1250 | 1850 | Multi-state artist palette with scene changes across the night. | Zone: Main Stage and Bar. Tier fit: T1; T4. Upgrades: Set-synced color choreography. Add-ons: Custom gobo set. Substitutions: Brand green/black wash. |  | 04 Physical | Build | SGT-40
5000.02.01-XOS-003 | 5000.02.01 | Artist-Themed Palette · Premium | experience | Y | 5500 | Expense · Production | CC-VENUE | each |  |  |  | Choreographed artist-palette show synced to set moments. | Zone: Main Stage and Bar. Tier fit: T1; T4. Upgrades: Set-synced color choreography. Add-ons: Custom gobo set. Substitutions: Brand green/black wash. |  | 04 Physical | Build | SGT-40
5000.02.01-GHXST-001 | 5000.02.01 | Blacklight - UV | equipment | X | 5500 | Expense · Production | CC-VENUE | each | 1650 | 2450 | 3550 | UV and blacklight fixture for glow effects and UV-reactive decor. | LED bar or LED flood ¦ 2ft or 4ft length. | 168 | 04 Physical | Procurement | TECH-LITE-STAT-007 · 5000.040.00
5000.02.01-GHXST-002 | 5000.02.01 | Blinder - Audience | equipment | X | 5500 | Expense · Production | CC-VENUE | each | 350 | 500 | 750 | High-intensity audience blinder for dramatic wash effects. | 2-lite or 4-lite ¦ DWE lamps. | 168 | 04 Physical | Procurement | TECH-LITE-STAT-004 · 5000.040.00
5000.02.01-XOS-004 | 5000.02.01 | Brand Wash (Green or Black) · Base | experience | Y | 5500 | Expense · Production | CC-VENUE | each | 650 | 950 | 1450 | Spotify-green and warm-white uplight wash across key walls. | Zone: All Zones. Tier fit: T1; T4. Upgrades: Pixel-mapped brand states. Add-ons: Logo gobo projection. Substitutions: Artist-themed palette wash. |  | 04 Physical | Build | SGT-39
5000.02.01-XOS-005 | 5000.02.01 | Brand Wash (Green or Black) · Elevated | experience | Y | 5500 | Expense · Production | CC-VENUE | each | 1250 | 1850 | 2650 | Layered green/black wash with accent pools and a branded gobo. | Zone: All Zones. Tier fit: T1; T4. Upgrades: Pixel-mapped brand states. Add-ons: Logo gobo projection. Substitutions: Artist-themed palette wash. |  | 04 Physical | Build | SGT-39
5000.02.01-XOS-006 | 5000.02.01 | Brand Wash (Green or Black) · Premium | experience | Y | 5500 | Expense · Production | CC-VENUE | each | 550 | 800 | 1200 | Full pixel-mapped brand environment with timecoded green/black states. | Zone: All Zones. Tier fit: T1; T4. Upgrades: Pixel-mapped brand states. Add-ons: Logo gobo projection. Substitutions: Artist-themed palette wash. |  | 04 Physical | Build | SGT-39
5000.02.01-XPMS-001 | 5000.02.01 | Console - Lighting | equipment | X | 5500 | Expense · Production | CC-VENUE | each | 950 | 1450 | 2150 | Professional lighting control console. | MA Lighting, ChamSys, ETC Eos, or Avolites. | 336 | 04 Physical | Procure
5000.02.01-XOS-007 | 5000.02.01 | Control or FOH · Base | experience | Y | 5500 | Expense · Production | CC-VENUE | each | 1850 | 2750 | 3950 | Single combined audio/light position with rental consoles. | Zone: Main Stage and Bar. Tier fit: T1; T4. Upgrades: Comms / intercom package. Add-ons: Show-caller station. Substitutions: Operator-shared single position. |  | 04 Physical | Build | SGT-15
5000.02.01-XOS-008 | 5000.02.01 | Control or FOH · Elevated | experience | Y | 5500 | Expense · Production | CC-VENUE | each | 450 | 650 | 950 | Dedicated FOH with separate audio and lighting ops and networked control. | Zone: Main Stage and Bar. Tier fit: T1; T4. Upgrades: Comms / intercom package. Add-ons: Show-caller station. Substitutions: Operator-shared single position. |  | 04 Physical | Build | SGT-15
5000.02.01-XOS-009 | 5000.02.01 | Control or FOH · Premium | experience | Y | 5500 | Expense · Production | CC-VENUE | each | 850 | 1250 | 1850 | Full production control: FOH, monitor world, lighting, video, and show-caller comms. | Zone: Main Stage and Bar. Tier fit: T1; T4. Upgrades: Comms / intercom package. Add-ons: Show-caller station. Substitutions: Operator-shared single position. |  | 04 Physical | Build | SGT-15
5000.02.01-XPMS-002 | 5000.02.01 | Dimmer Rack | equipment | X | 5500 | Expense · Production | CC-VENUE | each | 150 | 175 | 200 | Traditional dimmer rack for conventional incandescent fixtures. | 6 through 48 channels ¦ 2.4kW or 6kW per channel. | 336 | 04 Physical | Procure
5000.02.01-GHXST-003 | 5000.02.01 | Ellipsoidal - Source Four | equipment | X | 5500 | Expense · Production | CC-VENUE | each | 30 | 35 | 40 | Conventional or LED ellipsoidal spotlight for key and gobo projection. | ETC Source Four ¦ 19, 26, 36, or 50 degree lens. | 168 | 04 Physical | Procurement | TECH-LITE-STAT-002 · 5000.040.00
5000.02.01-XPMS-006 | 5000.02.01 | Exterior or Entry + Landscape Lighting | package | X | 5500 | Expense · Production | CC-VENUE | each | 1650 | 2450 | 3550 | Facade wash, entry approach + courtyard landscape lighting. |  |  | 04 Physical | Build
5000.02.01-GHXST-004 | 5000.02.01 | Followspot | equipment | X | 5500 | Expense · Production | CC-VENUE | each | 550 | 800 | 1200 | Manually operated followspot for performer tracking. | 800W through 2400W ¦ Long-throw and short-throw available. | 168 | 04 Physical | Procurement | TECH-LITE-STAT-003 · 5000.040.00
5000.02.01-XOS-010 | 5000.02.01 | Golden Hour or Patio · Base | experience | Y | 5500 | Expense · Production | CC-VENUE | each | 1200 | 1800 | 2600 | Warm string lights and amber wash on the patio. | Zone: El Patio. Tier fit: T1; T4. Upgrades: Sunset-matched dimming. Add-ons: Lantern / fixture rental. Substitutions: Cool patio wash. |  | 04 Physical | Build | SGT-43
5000.02.01-XOS-011 | 5000.02.01 | Golden Hour or Patio · Elevated | experience | Y | 5500 | Expense · Production | CC-VENUE | each | 2400 | 3500 | 5000 | Layered golden-hour scene with festoon, uplight, and lantern accents. | Zone: El Patio. Tier fit: T1; T4. Upgrades: Sunset-matched dimming. Add-ons: Lantern / fixture rental. Substitutions: Cool patio wash. |  | 04 Physical | Build | SGT-43
5000.02.01-XOS-012 | 5000.02.01 | Golden Hour or Patio · Premium | experience | Y | 5500 | Expense · Production | CC-VENUE | each | 850 | 1250 | 1850 | Tuned outdoor scene with sunset-matched dimming and architectural accenting. | Zone: El Patio. Tier fit: T1; T4. Upgrades: Sunset-matched dimming. Add-ons: Lantern / fixture rental. Substitutions: Cool patio wash. |  | 04 Physical | Build | SGT-43
5000.02.01-XOS-013 | 5000.02.01 | High-Energy Show · Base | experience | Y | 5500 | Expense · Production | CC-VENUE | each | 1650 | 2450 | 3550 | Color-changing wash with simple chases for peak moments. | Zone: Main Stage and Bar. Tier fit: T2; T4. Upgrades: Laser package; timecode. Add-ons: Audio-reactive control. Substitutions: Ambient-only program. |  | 04 Physical | Build | SGT-42
5000.02.01-XOS-014 | 5000.02.01 | High-Energy Show · Elevated | experience | Y | 5500 | Expense · Production | CC-VENUE | each | 3500 | 5000 | 7500 | Beam and strobe looks with audio-triggered chases. | Zone: Main Stage and Bar. Tier fit: T2; T4. Upgrades: Laser package; timecode. Add-ons: Audio-reactive control. Substitutions: Ambient-only program. |  | 04 Physical | Build | SGT-42
5000.02.01-XOS-015 | 5000.02.01 | High-Energy Show · Premium | experience | Y | 5500 | Expense · Production | CC-VENUE | each | 2500 | 3500 | 5000 | Full peak-moment show with movers, strobes, lasers, and timecode. | Zone: Main Stage and Bar. Tier fit: T2; T4. Upgrades: Laser package; timecode. Add-ons: Audio-reactive control. Substitutions: Ambient-only program. |  | 04 Physical | Build | SGT-42
5000.02.01-XPMS-005 | 5000.02.01 | House Ambient or Architectural Lighting | package | X | 5500 | Expense · Production | CC-VENUE | each | 4500 | 6500 | 9500 | All-room ambient incl. dramatic main volume. |  |  | 04 Physical | Build
5000.02.01-XPMS-004 | 5000.02.01 | Main Stage Performance Lighting Rig | package | X | 5500 | Expense · Production | CC-VENUE | each |  |  |  | Performance rig + control. |  |  | 04 Physical | Build
5000.02.01-XPMS-003 | 5000.02.01 | Node - DMX | equipment | X | 5500 | Expense · Production | CC-VENUE | each | 42 | 48.5 | 55 | DMX or network-based lighting signal distribution. | 2-port through 8-port ¦ sACN or Art-Net. | 336 | 04 Physical | Procure
5000.02.01-GHXST-005 | 5000.02.01 | PAR Can - LED | equipment | X | 5500 | Expense · Production | CC-VENUE | each | 26 | 30 | 34 | Static LED PAR wash for uplighting, stage wash, or decor. | RGBW or RGBAW+UV ¦ Battery-powered option available. | 168 | 04 Physical | Procurement | TECH-LITE-STAT-001 · 5000.040.00
5000.02.01-GHXST-006 | 5000.02.01 | Pixel Tape - LED | equipment | X | 5500 | Expense · Production | CC-VENUE | each | 7 | 8 | 9 | Individually addressable LED tape for scenic and decorative effects. | 5m (16.4ft) per roll ¦ 30, 60, or 144 pixels per meter ¦ RGB or RGBW. | 168 | 04 Physical | Procurement | TECH-LITE-STAT-008 · 5000.040.00
5000.02.01-XPMS-007 | 5000.02.01 | Podcast Video-Ready Lighting | service | Y | 5500 | Expense · Production | CC-VENUE | each | 2500 | 3500 | 5000 | Studio lighting. |  |  | 04 Physical | Build
5000.02.01-XOS-016 | 5000.02.01 | Stage Lighting Rig · Base | experience | Y | 5500 | Expense · Production | CC-VENUE | each | 1200 | 1800 | 2600 | Ground-supported uplights and a few moving heads on the stage; basic looks. | Zone: Main Stage and Bar. Tier fit: T1; T4. Upgrades: Timecode show programming; haze. Add-ons: Followspot operator. Substitutions: Architectural LFX wash only. |  | 04 Physical | Build | SGT-12
5000.02.01-XOS-017 | 5000.02.01 | Stage Lighting Rig · Elevated | experience | Y | 5500 | Expense · Production | CC-VENUE | each | 2500 | 3600 | 5200 | Front truss with wash, spot, and beam fixtures; programmed looks and color states. | Zone: Main Stage and Bar. Tier fit: T1; T4. Upgrades: Timecode show programming; haze. Add-ons: Followspot operator. Substitutions: Architectural LFX wash only. |  | 04 Physical | Build | SGT-12
5000.02.01-XOS-018 | 5000.02.01 | Stage Lighting Rig · Premium | experience | Y | 5500 | Expense · Production | CC-VENUE | each | 5000 | 7500 | 11000 | Full overhead rig with movers, beams, strobes, hazers, and a timecoded show on console. | Zone: Main Stage and Bar. Tier fit: T1; T4. Upgrades: Timecode show programming; haze. Add-ons: Followspot operator. Substitutions: Architectural LFX wash only. |  | 04 Physical | Build | SGT-12
5000.02.01-GHXST-007 | 5000.02.01 | String Lights - Bistro | equipment | X | 5500 | Expense · Production | CC-VENUE | each | 42 | 48.5 | 55 | Decorative string lights for ambiance and outdoor areas. | 48ft or 100ft ¦ LED Edison bulbs. | 48 | 04 Physical | Procurement | TECH-LITE-STAT-006 · 5000.040.00
5000.02.01-GHXST-008 | 5000.02.01 | Strobe - DMX | equipment | X | 5500 | Expense · Production | CC-VENUE | each | 50 | 60 | 70 | High-intensity strobe fixture for dramatic flash effects. | LED or xenon ¦ DMX controlled. | 168 | 04 Physical | Procurement | TECH-LITE-STAT-005 · 5000.040.00
5000.02.01-XOS-019 | 5000.02.01 | Warm Ambient Lounge · Base | experience | Y | 5500 | Expense · Production | CC-VENUE | each | 350 | 500 | 750 | Amber and warm-white pools for lounge and bar zones. | Zone: El Patio. Tier fit: T1; T4. Upgrades: Day-to-night dimming program. Add-ons: Pin-spot table lighting. Substitutions: Cool minimal wash. |  | 04 Physical | Build | SGT-41
5000.02.01-XOS-020 | 5000.02.01 | Warm Ambient Lounge · Elevated | experience | Y | 5500 | Expense · Production | CC-VENUE | each | 650 | 950 | 1450 | Layered warm wash with candle-level accents and pin spots. | Zone: El Patio. Tier fit: T1; T4. Upgrades: Day-to-night dimming program. Add-ons: Pin-spot table lighting. Substitutions: Cool minimal wash. |  | 04 Physical | Build | SGT-41
5000.02.01-XOS-021 | 5000.02.01 | Warm Ambient Lounge · Premium | experience | Y | 5500 | Expense · Production | CC-VENUE | each | 1250 | 1850 | 2650 | Tunable warm scene program with dimming curves for day-to-night. | Zone: El Patio. Tier fit: T1; T4. Upgrades: Day-to-night dimming program. Add-ons: Pin-spot table lighting. Substitutions: Cool minimal wash. |  | 04 Physical | Build | SGT-41
5000.02.02-XPMS-009 | 5000.02.02 | 2-Lite Blinder Fixture | equipment | X | 5500 | Expense · Production | CC-VENUE | each | 45 | 55 | 70 | Audience blinder, two-lamp, for impact looks and crowd light. |  |  | 05 Experiential | Operate
5000.02.02-XPMS-011 | 5000.02.02 | Exterior Architectural Wash Fixture | equipment | X | 5500 | Expense · Production | CC-VENUE | each | 65 | 85 | 115 | IP-rated color wash fixture for facades, trees, and exterior features. |  |  | 05 Experiential | Operate
5000.02.02-XPMS-010 | 5000.02.02 | Festoon String Lighting - 100ft | equipment | X | 5500 | Expense · Production | CC-VENUE | each | 40 | 50 | 65 | Commercial festoon string with warm LED lamps for canopies and perimeters. |  |  | 05 Experiential | Install
5000.02.02-XPMS-006 | 5000.02.02 | Follow Spot - 1200W LED Long Throw | equipment | X | 5500 | Expense · Production | CC-VENUE | each | 280 | 350 | 450 | Long-throw LED followspot with stand; operator quoted separately. |  |  | 05 Experiential | Operate
5000.02.02-XPMS-007 | 5000.02.02 | LED Batten or Strip Fixture - 1m | equipment | X | 5500 | Expense · Production | CC-VENUE | each | 45 | 60 | 80 | One-meter pixel-mappable LED batten for stage and scenic accents. |  |  | 05 Experiential | Operate
5000.02.02-XPMS-008 | 5000.02.02 | LED Ellipsoidal - Leko Profile | equipment | X | 5500 | Expense · Production | CC-VENUE | each | 30 | 40 | 55 | LED profile fixture with shutters and gobo slot for keys, gobos, and specials. |  |  | 05 Experiential | Operate
5000.02.02-XPMS-001 | 5000.02.02 | Moving Head - Beam | equipment | X | 5500 | Expense · Production | CC-VENUE | each | 130 | 150 | 170 | Tight-beam automated fixture for aerial effects. | 230 to 440W ¦ Narrow beam angle ¦ Prism effects. | 168 | 04 Physical | Procure
5000.02.02-XPMS-002 | 5000.02.02 | Moving Head - Profile | equipment | X | 5500 | Expense · Production | CC-VENUE | each | 190 | 225 | 260 | Automated profile fixture with framing shutters. | 600 to 1200W ¦ Framing shutters ¦ Gobos ¦ CMY and CTO. | 168 | 04 Physical | Procure
5000.02.02-XPMS-003 | 5000.02.02 | Moving Head - Spot | equipment | X | 5500 | Expense · Production | CC-VENUE | each | 170 | 200 | 230 | Automated spot fixture with gobo, prism, and CMY color mixing. | 300 to 1400W ¦ CMY or RGBW ¦ Gobos ¦ Prism ¦ Frost. | 168 | 04 Physical | Procure
5000.02.02-XPMS-004 | 5000.02.02 | Moving Head - Wash | equipment | X | 5500 | Expense · Production | CC-VENUE | each | 130 | 150 | 170 | Automated LED wash fixture for stage and event lighting. | 19 to 37 RGBW LEDs ¦ 15 to 60 degree zoom ¦ DMX and RDM. | 168 | 04 Physical | Procure
5000.02.02-XPMS-005 | 5000.02.02 | Wash Bar - LED | equipment | X | 5500 | Expense · Production | CC-VENUE | each | 50 | 60 | 70 | Linear LED wash fixture for wall wash or cyclorama lighting. | 1 to 4ft lengths ¦ RGBW or RGBAW+UV ¦ DMX. | 168 | 04 Physical | Procure
5000.03.01-XPMS-001 | 5000.03.01 | Display - Flat Panel | equipment | X | 5500 | Expense · Production | CC-VENUE | each | 85 | 100 | 115 | Professional flat panel display on stand or mount. |  |  | 04 Physical | Procure
5000.03.01-XPMS-002 | 5000.03.01 | LED Screen - Mobile | equipment | X | 5500 | Expense · Production | CC-VENUE | each | 2975 | 3500 | 4025 | Self-contained mobile LED screen on trailer. |  |  | 04 Physical | Procure
5000.03.01-XPMS-003 | 5000.03.01 | LED Tile - Floor or Ceiling | equipment | X | 5500 | Expense · Production | CC-VENUE | each | 130 | 150 | 170 | Walkable or overhead LED panel for immersive installations. |  |  | 04 Physical | Procure
5000.03.01-XPMS-004 | 5000.03.01 | LED Wall - Indoor | equipment | X | 5500 | Expense · Production | CC-VENUE | each | 85 | 100 | 115 | Modular LED video panel wall for stage backdrop or IMAG. |  |  | 04 Physical | Procure
5000.03.01-XPMS-005 | 5000.03.01 | LED Wall - Outdoor | equipment | X | 5500 | Expense · Production | CC-VENUE | each | 105 | 125 | 145 | Weather-rated LED panels for outdoor events. |  |  | 04 Physical | Procure
5000.03.01-XPMS-006 | 5000.03.01 | Monitor - Confidence | equipment | X | 5500 | Expense · Production | CC-VENUE | each | 85 | 100 | 115 | On-stage confidence monitor for presenters or performers. |  |  | 04 Physical | Procure
5000.03.01-XPMS-007 | 5000.03.01 | Podcast Multicam Camera + Capture | package | X | 5500 | Expense · Production | CC-VENUE | each | 3500 | 5000 | 7500 | Multicam capture package. |  |  | 04 Physical | Build
5000.03.02-XPMS-005 | 5000.03.02 | Laser Projector - 20K Lumen | equipment | X | 5500 | Expense · Production | CC-VENUE | each | 2100 | 2600 | 3200 | 20,000-lumen laser projector with lens for mapping and large-surface projection. |  |  | 05 Experiential | Operate
5000.03.02-XPMS-001 | 5000.03.02 | Projection Mapping | equipment | X | 5500 | Expense · Production | CC-VENUE | each | 8500 | 10000 | 11500 | Custom projection mapping on architectural surfaces or objects. | Single through multi-projector ¦ Interactive available. | 672 | 04 Physical | Procure
5000.03.02-XOS-001 | 5000.03.02 | Projection or Projection Mapping · Base | experience | Y | 5500 | Expense · Production | CC-VENUE | each | 850 | 1250 | 1850 | Single short-throw projector on a feature wall; looping content. | Zone: Exhibition Room. Tier fit: T2; T4. Upgrades: 360 mapped room; live trigger. Add-ons: Content design package. Substitutions: LED video wall. |  | 04 Physical | Build | SGT-14
5000.03.02-XOS-002 | 5000.03.02 | Projection or Projection Mapping · Elevated | experience | Y | 5500 | Expense · Production | CC-VENUE | each | 1850 | 2650 | 3850 | Dual-projector blend across a large surface with mapped content. | Zone: Exhibition Room. Tier fit: T2; T4. Upgrades: 360 mapped room; live trigger. Add-ons: Content design package. Substitutions: LED video wall. |  | 04 Physical | Build | SGT-14
5000.03.02-XOS-003 | 5000.03.02 | Projection or Projection Mapping · Premium | experience | Y | 5500 | Expense · Production | CC-VENUE | each | 3850 | 5500 | 8000 | Full-room 360 projection mapping with custom motion content and live triggering. | Zone: Exhibition Room. Tier fit: T2; T4. Upgrades: 360 mapped room; live trigger. Add-ons: Content design package. Substitutions: LED video wall. |  | 04 Physical | Build | SGT-14
5000.03.02-XPMS-002 | 5000.03.02 | Projector - Large Venue | equipment | X | 5500 | Expense · Production | CC-VENUE | each | 2550 | 3000 | 3450 | High-brightness laser projector for large venues and outdoor use. |  |  | 04 Physical | Procure
5000.03.02-XPMS-003 | 5000.03.02 | Projector - Standard | equipment | X | 5500 | Expense · Production | CC-VENUE | each | 340 | 400 | 460 | LCD or DLP projector for presentations and basic projection. |  |  | 04 Physical | Procure
5000.03.02-XPMS-004 | 5000.03.02 | Screen - Projection | equipment | X | 5500 | Expense · Production | CC-VENUE | each | 210 | 250 | 290 | Front or rear projection screen for presentations or IMAG. | 8ft through 20ft and above diagonal ¦ Fast-fold or truss. | 168 | 04 Physical | Procure
5000.04.01-XOS-001 | 5000.04.01 | 360 Center Stage (In-the-Round) · Base | experience | Y | 5500 | Expense · Production | CC-VENUE | each | 1200 | 1800 | 2600 | Round 14ft center riser with audience on all sides; ground-supported lighting halo above. | Zone: Main Stage and Bar. Tier fit: T3; T4. Upgrades: Rotating deck motor; floor projection ring. Add-ons: Aerial rig point for performer. Substitutions: Runway / catwalk T-stage. |  | 06 Theatrical | Build | SGT-03
5000.04.01-XOS-002 | 5000.04.01 | 360 Center Stage (In-the-Round) · Elevated | experience | Y | 5500 | Expense · Production | CC-VENUE | each | 2500 | 3600 | 5200 | 20ft rotating center stage with circular LED skirt and overhead truss ring with moving lights. | Zone: Main Stage and Bar. Tier fit: T3; T4. Upgrades: Rotating deck motor; floor projection ring. Add-ons: Aerial rig point for performer. Substitutions: Runway / catwalk T-stage. |  | 06 Theatrical | Build | SGT-03
5000.04.01-XOS-003 | 5000.04.01 | 360 Center Stage (In-the-Round) · Premium | experience | Y | 5500 | Expense · Production | CC-VENUE | each | 5000 | 7500 | 11000 | Kinetic in-the-round altar with rotating deck, suspended LED halo, and floor projection apron. | Zone: Main Stage and Bar. Tier fit: T3; T4. Upgrades: Rotating deck motor; floor projection ring. Add-ons: Aerial rig point for performer. Substitutions: Runway / catwalk T-stage. |  | 06 Theatrical | Build | SGT-03
5000.04.01-XOS-004 | 5000.04.01 | Amphitheater or Tiered Seating · Base | experience | Y | 5500 | Expense · Production | CC-VENUE | each | 850 | 1250 | 1850 | Two-tier rented seating risers fanned toward a ground stage; aisle lighting. | Zone: Main Stage and Bar. Tier fit: T2; T4. Upgrades: Upholstered seat upgrade; rail LED. Add-ons: Cup-holder seat tablets. Substitutions: Cabaret cluster seating. |  | 06 Theatrical | Build | SGT-05
5000.04.01-XOS-005 | 5000.04.01 | Amphitheater or Tiered Seating · Elevated | experience | Y | 5500 | Expense · Production | CC-VENUE | each | 1850 | 2650 | 3850 | Three-tier curved seating bank with upholstered chairs and tiered rail lighting. | Zone: Main Stage and Bar. Tier fit: T2; T4. Upgrades: Upholstered seat upgrade; rail LED. Add-ons: Cup-holder seat tablets. Substitutions: Cabaret cluster seating. |  | 06 Theatrical | Build | SGT-05
5000.04.01-XOS-006 | 5000.04.01 | Amphitheater or Tiered Seating · Premium | experience | Y | 5500 | Expense · Production | CC-VENUE | each | 3850 | 5500 | 8000 | Sculptural curved amphitheater build with integrated step lighting, VIP front bowl, and rail-mounted LED. | Zone: Main Stage and Bar. Tier fit: T2; T4. Upgrades: Upholstered seat upgrade; rail LED. Add-ons: Cup-holder seat tablets. Substitutions: Cabaret cluster seating. |  | 06 Theatrical | Build | SGT-05
5000.04.01-XPMS-001 | 5000.04.01 | Backdrop - Custom Print | equipment | X | 5500 | Expense · Production | CC-VENUE | each | 425 | 500 | 575 | Custom printed fabric or vinyl stage backdrop. | 10x20 through custom size ¦ Various materials. | 336 | 04 Physical | Build
5000.04.01-XOS-007 | 5000.04.01 | Box Theater or Black Box · Base | experience | Y | 5500 | Expense · Production | CC-VENUE | each | 750 | 1100 | 1600 | Flat-floor blackout room; movable seating; portable riser for talent; full light control. | Zone: Exhibition Room. Tier fit: T1; T3. Upgrades: Retractable seating system; quad-wall projection. Add-ons: Acoustic drape upgrade. Substitutions: Amphitheater tiered seating. |  | 05 Experiential | Build | SGT-04
5000.04.01-XOS-008 | 5000.04.01 | Box Theater or Black Box · Elevated | experience | Y | 5500 | Expense · Production | CC-VENUE | each | 1450 | 2100 | 3100 | Tiered modular seating risers (2; 3 rows), draped walls, and a defined performance pocket. | Zone: Exhibition Room. Tier fit: T1; T3. Upgrades: Retractable seating system; quad-wall projection. Add-ons: Acoustic drape upgrade. Substitutions: Amphitheater tiered seating. |  | 05 Experiential | Build | SGT-04
5000.04.01-XOS-009 | 5000.04.01 | Box Theater or Black Box · Premium | experience | Y | 5500 | Expense · Production | CC-VENUE | each | 2800 | 4000 | 5800 | Convertible black box with retractable seating bank, surround drape track, and projection on all four walls. | Zone: Exhibition Room. Tier fit: T1; T3. Upgrades: Retractable seating system; quad-wall projection. Add-ons: Acoustic drape upgrade. Substitutions: Amphitheater tiered seating. |  | 05 Experiential | Build | SGT-04
5000.04.01-XOS-010 | 5000.04.01 | Elevated Proscenium Stage · Base | experience | Y | 5500 | Expense · Production | CC-VENUE | each | 1200 | 1800 | 2600 | 36; 42in elevated stage at the nave head; rental decking, stairs, and pipe-and-drape surround. | Zone: Main Stage and Bar. Tier fit: T2; T4. Upgrades: Motorized reveal curtain; thrust extension. Add-ons: Confidence monitor; teleprompter. Substitutions: 360 center stage (in-the-round). |  | 06 Theatrical | Build | SGT-02
5000.04.01-XOS-011 | 5000.04.01 | Elevated Proscenium Stage · Elevated | experience | Y | 5500 | Expense · Production | CC-VENUE | each | 2500 | 3600 | 5200 | 48in stage with hard scenic proscenium frame, side fills, and branded header valance. | Zone: Main Stage and Bar. Tier fit: T2; T4. Upgrades: Motorized reveal curtain; thrust extension. Add-ons: Confidence monitor; teleprompter. Substitutions: 360 center stage (in-the-round). |  | 06 Theatrical | Build | SGT-02
5000.04.01-XOS-012 | 5000.04.01 | Elevated Proscenium Stage · Premium | experience | Y | 5500 | Expense · Production | CC-VENUE | each | 5000 | 7500 | 11000 | Architectural elevated stage with sculptural proscenium, integrated LED reveal, and orchestra-style downstage thrust. | Zone: Main Stage and Bar. Tier fit: T2; T4. Upgrades: Motorized reveal curtain; thrust extension. Add-ons: Confidence monitor; teleprompter. Substitutions: 360 center stage (in-the-round). |  | 06 Theatrical | Build | SGT-02
5000.04.01-XOS-013 | 5000.04.01 | Ground-Level Stage · Base | experience | Y | 5500 | Expense · Production | CC-VENUE | each | 650 | 950 | 1400 | Low-rise 12in deck stage on the sanctuary floor; audience on the same plane; intimate club-floor feel. | Zone: Main Stage and Bar. Tier fit: T1; T4. Upgrades: LED stage-front ribbon; rotating turntable riser. Add-ons: DJ booth scenic wrap; B-stage spur. Substitutions: Black box flat-floor (no deck). |  | 06 Theatrical | Build | SGT-01
5000.04.01-XOS-014 | 5000.04.01 | Ground-Level Stage · Elevated | experience | Y | 5500 | Expense · Production | CC-VENUE | each | 1350 | 1950 | 2850 | 16; 24in deck with skirted fascia, monitor wedges, and a defined DJ/performer zone; clear sightline lane. | Zone: Main Stage and Bar. Tier fit: T1; T4. Upgrades: LED stage-front ribbon; rotating turntable riser. Add-ons: DJ booth scenic wrap; B-stage spur. Substitutions: Black box flat-floor (no deck). |  | 06 Theatrical | Build | SGT-01
5000.04.01-XOS-015 | 5000.04.01 | Ground-Level Stage · Premium | experience | Y | 5500 | Expense · Production | CC-VENUE | each | 2800 | 4000 | 5800 | Custom-fabricated floor stage with integrated LED fascia, riser-built DJ altar, and surround standing pit. | Zone: Main Stage and Bar. Tier fit: T1; T4. Upgrades: LED stage-front ribbon; rotating turntable riser. Add-ons: DJ booth scenic wrap; B-stage spur. Substitutions: Black box flat-floor (no deck). |  | 06 Theatrical | Build | SGT-01
5000.04.01-XPMS-002 | 5000.04.01 | Pipe and Drape | equipment | X | 5500 | Expense · Production | CC-VENUE | each | 8 | 10 | 12 | Adjustable pipe and drape system for masking and backdrop. | 8 to 20ft uprights ¦ Various drape colors and fabrics. | 336 | 04 Physical | Build
5000.04.01-XPMS-003 | 5000.04.01 | Ramp - Photo Pit | equipment | X | 5500 | Expense · Production | CC-VENUE | each | 130 | 150 | 170 | ADA-compliant ramp from stage to crowd barricade for photographers. | 4ft wide ¦ 1:12 slope ¦ Non-slip surface ¦ Handrails. | 336 | 04 Physical | Build
5000.04.01-XOS-016 | 5000.04.01 | Runway or Catwalk (T-Stage) · Base | experience | Y | 5500 | Expense · Production | CC-VENUE | each | 850 | 1250 | 1850 | Straight 24ft runway off a ground stage; matte deck; edge lighting. | Zone: Main Stage and Bar. Tier fit: T3; T4. Upgrades: LED floor tiles; mirror deck finish. Add-ons: Branded runway graphic. Substitutions: Ground-level stage. |  | 06 Theatrical | Build | SGT-06
5000.04.01-XOS-017 | 5000.04.01 | Runway or Catwalk (T-Stage) · Elevated | experience | Y | 5500 | Expense · Production | CC-VENUE | each | 1850 | 2650 | 3850 | T-shaped runway with branded vinyl deck graphic and pixel-tape edge. | Zone: Main Stage and Bar. Tier fit: T3; T4. Upgrades: LED floor tiles; mirror deck finish. Add-ons: Branded runway graphic. Substitutions: Ground-level stage. |  | 06 Theatrical | Build | SGT-06
5000.04.01-XOS-018 | 5000.04.01 | Runway or Catwalk (T-Stage) · Premium | experience | Y | 5500 | Expense · Production | CC-VENUE | each | 3850 | 5500 | 8000 | Mirror-finish runway with embedded LED floor, end-cap reveal, and flanking standing pits. | Zone: Main Stage and Bar. Tier fit: T3; T4. Upgrades: LED floor tiles; mirror deck finish. Add-ons: Branded runway graphic. Substitutions: Ground-level stage. |  | 06 Theatrical | Build | SGT-06
5000.04.01-XPMS-004 | 5000.04.01 | Skirting - Stage | equipment | X | 5500 | Expense · Production | CC-VENUE | each | 3.4 | 4 | 4.6 | Fabric skirting to conceal stage legs and understructure. | Poly-knit, velour, box pleat, or shirred. | 336 | 04 Physical | Build
5000.04.02-XPMS-001 | 5000.04.02 | Riser - Drum | equipment | X | 5500 | Expense · Production | CC-VENUE | each | 130 | 150 | 170 | Rolling riser platform for backline, drums, or equipment. | 6x6 or 8x8 ¦ 8 to 24in height ¦ Carpet top ¦ Locking casters. | 168 | 04 Physical | Build
5000.04.02-XPMS-002 | 5000.04.02 | Runway - Stage | equipment | X | 5500 | Expense · Production | CC-VENUE | each | 130 | 150 | 170 | Extended stage platform for fashion, performance, or audience interaction. | 4ft wide ¦ 8ft sections ¦ With skirting ¦ Lit or unlit. | 168 | 04 Physical | Build
5000.04.02-XPMS-003 | 5000.04.02 | Shell - Acoustic | equipment | X | 5500 | Expense · Production | CC-VENUE | each | 1275 | 1500 | 1725 | Portable acoustic shell panels for orchestral and acoustic performance. | Wenger, StageRight, or custom ¦ Ceiling and side panels. | 168 | 04 Physical | Build
5000.04.02-XPMS-004 | 5000.04.02 | Stage Deck - 4x4 | equipment | X | 5500 | Expense · Production | CC-VENUE | each | 30 | 35 | 40 | 4ft x 4ft modular stage deck for fills and odd shapes. | 4x4ft ¦ Same heights as 4x8 ¦ Carpet or painted. | 168 | 04 Physical | Build
5000.04.02-XPMS-005 | 5000.04.02 | Stage Deck - 4x8 | equipment | X | 5500 | Expense · Production | CC-VENUE | each | 35 | 45 | 60 | Standard 4ft x 8ft modular stage deck. | 4x8ft ¦ 16in, 24in, 32in, or 48in leg heights. | 168 | 04 Physical | Build
5000.04.02-XPMS-006 | 5000.04.02 | Stage Platform · Adjustable Height Deck (6 Ft×1 Ft4 In) | equipment | X | 5500 | Expense · Production | CC-VENUE | each | 130 | 150 | 170 | Main stage centerpiece for hosts, DJ sets, remarks. |  |  | 04 Physical | Build
5000.04.02-XPMS-007 | 5000.04.02 | Stairs - Stage | equipment | X | 5500 | Expense · Production | CC-VENUE | each | 3500 | 5000 | 7500 | Portable staircase for stage access. | 2-step through 4-step ¦ Handrails and ADA ramp available. | 168 | 04 Physical | Build
5000.05.01-XPMS-001 | 5000.05.01 | Chain Motor - Half Ton | equipment | X | 5500 | Expense · Production | CC-VENUE | each | 35 | 48.5 | 55 | Half-ton (1,000 lb) electric chain hoist for lighting and scenic rigging. | 1/2 ton capacity ¦ 60ft chain ¦ Variable speed. | 168 | 04 Physical | Build
5000.05.01-XPMS-002 | 5000.05.01 | Chain Motor - One Ton | equipment | X | 5500 | Expense · Production | CC-VENUE | each | 47 | 56 | 65 | One ton (2,000 lb) electric chain hoist for heavy loads. | 1 ton capacity ¦ 60ft chain ¦ Variable speed. | 168 | 04 Physical | Build
5000.05.01-XPMS-003 | 5000.05.01 | Tower - Ground Support | equipment | X | 5500 | Expense · Production | CC-VENUE | each | 70 | 80 | 90 | Freestanding truss tower system requiring no ceiling rigging. | Base plates, towers, sleeves, top truss, outriggers. | 168 | 04 Physical | Build
5000.05.02-XPMS-002 | 5000.05.02 | AV Rigging or Mounting or Install Labor | package | Y | 5500 | Expense · Production | CC-VENUE | each | 100 | 120 | 140 | AV rig and mount labor. |  |  | 04 Physical | Build
5000.05.02-XPMS-001 | 5000.05.02 | Hardware Bundle - Rigging | equipment | X | 5500 | Expense · Production | CC-VENUE | each | 65 | 75 | 85 | Assorted rigging hardware including shackles, spansets, steels, and turnbuckles. | Rated WLL per component ¦ Steel or aluminum. | 24 | 04 Physical | Build
5000.05.03-XPMS-001 | 5000.05.03 | Truss - 12in Box | equipment | X | 5500 | Expense · Production | CC-VENUE | each | 65 | 75 | 85 | 12-inch aluminum box truss for light-duty spans. | 10ft, 8ft, 5ft, 4ft, or 2.5ft sections ¦ 6061-T6 aluminum. | 168 | 04 Physical | Build
5000.05.03-XPMS-002 | 5000.05.03 | Truss - 20.5in Box | equipment | X | 5500 | Expense · Production | CC-VENUE | each | 47 | 56 | 65 | 20.5-inch aluminum box truss for medium-duty stage and lighting. | 10ft, 8ft, or 5ft sections ¦ Spigoted ¦ Various brands. | 168 | 04 Physical | Build
5000.05.03-XPMS-003 | 5000.05.03 | Truss - 30in GP | equipment | X | 5500 | Expense · Production | CC-VENUE | each | 70 | 80 | 90 | 30-inch general purpose truss for heavy-duty spans and ground support. | 10ft, 8ft, or 5ft sections ¦ GP towers and sleeve blocks. | 168 | 04 Physical | Build
5000.05.03-XPMS-004 | 5000.05.03 | Truss - Circle | equipment | X | 5500 | Expense · Production | CC-VENUE | each | 100 | 120 | 140 | Pre-curved truss sections for circular or custom shapes. | Various radii ¦ 12in, 20.5in, or 30in chord sizes. | 168 | 04 Physical | Build
5000.06.01-XPMS-001 | 5000.06.01 | Battery Pack - Portable | equipment | X | 5500 | Expense · Production | CC-VENUE | each | 65 | 75 | 85 | Battery backup or solar power pack for off-grid areas. |  |  | 04 Physical | Install
5000.06.01-XPMS-002 | 5000.06.01 | Cable Run - Feeder | equipment | X | 5500 | Expense · Production | CC-VENUE | each | 65 | 75 | 85 | Temporary power cable from generator or utility to distribution point. |  |  | 04 Physical | Install
5000.06.01-XPMS-003 | 5000.06.01 | Distribution Box - Power | equipment | X | 5500 | Expense · Production | CC-VENUE | each | 105 | 125 | 145 | Temporary power distribution unit with circuit breakers. | 100A through 800A ¦ Cam-lock or pin and sleeve. | 48 | 04 Physical | Install
5000.06.01-XPMS-004 | 5000.06.01 | Generator - Towable | equipment | X | 5500 | Expense · Production | CC-VENUE | each | 675 | 800 | 925 | Towable diesel generator for temporary event power. |  |  | 04 Physical | Install
5000.06.01-XPMS-005 | 5000.06.01 | Light Tower - Portable | equipment | X | 5500 | Expense · Production | CC-VENUE | each | 130 | 150 | 170 | Towable light tower for site illumination and safety. |  |  | 04 Physical | Install
5000.06.01-XPMS-006 | 5000.06.01 | Tie-In - Electrical | equipment | X | 5500 | Expense · Production | CC-VENUE | each | 1025 | 1200 | 1375 | Licensed electrician to connect temporary power to permanent utility. | 100A through 800A and above service. | 168 | 04 Physical | Install
5000.07.01-XPMS-009 | 5000.07.01 | Atmospherics or SFX (Placeholder) | package | X | 5500 | Expense · Production | CC-VENUE | each | 2500 | 3500 | 5000 | N/A Phase 1. |  |  | 04 Physical | Build
5000.07.01-XPMS-001 | 5000.07.01 | Confetti Cannon | equipment | X | 5500 | Expense · Production | CC-VENUE | each | 130 | 150 | 170 | Confetti or streamer launcher for celebrations and effects. | Handheld, electric continuous, DMX, or CO2-powered. | 168 | 04 Physical | Procure
5000.07.01-XPMS-002 | 5000.07.01 | Cryo Jet - CO2 | equipment | X | 5500 | Expense · Production | CC-VENUE | each | 255 | 300 | 345 | High-pressure CO2 effect for stage bursts and crowd interaction. | Single jet or dual cannon ¦ With LED ¦ DMX triggered. | 168 | 04 Physical | Procure
5000.07.01-XPMS-003 | 5000.07.01 | Flame Effect - Propane | equipment | X | 5500 | Expense · Production | CC-VENUE | each | 425 | 500 | 575 | Propane or electric flame effect for stage pyrotechnics. | Propane or electric ¦ DMX-controlled ¦ 2 to 10ft column height. | 672 | 04 Physical | Procure
5000.07.01-XPMS-004 | 5000.07.01 | Fog Machine | equipment | X | 5500 | Expense · Production | CC-VENUE | each | 85 | 100 | 115 | Ground fog or standard fog machine for stage effects. | Standard glycol, low-lying CO2, or fazer. | 168 | 04 Physical | Procure
5000.07.01-XPMS-005 | 5000.07.01 | Hazer - DMX | equipment | X | 5500 | Expense · Production | CC-VENUE | each | 85 | 100 | 115 | Professional hazer for beam visibility and atmospheric effects. | Oil-based or water-based ¦ DMX controlled. | 168 | 04 Physical | Procure
5000.07.01-XPMS-006 | 5000.07.01 | Laser - Show | equipment | X | 5500 | Expense · Production | CC-VENUE | each | 500 | 600 | 700 | Professional show laser for aerial effects and ILDA graphics. | Single color through full-color RGB ¦ ILDA graphics capable. | 672 | 04 Physical | Procure
5000.07.01-XPMS-008 | 5000.07.01 | Professional Bubble Machine | equipment | X | 5500 | Expense · Production | CC-VENUE | each | 150 | 180 | 220 | High-output bubble machine with fluid for ambient and reveal moments. |  |  | 05 Experiential | Operate
5000.07.01-XPMS-007 | 5000.07.01 | Spark Machine - Cold | equipment | X | 5500 | Expense · Production | CC-VENUE | each | 1800 | 2500 | 3500 | Non-flammable titanium spark effect machine for indoor or outdoor use. | 1 to 5 meter height ¦ DMX triggered ¦ Cold to touch. | 168 | 04 Physical | Procure
5000.08.01-XPMS-009 | 5000.08.01 | Broadcast Master Delivery | service | Y | 5500 | Expense · Production | CC-VENUE | each | 675 | 800 | 925 | Conform, QC and delivery of broadcast or platform masters to the specification of each receiving outlet. |  |  | 05 Experiential | Amplify
5000.08.01-XPMS-001 | 5000.08.01 | Camera - IMAG | equipment | X | 5500 | Expense · Production | CC-VENUE | each | 550 | 650 | 800 | Broadcast-quality camera for live image magnification. |  |  | 04 Physical | Procure
5000.08.01-XPMS-006 | 5000.08.01 | Camera Operator | labor | Y | 5500 | Expense · Production | CC-VENUE | each | 4500 | 6500 | 9500 | Operated camera position for IMAG, capture, or broadcast; 10-hr day. |  |  | 05 Experiential | Operate
5000.08.01-XPMS-008 | 5000.08.01 | Capture & Broadcast Design | service | Y | 5500 | Expense · Production | CC-VENUE | each | 1500 | 2200 | 3000 | Specification of camera positions, capture formats, audio splits, redundancy and delivery paths for post-event content. Amplification cannot be retrofitted: a camera position not designed in is unrecoverable after doors. |  |  | 05 Experiential | Scope
5000.08.01-XPMS-007 | 5000.08.01 | Drone Aerial Capture Package | service | Y | 5500 | Expense · Production | CC-VENUE | each | 2550 | 3000 | 3450 | Part 107 pilot with cinema drone, permits, and insurance for aerial capture. |  |  | 05 Experiential | Operate
5000.08.01-XPMS-002 | 5000.08.01 | Livestream Package | equipment | X | 5500 | Expense · Production | CC-VENUE | each | 350 | 450 | 550 | Complete livestream setup with encoding and CDN delivery. |  |  | 04 Physical | Procure
5000.08.01-XPMS-004 | 5000.08.01 | PTZ Camera Kit | equipment | X | 5500 | Expense · Production | CC-VENUE | each | 200 | 250 | 320 | Pan-tilt-zoom broadcast camera with controller and SDI/NDI output. |  |  | 05 Experiential | Operate
5000.08.01-XPMS-005 | 5000.08.01 | Redundant Streaming Encoder Kit | equipment | X | 5500 | Expense · Production | CC-VENUE | each | 675 | 800 | 925 | Bonded-cellular or dual-path encoder kit for broadcast-grade streaming. |  |  | 02 Digital | Operate
5000.08.01-XPMS-003 | 5000.08.01 | Switcher - Video | equipment | X | 5500 | Expense · Production | CC-VENUE | each | 150 | 200 | 250 | Live video switching system for multi-camera production. |  |  | 04 Physical | Procure
5000.09.01-XPMS-003 | 5000.09.01 | Cue Light & Calling System Kit | equipment | X | 5500 | Expense · Production | CC-VENUE | each | 450 | 550 | 700 | Stage-manager calling desk with cue light stations and backstage signaling. |  |  | 05 Experiential | Operate
5000.09.01-XPMS-005 | 5000.09.01 | Playback Operator | labor | Y | 5500 | Expense · Production | CC-VENUE | each | 120 | 150 | 190 | Operator for QLab / media-server playback, cue programming, and show execution; 10-hr day. |  |  | 05 Experiential | Operate
5000.09.01-XPMS-004 | 5000.09.01 | SMPTE or MIDI Interface Kit | equipment | X | 5500 | Expense · Production | CC-VENUE | each | 350 | 450 | 580 | Interface and conversion kit linking timecode, MIDI show control, and OSC between systems. |  |  | 05 Experiential | Operate
5000.09.01-XPMS-001 | 5000.09.01 | Show Control Computer - QLab Rig Redundant | equipment | X | 5500 | Expense · Production | CC-VENUE | each | 120 | 150 | 190 | Primary plus hot-backup Mac playback rig with QLab licenses, audio and MIDI I/O. |  |  | 05 Experiential | Operate
5000.09.01-XPMS-002 | 5000.09.01 | Timecode Generator & Distribution Kit | equipment | X | 5500 | Expense · Production | CC-VENUE | each | 130 | 150 | 170 | SMPTE LTC generation and distribution to audio, lighting, video, and SFX departments. |  |  | 05 Experiential | Operate
5000.10.01-XPMS-001 | 5000.10.01 | DJ Booth - Freestanding | equipment | X | 5500 | Expense · Production | CC-VENUE | each | 130 | 150 | 170 | Freestanding DJ booth furniture with shelf, facade, and cable management. | 4ft through 8ft width ¦ With facade ¦ Lit or unlit. | 48 | 04 Physical | Procure
5000.10.01-XPMS-002 | 5000.10.01 | DJ Package - Premium | equipment | X | 5500 | Expense · Production | CC-VENUE | each | 2125 | 2500 | 2875 | Premium DJ setup with 4 CDJs, flagship mixer, monitors, and booth. | 4x Pioneer CDJ-3000 ¦ Pioneer DJM-V10-LF ¦ 2x Monitors ¦ Custom booth. | 48 | 04 Physical | Procure
5000.10.01-XPMS-003 | 5000.10.01 | DJ Package - Standard | equipment | X | 5500 | Expense · Production | CC-VENUE | each | 850 | 1000 | 1150 | Complete DJ setup with 2 CDJs, mixer, monitor, and cabling. | 2x Pioneer CDJ-3000 ¦ Pioneer DJM-900NXS2 ¦ 1x Monitor. | 48 | 04 Physical | Procure
5000.10.01-XPMS-004 | 5000.10.01 | Turntable Package - Vinyl | equipment | X | 5500 | Expense · Production | CC-VENUE | each | 500 | 600 | 700 | Vinyl turntable DJ package with mixer and cartridges. | 2x Technics SL-1200MK7 ¦ Mixer ¦ Cartridges ¦ Slipmats. | 48 | 04 Physical | Procure
5000.10.02-XPMS-001 | 5000.10.02 | Amplifier - Bass | equipment | X | 5500 | Expense · Production | CC-VENUE | each | 130 | 150 | 170 | Professional bass amplifier head and cabinet for live performance. | Various models and configurations. | 168 | 04 Physical | Procure
5000.10.02-XPMS-002 | 5000.10.02 | Amplifier - Guitar | equipment | X | 5500 | Expense · Production | CC-VENUE | each | 130 | 150 | 170 | Professional guitar amplifier head and cabinet for live performance. | Various models and configurations. | 168 | 04 Physical | Procure
5000.10.03-XPMS-001 | 5000.10.03 | Drum Kit - Acoustic | equipment | X | 5500 | Expense · Production | CC-VENUE | each | 300 | 350 | 400 | Professional acoustic drum kit for live performance. | Various brands and sizes. | 168 | 04 Physical | Procure
5000.10.03-XPMS-002 | 5000.10.03 | Drum Kit - Electronic | equipment | X | 5500 | Expense · Production | CC-VENUE | each | 255 | 300 | 345 | Electronic drum kit with sound module and mesh pads. | Various models. | 168 | 04 Physical | Procure
5000.10.04-XPMS-001 | 5000.10.04 | Guitar or Bass - Rental | equipment | X | 5500 | Expense · Production | CC-VENUE | each | 85 | 100 | 115 | Rental guitar or bass for backline or emergency backup. | Electric guitar, acoustic guitar, or bass guitar. | 168 | 04 Physical | Procure
5000.10.04-XPMS-002 | 5000.10.04 | Percussion Kit | equipment | X | 5500 | Expense · Production | CC-VENUE | each | 150 | 175 | 200 | Auxiliary percussion instruments for live performance. | Congas, bongos, timbales, cajon, shakers, and bells. | 168 | 04 Physical | Procure
5000.10.04-XPMS-003 | 5000.10.04 | Stand - Music | equipment | X | 5500 | Expense · Production | CC-VENUE | each | 5 | 6 | 7 | Professional folding music stand with optional light. | Standard, heavy-duty (orchestral), or conductor. | 168 | 04 Physical | Procure
5000.10.05-XPMS-001 | 5000.10.05 | Keyboard - Stage | equipment | X | 5500 | Expense · Production | CC-VENUE | each | 210 | 250 | 290 | Professional stage keyboard or synthesizer. | Various models from leading manufacturers. | 168 | 04 Physical | Procure
5000.10.05-XPMS-002 | 5000.10.05 | Stand - Keyboard | equipment | X | 5500 | Expense · Production | CC-VENUE | each | 17 | 20 | 23 | Professional keyboard stand for stage use. | X-stand, Z-stand (column), A-frame, or double-tier. | 168 | 04 Physical | Procure
5000.50.01-XOS-001 | 5000.50.01 | Venue Production Management | service | Y | 5500 | Expense · Production | CC-VENUE | lump sum | 6500 | 9500 | 14000 | Representative line for venue production management so the category can carry cost. Replace with the specific item on award. |  |  | 04 Physical | Procure | 5000.50.01-XOS-001
5000.50.02-XOS-001 | 5000.50.02 | Event Production Management | service | Y | 5500 | Expense · Production | CC-VENUE | lump sum | 5500 | 7500 | 11000 | Representative line for event production management so the category can carry cost. Replace with the specific item on award. |  |  | 04 Physical | Procure | 5000.50.02-XOS-001
5000.51.01-XOS-001 | 5000.51.01 | Stagehand | service | Y | 5500 | Expense · Production | CC-VENUE | lump sum | 350 | 450 | 600 | Representative line for stagehand so the category can carry cost. Replace with the specific item on award. |  |  | 04 Physical | Procure | 5000.51.01-XOS-001
5000.51.02-XOS-001 | 5000.51.02 | Rigging | service | Y | 5500 | Expense · Production | CC-VENUE | lump sum | 500 | 650 | 850 | Representative line for rigging so the category can carry cost. Replace with the specific item on award. |  |  | 04 Physical | Procure | 5000.51.02-XOS-001
5000.52.01-XOS-001 | 5000.52.01 | Equipment Rental | service | Y | 5500 | Expense · Production | CC-VENUE | lump sum | 3500 | 5000 | 7500 | Representative line for equipment rental so the category can carry cost. Replace with the specific item on award. |  |  | 04 Physical | Procure | 5000.52.01-XOS-001
5000.52.02-XOS-001 | 5000.52.02 | Trucking and Logistics | service | Y | 5500 | Expense · Production | CC-VENUE | lump sum | 2500 | 3500 | 5000 | Representative line for trucking and logistics so the category can carry cost. Replace with the specific item on award. |  |  | 04 Physical | Procure | 5000.52.02-XOS-001
5000.52.03-XOS-001 | 5000.52.03 | Rigging Engineering | service | Y | 5500 | Expense · Production | CC-VENUE | lump sum | 3500 | 5000 | 7500 | Representative line for rigging engineering so the category can carry cost. Replace with the specific item on award. |  |  | 04 Physical | Procure | 5000.52.03-XOS-001
5000.60.01-XOS-001 | 5000.60.01 | Scope Activities · Production | service | Y | 5500 | Expense · Production | CC-E00 | lump sum | 3500 | 5000 | 7500 | Representative line for scope activities so the category can carry cost. Replace with the specific item on award. |  |  | 04 Physical | Scope | 5000.60.01-XOS-001
5000.60.02-XOS-001 | 5000.60.02 | Engage Activities · Production | service | Y | 5500 | Expense · Production | CC-E00 | lump sum | 3500 | 5000 | 7500 | Representative line for engage activities so the category can carry cost. Replace with the specific item on award. |  |  | 04 Physical | Engage | 5000.60.02-XOS-001
5000.60.03-XOS-001 | 5000.60.03 | Advance Activities · Production | service | Y | 5500 | Expense · Production | CC-E00 | lump sum | 2500 | 3500 | 5000 | Representative line for advance activities so the category can carry cost. Replace with the specific item on award. |  |  | 04 Physical | Advance | 5000.60.03-XOS-001
5000.60.04-XOS-001 | 5000.60.04 | Procure Activities · Production | service | Y | 5500 | Expense · Production | CC-E00 | lump sum | 2500 | 3500 | 5000 | Representative line for procure activities so the category can carry cost. Replace with the specific item on award. |  |  | 04 Physical | Procure | 5000.60.04-XOS-001
5000.60.05-XOS-001 | 5000.60.05 | Build Activities · Production | service | Y | 5500 | Expense · Production | CC-E00 | lump sum | 3500 | 5000 | 7500 | Representative line for build activities so the category can carry cost. Replace with the specific item on award. |  |  | 04 Physical | Build | 5000.60.05-XOS-001
5000.60.06-XOS-001 | 5000.60.06 | Install Activities · Production | service | Y | 5500 | Expense · Production | CC-E00 | lump sum | 4500 | 6500 | 9500 | Representative line for install activities so the category can carry cost. Replace with the specific item on award. |  |  | 04 Physical | Install | 5000.60.06-XOS-001
5000.60.07-XOS-001 | 5000.60.07 | Operate Activities · Production | service | Y | 5500 | Expense · Production | CC-E00 | lump sum | 6500 | 9500 | 14000 | Representative line for operate activities so the category can carry cost. Replace with the specific item on award. |  |  | 04 Physical | Operate | 5000.60.07-XOS-001
5000.60.08-XOS-001 | 5000.60.08 | Amplify Activities · Production | service | Y | 5500 | Expense · Production | CC-E00 | lump sum | 3500 | 5000 | 7500 | Representative line for amplify activities so the category can carry cost. Replace with the specific item on award. |  |  | 04 Physical | Amplify | 5000.60.08-XOS-001
5000.60.09-XOS-001 | 5000.60.09 | Close Activities · Production | service | Y | 5500 | Expense · Production | CC-E00 | lump sum | 4500 | 6500 | 9500 | Representative line for close activities so the category can carry cost. Replace with the specific item on award. |  |  | 04 Physical | Close | 5000.60.09-XOS-001
6000.01.01-XOS-001 | 6000.01.01 | Bar Furniture · Base | experience | Y | 5600 | Expense · Operations | CC-VENUE | each | 250 | 350 | 480 | Standard highboy cocktail tables and bar stools. | Zone: Main Stage and Bar. Tier fit: T1; T4. Upgrades: LED / illuminated bar base. Add-ons: Backbar shelving display. Substitutions: Communal bar rail. |  | 04 Physical | Build | SGT-23
6000.01.01-XOS-002 | 6000.01.01 | Bar Furniture · Elevated | experience | Y | 5600 | Expense · Operations | CC-VENUE | each | 450 | 650 | 900 | Designer highboys with linen or LED bases and upholstered stools. | Zone: Main Stage and Bar. Tier fit: T1; T4. Upgrades: LED / illuminated bar base. Add-ons: Backbar shelving display. Substitutions: Communal bar rail. |  | 04 Physical | Build | SGT-23
6000.01.01-XOS-003 | 6000.01.01 | Bar Furniture · Premium | experience | Y | 5600 | Expense · Operations | CC-VENUE | each | 850 | 1200 | 1650 | Custom bar facades with stone tops, integrated lighting, and sculptural stools. | Zone: Main Stage and Bar. Tier fit: T1; T4. Upgrades: LED / illuminated bar base. Add-ons: Backbar shelving display. Substitutions: Communal bar rail. |  | 04 Physical | Build | SGT-23
6000.01.01-XPMS-001 | 6000.01.01 | Caller - Show | labor | Y | 5600 | Expense · Operations | CC-VENUE | each | 425 | 500 | 575 | Calls cues for multi-element shows including lighting, video, audio, and pyro. | Show-critical ¦ Headset and intercom ¦ Script and cue sheet. | 72 | 04 Physical | Operate
6000.01.01-XPMS-012 | 6000.01.01 | Cleaning or Waste | package | X | 5600 | Expense · Operations | CC-VENUE | each | 2500 | 3500 | 5000 | Operations · Cleaning / waste. |  |  | 04 Physical | Operate
6000.01.01-XOS-004 | 6000.01.01 | Cocktail or Standing Reception Flow · Base | experience | Y | 5600 | Expense · Operations | CC-VENUE | each | 450 | 650 | 950 | Open standing layout, scattered highboys, bar-forward circulation for 80; 150. | Zone: All Zones. Tier fit: T1; T4. Upgrades: Timed zone reveal lighting. Add-ons: Coat / bag check stand. Substitutions: Seated dinner layout. |  | 04 Physical | Scope | SGT-07
6000.01.01-XOS-005 | 6000.01.01 | Cocktail or Standing Reception Flow · Elevated | experience | Y | 5600 | Expense · Operations | CC-VENUE | each | 850 | 1250 | 1850 | Zoned standing layout with lounge islands, two bar positions, and a defined dance core. | Zone: All Zones. Tier fit: T1; T4. Upgrades: Timed zone reveal lighting. Add-ons: Coat / bag check stand. Substitutions: Seated dinner layout. |  | 04 Physical | Scope | SGT-07
6000.01.01-XOS-006 | 6000.01.01 | Cocktail or Standing Reception Flow · Premium | experience | Y | 5600 | Expense · Operations | CC-VENUE | each | 1650 | 2450 | 3550 | Choreographed reveal flow: arrival lounge to main reveal to after-room, with timed zone activation. | Zone: All Zones. Tier fit: T1; T4. Upgrades: Timed zone reveal lighting. Add-ons: Coat / bag check stand. Substitutions: Seated dinner layout. |  | 04 Physical | Scope | SGT-07
6000.01.01-XOS-007 | 6000.01.01 | Decor Accessories & Objets · Base | experience | Y | 5600 | Expense · Operations | CC-VENUE | each | 250 | 380 | 550 | Candles, simple vessels, and basic table accents. | Zone: All Zones. Tier fit: T2; T4. Upgrades: Sculptural prop package. Add-ons: Artist-themed objet set. Substitutions: No accessory styling. |  | 04 Physical | Build | SGT-27
6000.01.01-XOS-008 | 6000.01.01 | Decor Accessories & Objets · Elevated | experience | Y | 5600 | Expense · Operations | CC-VENUE | each | 450 | 680 | 980 | Curated objets, books, trays, and layered tabletop styling. | Zone: All Zones. Tier fit: T2; T4. Upgrades: Sculptural prop package. Add-ons: Artist-themed objet set. Substitutions: No accessory styling. |  | 04 Physical | Build | SGT-27
6000.01.01-XOS-009 | 6000.01.01 | Decor Accessories & Objets · Premium | experience | Y | 5600 | Expense · Operations | CC-VENUE | each | 850 | 1250 | 1850 | Gallery-grade props, sculptural objects, and bespoke styling kit per zone. | Zone: All Zones. Tier fit: T2; T4. Upgrades: Sculptural prop package. Add-ons: Artist-themed objet set. Substitutions: No accessory styling. |  | 04 Physical | Build | SGT-27
6000.01.01-XOS-010 | 6000.01.01 | Dining Tables & Chairs · Base | experience | Y | 5600 | Expense · Operations | CC-VENUE | each | 350 | 500 | 750 | House banquet tables with chiavari or folding chairs. | Zone: El Patio. Tier fit: T2; T4. Upgrades: Custom tabletops; statement chairs. Add-ons: Head-table feature build. Substitutions: Communal long benches. |  | 04 Physical | Build | SGT-24
6000.01.01-XOS-011 | 6000.01.01 | Dining Tables & Chairs · Elevated | experience | Y | 5600 | Expense · Operations | CC-VENUE | each | 650 | 950 | 1450 | Designer dining tables with upholstered chairs and layered linen. | Zone: El Patio. Tier fit: T2; T4. Upgrades: Custom tabletops; statement chairs. Add-ons: Head-table feature build. Substitutions: Communal long benches. |  | 04 Physical | Build | SGT-24
6000.01.01-XOS-012 | 6000.01.01 | Dining Tables & Chairs · Premium | experience | Y | 5600 | Expense · Operations | CC-VENUE | each | 1250 | 1850 | 2650 | Bespoke tables with stone/wood tops and statement chairs. | Zone: El Patio. Tier fit: T2; T4. Upgrades: Custom tabletops; statement chairs. Add-ons: Head-table feature build. Substitutions: Communal long benches. |  | 04 Physical | Build | SGT-24
6000.01.01-XPMS-002 | 6000.01.01 | Director - Technical | labor | Y | 5600 | Expense · Operations | CC-VENUE | each | 850 | 1000 | 1150 | Overall technical production lead, system design and oversight. | Full-day ¦ Pre-production plus show ¦ Cross-department technical authority. | 72 | 04 Physical | Operate
6000.01.01-XOS-013 | 6000.01.01 | Drape & Soft Goods · Base | experience | Y | 5600 | Expense · Operations | CC-VENUE | each | 450 | 650 | 950 | Black or white pipe-and-drape masking where needed. | Zone: Main Stage and Bar. Tier fit: T1; T4. Upgrades: Swagged ceiling; printed fabric. Add-ons: Fire-rated upgrade. Substitutions: Hard scenic walls. |  | 04 Physical | Build | SGT-26
6000.01.01-XOS-014 | 6000.01.01 | Drape & Soft Goods · Elevated | experience | Y | 5600 | Expense · Operations | CC-VENUE | each | 850 | 1250 | 1850 | Color-matched velour or sheer drape with valance treatments. | Zone: Main Stage and Bar. Tier fit: T1; T4. Upgrades: Swagged ceiling; printed fabric. Add-ons: Fire-rated upgrade. Substitutions: Hard scenic walls. |  | 04 Physical | Build | SGT-26
6000.01.01-XOS-015 | 6000.01.01 | Drape & Soft Goods · Premium | experience | Y | 5600 | Expense · Operations | CC-VENUE | each | 1650 | 2450 | 3550 | Sculptural soft-good installations, swagged ceilings, and printed fabric features. | Zone: Main Stage and Bar. Tier fit: T1; T4. Upgrades: Swagged ceiling; printed fabric. Add-ons: Fire-rated upgrade. Substitutions: Hard scenic walls. |  | 04 Physical | Build | SGT-26
6000.01.01-XOS-016 | 6000.01.01 | El Patio Outdoor Configuration · Base | experience | Y | 5600 | Expense · Operations | CC-VENUE | each | 1200 | 1800 | 2600 | Open patio with string lights, scattered cocktail seating, and a corner DJ position. | Zone: El Patio. Tier fit: T1; T4. Upgrades: Tented canopy; fire/water feature. Add-ons: Misting / climate fans. Substitutions: Indoor sanctuary configuration. |  | 04 Physical | Scope | SGT-10
6000.01.01-XOS-017 | 6000.01.01 | El Patio Outdoor Configuration · Elevated | experience | Y | 5600 | Expense · Operations | CC-VENUE | each | 2500 | 3600 | 5200 | Patio lounge with sectionals, shade structures, planters, and a built DJ booth. | Zone: El Patio. Tier fit: T1; T4. Upgrades: Tented canopy; fire/water feature. Add-ons: Misting / climate fans. Substitutions: Indoor sanctuary configuration. |  | 04 Physical | Scope | SGT-10
6000.01.01-XOS-018 | 6000.01.01 | El Patio Outdoor Configuration · Premium | experience | Y | 5600 | Expense · Operations | CC-VENUE | each | 5000 | 7500 | 11000 | Full patio transformation: tented canopy, layered lounge terraces, water/fire features, and golden-hour stage. | Zone: El Patio. Tier fit: T1; T4. Upgrades: Tented canopy; fire/water feature. Add-ons: Misting / climate fans. Substitutions: Indoor sanctuary configuration. |  | 04 Physical | Scope | SGT-10
6000.01.01-XPMS-009 | 6000.01.01 | Facilities & Maintenance Tech | opex | X | 5600 | Expense · Operations | CC-VENUE | each | 450 | 600 | 800 | Operations · Facilities and Maintenance Tech. |  |  | 04 Physical | Operate
6000.01.01-XOS-019 | 6000.01.01 | Floral Arrangements · Base | experience | Y | 5600 | Expense · Operations | CC-VENUE | each | 250 | 380 | 550 | Simple bud vases on bars and tables. | Zone: All Zones. Tier fit: T1; T4. Upgrades: Statement installs; daily refresh. Add-ons: Artist-themed bloom selection. Substitutions: Greenery-only arrangements. |  | 04 Physical | Build | SGT-46
6000.01.01-XOS-020 | 6000.01.01 | Floral Arrangements · Elevated | experience | Y | 5600 | Expense · Operations | CC-VENUE | each | 450 | 680 | 980 | Designer floral arrangements per zone in the palette. | Zone: All Zones. Tier fit: T1; T4. Upgrades: Statement installs; daily refresh. Add-ons: Artist-themed bloom selection. Substitutions: Greenery-only arrangements. |  | 04 Physical | Build | SGT-46
6000.01.01-XOS-021 | 6000.01.01 | Floral Arrangements · Premium | experience | Y | 5600 | Expense · Operations | CC-VENUE | each | 850 | 1250 | 1850 | Statement floral installations with daily fresh refresh. | Zone: All Zones. Tier fit: T1; T4. Upgrades: Statement installs; daily refresh. Add-ons: Artist-themed bloom selection. Substitutions: Greenery-only arrangements. |  | 04 Physical | Build | SGT-46
6000.01.01-XOS-022 | 6000.01.01 | Hanging or Vertical Garden · Base | experience | Y | 5600 | Expense · Operations | CC-VENUE | each | 350 | 550 | 850 | A few hanging plants over a single zone. | Zone: Exhibition Room. Tier fit: T2; T4. Upgrades: Living wall + irrigation. Add-ons: Preserved-moss panel. Substitutions: Floral wall instead. |  | 04 Physical | Build | SGT-45
6000.01.01-XOS-023 | 6000.01.01 | Hanging or Vertical Garden · Elevated | experience | Y | 5600 | Expense · Operations | CC-VENUE | each | 750 | 1100 | 1650 | Designed vertical greenery wall or hanging cluster. | Zone: Exhibition Room. Tier fit: T2; T4. Upgrades: Living wall + irrigation. Add-ons: Preserved-moss panel. Substitutions: Floral wall instead. |  | 04 Physical | Build | SGT-45
6000.01.01-XOS-024 | 6000.01.01 | Hanging or Vertical Garden · Premium | experience | Y | 5600 | Expense · Operations | CC-VENUE | each | 1450 | 2200 | 3200 | Engineered living wall with irrigation and integrated lighting. | Zone: Exhibition Room. Tier fit: T2; T4. Upgrades: Living wall + irrigation. Add-ons: Preserved-moss panel. Substitutions: Floral wall instead. |  | 04 Physical | Build | SGT-45
6000.01.01-XPMS-008 | 6000.01.01 | Janitorial & Cleaning (base) | opex | X | 5600 | Expense · Operations | CC-VENUE | each | 3500 | 5000 | 7500 | Operations · Janitorial and Cleaning (base). |  |  | 04 Physical | Operate
6000.01.01-XOS-025 | 6000.01.01 | Listening Room or Salon · Base | experience | Y | 5600 | Expense · Operations | CC-VENUE | each | 650 | 950 | 1400 | Lounge-seating semicircle facing a small performer pocket; carpet and warm lamps. | Zone: Exhibition Room. Tier fit: T1; T3. Upgrades: Spatial-audio seat array; vinyl wall. Add-ons: Headphone listening stations. Substitutions: Box theater. |  | 05 Experiential | Scope | SGT-09
6000.01.01-XOS-026 | 6000.01.01 | Listening Room or Salon · Elevated | experience | Y | 5600 | Expense · Operations | CC-VENUE | each | 1350 | 1950 | 2850 | Layered lounge salon with rugs, side tables, and an intimate elevated performer nook. | Zone: Exhibition Room. Tier fit: T1; T3. Upgrades: Spatial-audio seat array; vinyl wall. Add-ons: Headphone listening stations. Substitutions: Box theater. |  | 05 Experiential | Scope | SGT-09
6000.01.01-XOS-027 | 6000.01.01 | Listening Room or Salon · Premium | experience | Y | 5600 | Expense · Operations | CC-VENUE | each | 2800 | 4000 | 5800 | Acoustically tuned salon with tiered lounge terracing, vinyl wall, and spatial-audio listening seats. | Zone: Exhibition Room. Tier fit: T1; T3. Upgrades: Spatial-audio seat array; vinyl wall. Add-ons: Headphone listening stations. Substitutions: Box theater. |  | 05 Experiential | Scope | SGT-09
6000.01.01-XPMS-014 | 6000.01.01 | Logistics or Freight | package | Z | 5600 | Expense · Operations | CC-VENUE | each | 3500 | 5000 | 7500 | Operations · Logistics / freight. |  |  | 04 Physical | Operate
6000.01.01-XOS-028 | 6000.01.01 | Lounge Seating · Base | experience | Y | 5600 | Expense · Operations | CC-VENUE | each | 450 | 650 | 950 | House sofas and club chairs in neutral upholstery; standard rental. | Zone: El Patio. Tier fit: T1; T4. Upgrades: Custom upholstery; bespoke build. Add-ons: Ottoman / pouf clusters. Substitutions: Banquette built-ins. |  | 04 Physical | Build | SGT-22
6000.01.01-XOS-029 | 6000.01.01 | Lounge Seating · Elevated | experience | Y | 5600 | Expense · Operations | CC-VENUE | each | 850 | 1250 | 1850 | Designer modular sectionals with accent armchairs and curated palette. | Zone: El Patio. Tier fit: T1; T4. Upgrades: Custom upholstery; bespoke build. Add-ons: Ottoman / pouf clusters. Substitutions: Banquette built-ins. |  | 04 Physical | Build | SGT-22
6000.01.01-XOS-030 | 6000.01.01 | Lounge Seating · Premium | experience | Y | 5600 | Expense · Operations | CC-VENUE | each | 1650 | 2450 | 3550 | Custom-built or premium-brand lounge sets with bespoke upholstery and silhouettes. | Zone: El Patio. Tier fit: T1; T4. Upgrades: Custom upholstery; bespoke build. Add-ons: Ottoman / pouf clusters. Substitutions: Banquette built-ins. |  | 04 Physical | Build | SGT-22
6000.01.01-XPMS-010 | 6000.01.01 | Maintenance & Repairs Reserve | opex | X | 5600 | Expense · Operations | CC-VENUE | each | 2500 | 3500 | 5000 | Operations · Maintenance and Repairs Reserve. |  |  | 04 Physical | Operate
6000.01.01-XPMS-003 | 6000.01.01 | Manager - Production | labor | Y | 5600 | Expense · Operations | CC-VENUE | each | 675 | 800 | 925 | Overall production operations lead, manages crew and timeline. | Full-day (10 to 12hr) ¦ Pre-production plus show days ¦ Cross-departmental authority. | 72 | 04 Physical | Operate
6000.01.01-XPMS-004 | 6000.01.01 | Manager - Site Operations | labor | Y | 5600 | Expense · Operations | CC-VENUE | each | 600 | 700 | 800 | On-site operations lead for logistics, infrastructure, and site flow. | Full-day ¦ Multi-day build plus show ¦ Site-wide authority. | 72 | 04 Physical | Operate
6000.01.01-XPMS-005 | 6000.01.01 | Manager - Stage | labor | Y | 5600 | Expense · Operations | CC-VENUE | each | 550 | 650 | 750 | Manages stage flow, artist changeovers, and show calling. | Full-day ¦ Show-critical ¦ All-department communications. | 72 | 04 Physical | Operate
6000.01.01-XPMS-013 | 6000.01.01 | Medical (EMT) | service | Y | 5600 | Expense · Operations | CC-VENUE | each | 650 | 850 | 1150 | Operations · Medical (EMT). |  |  | 04 Physical | Operate
6000.01.01-XPMS-018 | 6000.01.01 | Operational Plan & Run of Show Development | service | Y | 5600 | Expense · Operations | CC-VENUE | each | 4500 | 6500 | 9500 | Development of the operational plan: run of show, crew calls, changeover choreography, contingency and escalation. The document the show is actually run from. |  |  | 05 Experiential | Scope
6000.01.01-XOS-031 | 6000.01.01 | Potted Floor Plants · Base | experience | Y | 5600 | Expense · Operations | CC-VENUE | each | 180 | 260 | 380 | Rental potted palms and greenery at key corners. | Zone: El Patio. Tier fit: T1; T4. Upgrades: Specimen trees; bespoke planters. Add-ons: Uplit planter package. Substitutions: Faux greenery substitution. |  | 04 Physical | Build | SGT-44
6000.01.01-XOS-032 | 6000.01.01 | Potted Floor Plants · Elevated | experience | Y | 5600 | Expense · Operations | CC-VENUE | each | 340 | 480 | 680 | Curated potted-plant program with designer planters in palette. | Zone: El Patio. Tier fit: T1; T4. Upgrades: Specimen trees; bespoke planters. Add-ons: Uplit planter package. Substitutions: Faux greenery substitution. |  | 04 Physical | Build | SGT-44
6000.01.01-XOS-033 | 6000.01.01 | Potted Floor Plants · Premium | experience | Y | 5600 | Expense · Operations | CC-VENUE | each | 680 | 950 | 1350 | Large specimen plants and trees in bespoke planters throughout. | Zone: El Patio. Tier fit: T1; T4. Upgrades: Specimen trees; bespoke planters. Add-ons: Uplit planter package. Substitutions: Faux greenery substitution. |  | 04 Physical | Build | SGT-44
6000.01.01-XOS-034 | 6000.01.01 | Restroom or ADA or Regulatory · Base | experience | Y | 5600 | Expense · Operations | CC-VENUE | each | 85 | 120 | 175 | Printed restroom and capacity/occupancy signage to code. | Zone: All Zones. Tier fit: T1; T4. Upgrades: Dimensional restroom ID. Add-ons: Bilingual (EN/ES) set. Substitutions: Standard code-only signage. |  | 04 Physical | Build | SGT-18
6000.01.01-XOS-035 | 6000.01.01 | Restroom or ADA or Regulatory · Elevated | experience | Y | 5600 | Expense · Operations | CC-VENUE | each | 160 | 220 | 310 | Branded restroom and regulatory signage on rigid substrate. | Zone: All Zones. Tier fit: T1; T4. Upgrades: Dimensional restroom ID. Add-ons: Bilingual (EN/ES) set. Substitutions: Standard code-only signage. |  | 04 Physical | Build | SGT-18
6000.01.01-XOS-036 | 6000.01.01 | Restroom or ADA or Regulatory · Premium | experience | Y | 5600 | Expense · Operations | CC-VENUE | each | 280 | 380 | 520 | Dimensional restroom identity and discreet code signage matched to the design system. | Zone: All Zones. Tier fit: T1; T4. Upgrades: Dimensional restroom ID. Add-ons: Bilingual (EN/ES) set. Substitutions: Standard code-only signage. |  | 04 Physical | Build | SGT-18
6000.01.01-XOS-037 | 6000.01.01 | Seated Dinner or Banquet · Base | experience | Y | 5600 | Expense · Operations | CC-VENUE | each | 650 | 950 | 1400 | Rounds of 10 with house linen; head table near stage; basic place settings. | Zone: El Patio. Tier fit: T2; T4. Upgrades: Sculptural centerpieces; chef's table. Add-ons: Lounge after-dinner conversion. Substitutions: Family-style long tables. |  | 04 Physical | Scope | SGT-08
6000.01.01-XOS-038 | 6000.01.01 | Seated Dinner or Banquet · Elevated | experience | Y | 5600 | Expense · Operations | CC-VENUE | each | 1250 | 1850 | 2650 | Mixed rounds and long kings tables, layered linen, and a centered performance sightline. | Zone: El Patio. Tier fit: T2; T4. Upgrades: Sculptural centerpieces; chef's table. Add-ons: Lounge after-dinner conversion. Substitutions: Family-style long tables. |  | 04 Physical | Scope | SGT-08
6000.01.01-XOS-039 | 6000.01.01 | Seated Dinner or Banquet · Premium | experience | Y | 5600 | Expense · Operations | CC-VENUE | each | 2450 | 3500 | 5000 | Designer tablescape program with custom runners, sculptural centerpieces, and a stage-integrated chef's table. | Zone: El Patio. Tier fit: T2; T4. Upgrades: Sculptural centerpieces; chef's table. Add-ons: Lounge after-dinner conversion. Substitutions: Family-style long tables. |  | 04 Physical | Scope | SGT-08
6000.01.01-XPMS-015 | 6000.01.01 | Security & Monitoring (base) | opex | X | 5600 | Expense · Operations | CC-VENUE | each | 4500 | 6500 | 9500 | Operations · Security and Monitoring (base). |  |  | 04 Physical | Operate
6000.01.01-XPMS-017 | 6000.01.01 | Site Measurement & As-Built Capture | service | Y | 5600 | Expense · Operations | CC-VENUE | each | 3500 | 5000 | 7500 | Dimensional capture of an existing space; laser, photogrammetry or LiDAR; producing a measured base drawing. Distinct from a survey: this yields geometry, not judgement. |  |  | 05 Experiential | Scope
6000.01.01-XPMS-016 | 6000.01.01 | Site Survey & Venue Assessment | service | Y | 5600 | Expense · Operations | CC-VENUE | each | 4500 | 6500 | 9500 | Physical assessment of a candidate venue: dimensions, load-in path and its tightest pinch point, dock height, power service, rigging structure, egress and documented capacities. The capability document a later requirement reconciles against. |  |  | 05 Experiential | Scope
6000.01.01-XOS-040 | 6000.01.01 | Soft Flooring & Rugs · Base | experience | Y | 5600 | Expense · Operations | CC-VENUE | each | 220 | 320 | 450 | Area rugs to define lounge zones; neutral tones. | Zone: All Zones. Tier fit: T1; T4. Upgrades: Custom printed rug / floor graphic. Add-ons: Anti-fatigue bar matting. Substitutions: Bare floor (no rugs). |  | 04 Physical | Build | SGT-25
6000.01.01-XOS-041 | 6000.01.01 | Soft Flooring & Rugs · Elevated | experience | Y | 5600 | Expense · Operations | CC-VENUE | each | 420 | 580 | 820 | Layered rug program in palette with runners and lounge anchors. | Zone: All Zones. Tier fit: T1; T4. Upgrades: Custom printed rug / floor graphic. Add-ons: Anti-fatigue bar matting. Substitutions: Bare floor (no rugs). |  | 04 Physical | Build | SGT-25
6000.01.01-XOS-042 | 6000.01.01 | Soft Flooring & Rugs · Premium | experience | Y | 5600 | Expense · Operations | CC-VENUE | each | 780 | 1100 | 1550 | Custom logo or pattern rugs and printed floor graphics throughout. | Zone: All Zones. Tier fit: T1; T4. Upgrades: Custom printed rug / floor graphic. Add-ons: Anti-fatigue bar matting. Substitutions: Bare floor (no rugs). |  | 04 Physical | Build | SGT-25
6000.01.01-XOS-043 | 6000.01.01 | Textiles & Pillows · Base | experience | Y | 5600 | Expense · Operations | CC-VENUE | each | 120 | 180 | 260 | Throw pillows in palette on lounge seating. | Zone: El Patio. Tier fit: T1; T4. Upgrades: Custom-printed cushions. Add-ons: Outdoor-rated textiles. Substitutions: No added textiles. |  | 04 Physical | Build | SGT-28
6000.01.01-XOS-044 | 6000.01.01 | Textiles & Pillows · Elevated | experience | Y | 5600 | Expense · Operations | CC-VENUE | each | 240 | 340 | 480 | Layered pillows, throws, and accent textiles per lounge. | Zone: El Patio. Tier fit: T1; T4. Upgrades: Custom-printed cushions. Add-ons: Outdoor-rated textiles. Substitutions: No added textiles. |  | 04 Physical | Build | SGT-28
6000.01.01-XOS-045 | 6000.01.01 | Textiles & Pillows · Premium | experience | Y | 5600 | Expense · Operations | CC-VENUE | each | 450 | 650 | 950 | Custom-printed textiles and bespoke cushions matched to the artist palette. | Zone: El Patio. Tier fit: T1; T4. Upgrades: Custom-printed cushions. Add-ons: Outdoor-rated textiles. Substitutions: No added textiles. |  | 04 Physical | Build | SGT-28
6000.01.01-GHXST-001 | 6000.01.01 | Tool Kit - Production | tool | X | 5600 | Expense · Operations | CC-VENUE | each | 50 | 60 | 70 | Comprehensive tool kit for on-site production work. | Drills, wrenches, pliers, tape measures, levels, hardware. | 24 | 04 Physical | Procurement | SITE-TOOL-HDWR-001 · 6000.020.00
6000.01.01-XOS-046 | 6000.01.01 | Tropical Canopy or Overhead · Base | experience | Y | 5600 | Expense · Operations | CC-VENUE | each | 650 | 950 | 1400 | Sparse hanging greenery accent overhead. | Zone: El Patio. Tier fit: T3; T4. Upgrades: Suspended floral canopy + lighting. Add-ons: Misting integration. Substitutions: Fabric ceiling instead. |  | 04 Physical | Build | SGT-47
6000.01.01-XOS-047 | 6000.01.01 | Tropical Canopy or Overhead · Elevated | experience | Y | 5600 | Expense · Operations | CC-VENUE | each | 1350 | 1950 | 2850 | Designed overhead greenery canopy over a lounge or bar. | Zone: El Patio. Tier fit: T3; T4. Upgrades: Suspended floral canopy + lighting. Add-ons: Misting integration. Substitutions: Fabric ceiling instead. |  | 04 Physical | Build | SGT-47
6000.01.01-XOS-048 | 6000.01.01 | Tropical Canopy or Overhead · Premium | experience | Y | 5600 | Expense · Operations | CC-VENUE | each | 2800 | 4000 | 5800 | Full tropical canopy build with lighting and suspended florals. | Zone: El Patio. Tier fit: T3; T4. Upgrades: Suspended floral canopy + lighting. Add-ons: Misting integration. Substitutions: Fabric ceiling instead. |  | 04 Physical | Build | SGT-47
6000.01.01-XPMS-006 | 6000.01.01 | Utilities · Power & HVAC | opex | X | 5600 | Expense · Operations | CC-VENUE | each | 1500 | 2200 | 3200 | Operations · Utilities; Power and HVAC. |  |  | 04 Physical | Operate
6000.01.01-XPMS-007 | 6000.01.01 | Utilities · Water & Sewer | opex | X | 5600 | Expense · Operations | CC-VENUE | each | 450 | 650 | 950 | Operations · Utilities; Water and Sewer. |  |  | 04 Physical | Operate
6000.01.01-XPMS-011 | 6000.01.01 | Venue Operations Staff (core) | opex | X | 5600 | Expense · Operations | CC-VENUE | each | 3500 | 5000 | 7500 | Operations · Venue Operations Leadership. |  |  | 04 Physical | Operate
6000.02.01-XPMS-006 | 6000.02.01 | Basement Storage Racking | service | Y | 5600 | Expense · Operations | CC-VENUE | each | 2500 | 3500 | 5000 | Racking + organization. |  |  | 04 Physical | Build
6000.02.01-XPMS-001 | 6000.02.01 | Forklift - Standard | equipment | X | 5600 | Expense · Operations | CC-VENUE | each | 300 | 350 | 400 | Warehouse or event forklift for loading and placement. |  |  | 04 Physical | Build
6000.02.01-XPMS-004 | 6000.02.01 | Freight or Delivery or Receiving | package | Z | 5600 | Expense · Operations | CC-VENUE | each | 1500 | 2200 | 3200 | FF&E + gear freight. |  |  | 04 Physical | Build
6000.02.01-GHXST-001 | 6000.02.01 | Hand Truck | tool | X | 5600 | Expense · Operations | CC-VENUE | each | 13 | 15 | 17 | Two-wheel hand truck or platform dolly for moving equipment. | Standard 2-wheel through appliance dolly. | 24 | 04 Physical | Procurement | SITE-TOOL-HDWR-004 · 6000.020.00
6000.02.01-GHXST-002 | 6000.02.01 | Ladder - A-Frame | tool | X | 5600 | Expense · Operations | CC-VENUE | each | 21 | 25 | 29 | Aluminum A-frame step ladder for general site work. | 6ft through 16ft. | 24 | 04 Physical | Procurement | SITE-TOOL-HDWR-002 · 6000.020.00
6000.02.01-GHXST-003 | 6000.02.01 | Ladder - Extension | tool | X | 5600 | Expense · Operations | CC-VENUE | each | 30 | 35 | 40 | Aluminum extension ladder for elevated access. | 20ft through 40ft. | 24 | 04 Physical | Procurement | SITE-TOOL-HDWR-003 · 6000.020.00
6000.02.01-XPMS-002 | 6000.02.01 | Loader - Skid Steer | equipment | X | 5600 | Expense · Operations | CC-VENUE | each | 300 | 350 | 400 | Compact loader for grading, moving material, and site prep. |  |  | 04 Physical | Build
6000.02.01-XPMS-007 | 6000.02.01 | Logistics Coordination Labor | service | Y | 5600 | Expense · Operations | CC-VENUE | each | 650 | 850 | 1150 | Coordination labor. |  |  | 04 Physical | Build
6000.02.01-GHXST-004 | 6000.02.01 | Metal Detector - Handheld | credential | X | 5600 | Expense · Operations | CC-VENUE | each | 13 | 15 | 17 | Portable wand metal detector for secondary screening. | Standard sensitivity ¦ Vibrate and audible alert. | 168 | 04 Physical | Advance | WORK-ACCS-ACTC-002 · 6000.110.00
6000.02.01-GHXST-005 | 6000.02.01 | Metal Detector - Walk-Through | credential | X | 5600 | Expense · Operations | CC-VENUE | each | 150 | 175 | 200 | Walk-through metal detector for venue entry screening. | 6-zone through 33-zone ¦ With person counter. | 168 | 04 Physical | Advance | WORK-ACCS-ACTC-001 · 6000.110.00
6000.02.01-XPMS-005 | 6000.02.01 | Offsite Storage During Build | service | Y | 5600 | Expense · Operations | CC-VENUE | each | 1200 | 1800 | 2600 | 3 months offsite storage. |  |  | 04 Physical | Build
6000.02.01-GHXST-006 | 6000.02.01 | Pallet Jack - Manual | tool | X | 5600 | Expense · Operations | CC-VENUE | each | 30 | 35 | 40 | Manual hydraulic pallet jack for moving loaded pallets. | 5,500 lb capacity ¦ 48in forks. | 24 | 04 Physical | Procurement | SITE-TOOL-HDWR-005 · 6000.020.00
6000.02.01-GHXST-007 | 6000.02.01 | Scanner Station - Ticket | credential | X | 5600 | Expense · Operations | CC-VENUE | each | 65 | 75 | 85 | Ticket scanning hardware and box office setup. | Handheld scanner, kiosk, or will-call station. | 672 | 04 Physical | Advance | WORK-ACCS-ACTC-004 · 6000.110.00
6000.02.01-XPMS-003 | 6000.02.01 | Telehandler | equipment | X | 5600 | Expense · Operations | CC-VENUE | each | 500 | 600 | 700 | Telescopic handler for high-reach material placement. |  |  | 04 Physical | Build
6000.02.02-XPMS-001 | 6000.02.02 | Baggage Fee - Excess | travel | Z | 5600 | Expense · Operations | CC-VENUE | each | 65 | 75 | 85 | Additional or overweight baggage fees for equipment transport. | Per checked bag ¦ Oversize and overweight surcharges. | 72 | 04 Physical | Advance
6000.02.02-XPMS-002 | 6000.02.02 | Flight - Charter | travel | Z | 5600 | Expense · Operations | CC-VENUE | each | 12800 | 15000 | 17200 | Private charter flight for talent or time-sensitive transport. | Turboprop through heavy jet. | 72 | 04 Physical | Advance
6000.02.02-XPMS-003 | 6000.02.02 | Flight - Domestic - Business or First | travel | Z | 5600 | Expense · Operations | CC-VENUE | each | 1025 | 1200 | 1375 | Round-trip domestic business or first class airfare. | Priority boarding ¦ Lounge access ¦ 2 or more bags included. | 72 | 04 Physical | Advance
6000.02.02-XPMS-004 | 6000.02.02 | Flight - Domestic - Economy | travel | Z | 5600 | Expense · Operations | CC-VENUE | each | 340 | 400 | 460 | Round-trip domestic economy airfare. | Coach class ¦ Carry-on included ¦ Checked bag varies by airline. | 72 | 04 Physical | Advance
6000.02.02-XPMS-005 | 6000.02.02 | Flight - International - Business or First | travel | Z | 5600 | Expense · Operations | CC-VENUE | each | 4250 | 5025 | 5800 | Round-trip international business or first class airfare. | Lie-flat seat ¦ Lounge access ¦ Priority everything. | 72 | 04 Physical | Advance
6000.02.02-XPMS-006 | 6000.02.02 | Flight - International - Economy | travel | Z | 5600 | Expense · Operations | CC-VENUE | each | 850 | 1000 | 1150 | Round-trip international economy airfare. | Coach class ¦ Checked bag typically included ¦ Meal service. | 72 | 04 Physical | Advance
6000.02.03-GHXST-001 | 6000.02.03 | Barrier - Jersey - Water-Filled | equipment | X | 5600 | Expense · Operations | CC-VENUE | each | 34 | 40 | 46 | Polyethylene water-filled traffic barrier for vehicle mitigation and perimeter control. | 72in L x 24in W x 42in H ¦ 150 lbs empty, 1500 lbs filled ¦ UV-resistant poly. | 48 | 04 Physical | Build | SITE-INFR-FENC-002 · 6000.020.00
6000.02.03-XPMS-001 | 6000.02.03 | Charter - Boat | travel | Z | 5600 | Expense · Operations | CC-VENUE | each | 340 | 400 | 460 | Water taxi or boat charter for waterfront events. | 6-pax through 50-pax and above ¦ Various vessel types. | 168 | 04 Physical | Advance
6000.02.04-XPMS-007 | 6000.02.04 | Last-Mile Courier Runner with Vehicle | labor | Y | 5600 | Expense · Operations | CC-VENUE | each | 350 | 450 | 600 | Dedicated runner with vehicle for purchases, pickups, and artist errands. |  |  | 04 Physical | Operate
6000.02.04-XPMS-001 | 6000.02.04 | Limousine | travel | Z | 5600 | Expense · Operations | CC-VENUE | each | 130 | 150 | 170 | Luxury sedan or limousine for VIP transport. | Sedan through stretch limo ¦ Chauffeur included. | 168 | 04 Physical | Advance
6000.02.04-GHXST-001 | 6000.02.04 | Mat - Ground Protection | equipment | X | 5600 | Expense · Operations | CC-VENUE | each | 21 | 25 | 29 | Heavy-duty composite ground protection mat for vehicles and pedestrians. | 4ft x 8ft ¦ 90 lbs ¦ 80-ton load capacity ¦ HDPE composite. | 168 | 04 Physical | Build | SITE-INFR-FLOR-001 · 6000.020.00
6000.02.04-XPMS-002 | 6000.02.04 | Motor Coach - Charter | travel | Z | 5600 | Expense · Operations | CC-VENUE | each | 1275 | 1500 | 1725 | Full-size charter motor coach for large group transport. | 40 to 56 passenger ¦ Restroom ¦ Climate control ¦ Luggage bays. | 168 | 04 Physical | Advance
6000.02.04-XPMS-003 | 6000.02.04 | Pedicab | travel | Z | 5600 | Expense · Operations | CC-VENUE | each | 170 | 200 | 230 | Human-powered pedicab for short-range guest transport. | 2 to 3 passenger ¦ With canopy ¦ Branded options. | 168 | 04 Physical | Advance
6000.02.04-XPMS-004 | 6000.02.04 | Shuttle - Airport | travel | Z | 5600 | Expense · Operations | CC-VENUE | each | 210 | 250 | 290 | Passenger van or shuttle for group airport transfers. | 12 to 40 passenger vehicles ¦ With luggage trailer available. | 168 | 04 Physical | Advance
6000.02.04-XPMS-005 | 6000.02.04 | Shuttle - Sprinter | travel | Z | 5600 | Expense · Operations | CC-VENUE | each | 500 | 600 | 700 | Mercedes Sprinter for VIP or artist transport. | 12 to 14 passenger ¦ Executive interior ¦ WiFi available. | 168 | 04 Physical | Advance
6000.02.04-XPMS-006 | 6000.02.04 | Transfer - Sedan | travel | Z | 5600 | Expense · Operations | CC-VENUE | each | 85 | 100 | 115 | Private sedan or SUV for airport-to-venue or hotel transport. | Sedan or SUV ¦ Up to 3 passengers plus luggage. | 168 | 04 Physical | Advance
6000.02.05-XPMS-001 | 6000.02.05 | Rental - Cargo Van or Box Truck | vehicle | X | 5600 | Expense · Operations | CC-VENUE | each | 85 | 100 | 115 | Cargo van or small box truck for equipment runs. | Cargo van through 15ft box truck ¦ Liftgate options. | 168 | 04 Physical | Procure
6000.02.05-XPMS-002 | 6000.02.05 | Rental Car - Economy | vehicle | X | 5600 | Expense · Operations | CC-VENUE | each | 47 | 56 | 65 | Economy or compact rental car for individual production use. | Economy or compact ¦ 4-door ¦ Automatic. | 168 | 04 Physical | Procure
6000.02.05-XPMS-003 | 6000.02.05 | Rental Car - Full-Size or SUV | vehicle | X | 5600 | Expense · Operations | CC-VENUE | each | 70 | 85 | 100 | Full-size sedan or SUV for production leads. | Full-size sedan through full-size SUV. | 168 | 04 Physical | Procure
6000.02.05-XPMS-004 | 6000.02.05 | Van - 15 Passenger | vehicle | X | 5600 | Expense · Operations | CC-VENUE | each | 150 | 175 | 200 | 15-passenger van for crew transport. | 15-passenger ¦ V8 ¦ Automatic ¦ Luggage space. | 168 | 04 Physical | Procure
6000.02.06-XPMS-001 | 6000.02.06 | ATV - All Terrain | vehicle | X | 5600 | Expense · Operations | CC-VENUE | each | 235 | 275 | 315 | All-terrain vehicle for off-road site access. | Gas ¦ 4x4 ¦ 500 to 1000cc ¦ Roll cage. | 168 | 04 Physical | Procure
6000.02.06-XPMS-002 | 6000.02.06 | Golf Cart - 4 Seat | vehicle | X | 5600 | Expense · Operations | CC-VENUE | each | 105 | 125 | 145 | Electric 4-passenger golf cart for site transportation. | 48V electric ¦ 15 to 25 mph ¦ 30 to 40 mile range. | 48 | 04 Physical | Procure
6000.02.06-XPMS-004 | 6000.02.06 | Scooter - Electric | vehicle | X | 5600 | Expense · Operations | CC-VENUE | each | 42 | 48.5 | 55 | Electric scooter for quick personal site transport. | Electric ¦ 15 to 20 mph ¦ 25 to 40 mile range. | 168 | 04 Physical | Procure
6000.02.06-XPMS-005 | 6000.02.06 | UTV - Utility Vehicle | vehicle | X | 5600 | Expense · Operations | CC-VENUE | each | 210 | 250 | 290 | John Deere Gator or equivalent with cargo dump bed. | Gas or electric ¦ 4x4 ¦ 1,000 lb cargo capacity ¦ Dump bed. | 48 | 04 Physical | Procure
6000.02.07-XPMS-001 | 6000.02.07 | Box Truck - 16ft | vehicle | X | 5600 | Expense · Operations | CC-VENUE | each | 210 | 250 | 290 | Medium-duty box truck for equipment and supply transport. | 16ft box ¦ 6,000 lb payload ¦ Liftgate available. | 168 | 04 Physical | Procure
6000.02.07-XPMS-002 | 6000.02.07 | Box Truck - 26ft | vehicle | X | 5600 | Expense · Operations | CC-VENUE | each | 300 | 350 | 400 | Large box truck for major load-in and load-out transport. | 26ft box ¦ 10,000 lb payload ¦ Liftgate. | 168 | 04 Physical | Procure
6000.02.07-XPMS-003 | 6000.02.07 | Tractor-Trailer - 53ft | vehicle | X | 5600 | Expense · Operations | CC-VENUE | each | 775 | 900 | 1025 | Full semi truck and trailer for large-scale equipment transport. | 53ft dry van or flatbed ¦ 45,000 lb payload ¦ Air ride. | 168 | 04 Physical | Procure
6000.02.07-XPMS-004 | 6000.02.07 | Truck - Flatbed | vehicle | X | 5600 | Expense · Operations | CC-VENUE | each | 425 | 500 | 575 | Flatbed truck for oversized loads, staging, and scenic transport. | 24 to 48ft bed ¦ 20,000 to 48,000 lb payload. | 168 | 04 Physical | Procure
6000.02.07-XPMS-005 | 6000.02.07 | Truck - Pickup | vehicle | X | 5600 | Expense · Operations | CC-VENUE | each | 105 | 125 | 145 | Full-size pickup truck for site operations. | Half-ton through 1-ton ¦ 4x4 available. | 168 | 04 Physical | Procure
6000.02.07-XPMS-006 | 6000.02.07 | Van - Sprinter | vehicle | X | 5600 | Expense · Operations | CC-VENUE | each | 170 | 200 | 230 | Cargo or passenger sprinter van for crew and equipment shuttle. | High roof ¦ 144in or 170in wheelbase ¦ 3,000 lb payload. | 168 | 04 Physical | Procure
6000.02.08-XPMS-001 | 6000.02.08 | Sweeper - Street | vehicle | X | 5600 | Expense · Operations | CC-VENUE | each | 425 | 500 | 575 | Mechanical street sweeper for paved areas and parking lots. | Compact through full-size ¦ Ride-on scrubber available. | 168 | 04 Physical | Procure
6000.02.08-XPMS-002 | 6000.02.08 | Truck - Fuel Service | vehicle | X | 5600 | Expense · Operations | CC-VENUE | each | 425 | 500 | 575 | Mobile fuel delivery truck for generators and vehicles. | 500 through 2,500 gallon ¦ Diesel or multi-fuel. | 168 | 04 Physical | Procure
6000.02.08-XPMS-003 | 6000.02.08 | Truck - Water | vehicle | X | 5600 | Expense · Operations | CC-VENUE | each | 500 | 600 | 700 | Tanker truck for dust suppression, site watering, or filling. | 2,000 through 6,000 gallon ¦ With spray bar. | 168 | 04 Physical | Procure
6000.03.01-XPMS-001 | 6000.03.01 | Designer - Lighting | labor | Y | 5600 | Expense · Operations | CC-VENUE | each | 650 | 750 | 850 | Lighting designer and console programmer. | Full-day ¦ Pre-viz plus programming plus show ¦ Console-specific. | 72 | 04 Physical | Operate
6000.03.01-XPMS-002 | 6000.03.01 | Director - Security | labor | Y | 5600 | Expense · Operations | CC-VENUE | each | 675 | 800 | 925 | Lead security operations, threat assessment, and team management. | Full-day ¦ Pre-event plus show ¦ Cross-agency coordination. | 72 | 04 Physical | Operate
6000.03.01-XPMS-003 | 6000.03.01 | Director - Video | labor | Y | 5600 | Expense · Operations | CC-VENUE | each | 600 | 700 | 800 | Video switching and directing lead for IMAG and content playback. | Full-day ¦ Show-critical ¦ Multi-camera or playback. | 72 | 04 Physical | Operate
6000.03.01-XPMS-004 | 6000.03.01 | Engineer - Audio FOH | labor | Y | 5600 | Expense · Operations | CC-VENUE | each | 600 | 700 | 800 | Front-of-house audio mix engineer for live performance. | Full-day ¦ Sound check plus show ¦ Console-specific. | 72 | 04 Physical | Operate
6000.03.01-GHXST-001 | 6000.03.01 | Hotel Block - Group Rate | lodging | X | 5600 | Expense · Operations | CC-VENUE | each | 110 | 130 | 150 | Negotiated group rate hotel block for production team. | 10 or more rooms ¦ Group rate ¦ Rooming list management ¦ Attrition clause. | 72 | 04 Physical | Advance | TRVL-LODG-HOTL-003 · 8000.100.00
6000.03.01-GHXST-002 | 6000.03.01 | Hotel Room - Standard | lodging | X | 5600 | Expense · Operations | CC-VENUE | each | 130 | 150 | 170 | Standard hotel room for crew and production staff. | Queen or King bed ¦ WiFi ¦ Near venue preferred. | 72 | 04 Physical | Advance | TRVL-LODG-HOTL-001 · 8000.100.00
6000.03.01-GHXST-003 | 6000.03.01 | Hotel Suite - Premium | lodging | X | 5600 | Expense · Operations | CC-VENUE | each | 425 | 500 | 575 | Suite or premium room for talent and senior production. | Suite with living area ¦ Premium amenities. | 72 | 04 Physical | Advance | TRVL-LODG-HOTL-002 · 8000.100.00
6000.03.01-XPMS-005 | 6000.03.01 | Manager - Catering | labor | Y | 5600 | Expense · Operations | CC-VENUE | each | 425 | 500 | 575 | Oversees all catering operations, meal planning, and dietary needs. | Full-day ¦ Multi-day ¦ Kitchen plus service management. | 72 | 04 Physical | Operate
6000.03.01-XPMS-006 | 6000.03.01 | Manager - Guest Experience | labor | Y | 5600 | Expense · Operations | CC-VENUE | each | 470 | 547.5 | 625 | Leads guest services, info, accessibility, and complaints. | Full-day ¦ FOH authority ¦ Guest-facing. | 72 | 04 Physical | Operate
6000.03.01-GHXST-004 | 6000.03.01 | RV - Motorhome | lodging | X | 5600 | Expense · Operations | CC-VENUE | each | 300 | 350 | 400 | RV or motorhome for mobile talent or crew accommodation. | Class A through travel trailer ¦ With hookups. | 72 | 04 Physical | Advance | TRVL-LODG-ALTL-002 · 8000.100.00
6000.03.01-GHXST-005 | 6000.03.01 | Rental - Vacation | lodging | X | 5600 | Expense · Operations | CC-VENUE | each | 210 | 250 | 290 | Short-term rental house or apartment for crew or talent. | 1-bedroom through 4-bedroom or more ¦ House or apartment. | 72 | 04 Physical | Advance | TRVL-LODG-ALTL-001 · 8000.100.00
6000.03.01-XPMS-007 | 6000.03.01 | Rigger - Head | labor | Y | 5600 | Expense · Operations | CC-VENUE | each | 675 | 800 | 925 | Lead rigger overseeing all overhead and structural rigging. | Full-day ¦ Build plus show ¦ Certified rigger (ETCP preferred). | 72 | 04 Physical | Operate
6000.03.02-XPMS-001 | 6000.03.02 | Driver - CDL | labor | Y | 5600 | Expense · Operations | CC-VENUE | each | 340 | 400 | 460 | Commercial driver for trucks over 26,001 GVWR. |  |  | 04 Physical | Build
6000.03.02-XPMS-002 | 6000.03.02 | Operator - Aerial Lift | labor | Y | 5600 | Expense · Operations | CC-VENUE | each | 320 | 375 | 430 | Certified aerial lift operator for elevated work. |  |  | 04 Physical | Build
6000.03.02-XPMS-003 | 6000.03.02 | Operator - Crane | labor | Y | 5600 | Expense · Operations | CC-VENUE | each | 675 | 800 | 925 | Certified crane operator for heavy lifts. |  |  | 04 Physical | Build
6000.03.02-XPMS-004 | 6000.03.02 | Operator - Forklift | labor | Y | 5600 | Expense · Operations | CC-VENUE | each | 300 | 350 | 400 | Certified forklift operator for loading, unloading, and placement. |  |  | 04 Physical | Build
6000.03.03-XPMS-001 | 6000.03.03 | Ambassador - Brand | labor | Y | 5600 | Expense · Operations | CC-VENUE | each | 170 | 200 | 230 | Outgoing promotional staff for activations and brand engagement. | 4 to 8hr shift ¦ On-brand appearance ¦ Trained on messaging. | 336 | 04 Physical | Operate
6000.03.03-XPMS-002 | 6000.03.03 | Attendant - Parking | labor | Y | 5600 | Expense · Operations | CC-VENUE | each | 130 | 150 | 170 | Parking lot and traffic flow management staff. | 6 to 10hr shift ¦ Reflective vest ¦ Flashlight and wand. | 336 | 04 Physical | Operate
6000.03.03-GHXST-001 | 6000.03.03 | Carpet - Event | equipment | X | 5600 | Expense · Operations | CC-VENUE | each | 2.55 | 3 | 3.45 | Event carpet for aisles, entrances, and VIP areas. | 6ft wide rolls ¦ Various pile heights. | 168 | 04 Physical | Build | SITE-INFR-FLOR-005 · 6000.020.00
6000.03.03-GHXST-002 | 6000.03.03 | Photographer - Event | labor | Y | 5600 | Expense · Operations | CC-VENUE | each | 500 | 600 | 700 | Professional event photographer for documentation and content. | 4 to 8hr coverage ¦ Edited deliverables ¦ Digital. | 672 | 04 Physical | Build | LABR-SKIL-CREA-001 · 6000.100.00
6000.03.03-XPMS-003 | 6000.03.03 | Runner - Production | labor | Y | 5600 | Expense · Operations | CC-VENUE | each | 170 | 200 | 230 | General production support, errands, equipment moves, and runner duties. | 8 to 12hr shift ¦ Vehicle access preferred ¦ Radio equipped. | 336 | 04 Physical | Operate
6000.03.03-XPMS-004 | 6000.03.03 | Security Guard - Armed | labor | Y | 5600 | Expense · Operations | CC-VENUE | each | 425 | 500 | 575 | Licensed armed security for high-value or executive protection. | 8 to 12hr shift ¦ State-licensed ¦ Armed ¦ Executive protection. | 336 | 04 Physical | Operate
6000.03.03-XPMS-005 | 6000.03.03 | Security Guard - Unarmed | labor | Y | 5600 | Expense · Operations | CC-VENUE | each | 190 | 225 | 260 | Licensed unarmed security guard for access control and crowd management. | 8 to 12hr shift ¦ State-licensed ¦ Uniformed. | 336 | 04 Physical | Operate
6000.03.03-XPMS-006 | 6000.03.03 | Staff - Janitorial | labor | Y | 5600 | Expense · Operations | CC-VENUE | each | 150 | 175 | 200 | On-site cleaning staff for restrooms, FOH, and BOH. | 8 to 12hr shift ¦ Restroom monitoring ¦ Trash runs ¦ FOH cleaning. | 336 | 04 Physical | Operate
6000.03.03-XPMS-007 | 6000.03.03 | Staff - Registration | labor | Y | 5600 | Expense · Operations | CC-VENUE | each | 150 | 175 | 200 | Front desk or registration table staff. | 6 to 10hr shift ¦ Trained on system ¦ Customer-facing. | 336 | 04 Physical | Operate
6000.03.03-XPMS-008 | 6000.03.03 | Usher - Event | labor | Y | 5600 | Expense · Operations | CC-VENUE | each | 130 | 150 | 170 | Front-of-house staff for ticket scanning, seating, and guest assistance. | 6 to 10hr shift ¦ Uniformed ¦ Trained on scanning system. | 336 | 04 Physical | Operate
6000.03.03-GHXST-003 | 6000.03.03 | Videographer - Event | labor | Y | 5600 | Expense · Operations | CC-VENUE | each | 675 | 800 | 925 | Professional videographer for recap or content capture. | 4 to 8hr ¦ Raw or edited deliverables ¦ 4K. | 672 | 04 Physical | Build | LABR-SKIL-CREA-002 · 6000.100.00
6000.03.04-XPMS-001 | 6000.03.04 | Attendant - Valet | labor | Y | 5600 | Expense · Operations | CC-VENUE | each | 150 | 175 | 200 | Professional valet driver for guest vehicle parking. | 4 to 8hr shift ¦ Licensed driver ¦ Insured service. | 672 | 04 Physical | Operate
6000.03.04-XPMS-002 | 6000.03.04 | Bartender - Event | labor | Y | 5600 | Expense · Operations | CC-VENUE | each | 210 | 250 | 290 | Licensed bartender for event bar service. | 6 to 10hr shift ¦ TIPS or ServSafe certified ¦ With bar tools. | 672 | 04 Physical | Operate
6000.03.04-XPMS-003 | 6000.03.04 | DJ - Event | labor | Y | 5600 | Expense · Operations | CC-VENUE | each | 650 | 750 | 850 | DJ for event entertainment. | 4 to 8hr set ¦ With equipment or gear provided. | 672 | 04 Physical | Operate
6000.03.04-XPMS-004 | 6000.03.04 | Fire Watch | labor | Y | 5600 | Expense · Operations | CC-VENUE | each | 300 | 350 | 400 | Required fire watch personnel for pyro, tents, or assembly permits. | Per fire marshal or permit requirement ¦ Certified. | 672 | 04 Physical | Operate
6000.03.04-XPMS-005 | 6000.03.04 | Flagger - Traffic | labor | Y | 5600 | Expense · Operations | CC-VENUE | each | 235 | 275 | 315 | Certified traffic control flagger for road closures and site access. | 8hr shift ¦ ATSSA or state-certified ¦ With PPE and equipment. | 672 | 04 Physical | Operate
6000.03.04-XPMS-006 | 6000.03.04 | Interpreter | labor | Y | 5600 | Expense · Operations | CC-VENUE | each | 600 | 700 | 800 | Professional interpreter for live events or meetings. | Simultaneous, consecutive, or sign language (ASL). | 672 | 04 Physical | Operate
6000.03.04-XPMS-008 | 6000.03.04 | Officer - Off-Duty | labor | Y | 5600 | Expense · Operations | CC-VENUE | each | 340 | 400 | 460 | Off-duty law enforcement for event security and traffic. | 4 to 8hr detail ¦ Armed ¦ Uniformed ¦ Jurisdictional. | 672 | 04 Physical | Operate
6000.03.04-XPMS-009 | 6000.03.04 | Server - Event | labor | Y | 5600 | Expense · Operations | CC-VENUE | each | 170 | 200 | 230 | Professional server for plated or passed service. | 6 to 10hr shift ¦ ServSafe preferred ¦ Uniformed. | 672 | 04 Physical | Operate
6000.03.05-XPMS-008 | 6000.03.05 | Build-Crew Radios or Comms | package | Y | 5600 | Expense · Operations | CC-VENUE | each | 1200 | 1800 | 2500 | Crew radios rental. |  |  | 04 Physical | Build
6000.03.05-XPMS-001 | 6000.03.05 | Carpenter - Scenic | labor | Y | 5600 | Expense · Operations | CC-VENUE | each | 340 | 400 | 460 | Skilled carpenter for scenic construction and stage builds. |  |  | 04 Physical | Build
6000.03.05-XPMS-002 | 6000.03.05 | Electrician - Licensed | labor | Y | 5600 | Expense · Operations | CC-VENUE | each | 470 | 547.5 | 625 | Licensed electrician for temporary power installation. |  |  | 04 Physical | Build
6000.03.05-XPMS-003 | 6000.03.05 | Rigger - Certified | labor | Y | 5600 | Expense · Operations | CC-VENUE | each | 470 | 547.5 | 625 | Arena or outdoor rigging technician, ETCP preferred. | 8 to 12hr shift ¦ Build plus show ¦ Working at height. | 672 | 04 Physical | Build
6000.03.05-XPMS-004 | 6000.03.05 | Technician - Audio | labor | Y | 5600 | Expense · Operations | CC-VENUE | each | 380 | 452.5 | 525 | Audio system tech, patch, RF coordination, and stage tech support. |  |  | 04 Physical | Build
6000.03.05-XPMS-005 | 6000.03.05 | Technician - Lighting | labor | Y | 5600 | Expense · Operations | CC-VENUE | each | 340 | 400 | 460 | Lighting focus, programming support, and fixture maintenance. |  |  | 04 Physical | Build
6000.03.05-XPMS-006 | 6000.03.05 | Technician - Video | labor | Y | 5600 | Expense · Operations | CC-VENUE | each | 360 | 425 | 490 | LED wall build, camera operation, and cable management. |  |  | 04 Physical | Build
6000.03.05-XPMS-007 | 6000.03.05 | Welder - Certified | labor | Y | 5600 | Expense · Operations | CC-VENUE | each | 470 | 547.5 | 625 | Certified welder for on-site fabrication and repair. | 8 to 12hr shift ¦ MIG, TIG, or Stick ¦ Structural or scenic. | 672 | 04 Physical | Build
6000.03.06-XPMS-001 | 6000.03.06 | Jacket - Staff | uniform | X | 5600 | Expense · Operations | CC-VENUE | each | 34 | 40 | 46 | Branded crew jacket or hoodie for cold-weather events. | S through 3XL ¦ Fleece, softshell, or puffer. | 672 | 04 Physical | Procure
6000.03.06-XPMS-002 | 6000.03.06 | Polo - Staff | uniform | X | 5600 | Expense · Operations | CC-VENUE | each | 21 | 25 | 29 | Custom embroidered or printed polo for leads and management. | S through 3XL ¦ Pique cotton or performance poly. | 672 | 04 Physical | Procure
6000.03.06-XPMS-003 | 6000.03.06 | Poncho - Rain | uniform | X | 5600 | Expense · Operations | CC-VENUE | each | 13 | 15 | 17 | Waterproof outerwear for wet-weather events. | S through 3XL ¦ Disposable poncho or reusable jacket. | 672 | 04 Physical | Procure
6000.03.06-XPMS-004 | 6000.03.06 | T-Shirt - Staff | uniform | X | 5600 | Expense · Operations | CC-VENUE | each | 10 | 12 | 14 | Custom printed staff t-shirt for identification. | S through 3XL ¦ Cotton or poly blend ¦ Screen print or DTG. | 672 | 04 Physical | Procure
6000.03.06-XPMS-005 | 6000.03.06 | Vest - Safety - Hi-Vis | uniform | X | 5600 | Expense · Operations | CC-VENUE | each | 10 | 12 | 14 | ANSI-rated high-visibility safety vest for site operations. | S through 5XL ¦ Class 2 or Class 3 ¦ With or without pockets. | 672 | 04 Physical | Procure
6000.03.07-XPMS-001 | 6000.03.07 | Stagehand - IATSE | labor | Y | 5600 | Expense · Operations | CC-VENUE | each | 425 | 500 | 575 | Union stagehand for load-in, show, and load-out. | 8hr call (minimum) ¦ IATSE local rates apply ¦ OT after 8hrs. | 168 | 04 Physical | Operate
6000.03.07-XPMS-002 | 6000.03.07 | Stagehand - Non-Union | labor | Y | 5600 | Expense · Operations | CC-VENUE | each | 210 | 250 | 290 | Non-union stagehand for load-in, show, and load-out. | 8 to 12hr shift ¦ General production labor. | 168 | 04 Physical | Operate
6000.04.01-XPMS-007 | 6000.04.01 | Bag Screening Station | equipment | X | 5600 | Expense · Operations | CC-VENUE | each | 350 | 450 | 600 | Screening table lane with bins, signage, and divestment flow at entry. |  |  | 04 Physical | Operate
6000.04.01-GHXST-001 | 6000.04.01 | Camera - Security - Temp | equipment | X | 5600 | Expense · Operations | CC-VENUE | each | 50 | 60 | 70 | Temporary security camera system for site monitoring. | Fixed, PTZ, or wireless ¦ With recording and night vision. | 336 | 04 Physical | Procurement | WORK-HLTH-SECU-001 · 6000.140.00
6000.04.01-XPMS-008 | 6000.04.01 | Event Safety & Security Plan | service | Y | 5600 | Expense · Operations | CC-VENUE | each | 4500 | 6500 | 9500 | Site-specific safety and security plan: CAD overlays, staffing plan, and AHJ submission package. |  |  | 04 Physical | Advance
6000.04.01-GHXST-002 | 6000.04.01 | Floor - Raised Access | equipment | X | 5600 | Expense · Operations | CC-VENUE | each | 7 | 8 | 9 | Modular raised floor system for leveling or cable management. | 2ft x 2ft panels ¦ Adjustable pedestals ¦ 4in to 24in height. | 168 | 04 Physical | Build | SITE-INFR-FLOR-007 · 6000.020.00
6000.04.01-XPMS-002 | 6000.04.01 | Handheld Security Wand | equipment | X | 5600 | Expense · Operations | CC-VENUE | each | 18 | 25 | 35 | Handheld metal-detection wand for secondary screening. |  |  | 04 Physical | Operate
6000.04.01-XPMS-003 | 6000.04.01 | K9 Explosive Sweep Team | service | Y | 5600 | Expense · Operations | CC-VENUE | each | 1800 | 2400 | 3200 | Certified explosive-detection canine team conducting pre-open and mid-event sweeps. |  |  | 04 Physical | Operate
6000.04.01-GHXST-003 | 6000.04.01 | Lighting - Security | equipment | X | 5600 | Expense · Operations | CC-VENUE | each | 30 | 35 | 40 | Temporary high-intensity security lighting. | LED flood, motion-activated, solar, or battery. | 336 | 04 Physical | Procurement | WORK-HLTH-SECU-002 · 6000.140.00
6000.04.01-XPMS-005 | 6000.04.01 | Overnight Site Security Patrol | service | Y | 5600 | Expense · Operations | CC-VENUE | each | 650 | 850 | 1150 | Overnight roving patrol protecting site, equipment, and compound during build and dark days. |  |  | 04 Physical | Build
6000.04.01-GHXST-004 | 6000.04.01 | Scanner - RFID Access | credential | X | 5600 | Expense · Operations | CC-VENUE | each | 105 | 125 | 145 | Automated access control scanning for credentialed entry. | Handheld reader, fixed turnstile reader, or tap gate. | 672 | 04 Physical | Advance | WORK-ACCS-ACTC-003 · 6000.110.00
6000.04.01-XPMS-006 | 6000.04.01 | Security Command Post Package | equipment | X | 5600 | Expense · Operations | CC-VENUE | each | 1200 | 1600 | 2200 | Staffed command-post setup with radios, CCTV feeds, incident log, and access manifests. |  |  | 04 Physical | Operate
6000.04.01-XPMS-001 | 6000.04.01 | Security Supervisor | labor | Y | 5600 | Expense · Operations | CC-VENUE | each | 550 | 700 | 850 | Shift supervisor managing guard posts, incident reporting, and client liaison. |  |  | 04 Physical | Operate
6000.04.01-XPMS-004 | 6000.04.01 | Temporary CCTV Kit - 4 Camera | equipment | X | 5600 | Expense · Operations | CC-VENUE | each | 850 | 1100 | 1450 | Rapid-deploy four-camera surveillance kit with NVR and monitor at security command. |  |  | 04 Physical | Operate
6000.05.01-XPMS-001 | 6000.05.01 | Defibrillator - AED | tool | X | 5600 | Expense · Operations | CC-VENUE | each | 85 | 100 | 115 | Portable AED unit with carrying case and signage. | Standard with cabinet and signage. | 24 | 04 Physical | Procure
6000.05.01-XPMS-002 | 6000.05.01 | Fire Extinguisher - ABC | tool | X | 5600 | Expense · Operations | CC-VENUE | each | 21 | 25 | 29 | ABC dry chemical fire extinguisher, event-rated. | 5 lb through 20 lb ¦ CO2 available for electrical. | 24 | 04 Physical | Procure
6000.05.01-XPMS-003 | 6000.05.01 | First Aid Kit - Event | tool | X | 5600 | Expense · Operations | CC-VENUE | each | 65 | 75 | 85 | Comprehensive first aid kit per OSHA and event standards. | 25-person through 100-person ¦ Trauma kit available. | 24 | 04 Physical | Procure
6000.05.01-XPMS-004 | 6000.05.01 | Kit - Crowd Management | tool | X | 5600 | Expense · Operations | CC-VENUE | each | 130 | 150 | 170 | Bull horns, traffic wands, flashlights, and reflective vests bundle. | 2 bull horns, 6 wands, 12 flashlights, 24 vests. | 24 | 04 Physical | Procure
6000.05.01-XPMS-005 | 6000.05.01 | Kit - Spill Containment | tool | X | 5600 | Expense · Operations | CC-VENUE | each | 65 | 75 | 85 | Containment and cleanup kit for fuel, chemical, or biohazard spills. | 5 gal through 55 gal capacity ¦ Biohazard options. | 24 | 04 Physical | Procure
6000.05.01-XPMS-006 | 6000.05.01 | Site Protection or Safety or PPE | package | X | 5600 | Expense · Operations | CC-VENUE | each | 1500 | 2200 | 3200 | Site protection and PPE. |  |  | 04 Physical | Build
6000.05.02-XPMS-001 | 6000.05.02 | Ambulance - Standby | equipment | X | 5600 | Expense · Operations | CC-VENUE | each | 850 | 1000 | 1150 | Dedicated ambulance and crew on-site for medical emergencies. | BLS or ALS ambulance ¦ With 2-person crew. | 336 | 04 Physical | Procure
6000.05.02-XPMS-002 | 6000.05.02 | EMT - On-Site | equipment | X | 5600 | Expense · Operations | CC-VENUE | each | 340 | 400 | 460 | Licensed EMT or paramedic for on-site medical coverage. | EMT-Basic, EMT-Intermediate, or Paramedic (ALS). | 336 | 04 Physical | Procure
6000.05.02-XPMS-004 | 6000.05.02 | EMT Team - 2 Person with Kit | labor | Y | 5600 | Expense · Operations | CC-VENUE | each | 700 | 850 | 1050 | Two licensed EMTs with BLS kit and AED posted on site; 10-hr day. |  |  | 04 Physical | Operate
6000.05.02-XPMS-003 | 6000.05.02 | Station - Medical | equipment | X | 5600 | Expense · Operations | CC-VENUE | each | 425 | 500 | 575 | Dedicated medical treatment area with supplies and cots. | 10x10 through 20x20 ¦ With AC, lighting, and privacy curtains. | 336 | 04 Physical | Procure
6000.05.03-XPMS-001 | 6000.05.03 | Glasses - Safety | equipment | X | 5600 | Expense · Operations | CC-VENUE | each | 5 | 6 | 7 | ANSI Z87.1 rated eye protection. | Clear, tinted, anti-fog, or over-glasses (OTG). | 48 | 04 Physical | Procure
6000.05.03-XPMS-002 | 6000.05.03 | Gloves - Work | equipment | X | 5600 | Expense · Operations | CC-VENUE | each | 8 | 10 | 12 | Protective work gloves for rigging, loading, and construction. | Leather, mechanic, cut-resistant, or insulated. | 48 | 04 Physical | Procure
6000.05.03-XPMS-003 | 6000.05.03 | Hard Hat - ANSI | equipment | X | 5600 | Expense · Operations | CC-VENUE | each | 13 | 15 | 17 | ANSI-rated construction hard hat for site operations. | Type I (top impact) or Type II (top plus lateral) ¦ Face shield option. | 48 | 04 Physical | Procure
6000.05.03-XPMS-004 | 6000.05.03 | Hearing Protection | equipment | X | 5600 | Expense · Operations | CC-VENUE | each | 4.25 | 5.12 | 6 | Noise reduction ear plugs or ear muffs. | Foam plugs (NRR 32), reusable plugs, over-ear muffs, or custom molded. | 48 | 04 Physical | Procure
6000.06.01-XPMS-001 | 6000.06.01 | Fuel Card - Prepaid | vehicle | X | 5600 | Expense · Operations | CC-VENUE | each | 210 | 250 | 290 | Prepaid fuel card for rental vehicle fleet. | 100 through 500 dollar denominations ¦ Fleet card options. | 72 | 04 Physical | Procure
6000.06.01-XPMS-002 | 6000.06.01 | Parking Pass - Off-Site | vehicle | X | 5600 | Expense · Operations | CC-VENUE | each | 21 | 25 | 29 | Pre-paid parking for off-site crew parking or overflow. | Daily through monthly ¦ Garage or surface lot. | 72 | 04 Physical | Procure
6000.06.01-XPMS-005 | 6000.06.01 | Permit Fees & Inspections | service | Y | 5600 | Expense · Operations | CC-VENUE | each | 1500 | 2200 | 3200 | BY OWNER (Spotify). |  |  | 04 Physical | Build
6000.06.01-XPMS-004 | 6000.06.01 | Pressure Washer with Operator | equipment | X | 5600 | Expense · Operations | CC-VENUE | each | 350 | 450 | 600 | Hot-water pressure washing for site restoration and surface cleaning. |  |  | 04 Physical | Close
6000.06.01-XPMS-003 | 6000.06.01 | Trailer - Enclosed | vehicle | X | 5600 | Expense · Operations | CC-VENUE | each | 65 | 75 | 85 | Enclosed trailer for equipment or merchandise transport. | 6x12 through 8.5x24 ¦ With ramp. | 72 | 04 Physical | Procure
6000.06.02-XPMS-008 | 6000.06.02 | ADA Ramp System - Modular | equipment | X | 5600 | Expense · Operations | CC-VENUE | each | 120 | 150 | 190 | Code-compliant modular ramp run with handrails for stage or threshold access. |  |  | 04 Physical | Install
6000.06.02-XPMS-001 | 6000.06.02 | Booth - Guard | equipment | X | 5600 | Expense · Operations | CC-VENUE | each |  |  |  | Small portable booth for security checkpoints or ticketing. |  |  | 04 Physical | Build
6000.06.02-GHXST-001 | 6000.06.02 | Dance Floor - Portable | equipment | X | 5600 | Expense · Operations | CC-VENUE | each | 3.4 | 4 | 4.6 | Modular interlocking dance floor panels, indoor and outdoor rated. | 3ft x 3ft panels ¦ Multiple finishes available. | 168 | 04 Physical | Build | SITE-INFR-FLOR-002 · 6000.020.00
6000.06.02-XPMS-002 | 6000.06.02 | Hand Wash Station - Portable | equipment | X | 5600 | Expense · Operations | CC-VENUE | each | 65 | 75 | 85 | Freestanding portable hand washing station with foot pump. | 2-basin or 4-basin ¦ With soap and paper towels. | 48 | 04 Physical | Build
6000.06.02-XPMS-003 | 6000.06.02 | Restroom - Portable - ADA | equipment | X | 5600 | Expense · Operations | CC-VENUE | each | 150 | 175 | 200 | Wheelchair-accessible single-unit portable restroom with ramp. | 60in x 60in x 88in ¦ Wide door ¦ Grab bars ¦ Ramp. | 48 | 04 Physical | Build
6000.06.02-XPMS-004 | 6000.06.02 | Restroom - Portable - Standard | equipment | X | 5600 | Expense · Operations | CC-VENUE | each | 105 | 125 | 145 | Single-unit portable toilet with hand sanitizer dispenser. | 44in x 48in x 90in ¦ 175 lbs ¦ 60 gal holding tank. | 48 | 04 Physical | Build
6000.06.02-XPMS-005 | 6000.06.02 | Restroom Trailer - Luxury | equipment | X | 5600 | Expense · Operations | CC-VENUE | each | 130 | 150 | 170 | Multi-stall climate-controlled restroom trailer with running water and flushing toilets. |  |  | 04 Physical | Build
6000.06.02-XPMS-006 | 6000.06.02 | Shower Trailer - Portable | equipment | X | 5600 | Expense · Operations | CC-VENUE | each | 210 | 250 | 290 | Multi-stall shower trailer for crew, talent, or camping events. | 2-stall through 8-stall ¦ With changing area. | 336 | 04 Physical | Build
6000.06.02-XPMS-007 | 6000.06.02 | Trailer - Office | equipment | X | 5600 | Expense · Operations | CC-VENUE | each | 340 | 400 | 460 | Temporary office trailer for production and administration. | 8x20 through 12x60 ¦ Double-wide available. | 336 | 04 Physical | Build
6000.06.03-XPMS-001 | 6000.06.03 | Air Conditioner - Portable | equipment | X | 5600 | Expense · Operations | CC-VENUE | each | 42 | 48.5 | 55 | Spot cooler or portable AC unit for tents and structures. |  |  | 04 Physical | Install
6000.06.03-XPMS-002 | 6000.06.03 | Fan - Industrial | equipment | X | 5600 | Expense · Operations | CC-VENUE | each | 150 | 175 | 200 | High-volume air mover for ventilation and cooling. |  |  | 04 Physical | Install
6000.06.03-XPMS-003 | 6000.06.03 | Heater - Portable | equipment | X | 5600 | Expense · Operations | CC-VENUE | each | 120 | 150 | 190 | Forced air or radiant heater for cold-weather events. |  |  | 04 Physical | Install
6000.06.03-XPMS-004 | 6000.06.03 | Industrial Misting Fan | equipment | X | 5600 | Expense · Operations | CC-VENUE | each | 55 | 70 | 90 | High-volume misting fan for outdoor heat mitigation. |  |  | 04 Physical | Operate
6000.06.03-XPMS-005 | 6000.06.03 | Propane Patio Heater | equipment | X | 5600 | Expense · Operations | CC-VENUE | each | 130 | 150 | 170 | Freestanding propane patio heater with tank for outdoor comfort. |  |  | 04 Physical | Operate
6000.06.04-XPMS-001 | 6000.06.04 | Tank - Gray Water | equipment | X | 5600 | Expense · Operations | CC-VENUE | each | 210 | 250 | 290 | Gray water collection tank for sink and shower drainage. |  |  | 04 Physical | Install
6000.06.04-XPMS-002 | 6000.06.04 | Water Tank - Potable | equipment | X | 5600 | Expense · Operations | CC-VENUE | each | 15 | 20 | 28 | Mobile potable water storage for events without municipal access. |  |  | 04 Physical | Install
6000.07.01-XPMS-001 | 6000.07.01 | All-Access Credential · Production | credential | X | 5600 | Expense · Operations | CC-VENUE | each | 4.25 | 5.12 | 6 | Auto-created during 0063 backfill from deliverables.ee120edb-2e95-4884-9f19-499cb584b1a3. |  |  | 04 Physical | Advance
6000.07.01-XPMS-002 | 6000.07.01 | Badge - Credential | credential | X | 5600 | Expense · Operations | CC-VENUE | each | 2.55 | 3 | 3.45 | Custom printed credential with lanyard for staff, artist, or vendor. | PVC card ¦ Holographic ¦ RFID or NFC ¦ Tyvek wristband alternative. | 336 | 04 Physical | Advance
6000.07.01-XPMS-003 | 6000.07.01 | Pass - Parking | credential | X | 5600 | Expense · Operations | CC-VENUE | each | 1 | 1.08 | 1.15 | Vehicle access credential for parking lots and restricted areas. | Hang tag, dashboard placard, windshield sticker, or RFID. | 336 | 04 Physical | Advance
6000.07.01-XPMS-004 | 6000.07.01 | Wristband - Event | credential | X | 5600 | Expense · Operations | CC-VENUE | each | 1 | 1.08 | 1.15 | Event wristband for general admission or tiered access. | Tyvek (paper), cloth (fabric), silicone, or RFID-enabled. | 336 | 04 Physical | Advance
6000.08.01-XPMS-001 | 6000.08.01 | Cable Ties - Assorted | tool | X | 5600 | Expense · Operations | CC-VENUE | each | 2500 | 3500 | 5000 | Nylon cable ties in assorted sizes. | 4in through 24in ¦ Velcro alternative available. | 24 | 04 Physical | Procure
6000.08.01-XPMS-006 | 6000.08.01 | New Accent Furniture | service | Y | 5600 | Expense · Operations | CC-VENUE | each | 1500 | 2200 | 3200 | Gaps vs owned inventory. |  |  | 04 Physical | Build
6000.08.01-XPMS-005 | 6000.08.01 | Owned Lounge or High-Top Furniture (Relocate & Refurb) | package | X | 5600 | Expense · Operations | CC-VENUE | each | 5 | 6 | 7 | Existing inventory refurb. |  |  | 04 Physical | Build
6000.08.01-XPMS-002 | 6000.08.01 | Sandbag - Ballast | tool | X | 5600 | Expense · Operations | CC-VENUE | each | 8 | 10 | 12 | Filled or unfilled sandbag for ballast and anchoring. | 25 lb through 50 lb ¦ Saddle-style for pipe. | 24 | 04 Physical | Procure
6000.08.01-XPMS-003 | 6000.08.01 | Strap - Ratchet | tool | X | 5600 | Expense · Operations | CC-VENUE | each | 13 | 15 | 17 | Ratchet or cam buckle tie-down strap for securing loads. | 1in through 4in widths ¦ 15 to 27ft lengths. | 24 | 04 Physical | Procure
6000.08.01-XPMS-004 | 6000.08.01 | Tape - Gaffer | tool | X | 5600 | Expense · Operations | CC-VENUE | each | 3.4 | 4 | 4.6 | Professional-grade cloth gaffer tape for production. | 2in x 60yd ¦ Matte finish ¦ Residue-free. | 24 | 04 Physical | Procure
6000.08.02-XPMS-001 | 6000.08.02 | Chair - Folding | equipment | X | 5600 | Expense · Operations | CC-VENUE | each | 170 | 200 | 230 | Standard folding event chair. |  |  | 04 Physical | Procure
6000.08.02-XPMS-002 | 6000.08.02 | Office Package - Production | equipment | X | 5600 | Expense · Operations | CC-VENUE | each | 50 | 60 | 70 | Complete temporary production office with furniture and equipment. | Desk, chair, whiteboard, printer, power strip, trash can, and supplies. | 48 | 04 Physical | Procure
6000.08.02-XPMS-003 | 6000.08.02 | Printer - Portable | equipment | X | 5600 | Expense · Operations | CC-VENUE | each | 425 | 500 | 575 | Temporary printer or multifunction device for production office. | Inkjet, laser, MFP, or large format. | 48 | 04 Physical | Procure
6000.08.02-GHXST-001 | 6000.08.02 | Shipping Container - Office | equipment | X | 5600 | Expense · Operations | CC-VENUE | each | 13 | 15 | 17 | Modified ISO container for bar, retail, greenroom, or storage use. | 20ft or 40ft ¦ Single or double door ¦ With HVAC and electric. | 336 | 04 Physical | Build | SITE-INFR-TENT-006 · 6000.020.00
6000.08.02-XPMS-004 | 6000.08.02 | Table - Cocktail | equipment | X | 5600 | Expense · Operations | CC-VENUE | each | 10 | 12 | 14 | Cocktail-height round table for standing events. |  |  | 04 Physical | Procure
6000.08.02-XPMS-005 | 6000.08.02 | Table - Folding - 6ft | equipment | X | 5600 | Expense · Operations | CC-VENUE | each | 13 | 15 | 17 | Standard 6ft rectangular folding banquet table. |  |  | 04 Physical | Procure
6000.08.02-XPMS-006 | 6000.08.02 | Table - Folding - 8ft | equipment | X | 5600 | Expense · Operations | CC-VENUE | each | 15 | 18 | 21 | Standard 8ft rectangular folding banquet table. |  |  | 04 Physical | Procure
6000.08.02-XPMS-007 | 6000.08.02 | Table - Round - 60in or 72in | equipment | X | 5600 | Expense · Operations | CC-VENUE | each | 17 | 20 | 23 | Standard 60 or 72 inch round banquet table for dining or meetings. |  |  | 04 Physical | Procure
6000.08.02-XPMS-008 | 6000.08.02 | Whiteboard - Freestanding | equipment | X | 5600 | Expense · Operations | CC-VENUE | each | 17 | 20 | 23 | Freestanding whiteboard or corkboard for production office. |  |  | 04 Physical | Procure
6000.09.01-XPMS-001 | 6000.09.01 | Compactor - Portable | equipment | X | 5600 | Expense · Operations | CC-VENUE | each | 210 | 250 | 290 | On-site waste compactor to reduce haul frequency. |  |  | 04 Physical | Install
6000.09.01-XPMS-002 | 6000.09.01 | Dumpster - Roll-Off | equipment | X | 5600 | Expense · Operations | CC-VENUE | each | 425 | 500 | 575 | Open-top roll-off dumpster for construction and event waste. |  |  | 04 Physical | Install
6000.09.01-XPMS-003 | 6000.09.01 | Receptacle - Trash and Recycling | equipment | X | 5600 | Expense · Operations | CC-VENUE | each | 8 | 10 | 12 | Event-grade waste receptacle with liner and signage. |  |  | 04 Physical | Install
6000.09.01-XPMS-004 | 6000.09.01 | Service - Waste Removal | equipment | X | 5600 | Expense · Operations | CC-VENUE | each | 1025 | 1200 | 1375 | Scheduled waste collection and disposal during multi-day events. |  |  | 04 Physical | Install
6000.50.01-XOS-001 | 6000.50.01 | Benefits | payroll | Y | 5600 | Expense · Operations | CC-VENUE | year | 15000 | 20000 | 28000 | Health and other benefits. |  |  | 04 Physical | Procure | 6000.50.01-XOS-6120-1471
6000.50.01-XOS-007 | 6000.50.01 | House Management | service | Y | 5600 | Expense · Operations | CC-VENUE | lump sum | 5500 | 7500 | 11000 | Representative line for house management so the category can carry cost. Replace with the specific item on award. |  |  | 04 Physical | Procure | 6000.50.01-XOS-001
6000.50.01-XOS-002 | 6000.50.01 | Payroll Taxes | payroll | Y | 5600 | Expense · Operations | CC-VENUE | year | 12000 | 16000 | 22000 | Employer payroll taxes at the statutory rate. |  |  | 04 Physical | Procure | 6000.50.01-XOS-6120-1470
6000.50.01-XOS-003 | 6000.50.01 | Salary · Deputy House Manager | payroll | Y | 5600 | Expense · Operations | CC-VENUE | year | 65000 | 75000 | 90000 | Annual salary. |  |  | 04 Physical | Procure | 6000.50.01-XOS-6110-1467
6000.50.01-XOS-004 | 6000.50.01 | Salary · Front of House Lead | payroll | Y | 5600 | Expense · Operations | CC-VENUE | year | 45000 | 55000 | 68000 | Part-time salary. |  |  | 04 Physical | Procure | 6000.50.01-XOS-6110-1468
6000.50.01-XOS-005 | 6000.50.01 | Salary · House Manager | payroll | Y | 5600 | Expense · Operations | CC-VENUE | year | 95000 | 115000 | 140000 | Annual salary. |  |  | 04 Physical | Procure | 6000.50.01-XOS-6110-1466
6000.50.01-XOS-006 | 6000.50.01 | Salary · Programming Lead | payroll | Y | 5600 | Expense · Operations | CC-VENUE | year | 75000 | 90000 | 110000 | Annual salary. |  |  | 04 Physical | Procure | 6000.50.01-XOS-6110-1469
6000.50.02-XOS-001 | 6000.50.02 | Deputy House Management | service | Y | 5600 | Expense · Operations | CC-VENUE | lump sum | 4500 | 6500 | 9500 | Representative line for deputy house management so the category can carry cost. Replace with the specific item on award. |  |  | 04 Physical | Procure | 6000.50.02-XOS-001
6000.51.01-XOS-001 | 6000.51.01 | Janitorial | service | Y | 5600 | Expense · Operations | CC-VENUE | lump sum | 3500 | 5000 | 7500 | Representative line for janitorial so the category can carry cost. Replace with the specific item on award. |  |  | 04 Physical | Procure | 6000.51.01-XOS-001
6000.51.02-XOS-001 | 6000.51.02 | Waste and Recycling | service | Y | 5600 | Expense · Operations | CC-VENUE | lump sum | 1800 | 2500 | 3500 | Representative line for waste and recycling so the category can carry cost. Replace with the specific item on award. |  |  | 04 Physical | Procure | 6000.51.02-XOS-001
6000.51.03-XOS-001 | 6000.51.03 | Pest Control | service | Y | 5600 | Expense · Operations | CC-VENUE | lump sum | 450 | 650 | 950 | Representative line for pest control so the category can carry cost. Replace with the specific item on award. |  |  | 04 Physical | Procure | 6000.51.03-XOS-001
6000.51.04-XOS-001 | 6000.51.04 | Fire and Life Safety | service | Y | 5600 | Expense · Operations | CC-VENUE | lump sum | 1200 | 1600 | 2200 | Representative line for fire and life safety so the category can carry cost. Replace with the specific item on award. |  |  | 04 Physical | Procure | 6000.51.04-XOS-001
6000.51.05-XOS-001 | 6000.51.05 | Key and Access Control | service | Y | 5600 | Expense · Operations | CC-VENUE | lump sum | 850 | 1200 | 1650 | Representative line for key and access control so the category can carry cost. Replace with the specific item on award. |  |  | 04 Physical | Procure | 6000.51.05-XOS-001
6000.52.01-XOS-001 | 6000.52.01 | Security Supervision | service | Y | 5600 | Expense · Operations | CC-VENUE | lump sum | 2500 | 3500 | 5000 | Representative line for security supervision so the category can carry cost. Replace with the specific item on award. |  |  | 04 Physical | Procure | 6000.52.01-XOS-001
6000.52.02-XOS-001 | 6000.52.02 | Security Officer | service | Y | 5600 | Expense · Operations | CC-VENUE | lump sum | 1800 | 2500 | 3500 | Representative line for security officer so the category can carry cost. Replace with the specific item on award. |  |  | 04 Physical | Procure | 6000.52.02-XOS-001
6000.53.01-XOS-001 | 6000.53.01 | Base Rent | space | X | 5600 | Expense · Operations | CC-VENUE | sq ft per year | 35 | 45 | 55 | Representative line for base rent so the category can carry cost. Replace with the specific item on award. |  |  | 04 Physical | Procure | 6000.53.01-XOS-001
6000.53.02-XOS-001 | 6000.53.02 | Operating Expense Recovery | space | X | 5600 | Expense · Operations | CC-VENUE | sq ft per year | 8.5 | 12 | 16 | Representative line for operating expense recovery so the category can carry cost. Replace with the specific item on award. |  |  | 04 Physical | Procure | 6000.53.02-XOS-001
6000.53.03-XOS-001 | 6000.53.03 | Real Estate Taxes | space | X | 5600 | Expense · Operations | CC-VENUE | sq ft per year | 4.5 | 6.5 | 9 | Representative line for real estate taxes so the category can carry cost. Replace with the specific item on award. |  |  | 04 Physical | Procure | 6000.53.03-XOS-001
6000.53.04-XOS-001 | 6000.53.04 | Electricity | space | X | 5600 | Expense · Operations | CC-VENUE | sq ft per year | 3.5 | 5 | 7 | Representative line for electricity so the category can carry cost. Replace with the specific item on award. |  |  | 04 Physical | Procure | 6000.53.04-XOS-001
6000.53.05-XOS-001 | 6000.53.05 | Water and Sewer | space | X | 5600 | Expense · Operations | CC-VENUE | sq ft per year | 1.2 | 1.8 | 2.5 | Representative line for water and sewer so the category can carry cost. Replace with the specific item on award. |  |  | 04 Physical | Procure | 6000.53.05-XOS-001
6000.60.01-XOS-001 | 6000.60.01 | Scope Activities · Operations | service | Y | 5600 | Expense · Operations | CC-E00 | lump sum | 3500 | 5000 | 7500 | Representative line for scope activities so the category can carry cost. Replace with the specific item on award. |  |  | 04 Physical | Scope | 6000.60.01-XOS-001
6000.60.02-XOS-001 | 6000.60.02 | Engage Activities · Operations | service | Y | 5600 | Expense · Operations | CC-E00 | lump sum | 3500 | 5000 | 7500 | Representative line for engage activities so the category can carry cost. Replace with the specific item on award. |  |  | 04 Physical | Engage | 6000.60.02-XOS-001
6000.60.03-XOS-001 | 6000.60.03 | Advance Activities · Operations | service | Y | 5600 | Expense · Operations | CC-E00 | lump sum | 2500 | 3500 | 5000 | Representative line for advance activities so the category can carry cost. Replace with the specific item on award. |  |  | 04 Physical | Advance | 6000.60.03-XOS-001
6000.60.04-XOS-001 | 6000.60.04 | Procure Activities · Operations | service | Y | 5600 | Expense · Operations | CC-E00 | lump sum | 2500 | 3500 | 5000 | Representative line for procure activities so the category can carry cost. Replace with the specific item on award. |  |  | 04 Physical | Procure | 6000.60.04-XOS-001
6000.60.05-XOS-001 | 6000.60.05 | Build Activities · Operations | service | Y | 5600 | Expense · Operations | CC-E00 | lump sum | 3500 | 5000 | 7500 | Representative line for build activities so the category can carry cost. Replace with the specific item on award. |  |  | 04 Physical | Build | 6000.60.05-XOS-001
6000.60.06-XOS-001 | 6000.60.06 | Install Activities · Operations | service | Y | 5600 | Expense · Operations | CC-E00 | lump sum | 4500 | 6500 | 9500 | Representative line for install activities so the category can carry cost. Replace with the specific item on award. |  |  | 04 Physical | Install | 6000.60.06-XOS-001
6000.60.07-XOS-001 | 6000.60.07 | Operate Activities · Operations | service | Y | 5600 | Expense · Operations | CC-E00 | lump sum | 6500 | 9500 | 14000 | Representative line for operate activities so the category can carry cost. Replace with the specific item on award. |  |  | 04 Physical | Operate | 6000.60.07-XOS-001
6000.60.08-XOS-001 | 6000.60.08 | Amplify Activities · Operations | service | Y | 5600 | Expense · Operations | CC-E00 | lump sum | 3500 | 5000 | 7500 | Representative line for amplify activities so the category can carry cost. Replace with the specific item on award. |  |  | 04 Physical | Amplify | 6000.60.08-XOS-001
6000.60.09-XOS-001 | 6000.60.09 | Close Activities · Operations | service | Y | 5600 | Expense · Operations | CC-E00 | lump sum | 5500 | 7500 | 11000 | Representative line for close activities so the category can carry cost. Replace with the specific item on award. |  |  | 04 Physical | Close | 6000.60.09-XOS-001
7000.01.01-XPMS-005 | 7000.01.01 | ADA Accessibility Compliance Package | service | Y | 5700 | Expense · Experience | CC-VENUE | each | 2500 | 3500 | 5000 | Accessibility audit plus ramp, viewing-platform, and service provisions to meet ADA at temporary events. |  |  | 04 Physical | Advance
7000.01.01-GHXST-001 | 7000.01.01 | ATM - Portable | equipment | X | 5700 | Expense · Experience | CC-VENUE | each | 210 | 250 | 290 | Portable ATM for cash access at events. | Freestanding or countertop ¦ With surcharge configuration. | 72 | 04 Physical | Procurement | RETL-MRCH-POST-003 · 7000.080.00
7000.01.01-XPMS-010 | 7000.01.01 | Accessibility & Inclusive Design Review | service | Y | 5700 | Expense · Experience | CC-VENUE | each | 3500 | 5000 | 7500 | Review of the design against accessibility requirements for its jurisdiction and against inclusive-design practice beyond the legal minimum. Gate 6 verifies as-built; this establishes intent. |  |  | 05 Experiential | Scope
7000.01.01-XOS-007 | 7000.01.01 | Accessories (Totes or Socks or Patches) · Base | experience | Y | 5700 | Expense · Experience | CC-VENUE | each | 8 | 12 | 18 | Printed tote or single accessory item. | Zone: Entrance / Lobby. Tier fit: T1; T4. Upgrades: Enamel pin / woven patch set. Add-ons: Artist-collab accessory. Substitutions: Sticker pack only. |  | 01 Social | Advance | TCH-02
7000.01.01-XOS-008 | 7000.01.01 | Accessories (Totes or Socks or Patches) · Elevated | experience | Y | 5700 | Expense · Experience | CC-VENUE | each | 18 | 26 | 38 | Accessory set (tote, socks, sticker pack) in palette. | Zone: Entrance / Lobby. Tier fit: T1; T4. Upgrades: Enamel pin / woven patch set. Add-ons: Artist-collab accessory. Substitutions: Sticker pack only. |  | 01 Social | Advance | TCH-02
7000.01.01-XOS-009 | 7000.01.01 | Accessories (Totes or Socks or Patches) · Premium | experience | Y | 5700 | Expense · Experience | CC-VENUE | each | 35 | 50 | 75 | Premium accessory line with woven, enamel, and specialty finishes. | Zone: Entrance / Lobby. Tier fit: T1; T4. Upgrades: Enamel pin / woven patch set. Add-ons: Artist-collab accessory. Substitutions: Sticker pack only. |  | 01 Social | Advance | TCH-02
7000.01.01-XOS-010 | 7000.01.01 | Apparel (Tees or Caps or Hoodies) · Base | experience | Y | 5700 | Expense · Experience | CC-VENUE | each | 14 | 20 | 30 | Screen-printed tee with event/brand mark. | Zone: Entrance / Lobby. Tier fit: T1; T4. Upgrades: Cut-and-sew; embroidery. Add-ons: On-site DTG personalization. Substitutions: Cap / beanie only. |  | 01 Social | Advance | TCH-01
7000.01.01-XOS-011 | 7000.01.01 | Apparel (Tees or Caps or Hoodies) · Elevated | experience | Y | 5700 | Expense · Experience | CC-VENUE | each | 28 | 40 | 60 | Premium-blank apparel range (tee, cap) with multi-placement print. | Zone: Entrance / Lobby. Tier fit: T1; T4. Upgrades: Cut-and-sew; embroidery. Add-ons: On-site DTG personalization. Substitutions: Cap / beanie only. |  | 01 Social | Advance | TCH-01
7000.01.01-XOS-012 | 7000.01.01 | Apparel (Tees or Caps or Hoodies) · Premium | experience | Y | 5700 | Expense · Experience | CC-VENUE | each | 55 | 80 | 120 | Designer cut-and-sew capsule with embroidery and custom trims. | Zone: Entrance / Lobby. Tier fit: T1; T4. Upgrades: Cut-and-sew; embroidery. Add-ons: On-site DTG personalization. Substitutions: Cap / beanie only. |  | 01 Social | Advance | TCH-01
7000.01.01-XOS-013 | 7000.01.01 | Giveaway or Swag · Base | experience | Y | 5700 | Expense · Experience | CC-VENUE | each | 4.5 | 6.5 | 9.5 | Stickers and a wristband at entry. | Zone: All Zones. Tier fit: T1; T4. Upgrades: Swag-drop reveal moment. Add-ons: Spin-to-win swag station. Substitutions: Sticker / wristband only. |  | 01 Social | Advance | TCH-05
7000.01.01-XOS-014 | 7000.01.01 | Giveaway or Swag · Elevated | experience | Y | 5700 | Expense · Experience | CC-VENUE | each | 12 | 18 | 26 | Branded swag set (drinkware, pin, koozie) per guest. | Zone: All Zones. Tier fit: T1; T4. Upgrades: Swag-drop reveal moment. Add-ons: Spin-to-win swag station. Substitutions: Sticker / wristband only. |  | 01 Social | Advance | TCH-05
7000.01.01-XOS-015 | 7000.01.01 | Giveaway or Swag · Premium | experience | Y | 5700 | Expense · Experience | CC-VENUE | each | 25 | 38 | 55 | Designed swag drop with premium items and a reveal moment. | Zone: All Zones. Tier fit: T1; T4. Upgrades: Swag-drop reveal moment. Add-ons: Spin-to-win swag station. Substitutions: Sticker / wristband only. |  | 01 Social | Advance | TCH-05
7000.01.01-XPMS-001 | 7000.01.01 | Guest Journey Mapping Workshop | service | Y | 5700 | Expense · Experience | CC-VENUE | each | 4500 | 6500 | 9500 | Facilitated journey-mapping session producing touchpoint map and service blueprint for the activation. |  |  | 05 Experiential | Scope
7000.01.01-XPMS-004 | 7000.01.01 | Guest Services Concierge | labor | Y | 5700 | Expense · Experience | CC-VENUE | each | 350 | 450 | 600 | Trained concierge handling guest questions, escorts, and white-glove touches. |  |  | 05 Experiential | Operate
7000.01.01-XPMS-006 | 7000.01.01 | Guest Survey & Feedback Program | service | Y | 5700 | Expense · Experience | CC-VENUE | each | 2500 | 3500 | 5000 | Designed intercept and post-event survey program with response analysis. |  |  | 02 Digital | Amplify
7000.01.01-XPMS-009 | 7000.01.01 | Merch or Premiums or Goodies | package | X | 5700 | Expense · Experience | CC-VENUE | each | 2500 | 3500 | 5000 | Experience · Merch / premiums / goodies. |  |  | 04 Physical | Operate
7000.01.01-XOS-016 | 7000.01.01 | Music Keepsake (Vinyl or Cassette) · Base | experience | Y | 5700 | Expense · Experience | CC-VENUE | each | 6.5 | 9.5 | 14.5 | Branded download card or playlist QR keepsake. | Zone: Exhibition Room. Tier fit: T2; T4. Upgrades: Numbered / signed pressing. Add-ons: Lathe-cut one-off edition. Substitutions: Digital QR keepsake. |  | 01 Social | Advance | TCH-03
7000.01.01-XOS-017 | 7000.01.01 | Music Keepsake (Vinyl or Cassette) · Elevated | experience | Y | 5700 | Expense · Experience | CC-VENUE | each | 18 | 26 | 38 | Limited cassette or 7-inch with custom sleeve. | Zone: Exhibition Room. Tier fit: T2; T4. Upgrades: Numbered / signed pressing. Add-ons: Lathe-cut one-off edition. Substitutions: Digital QR keepsake. |  | 01 Social | Advance | TCH-03
7000.01.01-XOS-018 | 7000.01.01 | Music Keepsake (Vinyl or Cassette) · Premium | experience | Y | 5700 | Expense · Experience | CC-VENUE | each | 35 | 50 | 75 | Numbered vinyl pressing with gatefold art as a collectible. | Zone: Exhibition Room. Tier fit: T2; T4. Upgrades: Numbered / signed pressing. Add-ons: Lathe-cut one-off edition. Substitutions: Digital QR keepsake. |  | 01 Social | Advance | TCH-03
7000.01.01-GHXST-002 | 7000.01.01 | POS System - Mobile | equipment | X | 5700 | Expense · Experience | CC-VENUE | each | 42 | 48.5 | 55 | Mobile point-of-sale system for merch and concession sales. | Square, Clover, Toast, or Shopify POS. | 72 | 04 Physical | Procurement | RETL-MRCH-POST-001 · 7000.080.00
7000.01.01-XPMS-007 | 7000.01.01 | Permanent Community Portrait Gallery ( FtHumans of Miami Ft) | service | Y | 5700 | Expense · Experience | CC-VENUE | each | 3500 | 5000 | 7500 | Experience · Permanent Community Portrait Gallery ('Humans of Miami'). |  |  | 04 Physical | Build
7000.01.01-XPMS-008 | 7000.01.01 | Photo or Interactive or Guest Moment | package | X | 5700 | Expense · Experience | CC-VENUE | each | 2500 | 3500 | 5000 | Experience · Photo / interactive / guest moment. |  |  | 04 Physical | Operate
7000.01.01-XPMS-011 | 7000.01.01 | Post-Event Guest Survey & NPS | service | Y | 5700 | Expense · Experience | CC-VENUE | each | 2500 | 3500 | 5000 | Fielding and analysis of post-event guest research, delivering satisfaction and recommendation measures with sample size and method stated. |  |  | 05 Experiential | Amplify
7000.01.01-XPMS-003 | 7000.01.01 | Queue Management Package | equipment | X | 5700 | Expense · Experience | CC-VENUE | each | 850 | 1200 | 1650 | Stanchion, belt, and queue-signage package with flow plan for a managed entry zone. |  |  | 04 Physical | Operate
7000.01.01-XOS-001 | 7000.01.01 | Sculptural Centerpiece · Base | experience | Y | 5700 | Expense · Experience | CC-VENUE | each | 1200 | 1800 | 2600 | Single rented sculptural object as a focal point. | Zone: Exhibition Room. Tier fit: T2; T4. Upgrades: Engineered hero scale; motion. Add-ons: Local-artist commission credit. Substitutions: Floral sculptural feature. |  | 05 Experiential | Build | SGT-29
7000.01.01-XOS-002 | 7000.01.01 | Sculptural Centerpiece · Elevated | experience | Y | 5700 | Expense · Experience | CC-VENUE | each | 2500 | 3600 | 5200 | Commissioned mid-scale sculpture in the design palette. | Zone: Exhibition Room. Tier fit: T2; T4. Upgrades: Engineered hero scale; motion. Add-ons: Local-artist commission credit. Substitutions: Floral sculptural feature. |  | 05 Experiential | Build | SGT-29
7000.01.01-XOS-003 | 7000.01.01 | Sculptural Centerpiece · Premium | experience | Y | 5700 | Expense · Experience | CC-VENUE | each | 5000 | 7500 | 11000 | Large-scale commissioned hero sculpture engineered as the room's anchor moment. | Zone: Exhibition Room. Tier fit: T2; T4. Upgrades: Engineered hero scale; motion. Add-ons: Local-artist commission credit. Substitutions: Floral sculptural feature. |  | 05 Experiential | Build | SGT-29
7000.01.01-XOS-004 | 7000.01.01 | Suspended or Aerial Installation · Base | experience | Y | 5700 | Expense · Experience | CC-VENUE | each | 1200 | 1800 | 2600 | Hanging mobile or cluster from existing rig points. | Zone: Main Stage and Bar. Tier fit: T3; T4. Upgrades: Kinetic motion; integrated lighting. Add-ons: Sound-reactive control. Substitutions: Ground sculpture instead. |  | 05 Experiential | Build | SGT-30
7000.01.01-XOS-005 | 7000.01.01 | Suspended or Aerial Installation · Elevated | experience | Y | 5700 | Expense · Experience | CC-VENUE | each | 2500 | 3600 | 5200 | Designed suspended element (fabric, panels, or objects) over a key zone. | Zone: Main Stage and Bar. Tier fit: T3; T4. Upgrades: Kinetic motion; integrated lighting. Add-ons: Sound-reactive control. Substitutions: Ground sculpture instead. |  | 05 Experiential | Build | SGT-30
7000.01.01-XOS-006 | 7000.01.01 | Suspended or Aerial Installation · Premium | experience | Y | 5700 | Expense · Experience | CC-VENUE | each | 5000 | 7500 | 11000 | Engineered kinetic aerial installation with lighting and optional motion. | Zone: Main Stage and Bar. Tier fit: T3; T4. Upgrades: Kinetic motion; integrated lighting. Add-ons: Sound-reactive control. Substitutions: Ground sculpture instead. |  | 05 Experiential | Build | SGT-30
7000.01.01-XPMS-002 | 7000.01.01 | Wayfinding Program Design & Plan | service | Y | 5700 | Expense · Experience | CC-VENUE | each | 2500 | 3500 | 5000 | Site-wide wayfinding strategy, sign schedule, and placement plan handed to signage fabrication. |  |  | 05 Experiential | Scope
7000.01.01-XOS-019 | 7000.01.01 | Welcome or Premium Gift · Base | experience | Y | 5700 | Expense · Experience | CC-VENUE | each | 25 | 40 | 60 | Single welcome item at check-in. | Zone: Entrance / Lobby. Tier fit: T1; T4. Upgrades: On-site personalization / engraving. Add-ons: Gifting-suite attendant. Substitutions: Single gift item. |  | 01 Social | Advance | TCH-04
7000.01.01-XOS-020 | 7000.01.01 | Welcome or Premium Gift · Elevated | experience | Y | 5700 | Expense · Experience | CC-VENUE | each | 50 | 80 | 120 | Curated welcome gift box with two to three items. | Zone: Entrance / Lobby. Tier fit: T1; T4. Upgrades: On-site personalization / engraving. Add-ons: Gifting-suite attendant. Substitutions: Single gift item. |  | 01 Social | Advance | TCH-04
7000.01.01-XOS-021 | 7000.01.01 | Welcome or Premium Gift · Premium | experience | Y | 5700 | Expense · Experience | CC-VENUE | each | 120 | 180 | 260 | Luxury gifting suite with personalization and premium packaging. | Zone: Entrance / Lobby. Tier fit: T1; T4. Upgrades: On-site personalization / engraving. Add-ons: Gifting-suite attendant. Substitutions: Single gift item. |  | 01 Social | Advance | TCH-04
7000.02.01-XPMS-001 | 7000.02.01 | Artist - Hair and Makeup | labor | Y | 5700 | Expense · Experience | CC-VENUE | each | 130 | 150 | 170 | Professional hair and makeup for talent or branding. |  |  | 04 Physical | Build
7000.02.01-XPMS-002 | 7000.02.01 | Designer - Graphic | labor | Y | 5700 | Expense · Experience | CC-VENUE | each | 425 | 500 | 575 | On-site graphic designer for day-of signage and changes. |  |  | 04 Physical | Build
7000.02.01-XPMS-003 | 7000.02.01 | Drone Pilot - Licensed | labor | Y | 5700 | Expense · Experience | CC-VENUE | each | 850 | 1000 | 1150 | FAA Part 107 licensed drone pilot for aerial capture. |  |  | 04 Physical | Build
7000.02.01-XPMS-007 | 7000.02.01 | Exhibition Rotating Content Production | service | Y | 5700 | Expense · Experience | CC-VENUE | each | 3500 | 5000 | 7500 | Launch content set. |  |  | 04 Physical | Build
7000.02.01-XPMS-004 | 7000.02.01 | Photographer - Event | labor | Y | 5700 | Expense · Experience | CC-VENUE | each | 500 | 600 | 700 | Professional event photographer for documentation and content. |  |  | 04 Physical | Build
7000.02.01-XPMS-008 | 7000.02.01 | Spotify Branding Integration Elements | package | X | 5700 | Expense · Experience | CC-VENUE | each | 3500 | 5000 | 7500 | Room-level brand integration. |  |  | 04 Physical | Build
7000.02.01-XPMS-005 | 7000.02.01 | Stylist - Wardrobe | labor | Y | 5700 | Expense · Experience | CC-VENUE | each | 425 | 500 | 575 | Wardrobe management and costume coordination for talent. |  |  | 04 Physical | Build
7000.02.01-XPMS-006 | 7000.02.01 | Videographer - Event | labor | Y | 5700 | Expense · Experience | CC-VENUE | each | 675 | 800 | 925 | Professional videographer for recap or content capture. |  |  | 04 Physical | Operate
7000.02.02-XOS-001 | 7000.02.02 | Party Props & Hand-Held · Base | experience | Y | 5700 | Expense · Experience | CC-VENUE | each | 15 | 25 | 40 | Branded fans or glasses for peak moments. | Zone: Main Stage and Bar. Tier fit: T1; T4. Upgrades: LED wristband sync; confetti drop. Add-ons: Photo-prop styling set. Substitutions: Confetti cannon only. |  | 05 Experiential | Show | TCH-06
7000.02.02-XOS-002 | 7000.02.02 | Party Props & Hand-Held · Elevated | experience | Y | 5700 | Expense · Experience | CC-VENUE | each | 35 | 55 | 85 | Props kit (LED wristbands, fans, signs) distributed for the show. | Zone: Main Stage and Bar. Tier fit: T1; T4. Upgrades: LED wristband sync; confetti drop. Add-ons: Photo-prop styling set. Substitutions: Confetti cannon only. |  | 05 Experiential | Show | TCH-06
7000.02.02-XOS-003 | 7000.02.02 | Party Props & Hand-Held · Premium | experience | Y | 5700 | Expense · Experience | CC-VENUE | each | 75 | 110 | 165 | Choreographed prop moment with custom LED and confetti for the climax. | Zone: Main Stage and Bar. Tier fit: T1; T4. Upgrades: LED wristband sync; confetti drop. Add-ons: Photo-prop styling set. Substitutions: Confetti cannon only. |  | 05 Experiential | Show | TCH-06
7000.02.02-XPMS-001 | 7000.02.02 | Party Props & Interactive Props | service | Y | 5700 | Expense · Experience | CC-VENUE | each | 2500 | 3500 | 5000 | Branded party and interactive props. |  |  | 05 Experiential | Operate
7000.02.03-XPMS-001 | 7000.02.03 | Verbal Identity Activation | service | Y | 5700 | Expense · Experience | CC-VENUE | each | 1500 | 2200 | 3200 | In-experience verbal identity moments. |  |  | 05 Experiential | Operate
7000.03.01-XPMS-001 | 7000.03.01 | Activation Space - Sponsor | equipment | X | 5700 | Expense · Experience | CC-VENUE | each | 500 | 600 | 700 | Dedicated footprint for sponsor brand activation. | 10x10 through custom ¦ Tented, hard-wall, or full build-out. | 336 | 04 Physical | Procure
7000.03.01-XPMS-002 | 7000.03.01 | Booth Space - Vendor | equipment | X | 5700 | Expense · Experience | CC-VENUE | each | 130 | 150 | 170 | Designated vendor marketplace booth with power and table. | 10x10 through 10x20 ¦ Shared tent or open-air. | 336 | 04 Physical | Procure
7000.03.01-XPMS-004 | 7000.03.01 | Retail or Merch Micro-Nook Fixtures | package | X | 5700 | Expense · Experience | CC-VENUE | each | 1500 | 2200 | 3200 | Retail nook fixtures. |  |  | 04 Physical | Build
7000.03.01-XPMS-003 | 7000.03.01 | Vendor Pad - Food Truck | equipment | X | 5700 | Expense · Experience | CC-VENUE | each | 210 | 250 | 290 | Level prepared pad for food truck or food vendor tent. | 10x20 through 20x30 ¦ With power, water, and waste. | 336 | 04 Physical | Procure
7000.03.02-XPMS-001 | 7000.03.02 | Bag - Shopping - Branded | equipment | X | 5700 | Expense · Experience | CC-VENUE | each | 42 | 48.5 | 55 | Custom branded bags for merchandise purchases. | Small through large ¦ Paper, plastic, or reusable. | 72 | 04 Physical | Procure
7000.03.02-GHXST-001 | 7000.03.02 | Supplies - Cash Handling | equipment | X | 5700 | Expense · Experience | CC-VENUE | each | 50 | 60 | 70 | Cash drawer, coin changer, counterfeit detector, and money bags. | Drawer, counter, changer, and detection. | 72 | 04 Physical | Procurement | RETL-MRCH-POST-002 · 7000.080.00
7000.03.02-XPMS-002 | 7000.03.02 | Supplies - Retail Packaging | equipment | X | 5700 | Expense · Experience | CC-VENUE | each | 26 | 30 | 34 | Receipt paper, tissue paper, stickers, and gift wrap. | Receipt rolls, tissue, brand stickers, and wrapping. | 72 | 04 Physical | Procure
7000.03.03-XPMS-001 | 7000.03.03 | Booth - Merchandise | equipment | X | 5700 | Expense · Experience | CC-VENUE | each | 425 | 500 | 575 | Dedicated merch sales structure with counter and display. | 10x10 through 20x20 ¦ With lighting, counter, racks, and POS. | 72 | 04 Physical | Procure
7000.03.03-XPMS-002 | 7000.03.03 | Display Case - Lockable | equipment | X | 5700 | Expense · Experience | CC-VENUE | each | 34 | 40 | 46 | Secure glass or acrylic display case for high-value items. | 2ft through 4ft ¦ Countertop and freestanding options. | 72 | 04 Physical | Procure
7000.03.03-XPMS-003 | 7000.03.03 | Mannequin - Display | equipment | X | 5700 | Expense · Experience | CC-VENUE | each | 26 | 30 | 34 | Display mannequin for apparel merchandising. | Full body, half body, or dress form. | 72 | 04 Physical | Procure
7000.03.03-XPMS-004 | 7000.03.03 | Rack - Garment | equipment | X | 5700 | Expense · Experience | CC-VENUE | each | 17 | 20 | 23 | Rolling or stationary garment display rack. | Single bar, double bar, round, or Z-rack. | 72 | 04 Physical | Procure
7000.03.03-XPMS-005 | 7000.03.03 | Shelving - Display | equipment | X | 5700 | Expense · Experience | CC-VENUE | each | 26 | 30 | 34 | Modular display shelving for product merchandising. | Gridwall (2x6, 2x8), slatwall panel, or wire shelving. | 72 | 04 Physical | Procure
7000.03.03-XPMS-006 | 7000.03.03 | Table - Display | equipment | X | 5700 | Expense · Experience | CC-VENUE | each | 26 | 30 | 34 | Merchandise display table or sales counter. | 4ft through 8ft ¦ Folding and custom options. | 72 | 04 Physical | Procure
7000.03.04-XPMS-001 | 7000.03.04 | Blacklight - UV | equipment | X | 5700 | Expense · Experience | CC-VENUE | each | 26 | 30 | 34 | UV and blacklight fixture for glow effects and UV-reactive decor. |  |  | 04 Physical | Procure
7000.03.04-XPMS-002 | 7000.03.04 | Blinder - Audience | equipment | X | 5700 | Expense · Experience | CC-VENUE | each | 42 | 48.5 | 55 | High-intensity audience blinder for dramatic wash effects. |  |  | 04 Physical | Procure
7000.03.04-XPMS-003 | 7000.03.04 | Ellipsoidal - Source Four | equipment | X | 5700 | Expense · Experience | CC-VENUE | each | 30 | 35 | 40 | Conventional or LED ellipsoidal spotlight for key and gobo projection. |  |  | 04 Physical | Procure
7000.03.04-XPMS-004 | 7000.03.04 | Followspot | equipment | X | 5700 | Expense · Experience | CC-VENUE | each | 300 | 350 | 400 | Manually operated followspot for performer tracking. |  |  | 04 Physical | Procure
7000.03.04-XPMS-005 | 7000.03.04 | PAR Can - LED | equipment | X | 5700 | Expense · Experience | CC-VENUE | each | 26 | 30 | 34 | Static LED PAR wash for uplighting, stage wash, or decor. |  |  | 04 Physical | Procure
7000.03.04-XPMS-006 | 7000.03.04 | Pixel Tape - LED | equipment | X | 5700 | Expense · Experience | CC-VENUE | each | 7 | 8 | 9 | Individually addressable LED tape for scenic and decorative effects. |  |  | 04 Physical | Procure
7000.03.04-XPMS-007 | 7000.03.04 | String Lights - Bistro | equipment | X | 5700 | Expense · Experience | CC-VENUE | each | 42 | 48.5 | 55 | Decorative string lights for ambiance and outdoor areas. |  |  | 04 Physical | Procure
7000.03.04-XPMS-008 | 7000.03.04 | Strobe - DMX | equipment | X | 5700 | Expense · Experience | CC-VENUE | each | 50 | 60 | 70 | High-intensity strobe fixture for dramatic flash effects. |  |  | 04 Physical | Procure
7000.03.05-XPMS-001 | 7000.03.05 | Custom Merchandise Program | service | Y | 5700 | Expense · Experience | CC-VENUE | each | 3500 | 5000 | 7500 | Custom merch design, production, fulfillment. |  |  | 05 Experiential | Operate
7000.04.01-XOS-001 | 7000.04.01 | Candles & Open Flame · Base | experience | Y | 5700 | Expense · Experience | CC-VENUE | each | 120 | 180 | 260 | Unscented pillar candles for ambiance. | Zone: El Patio. Tier fit: T1; T4. Upgrades: Custom branded candle vessel. Add-ons: Artist-themed scent story. Substitutions: Flameless LED candles. |  | 05 Experiential | Build | SCT-03
7000.04.01-XOS-002 | 7000.04.01 | Candles & Open Flame · Elevated | experience | Y | 5700 | Expense · Experience | CC-VENUE | each | 250 | 360 | 520 | Scented candle program in palette across bars and tables. | Zone: El Patio. Tier fit: T1; T4. Upgrades: Custom branded candle vessel. Add-ons: Artist-themed scent story. Substitutions: Flameless LED candles. |  | 05 Experiential | Build | SCT-03
7000.04.01-XOS-003 | 7000.04.01 | Candles & Open Flame · Premium | experience | Y | 5700 | Expense · Experience | CC-VENUE | each | 450 | 650 | 950 | Custom-poured signature candles with branded vessels (also gift-ready). | Zone: El Patio. Tier fit: T1; T4. Upgrades: Custom branded candle vessel. Add-ons: Artist-themed scent story. Substitutions: Flameless LED candles. |  | 05 Experiential | Build | SCT-03
7000.04.01-XPMS-002 | 7000.04.01 | Cold-Air Scent Diffuser (Standalone) | equipment | X | 5700 | Expense · Experience | CC-VENUE | each | 180 | 240 | 320 | Standalone cold-air nebulizing diffuser. |  |  | 05 Experiential | Operate
7000.04.01-XOS-004 | 7000.04.01 | Fresh Florals & Botanicals (Aroma) · Base | experience | Y | 5700 | Expense · Experience | CC-VENUE | each | 250 | 380 | 550 | Lightly fragrant blooms at the entry. | Zone: Entrance / Lobby. Tier fit: T1; T4. Upgrades: Aromatic herb / citrus accents. Add-ons: Daily fresh refresh. Substitutions: Non-fragrant greenery. |  | 05 Experiential | Build | SCT-04
7000.04.01-XOS-005 | 7000.04.01 | Fresh Florals & Botanicals (Aroma) · Elevated | experience | Y | 5700 | Expense · Experience | CC-VENUE | each | 450 | 680 | 980 | Aromatic floral selection (jasmine, eucalyptus) placed for scent throw. | Zone: Entrance / Lobby. Tier fit: T1; T4. Upgrades: Aromatic herb / citrus accents. Add-ons: Daily fresh refresh. Substitutions: Non-fragrant greenery. |  | 05 Experiential | Build | SCT-04
7000.04.01-XOS-006 | 7000.04.01 | Fresh Florals & Botanicals (Aroma) · Premium | experience | Y | 5700 | Expense · Experience | CC-VENUE | each | 850 | 1250 | 1850 | Designed aromatic botanical program coordinated with the floral and greenery plan. | Zone: Entrance / Lobby. Tier fit: T1; T4. Upgrades: Aromatic herb / citrus accents. Add-ons: Daily fresh refresh. Substitutions: Non-fragrant greenery. |  | 05 Experiential | Build | SCT-04
7000.04.01-XPMS-001 | 7000.04.01 | HVAC Scent Diffusion System | equipment | X | 5700 | Expense · Experience | CC-VENUE | each | 1200 | 1600 | 2200 | Ducted scent injection across HVAC. |  |  | 05 Experiential | Operate
7000.04.01-XOS-007 | 7000.04.01 | Signature Space Scent (HVAC Diffusion) · Base | experience | Y | 5700 | Expense · Experience | CC-VENUE | each | 450 | 650 | 950 | Single diffuser scenting the main entry zone. | Zone: All Zones. Tier fit: T1; T4. Upgrades: Custom scent blend; per-zone control. Add-ons: Scent transition by set moment. Substitutions: Standalone diffusers only. |  | 05 Experiential | Build | SCT-01
7000.04.01-XOS-008 | 7000.04.01 | Signature Space Scent (HVAC Diffusion) · Elevated | experience | Y | 5700 | Expense · Experience | CC-VENUE | each | 850 | 1250 | 1850 | Multi-point cold-air diffusion across primary zones with one signature scent. | Zone: All Zones. Tier fit: T1; T4. Upgrades: Custom scent blend; per-zone control. Add-ons: Scent transition by set moment. Substitutions: Standalone diffusers only. |  | 05 Experiential | Build | SCT-01
7000.04.01-XOS-009 | 7000.04.01 | Signature Space Scent (HVAC Diffusion) · Premium | experience | Y | 5700 | Expense · Experience | CC-VENUE | each | 1650 | 2450 | 3550 | Full HVAC-integrated scent system zoned per room with a custom-blended signature scent. | Zone: All Zones. Tier fit: T1; T4. Upgrades: Custom scent blend; per-zone control. Add-ons: Scent transition by set moment. Substitutions: Standalone diffusers only. |  | 05 Experiential | Build | SCT-01
7000.04.01-XOS-010 | 7000.04.01 | Standalone Diffusers or Nebulizers · Base | experience | Y | 5700 | Expense · Experience | CC-VENUE | each | 250 | 350 | 500 | Two plug-in nebulizers in lounge zones. | Zone: Exhibition Room. Tier fit: T1; T4. Upgrades: Density-tuned scheduling. Add-ons: Discreet concealment housing. Substitutions: HVAC integration instead. |  | 05 Experiential | Build | SCT-02
7000.04.01-XOS-011 | 7000.04.01 | Standalone Diffusers or Nebulizers · Elevated | experience | Y | 5700 | Expense · Experience | CC-VENUE | each | 450 | 650 | 950 | Designer nebulizer units placed per zone with scheduled intensity. | Zone: Exhibition Room. Tier fit: T1; T4. Upgrades: Density-tuned scheduling. Add-ons: Discreet concealment housing. Substitutions: HVAC integration instead. |  | 05 Experiential | Build | SCT-02
7000.04.01-XOS-012 | 7000.04.01 | Standalone Diffusers or Nebulizers · Premium | experience | Y | 5700 | Expense · Experience | CC-VENUE | each | 850 | 1250 | 1850 | Concealed nebulizer network tuned to crowd density and time of night. | Zone: Exhibition Room. Tier fit: T1; T4. Upgrades: Density-tuned scheduling. Add-ons: Discreet concealment housing. Substitutions: HVAC integration instead. |  | 05 Experiential | Build | SCT-02
7000.04.01-XOS-013 | 7000.04.01 | Take-Home Signature Scent · Base | experience | Y | 5700 | Expense · Experience | CC-VENUE | each | 15 | 25 | 40 | Scented sachet or card as a parting touch. | Zone: Entrance / Lobby. Tier fit: T2; T4. Upgrades: Branded scent kit packaging. Add-ons: Artist-collab scent edition. Substitutions: No take-home scent. |  | 05 Experiential | Advance | SCT-06
7000.04.01-XOS-014 | 7000.04.01 | Take-Home Signature Scent · Elevated | experience | Y | 5700 | Expense · Experience | CC-VENUE | each | 35 | 55 | 85 | Travel candle or room spray in the signature scent as a gift. | Zone: Entrance / Lobby. Tier fit: T2; T4. Upgrades: Branded scent kit packaging. Add-ons: Artist-collab scent edition. Substitutions: No take-home scent. |  | 05 Experiential | Advance | SCT-06
7000.04.01-XOS-015 | 7000.04.01 | Take-Home Signature Scent · Premium | experience | Y | 5700 | Expense · Experience | CC-VENUE | each | 75 | 110 | 165 | Full take-home scent kit (candle, spray, oil) in branded packaging. | Zone: Entrance / Lobby. Tier fit: T2; T4. Upgrades: Branded scent kit packaging. Add-ons: Artist-collab scent edition. Substitutions: No take-home scent. |  | 05 Experiential | Advance | SCT-06
7000.04.02-XPMS-002 | 7000.04.02 | Branded Candle or Reed Diffuser | equipment | X | 5700 | Expense · Experience | CC-VENUE | each | 25 | 35 | 50 | Ambient branded candle or reed diffuser. |  |  | 05 Experiential | Operate
7000.04.02-XPMS-001 | 7000.04.02 | Signature Aroma Oil or Cartridge | equipment | X | 5700 | Expense · Experience | CC-VENUE | each | 45 | 65 | 90 | Fragrance oil cartridge for diffuser. |  |  | 05 Experiential | Operate
7000.04.03-XPMS-001 | 7000.04.03 | Signature Scent Design & Formulation | service | Y | 5700 | Expense · Experience | CC-VENUE | each | 3500 | 5000 | 7500 | Bespoke scent design and formulation. |  |  | 05 Experiential | Operate
7000.04.04-XPMS-001 | 7000.04.04 | Scenting Technician | labor | Y | 5700 | Expense · Experience | CC-VENUE | each | 350 | 450 | 600 | On-site scenting setup and service. |  |  | 05 Experiential | Operate
7000.04.05-XPMS-001 | 7000.04.05 | Ambient Soundscape Design & Playback | service | Y | 5700 | Expense · Experience | CC-VENUE | each | 2500 | 3500 | 5000 | Ambient soundscape design and playback. |  |  | 05 Experiential | Operate
7000.05.01-XPMS-002 | 7000.05.01 | 360 Photo Booth with Attendant | equipment | X | 5700 | Expense · Experience | CC-VENUE | each | 750 | 950 | 1250 | Rotating-arm 360 video booth with attendant, lighting, and instant share station. |  |  | 05 Experiential | Operate
7000.05.01-XOS-001 | 7000.05.01 | Floral or Greenery Moment · Base | experience | Y | 5700 | Expense · Experience | CC-VENUE | each | 450 | 650 | 950 | Single floral cluster against a clean wall. | Zone: Entrance / Lobby. Tier fit: T1; T4. Upgrades: Floral archway; overhead cascade. Add-ons: Fresh-flower daily refresh. Substitutions: Neon photo moment. |  | 05 Experiential | Build | SGT-37
7000.05.01-XOS-002 | 7000.05.01 | Floral or Greenery Moment · Elevated | experience | Y | 5700 | Expense · Experience | CC-VENUE | each | 850 | 1250 | 1850 | Floral or greenery feature wall sized for group photos. | Zone: Entrance / Lobby. Tier fit: T1; T4. Upgrades: Floral archway; overhead cascade. Add-ons: Fresh-flower daily refresh. Substitutions: Neon photo moment. |  | 05 Experiential | Build | SGT-37
7000.05.01-XOS-003 | 7000.05.01 | Floral or Greenery Moment · Premium | experience | Y | 5700 | Expense · Experience | CC-VENUE | each | 1650 | 2450 | 3550 | Cascading floral installation with a sculptural arch and lighting. | Zone: Entrance / Lobby. Tier fit: T1; T4. Upgrades: Floral archway; overhead cascade. Add-ons: Fresh-flower daily refresh. Substitutions: Neon photo moment. |  | 05 Experiential | Build | SGT-37
7000.05.01-XOS-004 | 7000.05.01 | Immersive Set or Room · Base | experience | Y | 5700 | Expense · Experience | CC-VENUE | each | 1200 | 1800 | 2600 | Single themed corner set with a prop and lighting. | Zone: Exhibition Room. Tier fit: T2; T4. Upgrades: Multi-room immersive set. Add-ons: Attendant + content capture. Substitutions: Backdrop photo wall. |  | 05 Experiential | Build | SGT-35
7000.05.01-XOS-005 | 7000.05.01 | Immersive Set or Room · Elevated | experience | Y | 5700 | Expense · Experience | CC-VENUE | each | 2500 | 3600 | 5200 | Built themed vignette room guests step into for content. | Zone: Exhibition Room. Tier fit: T2; T4. Upgrades: Multi-room immersive set. Add-ons: Attendant + content capture. Substitutions: Backdrop photo wall. |  | 05 Experiential | Build | SGT-35
7000.05.01-XOS-006 | 7000.05.01 | Immersive Set or Room · Premium | experience | Y | 5700 | Expense · Experience | CC-VENUE | each | 5000 | 7500 | 11000 | Full immersive themed environment with scenic, lighting, and a signature hero prop. | Zone: Exhibition Room. Tier fit: T2; T4. Upgrades: Multi-room immersive set. Add-ons: Attendant + content capture. Substitutions: Backdrop photo wall. |  | 05 Experiential | Build | SGT-35
7000.05.01-XPMS-003 | 7000.05.01 | Instant Print Photo Station | equipment | X | 5700 | Expense · Experience | CC-VENUE | each | 650 | 850 | 1150 | Photo station with dye-sub printing, branded templates, and digital delivery. |  |  | 05 Experiential | Operate
7000.05.01-XOS-007 | 7000.05.01 | Interactive or 360 Booth · Base | experience | Y | 5700 | Expense · Experience | CC-VENUE | each | 650 | 950 | 1400 | Open-air photo booth with branded print template. | Zone: All Zones. Tier fit: T1; T4. Upgrades: AI content studio; live gallery. Add-ons: Glam / GIF station. Substitutions: Roaming photographer. |  | 05 Experiential | Build | SGT-36
7000.05.01-XOS-008 | 7000.05.01 | Interactive or 360 Booth · Elevated | experience | Y | 5700 | Expense · Experience | CC-VENUE | each | 1250 | 1850 | 2650 | 360 spin booth with branded overlay and instant share. | Zone: All Zones. Tier fit: T1; T4. Upgrades: AI content studio; live gallery. Add-ons: Glam / GIF station. Substitutions: Roaming photographer. |  | 05 Experiential | Build | SGT-36
7000.05.01-XOS-009 | 7000.05.01 | Interactive or 360 Booth · Premium | experience | Y | 5700 | Expense · Experience | CC-VENUE | each | 2450 | 3500 | 5000 | Premium 360 / AI content studio with custom motion templates and live gallery. | Zone: All Zones. Tier fit: T1; T4. Upgrades: AI content studio; live gallery. Add-ons: Glam / GIF station. Substitutions: Roaming photographer. |  | 05 Experiential | Build | SGT-36
7000.05.01-XOS-010 | 7000.05.01 | Neon or Light Moment · Base | experience | Y | 5700 | Expense · Experience | CC-VENUE | each | 350 | 500 | 750 | Single neon catchphrase sign on a painted wall. | Zone: Exhibition Room. Tier fit: T1; T4. Upgrades: Infinity mirror room; reactive light. Add-ons: Custom neon phrase. Substitutions: Floral moment instead. |  | 05 Experiential | Build | SGT-38
7000.05.01-XOS-011 | 7000.05.01 | Neon or Light Moment · Elevated | experience | Y | 5700 | Expense · Experience | CC-VENUE | each | 650 | 950 | 1450 | Neon-on-textured-wall moment with foreground styling. | Zone: Exhibition Room. Tier fit: T1; T4. Upgrades: Infinity mirror room; reactive light. Add-ons: Custom neon phrase. Substitutions: Floral moment instead. |  | 05 Experiential | Build | SGT-38
7000.05.01-XOS-012 | 7000.05.01 | Neon or Light Moment · Premium | experience | Y | 5700 | Expense · Experience | CC-VENUE | each | 1250 | 1850 | 2650 | Multi-element light room with neon, mirrors, and reactive lighting. | Zone: Exhibition Room. Tier fit: T1; T4. Upgrades: Infinity mirror room; reactive light. Add-ons: Custom neon phrase. Substitutions: Floral moment instead. |  | 05 Experiential | Build | SGT-38
7000.05.01-XPMS-001 | 7000.05.01 | Photo Moment or Step-and-Repeat | service | Y | 5700 | Expense · Experience | CC-VENUE | each | 2500 | 3500 | 5000 | Photo moment design and build. |  |  | 05 Experiential | Operate
7000.05.01-XOS-013 | 7000.05.01 | Step-and-Repeat · Base | experience | Y | 5700 | Expense · Experience | CC-VENUE | each | 450 | 650 | 950 | 8x8 printed step-and-repeat with brand logos and a carpet runner. | Zone: Entrance / Lobby. Tier fit: T1; T4. Upgrades: Backlit logo wall; styled foreground. Add-ons: Press riser; photographer. Substitutions: Branded backdrop wall. |  | 05 Experiential | Build | SGT-34
7000.05.01-XOS-014 | 7000.05.01 | Step-and-Repeat · Elevated | experience | Y | 5700 | Expense · Experience | CC-VENUE | each | 850 | 1250 | 1850 | Tensioned-fabric step-and-repeat with lit header and floor mark. | Zone: Entrance / Lobby. Tier fit: T1; T4. Upgrades: Backlit logo wall; styled foreground. Add-ons: Press riser; photographer. Substitutions: Branded backdrop wall. |  | 05 Experiential | Build | SGT-34
7000.05.01-XOS-015 | 7000.05.01 | Step-and-Repeat · Premium | experience | Y | 5700 | Expense · Experience | CC-VENUE | each | 1650 | 2450 | 3550 | Dimensional step-and-repeat with backlit logos and a styled foreground set. | Zone: Entrance / Lobby. Tier fit: T1; T4. Upgrades: Backlit logo wall; styled foreground. Add-ons: Press riser; photographer. Substitutions: Branded backdrop wall. |  | 05 Experiential | Build | SGT-34
7000.06.01-XPMS-001 | 7000.06.01 | Curated Gift or Welcome Amenity | service | Y | 5700 | Expense · Experience | CC-VENUE | each | 2500 | 3500 | 5000 | Curated gifting and welcome amenities. |  |  | 05 Experiential | Operate
7000.06.02-XPMS-001 | 7000.06.02 | Branded Swag & Premiums | service | Y | 5700 | Expense · Experience | CC-VENUE | each | 3500 | 5000 | 7500 | Branded premiums and giveaways. |  |  | 05 Experiential | Operate
7000.07.01-XPMS-003 | 7000.07.01 | Proof-of-Performance Report | service | Y | 5700 | Expense · Experience | CC-VENUE | each | 1800 | 2500 | 3500 | Photo-documented audit of delivered sponsor assets with impressions and recap deck. |  |  | 02 Digital | Amplify
7000.07.01-XPMS-001 | 7000.07.01 | Sponsor Asset Production Coordination | service | Y | 5700 | Expense · Experience | CC-VENUE | each | 3500 | 5000 | 7500 | Coordinator trafficking sponsor logos, proofs, and asset production across fabrication and digital. |  |  | 05 Experiential | Advance
7000.07.01-XPMS-002 | 7000.07.01 | Sponsor Booth Turnkey Package - 10x10 | equipment | X | 5700 | Expense · Experience | CC-VENUE | each | 1500 | 2000 | 2800 | Turnkey 10x10 sponsor footprint: structure, counter, graphics, power drop, and furniture. |  |  | 05 Experiential | Install
7000.07.01-XPMS-004 | 7000.07.01 | Sponsor Hospitality Allocation Management | service | Y | 5700 | Expense · Experience | CC-VENUE | each | 2500 | 3500 | 5000 | Management of sponsor ticket banks, VIP allocations, and on-site hosting obligations. |  |  | 05 Experiential | Operate
7000.07.01-XPMS-005 | 7000.07.01 | Sponsor Recap & Fulfilment Evidence | service | Y | 5700 | Expense · Experience | CC-VENUE | each | 2500 | 3500 | 5000 | Compilation of contracted sponsor deliverables with dated photographic and measurement evidence for each. This is where a sponsorship contract is actually satisfied or actually breached, so gate 8 blocks on it. |  |  | 05 Experiential | Amplify
7000.08.01-XPMS-006 | 7000.08.01 | Custom Interactive Experience Development | service | Y | 5700 | Expense · Experience | CC-VENUE | each | 7500 | 12000 | 18000 | Custom software build for games, configurators, or immersive interactives to brief. |  |  | 03 Virtual | Scope
7000.08.01-XPMS-008 | 7000.08.01 | Experiential Moments or Interactive Touchpoints | package | X | 5700 | Expense · Experience | CC-VENUE | each | 3500 | 5000 | 7500 | Interactive touchpoints. |  |  | 04 Physical | Build
7000.08.01-XPMS-005 | 7000.08.01 | Gesture-Controlled Display Experience | equipment | X | 5700 | Expense · Experience | CC-VENUE | each | 1200 | 1600 | 2200 | Camera-tracked gesture interface driving screen content without touch. |  |  | 05 Experiential | Operate
7000.08.01-XPMS-004 | 7000.08.01 | Interactive Floor Projection System | equipment | X | 5700 | Expense · Experience | CC-VENUE | each | 1800 | 2500 | 3500 | Downward projection with IR tracking creating reactive floor games and effects. |  |  | 05 Experiential | Operate
7000.08.01-XPMS-001 | 7000.08.01 | Interactive Touchscreen Kiosk - 55in | equipment | X | 5700 | Expense · Experience | CC-VENUE | each | 650 | 850 | 1150 | Freestanding 55-inch touch kiosk with custom interactive content loaded. |  |  | 05 Experiential | Operate
7000.08.01-XPMS-007 | 7000.08.01 | Live Photo Mosaic Wall | equipment | X | 5700 | Expense · Experience | CC-VENUE | each | 2500 | 3500 | 5000 | Guest photos print and assemble live into a large mosaic brand image. |  |  | 05 Experiential | Operate
7000.08.01-XPMS-002 | 7000.08.01 | Motion-Reactive Interactive Wall | equipment | X | 5700 | Expense · Experience | CC-VENUE | each | 2500 | 3500 | 5000 | Sensor-driven projection or LED wall reacting to guest movement; includes tech. |  |  | 05 Experiential | Operate
7000.08.01-XPMS-003 | 7000.08.01 | RFID Guest Engagement System | equipment | X | 5700 | Expense · Experience | CC-VENUE | each | 1500 | 2200 | 3200 | Wristband-triggered experiences, photo tagging, and data capture across activation stations. |  |  | 02 Digital | Operate
7000.50.01-XOS-001 | 7000.50.01 | Front of House Leadership | service | Y | 5700 | Expense · Experience | CC-VENUE | lump sum | 4500 | 6500 | 9500 | Representative line for front of house leadership so the category can carry cost. Replace with the specific item on award. |  |  | 04 Physical | Procure | 7000.50.01-XOS-001
7000.50.02-XOS-001 | 7000.50.02 | Credential Check | service | Y | 5700 | Expense · Experience | CC-VENUE | lump sum | 2500 | 3500 | 5000 | Representative line for credential check so the category can carry cost. Replace with the specific item on award. |  |  | 04 Physical | Procure | 7000.50.02-XOS-001
7000.50.03-XOS-001 | 7000.50.03 | Guest Services | service | Y | 5700 | Expense · Experience | CC-VENUE | lump sum | 2500 | 3500 | 5000 | Representative line for guest services so the category can carry cost. Replace with the specific item on award. |  |  | 04 Physical | Procure | 7000.50.03-XOS-001
7000.50.04-XOS-001 | 7000.50.04 | Coat Check | service | Y | 5700 | Expense · Experience | CC-VENUE | lump sum | 1500 | 2200 | 3200 | Representative line for coat check so the category can carry cost. Replace with the specific item on award. |  |  | 04 Physical | Procure | 7000.50.04-XOS-001
7000.51.01-XOS-001 | 7000.51.01 | Event Medical | service | Y | 5700 | Expense · Experience | CC-VENUE | lump sum | 3500 | 5000 | 7500 | Representative line for event medical so the category can carry cost. Replace with the specific item on award. |  |  | 04 Physical | Procure | 7000.51.01-XOS-001
7000.60.01-XOS-001 | 7000.60.01 | Scope Activities · Experience | service | Y | 5700 | Expense · Experience | CC-E00 | lump sum | 3500 | 5000 | 7500 | Representative line for scope activities so the category can carry cost. Replace with the specific item on award. |  |  | 04 Physical | Scope | 7000.60.01-XOS-001
7000.60.02-XOS-001 | 7000.60.02 | Engage Activities · Experience | service | Y | 5700 | Expense · Experience | CC-E00 | lump sum | 3500 | 5000 | 7500 | Representative line for engage activities so the category can carry cost. Replace with the specific item on award. |  |  | 04 Physical | Engage | 7000.60.02-XOS-001
7000.60.03-XOS-001 | 7000.60.03 | Advance Activities · Experience | service | Y | 5700 | Expense · Experience | CC-E00 | lump sum | 2500 | 3500 | 5000 | Representative line for advance activities so the category can carry cost. Replace with the specific item on award. |  |  | 04 Physical | Advance | 7000.60.03-XOS-001
7000.60.04-XOS-001 | 7000.60.04 | Procure Activities · Experience | service | Y | 5700 | Expense · Experience | CC-E00 | lump sum | 2500 | 3500 | 5000 | Representative line for procure activities so the category can carry cost. Replace with the specific item on award. |  |  | 04 Physical | Procure | 7000.60.04-XOS-001
7000.60.05-XOS-001 | 7000.60.05 | Build Activities · Experience | service | Y | 5700 | Expense · Experience | CC-E00 | lump sum | 3500 | 5000 | 7500 | Representative line for build activities so the category can carry cost. Replace with the specific item on award. |  |  | 04 Physical | Build | 7000.60.05-XOS-001
7000.60.06-XOS-001 | 7000.60.06 | Install Activities · Experience | service | Y | 5700 | Expense · Experience | CC-E00 | lump sum | 4500 | 6500 | 9500 | Representative line for install activities so the category can carry cost. Replace with the specific item on award. |  |  | 04 Physical | Install | 7000.60.06-XOS-001
7000.60.07-XOS-001 | 7000.60.07 | Operate Activities · Experience | service | Y | 5700 | Expense · Experience | CC-E00 | lump sum | 6500 | 9500 | 14000 | Representative line for operate activities so the category can carry cost. Replace with the specific item on award. |  |  | 04 Physical | Operate | 7000.60.07-XOS-001
7000.60.08-XOS-001 | 7000.60.08 | Amplify Activities · Experience | service | Y | 5700 | Expense · Experience | CC-E00 | lump sum | 3500 | 5000 | 7500 | Representative line for amplify activities so the category can carry cost. Replace with the specific item on award. |  |  | 04 Physical | Amplify | 7000.60.08-XOS-001
7000.60.09-XOS-001 | 7000.60.09 | Close Activities · Experience | service | Y | 5700 | Expense · Experience | CC-E00 | lump sum | 5500 | 7500 | 11000 | Representative line for close activities so the category can carry cost. Replace with the specific item on award. |  |  | 04 Physical | Close | 7000.60.09-XOS-001
8000.01.01-XPMS-006 | 8000.01.01 | Bar or Catering Staff | package | X | 5800 | Expense · Hospitality | CC-VENUE | each | 4500 | 6500 | 9500 | Hospitality · Bar / catering staff. |  |  | 04 Physical | Operate
8000.01.01-XPMS-001 | 8000.01.01 | Beverage Service | catering | Y | 5800 | Expense · Hospitality | CC-VENUE | lot | 2500 | 3500 | 5000 | Non-alcoholic beverage service for guests or crew. | Water, soft drinks, juice, coffee, and tea ¦ Coolers and ice. | 336 | 04 Physical | Operate
8000.01.01-XOS-001 | 8000.01.01 | Branded or Logo Ftd F&B · Base | experience | Y | 5800 | Expense · Hospitality | CC-VENUE | each | 10 | 12 | 14 | Logo cocktail napkins and pick flags. | Zone: All Zones. Tier fit: T1; T4. Upgrades: Edible logo / custom imaging. Add-ons: Custom packaging program. Substitutions: Standard service ware. |  | 04 Physical | Show | TST-12
8000.01.01-XOS-002 | 8000.01.01 | Branded or Logo Ftd F&B · Elevated | experience | Y | 5800 | Expense · Hospitality | CC-VENUE | each | 2.5 | 4.5 | 7.5 | Branded drinkware, edible logo prints, and custom garnishes. | Zone: All Zones. Tier fit: T1; T4. Upgrades: Edible logo / custom imaging. Add-ons: Custom packaging program. Substitutions: Standard service ware. |  | 04 Physical | Show | TST-12
8000.01.01-XOS-003 | 8000.01.01 | Branded or Logo Ftd F&B · Premium | experience | Y | 5800 | Expense · Hospitality | CC-VENUE | each | 6 | 9.5 | 15 | Fully branded F&B story: custom packaging, edible imaging, and named menu items. | Zone: All Zones. Tier fit: T1; T4. Upgrades: Edible logo / custom imaging. Add-ons: Custom packaging program. Substitutions: Standard service ware. |  | 04 Physical | Show | TST-12
8000.01.01-XPMS-002 | 8000.01.01 | Catering Package - VIP | catering | Y | 5800 | Expense · Hospitality | CC-VENUE | lot | 12 | 18 | 28 | Elevated food and beverage service for VIP guests. | Passed hors d'oeuvres, stations, premium beverages, dessert. | 336 | 04 Physical | Operate
8000.01.01-XOS-004 | 8000.01.01 | Coffee or Café Program · Base | experience | Y | 5800 | Expense · Hospitality | CC-VENUE | each | 85 | 100 | 115 | Drip coffee and tea service. | Zone: El Patio. Tier fit: T1; T4. Upgrades: Branded café build; latte art. Add-ons: Cold brew / nitro tap. Substitutions: Self-serve coffee station. |  | 04 Physical | Show | TST-11
8000.01.01-XOS-005 | 8000.01.01 | Coffee or Café Program · Elevated | experience | Y | 5800 | Expense · Hospitality | CC-VENUE | each | 4.5 | 6.5 | 9 | Espresso cart with barista and a couple of signature drinks. | Zone: El Patio. Tier fit: T1; T4. Upgrades: Branded café build; latte art. Add-ons: Cold brew / nitro tap. Substitutions: Self-serve coffee station. |  | 04 Physical | Show | TST-11
8000.01.01-XOS-006 | 8000.01.01 | Coffee or Café Program · Premium | experience | Y | 5800 | Expense · Hospitality | CC-VENUE | each | 8.5 | 12 | 16 | Branded café experience with specialty drinks, latte art, and to-go cups. | Zone: El Patio. Tier fit: T1; T4. Upgrades: Branded café build; latte art. Add-ons: Cold brew / nitro tap. Substitutions: Self-serve coffee station. |  | 04 Physical | Show | TST-11
8000.01.01-XOS-007 | 8000.01.01 | Dessert or Sweets · Base | experience | Y | 5800 | Expense · Hospitality | CC-VENUE | each | 6 | 8.5 | 12 | Plated or passed single dessert. | Zone: El Patio. Tier fit: T1; T4. Upgrades: Live dessert action station. Add-ons: Artist-themed confection. Substitutions: No dessert course. |  | 04 Physical | Show | TST-06
8000.01.01-XOS-008 | 8000.01.01 | Dessert or Sweets · Elevated | experience | Y | 5800 | Expense · Hospitality | CC-VENUE | each | 12 | 16 | 22 | Dessert station with multiple sweets and a signature item. | Zone: El Patio. Tier fit: T1; T4. Upgrades: Live dessert action station. Add-ons: Artist-themed confection. Substitutions: No dessert course. |  | 04 Physical | Show | TST-06
8000.01.01-XOS-009 | 8000.01.01 | Dessert or Sweets · Premium | experience | Y | 5800 | Expense · Hospitality | CC-VENUE | each | 20 | 28 | 38 | Dessert showpiece or live dessert action station with artist-themed sweets. | Zone: El Patio. Tier fit: T1; T4. Upgrades: Live dessert action station. Add-ons: Artist-themed confection. Substitutions: No dessert course. |  | 04 Physical | Show | TST-06
8000.01.01-XOS-028 | 8000.01.01 | F&B Aromatics (Live Cues) · Base | experience | Y | 5800 | Expense · Hospitality | CC-VENUE | each | 250 | 350 | 500 | Coffee/espresso aroma from the café position. | Zone: El Patio. Tier fit: T1; T4. Upgrades: Aroma-timed to journey beats. Add-ons: Smoke / wood-fire cue. Substitutions: No live aromatics. |  | 04 Physical | Show | SCT-05
8000.01.01-XOS-029 | 8000.01.01 | F&B Aromatics (Live Cues) · Elevated | experience | Y | 5800 | Expense · Hospitality | CC-VENUE | each | 450 | 650 | 900 | Live aromatic cues (grill, citrus, herbs) from open finishing stations. | Zone: El Patio. Tier fit: T1; T4. Upgrades: Aroma-timed to journey beats. Add-ons: Smoke / wood-fire cue. Substitutions: No live aromatics. |  | 04 Physical | Show | SCT-05
8000.01.01-XOS-030 | 8000.01.01 | F&B Aromatics (Live Cues) · Premium | experience | Y | 5800 | Expense · Hospitality | CC-VENUE | each | 850 | 1200 | 1650 | Choreographed aroma-and-taste pairings timed to the guest journey. | Zone: El Patio. Tier fit: T1; T4. Upgrades: Aroma-timed to journey beats. Add-ons: Smoke / wood-fire cue. Substitutions: No live aromatics. |  | 04 Physical | Show | SCT-05
8000.01.01-XPMS-003 | 8000.01.01 | Food Truck - Contracted | catering | Y | 5800 | Expense · Hospitality | CC-VENUE | lot | 1025 | 1200 | 1375 | Contracted food truck vendor for guest or crew service. | Full menu, specialty cuisine, or branded options. | 672 | 04 Physical | Operate
8000.01.01-XOS-010 | 8000.01.01 | Late-Night Bites · Base | experience | Y | 5800 | Expense · Hospitality | CC-VENUE | each | 12 | 16 | 22 | One late-night snack pass (e.g., sliders or churros). | Zone: Main Stage and Bar. Tier fit: T1; T4. Upgrades: Branded food cart build. Add-ons: To-go boxed snack. Substitutions: No late-night service. |  | 04 Physical | Show | TST-05
8000.01.01-XOS-011 | 8000.01.01 | Late-Night Bites · Elevated | experience | Y | 5800 | Expense · Hospitality | CC-VENUE | each | 22 | 30 | 40 | Late-night street-food cart with two to three items. | Zone: Main Stage and Bar. Tier fit: T1; T4. Upgrades: Branded food cart build. Add-ons: To-go boxed snack. Substitutions: No late-night service. |  | 04 Physical | Show | TST-05
8000.01.01-XOS-012 | 8000.01.01 | Late-Night Bites · Premium | experience | Y | 5800 | Expense · Hospitality | CC-VENUE | each | 35 | 48 | 65 | Signature late-night moment with a branded cart and culturally rooted snacks. | Zone: Main Stage and Bar. Tier fit: T1; T4. Upgrades: Branded food cart build. Add-ons: To-go boxed snack. Substitutions: No late-night service. |  | 04 Physical | Show | TST-05
8000.01.01-XOS-013 | 8000.01.01 | Mocktail or Non-Alc Program · Base | experience | Y | 5800 | Expense · Hospitality | CC-VENUE | each | 8 | 12 | 16 | Two non-alcoholic options at the bar. | Zone: Main Stage and Bar. Tier fit: T1; T4. Upgrades: Craft non-alc spirit bar. Add-ons: Functional / wellness drinks. Substitutions: Soft drinks only. |  | 04 Physical | Show | TST-10
8000.01.01-XOS-014 | 8000.01.01 | Mocktail or Non-Alc Program · Elevated | experience | Y | 5800 | Expense · Hospitality | CC-VENUE | each | 14 | 18 | 25 | Dedicated mocktail menu matched to the cocktail program. | Zone: Main Stage and Bar. Tier fit: T1; T4. Upgrades: Craft non-alc spirit bar. Add-ons: Functional / wellness drinks. Substitutions: Soft drinks only. |  | 04 Physical | Show | TST-10
8000.01.01-XOS-015 | 8000.01.01 | Mocktail or Non-Alc Program · Premium | experience | Y | 5800 | Expense · Hospitality | CC-VENUE | each | 22 | 28 | 38 | Full zero-proof bar with craft non-alc spirits and a named menu. | Zone: Main Stage and Bar. Tier fit: T1; T4. Upgrades: Craft non-alc spirit bar. Add-ons: Functional / wellness drinks. Substitutions: Soft drinks only. |  | 04 Physical | Show | TST-10
8000.01.01-XOS-016 | 8000.01.01 | Passed Canapés & Bites · Base | experience | Y | 5800 | Expense · Hospitality | CC-VENUE | each | 18 | 25 | 35 | Three passed bites on standard service for the first hour. | Zone: All Zones. Tier fit: T1; T4. Upgrades: Live finishing station; caviar bump. Add-ons: Dietary / allergen flagged set. Substitutions: Stationed grazing instead. |  | 04 Physical | Show | TST-01
8000.01.01-XOS-017 | 8000.01.01 | Passed Canapés & Bites · Elevated | experience | Y | 5800 | Expense · Hospitality | CC-VENUE | each | 32 | 42 | 56 | Five chef-designed passed canapés with dietary options, full reception coverage. | Zone: All Zones. Tier fit: T1; T4. Upgrades: Live finishing station; caviar bump. Add-ons: Dietary / allergen flagged set. Substitutions: Stationed grazing instead. |  | 04 Physical | Show | TST-01
8000.01.01-XOS-018 | 8000.01.01 | Passed Canapés & Bites · Premium | experience | Y | 5800 | Expense · Hospitality | CC-VENUE | each | 55 | 75 | 105 | Curated passed-bite progression with premium ingredients and live finishing stations. | Zone: All Zones. Tier fit: T1; T4. Upgrades: Live finishing station; caviar bump. Add-ons: Dietary / allergen flagged set. Substitutions: Stationed grazing instead. |  | 04 Physical | Show | TST-01
8000.01.01-XOS-019 | 8000.01.01 | Premium or Top-Shelf Spirits · Base | experience | Y | 5800 | Expense · Hospitality | CC-VENUE | each | 18 | 24 | 32 | Call-brand spirits at the main bar. | Zone: Main Stage and Bar. Tier fit: T2; T4. Upgrades: Reserve tasting moment; premium glass. Add-ons: Sponsor spirit integration. Substitutions: Call-brand only. |  | 04 Physical | Show | TST-09
8000.01.01-XOS-020 | 8000.01.01 | Premium or Top-Shelf Spirits · Elevated | experience | Y | 5800 | Expense · Hospitality | CC-VENUE | each | 28 | 38 | 50 | Top-shelf spirit selection with branded backbar display. | Zone: Main Stage and Bar. Tier fit: T2; T4. Upgrades: Reserve tasting moment; premium glass. Add-ons: Sponsor spirit integration. Substitutions: Call-brand only. |  | 04 Physical | Show | TST-09
8000.01.01-XOS-021 | 8000.01.01 | Premium or Top-Shelf Spirits · Premium | experience | Y | 5800 | Expense · Hospitality | CC-VENUE | each | 45 | 60 | 85 | Reserve / luxury spirit program with a tasting moment and premium glassware. | Zone: Main Stage and Bar. Tier fit: T2; T4. Upgrades: Reserve tasting moment; premium glass. Add-ons: Sponsor spirit integration. Substitutions: Call-brand only. |  | 04 Physical | Show | TST-09
8000.01.01-XOS-022 | 8000.01.01 | Signature Cocktail Program · Base | experience | Y | 5800 | Expense · Hospitality | CC-VENUE | each | 14 | 18 | 24 | Two batched signature cocktails plus standard bar. | Zone: Main Stage and Bar. Tier fit: T1; T4. Upgrades: Premium spirit tier; smoke / theater garnish. Add-ons: Named after set / song titles. Substitutions: Beer-and-wine only. |  | 04 Physical | Show | TST-07
8000.01.01-XOS-023 | 8000.01.01 | Signature Cocktail Program · Elevated | experience | Y | 5800 | Expense · Hospitality | CC-VENUE | each | 22 | 28 | 38 | Three to four art-directed signature cocktails with garnish program. | Zone: Main Stage and Bar. Tier fit: T1; T4. Upgrades: Premium spirit tier; smoke / theater garnish. Add-ons: Named after set / song titles. Substitutions: Beer-and-wine only. |  | 04 Physical | Show | TST-07
8000.01.01-XOS-024 | 8000.01.01 | Signature Cocktail Program · Premium | experience | Y | 5800 | Expense · Hospitality | CC-VENUE | each | 34 | 45 | 60 | Full craft cocktail menu with named drinks, premium spirits, and theater garnishes. | Zone: Main Stage and Bar. Tier fit: T1; T4. Upgrades: Premium spirit tier; smoke / theater garnish. Add-ons: Named after set / song titles. Substitutions: Beer-and-wine only. |  | 04 Physical | Show | TST-07
8000.01.01-XPMS-004 | 8000.01.01 | Station - Dessert | catering | Y | 5800 | Expense · Hospitality | CC-VENUE | lot | 340 | 400 | 460 | Dedicated dessert display or live dessert service station. | Plated desserts, dessert bar, ice cream cart, or custom. | 336 | 04 Physical | Operate
8000.01.01-XOS-025 | 8000.01.01 | Stationed or Grazing Tables · Base | experience | Y | 5800 | Expense · Hospitality | CC-VENUE | each | 18 | 25 | 35 | Single grazing table with cheese, charcuterie, and crudité. | Zone: El Patio. Tier fit: T1; T4. Upgrades: Sculptural grazing build. Add-ons: Regional / artist-themed station. Substitutions: Passed bites instead. |  | 04 Physical | Show | TST-02
8000.01.01-XOS-026 | 8000.01.01 | Stationed or Grazing Tables · Elevated | experience | Y | 5800 | Expense · Hospitality | CC-VENUE | each | 32 | 42 | 56 | Multiple themed grazing stations with attendant carving and dips. | Zone: El Patio. Tier fit: T1; T4. Upgrades: Sculptural grazing build. Add-ons: Regional / artist-themed station. Substitutions: Passed bites instead. |  | 04 Physical | Show | TST-02
8000.01.01-XOS-027 | 8000.01.01 | Stationed or Grazing Tables · Premium | experience | Y | 5800 | Expense · Hospitality | CC-VENUE | each | 55 | 75 | 105 | Designed grazing landscape with sculptural display and premium selections. | Zone: El Patio. Tier fit: T1; T4. Upgrades: Sculptural grazing build. Add-ons: Regional / artist-themed station. Substitutions: Passed bites instead. |  | 04 Physical | Show | TST-02
8000.01.01-XPMS-005 | 8000.01.01 | Supplies & Consumables (base) | opex | X | 5800 | Expense · Hospitality | CC-VENUE | each | 1500 | 2200 | 3200 | Hospitality · Supplies and Consumables (base). |  |  | 04 Physical | Operate
8000.01.02-XOS-001 | 8000.01.02 | Artist-Rooted Cultural Menu · Base | experience | Y | 5800 | Expense · Hospitality | CC-VENUE | each | 25 | 35 | 48 | One signature dish referencing the artist's culture (e.g., Argentine empanadas). | Zone: El Patio. Tier fit: T1; T4. Upgrades: Guest-chef collaboration. Add-ons: Bilingual menu storytelling. Substitutions: Standard reception menu. |  | 04 Physical | Show | TST-03
8000.01.02-XOS-002 | 8000.01.02 | Artist-Rooted Cultural Menu · Elevated | experience | Y | 5800 | Expense · Hospitality | CC-VENUE | each | 45 | 60 | 80 | Multi-course menu rooted in the artist's heritage with regional ingredients. | Zone: El Patio. Tier fit: T1; T4. Upgrades: Guest-chef collaboration. Add-ons: Bilingual menu storytelling. Substitutions: Standard reception menu. |  | 04 Physical | Show | TST-03
8000.01.02-XOS-003 | 8000.01.02 | Artist-Rooted Cultural Menu · Premium | experience | Y | 5800 | Expense · Hospitality | CC-VENUE | each | 75 | 105 | 145 | Chef-collaboration tasting menu authentically rooted in the artist's culture and region. | Zone: El Patio. Tier fit: T1; T4. Upgrades: Guest-chef collaboration. Add-ons: Bilingual menu storytelling. Substitutions: Standard reception menu. |  | 04 Physical | Show | TST-03
8000.01.02-XPMS-007 | 8000.01.02 | Build-Phase Crew Meals & Hydration | service | Y | 5800 | Expense · Hospitality | CC-VENUE | each | 3500 | 5000 | 7500 | Crew meals during build. |  |  | 04 Physical | Build
8000.01.02-XPMS-001 | 8000.01.02 | Coffee Service | catering | Y | 5800 | Expense · Hospitality | CC-VENUE | lot | 170 | 200 | 230 | Dedicated coffee and espresso bar for crew or VIP. | Drip coffee, espresso machine, cold brew, or pour-over. | 336 | 04 Physical | Operate
8000.01.02-XPMS-002 | 8000.01.02 | Craft Services | catering | Y | 5800 | Expense · Hospitality | CC-VENUE | lot | 300 | 350 | 400 | All-day snack and beverage station for crew and production. | Snacks, fruit, coffee, water, sodas, energy drinks, candy. | 336 | 04 Physical | Operate
8000.01.02-XPMS-003 | 8000.01.02 | EDC LV · Mainstage Crew Catering Pack | catering | Y | 5800 | Expense · Hospitality | CC-VENUE | lot | 1800 | 2400 | 3200 | Auto-created during 0063 backfill from deliverables.07a084d4-45be-4c7b-8a73-161ad6345aef. |  |  | 04 Physical | Operate
8000.01.02-XPMS-004 | 8000.01.02 | Meal Service - Artist | catering | Y | 5800 | Expense · Hospitality | CC-VENUE | lot | 38 | 44 | 50 | Hot meal service for artists and talent per rider specifications. | Entree plus 2 sides, salad, dessert, and beverages ¦ Dietary accommodations. | 336 | 04 Physical | Operate
8000.01.02-XPMS-005 | 8000.01.02 | Meal Service - Crew | catering | Y | 5800 | Expense · Hospitality | CC-VENUE | lot | 21 | 25 | 29 | Hot meal service for production crew and staff. | Entree plus 2 sides, salad, and beverage ¦ Buffet style. | 336 | 04 Physical | Operate
8000.01.02-XPMS-006 | 8000.01.02 | Water and Ice Service | catering | Y | 5800 | Expense · Hospitality | CC-VENUE | lot | 105 | 125 | 145 | Bulk water and ice delivery for crew hydration. | 5-gallon jugs, coolers, bulk ice, and dispensers. | 336 | 04 Physical | Operate
8000.01.03-XOS-001 | 8000.01.03 | Beer & Wine Service · Base | experience | Y | 5800 | Expense · Hospitality | CC-VENUE | each | 12 | 16 | 22 | House beer and wine selection. | Zone: Main Stage and Bar. Tier fit: T1; T4. Upgrades: Sommelier-curated list. Add-ons: Local-brewery feature. Substitutions: Cocktail program instead. |  | 04 Physical | Show | TST-08
8000.01.03-XOS-002 | 8000.01.03 | Beer & Wine Service · Elevated | experience | Y | 5800 | Expense · Hospitality | CC-VENUE | each | 18 | 24 | 32 | Curated regional beer and wine list in palette with the menu. | Zone: Main Stage and Bar. Tier fit: T1; T4. Upgrades: Sommelier-curated list. Add-ons: Local-brewery feature. Substitutions: Cocktail program instead. |  | 04 Physical | Show | TST-08
8000.01.03-XOS-003 | 8000.01.03 | Beer & Wine Service · Premium | experience | Y | 5800 | Expense · Hospitality | CC-VENUE | each | 28 | 36 | 48 | Premium and artist-region wine/beer program with sommelier guidance. | Zone: Main Stage and Bar. Tier fit: T1; T4. Upgrades: Sommelier-curated list. Add-ons: Local-brewery feature. Substitutions: Cocktail program instead. |  | 04 Physical | Show | TST-08
8000.01.03-XPMS-001 | 8000.01.03 | Chafing Dish | catering | Y | 5800 | Expense · Hospitality | CC-VENUE | lot | 17 | 20 | 23 | Stainless steel chafer for buffet hot food service. | Full-size, half-size, or round ¦ With fuel cans. | 48 | 04 Physical | Operate
8000.01.03-XPMS-002 | 8000.01.03 | Dispenser - Beverage | catering | Y | 5800 | Expense · Hospitality | CC-VENUE | lot | 13 | 15 | 17 | Large beverage dispenser for self-serve stations. | 3 gallon or 5 gallon ¦ Insulated and glass options. | 48 | 04 Physical | Operate
8000.01.03-XPMS-003 | 8000.01.03 | Flatware and China - Rental | catering | Y | 5800 | Expense · Hospitality | CC-VENUE | lot | 7 | 8 | 9 | Rental place settings for plated service. | Dinner plate, salad plate, bread plate, full flatware, and charger. | 48 | 04 Physical | Operate
8000.01.03-XPMS-004 | 8000.01.03 | Linen - Table | catering | Y | 5800 | Expense · Hospitality | CC-VENUE | lot | 10 | 12 | 14 | Table linen rental with sizing and color options. | 90x90 through 120in round ¦ Runners and napkins. | 48 | 04 Physical | Operate
8000.01.03-XOS-004 | 8000.01.03 | Plated Dinner Service · Base | experience | Y | 5800 | Expense · Hospitality | CC-VENUE | each | 45 | 65 | 90 | Two-course plated dinner with one entrée choice. | Zone: El Patio. Tier fit: T2; T4. Upgrades: Sommelier pairing; tableside finish. Add-ons: Chef's-table seating. Substitutions: Family-style service. |  | 04 Physical | Show | TST-04
8000.01.03-XOS-005 | 8000.01.03 | Plated Dinner Service · Elevated | experience | Y | 5800 | Expense · Hospitality | CC-VENUE | each | 75 | 105 | 145 | Three-course plated dinner with protein/vegetarian choice and wine pairing. | Zone: El Patio. Tier fit: T2; T4. Upgrades: Sommelier pairing; tableside finish. Add-ons: Chef's-table seating. Substitutions: Family-style service. |  | 04 Physical | Show | TST-04
8000.01.03-XOS-006 | 8000.01.03 | Plated Dinner Service · Premium | experience | Y | 5800 | Expense · Hospitality | CC-VENUE | each | 125 | 175 | 245 | Multi-course tasting with sommelier pairing and tableside finishing. | Zone: El Patio. Tier fit: T2; T4. Upgrades: Sommelier pairing; tableside finish. Add-ons: Chef's-table seating. Substitutions: Family-style service. |  | 04 Physical | Show | TST-04
8000.01.03-XPMS-005 | 8000.01.03 | Utensils and Trays | catering | Y | 5800 | Expense · Hospitality | CC-VENUE | lot | 26 | 30 | 34 | Serving spoons, tongs, trays, and platters for catering. | Various types and materials. | 48 | 04 Physical | Operate
8000.01.04-XPMS-001 | 8000.01.04 | Grill - Portable | catering | Y | 5800 | Expense · Hospitality | CC-VENUE | lot | 105 | 125 | 145 | Freestanding commercial-grade grill for outdoor events. | 24in through 48in ¦ Multiple fuel types. | 168 | 04 Physical | Operate
8000.01.04-XPMS-002 | 8000.01.04 | Ice Machine - Portable | catering | Y | 5800 | Expense · Hospitality | CC-VENUE | lot | 130 | 150 | 170 | Temporary ice-making machine for high-volume events. | 250, 500, or 1,000 lb per day ¦ With bin. | 168 | 04 Physical | Operate
8000.01.04-XPMS-003 | 8000.01.04 | Kitchen Trailer - Mobile | catering | Y | 5800 | Expense · Hospitality | CC-VENUE | lot | 1275 | 1500 | 1725 | Fully equipped mobile kitchen trailer for on-site cooking. | 16ft through 36ft ¦ With hood, cooktop, oven, fridge, and handwash. | 672 | 04 Physical | Operate
8000.01.04-XPMS-004 | 8000.01.04 | Prep Table - Stainless | catering | Y | 5800 | Expense · Hospitality | CC-VENUE | lot | 26 | 30 | 34 | Stainless steel prep table for food preparation. | 24x48 through 30x72 ¦ With undershelf and backsplash options. | 168 | 04 Physical | Operate
8000.01.04-XPMS-005 | 8000.01.04 | Refrigerator - Portable | catering | Y | 5800 | Expense · Hospitality | CC-VENUE | lot | 170 | 200 | 230 | Temporary refrigeration for food and beverage storage. | Reach-in 1-door through walk-in 8x20 ¦ Freezer options. | 168 | 04 Physical | Operate
8000.01.04-XPMS-007 | 8000.01.04 | Supplemental Kitchen or Staff Kitchen Fit | package | X | 5800 | Expense · Hospitality | CC-VENUE | each | 4500 | 6500 | 9500 | Staff kitchenette + minor adaptations only. |  |  | 04 Physical | Build
8000.01.04-XPMS-006 | 8000.01.04 | Warmer - Food Holding | catering | Y | 5800 | Expense · Hospitality | CC-VENUE | lot | 50 | 60 | 70 | Portable food warming cabinet or steam table for hot holding. | Half-size, full-size, or steam table ¦ Heat lamp options. | 168 | 04 Physical | Operate
8000.02.01-XPMS-001 | 8000.02.01 | Bar - Portable | catering | Y | 5800 | Expense · Hospitality | CC-VENUE | lot | 300 | 350 | 400 | Freestanding portable bar with speed rail and ice well. | 6ft or 8ft ¦ Custom available ¦ With sink ¦ LED-lit options. | 168 | 04 Physical | Operate
8000.02.01-XPMS-008 | 8000.02.01 | Bar Equipment Package | package | X | 5800 | Expense · Hospitality | CC-VENUE | each | 3500 | 4800 | 6500 | Ice, refrigeration, espresso, juice. |  |  | 04 Physical | Build
8000.02.01-XPMS-002 | 8000.02.01 | Beer System - Draft | catering | Y | 5800 | Expense · Hospitality | CC-VENUE | lot | 210 | 250 | 290 | Mobile draft beer dispensing system with jockey box or glycol. | 2-tap through 8-tap ¦ Glycol long-draw available. | 168 | 04 Physical | Operate
8000.02.01-XPMS-003 | 8000.02.01 | Display - Back Bar | catering | Y | 5800 | Expense · Hospitality | CC-VENUE | lot | 65 | 75 | 85 | Illuminated back bar shelving for bottle display. | 3-tier or 4-tier ¦ LED-lit and mirrored options. | 168 | 04 Physical | Operate
8000.02.01-XPMS-006 | 8000.02.01 | Frozen Drink Machine - Dual Bowl | equipment | X | 5800 | Expense · Hospitality | CC-VENUE | each | 120 | 160 | 210 | Dual-bowl frozen beverage machine with NSF certification. |  |  | 05 Experiential | Operate
8000.02.01-XPMS-004 | 8000.02.01 | Ice Bin - Portable | catering | Y | 5800 | Expense · Hospitality | CC-VENUE | lot | 65 | 75 | 85 | Portable ice maker or insulated ice storage bin. | 100 lb through 500 lb ¦ Ice maker option. | 168 | 04 Physical | Operate
8000.02.01-XPMS-007 | 8000.02.01 | Kegerator - Dual Tap | equipment | X | 5800 | Expense · Hospitality | CC-VENUE | each | 140 | 180 | 240 | Dual-tap refrigerated keg dispenser with CO2 system. |  |  | 05 Experiential | Operate
8000.02.01-XPMS-005 | 8000.02.01 | Kit - Bar Tools | catering | Y | 5800 | Expense · Hospitality | CC-VENUE | lot | 42 | 48.5 | 55 | Complete bartender tool kit with speed rail, shakers, and pourers. | Speed rail, shaker set, jiggers, strainers, muddler, pourers, bar mats. | 168 | 04 Physical | Operate
8000.02.01-XPMS-009 | 8000.02.01 | Smallwares + Bar Service Kit | package | Y | 5800 | Expense · Hospitality | CC-VENUE | each | 1200 | 1800 | 2600 | Glassware, tools, service kit. |  |  | 04 Physical | Build
8000.02.02-XPMS-001 | 8000.02.02 | Drinkware - Disposable | catering | Y | 5800 | Expense · Hospitality | CC-VENUE | lot | 50 | 60 | 70 | Single-use cups and drinkware for high-volume events. | 16oz through 24oz ¦ Plastic, compostable, or aluminum. | 24 | 04 Physical | Operate
8000.02.02-XPMS-002 | 8000.02.02 | Glassware - Rental | catering | Y | 5800 | Expense · Hospitality | CC-VENUE | lot | 1.7 | 2 | 2.3 | Rental glassware for bar service. | Rocks, highball, wine, champagne, pint, shot, or martini. | 24 | 04 Physical | Operate
8000.02.02-XPMS-003 | 8000.02.02 | Kit - Garnish and Mixers | catering | Y | 5800 | Expense · Hospitality | CC-VENUE | lot | 50 | 60 | 70 | Pre-portioned garnish and mixer kit for craft cocktails. | Citrus, herbs, simple syrup, tonic, bitters, and specialty items. | 24 | 04 Physical | Operate
8000.03.01-XPMS-001 | 8000.03.01 | Cart - Beverage | catering | Y | 5800 | Expense · Hospitality | CC-VENUE | lot | 105 | 125 | 145 | Rolling beverage cart for roaming drink service. | Iced beverages, pre-mixed cocktails, beer and wine, or non-alcoholic. | 168 | 04 Physical | Operate
8000.03.01-XPMS-002 | 8000.03.01 | Cart - Specialty Food | catering | Y | 5800 | Expense · Hospitality | CC-VENUE | lot | 300 | 350 | 400 | Specialty mobile cart for single-product food service. | Coffee, gelato, popcorn, cotton candy, or pretzel. | 168 | 04 Physical | Operate
8000.03.01-XPMS-003 | 8000.03.01 | Concession Stand | catering | Y | 5800 | Expense · Hospitality | CC-VENUE | lot | 425 | 500 | 575 | Pop-up or built concession stand for food sales. | 8ft through 12ft window ¦ With equipment or shell only. | 168 | 04 Physical | Operate
8000.04.01-XPMS-001 | 8000.04.01 | Booth - Guest Services | catering | Y | 5800 | Expense · Hospitality | CC-VENUE | lot | 150 | 175 | 200 | Staffed information booth for guest assistance and wayfinding. | Table or kiosk ¦ Signage ¦ Staff ¦ FAQ materials. | 48 | 04 Physical | Operate
8000.04.01-XPMS-002 | 8000.04.01 | Charging Station - Phone | catering | Y | 5800 | Expense · Hospitality | CC-VENUE | lot | 105 | 125 | 145 | Shared phone charging station for guests or crew. | 8-port, 16-port, locker-style, or wireless. | 48 | 04 Physical | Operate
8000.04.01-XPMS-003 | 8000.04.01 | Coat Check | catering | Y | 5800 | Expense · Hospitality | CC-VENUE | lot | 210 | 250 | 290 | Staffed coat check or bag storage service. | Racks, tickets, staff, and secure area. | 48 | 04 Physical | Operate
8000.04.01-XPMS-005 | 8000.04.01 | El Balcón or Mezzanine VIP Lounge Fit-Out | package | X | 5800 | Expense · Hospitality | CC-VENUE | each | 6500 | 9500 | 14000 | Lounge furniture, finishes, rail + accent lighting for mezzanine VIP. |  |  | 04 Physical | Build
8000.04.01-XPMS-004 | 8000.04.01 | Station - Lost and Found | catering | Y | 5800 | Expense · Hospitality | CC-VENUE | lot | 65 | 75 | 85 | Organized lost and found collection and return station. | Bins, log book or app, signage, and staff. | 48 | 04 Physical | Operate
8000.04.02-XPMS-001 | 8000.04.02 | Bottle Service - VIP | catering | Y | 5800 | Expense · Hospitality | CC-VENUE | lot | 300 | 350 | 400 | VIP table and bottle service with sparklers, mixers, and ice. | Table, bucket, sparklers, mixers, ice, and server. | 168 | 04 Physical | Operate
8000.04.02-XPMS-002 | 8000.04.02 | Hookah Lounge | catering | Y | 5800 | Expense · Hospitality | CC-VENUE | lot | 340 | 400 | 460 | Hookah lounge setup with hookahs, coals, flavors, and seating. | 2 to 4 hookahs ¦ Coals ¦ Flavors ¦ Low seating ¦ Tent or canopy. | 336 | 04 Physical | Operate
8000.04.02-XPMS-003 | 8000.04.02 | Lounge - VIP | catering | Y | 5800 | Expense · Hospitality | CC-VENUE | lot | 1275 | 1500 | 1725 | Complete VIP lounge area with furniture, decor, and service. | Lounge seating, tables, decor, lighting, and rope or stanchion. | 336 | 04 Physical | Operate
8000.04.02-XPMS-004 | 8000.04.02 | Roaming Champagne & Beverage Cart | equipment | X | 5800 | Expense · Hospitality | CC-VENUE | each | 180 | 240 | 320 | Styled roaming cart for champagne or specialty beverage service in VIP zones. |  |  | 05 Experiential | Operate
8000.04.03-XPMS-001 | 8000.04.03 | Dressing Room | catering | Y | 5800 | Expense · Hospitality | CC-VENUE | lot | 210 | 250 | 290 | Private dressing and changing room with mirror, lighting, and rack. | Mirror, lighting, garment rack, steamer, and seating. | 168 | 04 Physical | Operate
8000.04.03-XPMS-002 | 8000.04.03 | Green Room | catering | Y | 5800 | Expense · Hospitality | CC-VENUE | lot | 425 | 500 | 575 | Artist green room hospitality package per rider. | Furniture, refreshments, towels, mirror, garment rack, and snacks per rider. | 168 | 04 Physical | Operate
8000.04.03-XPMS-003 | 8000.04.03 | Per Diem - Artist | catering | Y | 5800 | Expense · Hospitality | CC-VENUE | lot | 65 | 75 | 85 | Cash per diem or meal buyout in lieu of provided catering. | Per rider specification ¦ Cash or prepaid card. | 168 | 04 Physical | Operate
8000.04.03-XPMS-004 | 8000.04.03 | Rider Fulfillment | catering | Y | 5800 | Expense · Hospitality | CC-VENUE | lot | 170 | 200 | 230 | Miscellaneous rider items including specific brands, towels, and candles. | Per artist or talent rider ¦ Itemized procurement. | 168 | 04 Physical | Operate
8000.04.04-XPMS-001 | 8000.04.04 | Furniture Set - Lounge | equipment | X | 5800 | Expense · Hospitality | CC-VENUE | each | 300 | 350 | 400 | Styled lounge seating group with sofa, chairs, and coffee table. |  |  | 04 Physical | Procure
8000.04.04-XPMS-002 | 8000.04.04 | Ottoman | equipment | X | 5800 | Expense · Hospitality | CC-VENUE | each | 26 | 30 | 34 | Accent seating ottoman or pouf for lounge areas. |  |  | 04 Physical | Procure
8000.04.04-XPMS-003 | 8000.04.04 | Stool - Bar | equipment | X | 5800 | Expense · Hospitality | CC-VENUE | each | 8 | 10 | 12 | Tall seating for bars and high-top tables. |  |  | 04 Physical | Procure
8000.05.01-XPMS-001 | 8000.05.01 | Hotel Block - Group Rate | lodging | X | 5800 | Expense · Hospitality | CC-VENUE | each | 110 | 130 | 150 | Negotiated group rate hotel block for production team. |  |  | 04 Physical | Advance
8000.05.01-XPMS-002 | 8000.05.01 | Hotel Room - Standard | lodging | X | 5800 | Expense · Hospitality | CC-VENUE | each | 130 | 150 | 170 | Standard hotel room for crew and production staff. |  |  | 04 Physical | Advance
8000.05.01-XPMS-003 | 8000.05.01 | Hotel Suite - Premium | lodging | X | 5800 | Expense · Hospitality | CC-VENUE | each | 425 | 500 | 575 | Suite or premium room for talent and senior production. |  |  | 04 Physical | Advance
8000.05.02-XPMS-002 | 8000.05.02 | RV - Motorhome | lodging | X | 5800 | Expense · Hospitality | CC-VENUE | each | 300 | 350 | 400 | RV or motorhome for mobile talent or crew accommodation. |  |  | 04 Physical | Advance
8000.05.02-XPMS-001 | 8000.05.02 | Rental - Vacation | lodging | X | 5800 | Expense · Hospitality | CC-VENUE | each | 210 | 250 | 290 | Short-term rental house or apartment for crew or talent. |  |  | 04 Physical | Advance
8000.06.01-XPMS-003 | 8000.06.01 | Box Office Staff | labor | Y | 5800 | Expense · Hospitality | CC-VENUE | each | 180 | 220 | 280 | Will-call and box-office attendant handling lists, comps, and on-site sales. |  |  | 05 Experiential | Operate
8000.06.01-XPMS-001 | 8000.06.01 | FOH Manager | labor | Y | 5800 | Expense · Hospitality | CC-VENUE | each | 600 | 750 | 900 | Front-of-house manager owning doors, ingress flow, and guest-facing staff. |  |  | 05 Experiential | Operate
8000.06.01-XPMS-002 | 8000.06.01 | Usher or Guest Services Staff | labor | Y | 5800 | Expense · Hospitality | CC-VENUE | each | 150 | 180 | 220 | Trained usher for seating, directions, and guest assistance; 10-hr day. |  |  | 05 Experiential | Operate
8000.50.01-XOS-001 | 8000.50.01 | Bartending | service | Y | 5800 | Expense · Hospitality | CC-VENUE | lump sum | 350 | 450 | 550 | Representative line for bartending so the category can carry cost. Replace with the specific item on award. |  |  | 04 Physical | Procure | 8000.50.01-XOS-001
8000.50.02-XOS-001 | 8000.50.02 | Bar Support | service | Y | 5800 | Expense · Hospitality | CC-VENUE | lump sum | 200 | 250 | 320 | Representative line for bar support so the category can carry cost. Replace with the specific item on award. |  |  | 04 Physical | Procure | 8000.50.02-XOS-001
8000.51.01-XOS-001 | 8000.51.01 | Catering Supervision | service | Y | 5800 | Expense · Hospitality | CC-VENUE | lump sum | 450 | 550 | 700 | Representative line for catering supervision so the category can carry cost. Replace with the specific item on award. |  |  | 04 Physical | Procure | 8000.51.01-XOS-001
8000.51.02-XOS-001 | 8000.51.02 | Catering Service | service | Y | 5800 | Expense · Hospitality | CC-VENUE | lump sum | 200 | 260 | 340 | Representative line for catering service so the category can carry cost. Replace with the specific item on award. |  |  | 04 Physical | Procure | 8000.51.02-XOS-001
8000.51.03-XOS-001 | 8000.51.03 | Food and Beverage Provision | service | Y | 5800 | Expense · Hospitality | CC-VENUE | lump sum | 4500 | 6500 | 9500 | Representative line for food and beverage provision so the category can carry cost. Replace with the specific item on award. |  |  | 04 Physical | Procure | 8000.51.03-XOS-001
8000.52.01-XOS-001 | 8000.52.01 | Linen and Furniture Rental | service | Y | 5800 | Expense · Hospitality | CC-VENUE | lump sum | 1500 | 2200 | 3200 | Representative line for linen and furniture rental so the category can carry cost. Replace with the specific item on award. |  |  | 04 Physical | Procure | 8000.52.01-XOS-001
8000.60.01-XOS-001 | 8000.60.01 | Scope Activities · Hospitality | service | Y | 5800 | Expense · Hospitality | CC-E00 | lump sum | 3500 | 5000 | 7500 | Representative line for scope activities so the category can carry cost. Replace with the specific item on award. |  |  | 04 Physical | Scope | 8000.60.01-XOS-001
8000.60.02-XOS-001 | 8000.60.02 | Engage Activities · Hospitality | service | Y | 5800 | Expense · Hospitality | CC-E00 | lump sum | 3500 | 5000 | 7500 | Representative line for engage activities so the category can carry cost. Replace with the specific item on award. |  |  | 04 Physical | Engage | 8000.60.02-XOS-001
8000.60.03-XOS-001 | 8000.60.03 | Advance Activities · Hospitality | service | Y | 5800 | Expense · Hospitality | CC-E00 | lump sum | 2500 | 3500 | 5000 | Representative line for advance activities so the category can carry cost. Replace with the specific item on award. |  |  | 04 Physical | Advance | 8000.60.03-XOS-001
8000.60.04-XOS-001 | 8000.60.04 | Procure Activities · Hospitality | service | Y | 5800 | Expense · Hospitality | CC-E00 | lump sum | 2500 | 3500 | 5000 | Representative line for procure activities so the category can carry cost. Replace with the specific item on award. |  |  | 04 Physical | Procure | 8000.60.04-XOS-001
8000.60.05-XOS-001 | 8000.60.05 | Build Activities · Hospitality | service | Y | 5800 | Expense · Hospitality | CC-E00 | lump sum | 3500 | 5000 | 7500 | Representative line for build activities so the category can carry cost. Replace with the specific item on award. |  |  | 04 Physical | Build | 8000.60.05-XOS-001
8000.60.06-XOS-001 | 8000.60.06 | Install Activities · Hospitality | service | Y | 5800 | Expense · Hospitality | CC-E00 | lump sum | 4500 | 6500 | 9500 | Representative line for install activities so the category can carry cost. Replace with the specific item on award. |  |  | 04 Physical | Install | 8000.60.06-XOS-001
8000.60.07-XOS-001 | 8000.60.07 | Operate Activities · Hospitality | service | Y | 5800 | Expense · Hospitality | CC-E00 | lump sum | 6500 | 9500 | 14000 | Representative line for operate activities so the category can carry cost. Replace with the specific item on award. |  |  | 04 Physical | Operate | 8000.60.07-XOS-001
8000.60.08-XOS-001 | 8000.60.08 | Amplify Activities · Hospitality | service | Y | 5800 | Expense · Hospitality | CC-E00 | lump sum | 3500 | 5000 | 7500 | Representative line for amplify activities so the category can carry cost. Replace with the specific item on award. |  |  | 04 Physical | Amplify | 8000.60.08-XOS-001
8000.60.09-XOS-001 | 8000.60.09 | Close Activities · Hospitality | service | Y | 5800 | Expense · Hospitality | CC-E00 | lump sum | 5500 | 7500 | 11000 | Representative line for close activities so the category can carry cost. Replace with the specific item on award. |  |  | 04 Physical | Close | 8000.60.09-XOS-001
9000.01.01-XPMS-004 | 9000.01.01 | Cat6 Cable Run Package | equipment | X | 5900 | Expense · Technology | CC-VENUE | each | 4500 | 6500 | 9500 | Terminated Cat6 runs with protective covering between network nodes. |  |  | 02 Digital | Install
9000.01.01-XPMS-002 | 9000.01.01 | Enterprise Wireless Access Point | equipment | X | 5900 | Expense · Technology | CC-VENUE | each | 350 | 450 | 600 | Enterprise AP node extending managed WiFi coverage. |  |  | 02 Digital | Operate
9000.01.01-XPMS-005 | 9000.01.01 | Event Core Router or Firewall | equipment | X | 5900 | Expense · Technology | CC-VENUE | each | 120 | 160 | 220 | Core routing and firewall appliance segmenting production, vendor, and guest networks. |  |  | 02 Digital | Operate
9000.01.01-XPMS-006 | 9000.01.01 | IT Helpdesk Technician | labor | Y | 5900 | Expense · Technology | CC-VENUE | each | 350 | 450 | 600 | On-site tech supporting printers, laptops, credentials systems, and AV-adjacent IT. |  |  | 02 Digital | Operate
9000.01.01-XPMS-008 | 9000.01.01 | IT Room Build: Rack, Server, UPS | service | Y | 5900 | Expense · Technology | CC-VENUE | each | 450 | 550 | 700 | Core IT room. |  |  | 04 Physical | Build
9000.01.01-XOS-001 | 9000.01.01 | Interactive or Kinetic Installation · Base | experience | Y | 5900 | Expense · Technology | CC-VENUE | each | 3500 | 5000 | 7500 | Simple touch or motion-triggered light piece. | Zone: Exhibition Room. Tier fit: T3; T4. Upgrades: Gesture / app control; data capture. Add-ons: Custom content design. Substitutions: Static art piece. |  | 05 Experiential | Build | SGT-31
9000.01.01-XOS-002 | 9000.01.01 | Interactive or Kinetic Installation · Elevated | experience | Y | 5900 | Expense · Technology | CC-VENUE | each | 850 | 1200 | 1650 | Sensor-driven interactive installation guests can influence. | Zone: Exhibition Room. Tier fit: T3; T4. Upgrades: Gesture / app control; data capture. Add-ons: Custom content design. Substitutions: Static art piece. |  | 05 Experiential | Build | SGT-31
9000.01.01-XOS-003 | 9000.01.01 | Interactive or Kinetic Installation · Premium | experience | Y | 5900 | Expense · Technology | CC-VENUE | each | 1850 | 2600 | 3600 | Bespoke interactive artwork with app or gesture control and data capture. | Zone: Exhibition Room. Tier fit: T3; T4. Upgrades: Gesture / app control; data capture. Add-ons: Custom content design. Substitutions: Static art piece. |  | 05 Experiential | Build | SGT-31
9000.01.01-XPMS-001 | 9000.01.01 | Managed Network Switch - 24 or 48 Port | equipment | X | 5900 | Expense · Technology | CC-VENUE | each | 3800 | 5200 | 7200 | Managed gigabit switch with VLAN config for production networks. |  |  | 02 Digital | Operate
9000.01.01-XPMS-003 | 9000.01.01 | Network Engineer or NOC Tech | labor | Y | 5900 | Expense · Technology | CC-VENUE | each | 120 | 160 | 220 | Engineer building and monitoring the production network through show. |  |  | 02 Digital | Operate
9000.01.01-XPMS-010 | 9000.01.01 | Podcast Production Tech | service | Y | 5900 | Expense · Technology | CC-VENUE | each | 3500 | 5000 | 7500 | Interfaces, recorders, storage. |  |  | 04 Physical | Build
9000.01.01-XPMS-007 | 9000.01.01 | Rack UPS Battery Backup | equipment | X | 5900 | Expense · Technology | CC-VENUE | each | 120 | 160 | 220 | Rack-mount UPS protecting network core and show-critical compute. |  |  | 02 Digital | Operate
9000.01.01-XPMS-009 | 9000.01.01 | Venue Network: Switches, WAPs, Cabling | service | Y | 5900 | Expense · Technology | CC-VENUE | each | 7500 | 11000 | 16000 | Structured cabling + WiFi. |  |  | 04 Physical | Build
9000.02.01-XPMS-001 | 9000.02.01 | Network - Ethernet - Temp | equipment | X | 5900 | Expense · Technology | CC-VENUE | each | 30 | 35 | 40 | Temporary ethernet infrastructure for production and POS. |  |  | 04 Physical | Install
9000.02.01-XPMS-004 | 9000.02.01 | Satellite Internet Kit - LEO | equipment | X | 5900 | Expense · Technology | CC-VENUE | each | 450 | 600 | 800 | Low-earth-orbit satellite internet terminal for venues without terrestrial service. |  |  | 02 Digital | Operate
9000.02.01-XPMS-002 | 9000.02.01 | Signal Booster - Cellular | equipment | X | 5900 | Expense · Technology | CC-VENUE | each | 2125 | 2500 | 2875 | Temporary distributed antenna system or cellular booster. |  |  | 04 Physical | Install
9000.02.01-XPMS-003 | 9000.02.01 | WiFi Network - Temporary | equipment | X | 5900 | Expense · Technology | CC-VENUE | each | 1700 | 2000 | 2300 | Managed WiFi network for event operations and guest access. |  |  | 04 Physical | Install
9000.03.01-XPMS-001 | 9000.03.01 | Charger - Radio - Multi-Bay | radio | X | 5900 | Expense · Technology | CC-VENUE | each | 21 | 25 | 29 | 6-unit or 12-unit charging station for radios. |  |  | 04 Physical | Procure
9000.03.01-XPMS-002 | 9000.03.01 | Motorola XPR7550 Two-Way Radio | radio | X | 5900 | Expense · Technology | CC-VENUE | each | 550 | 650 | 750 | UHF digital radio, 5W, 1000 channels. |  |  | 04 Physical | Procure
9000.03.01-XPMS-003 | 9000.03.01 | Radio - Two-Way - Digital | radio | X | 5900 | Expense · Technology | CC-VENUE | each | 26 | 30 | 34 | Advanced digital radio for large-scale operations. | Motorola SL300 ¦ XPR 7550e ¦ Hytera PD682. | 168 | 04 Physical | Procure
9000.03.01-XPMS-004 | 9000.03.01 | Radio - Two-Way - Standard | radio | X | 5900 | Expense · Technology | CC-VENUE | each | 13 | 15 | 17 | UHF or VHF handheld two-way radio for event operations. |  |  | 04 Physical | Procure
9000.03.01-XPMS-005 | 9000.03.01 | Repeater - Radio | radio | X | 5900 | Expense · Technology | CC-VENUE | each | 105 | 125 | 145 | Signal repeater to extend radio coverage across large sites. |  |  | 04 Physical | Procure
9000.03.02-XPMS-001 | 9000.03.02 | Intercom - Wired | radio | X | 5900 | Expense · Technology | CC-VENUE | each | 50 | 60 | 70 | Hard-wired intercom for stage management and production. |  |  | 04 Physical | Procure
9000.03.02-XPMS-002 | 9000.03.02 | Intercom - Wireless | radio | X | 5900 | Expense · Technology | CC-VENUE | each | 85 | 100 | 115 | Digital wireless intercom for mobile production staff. |  |  | 04 Physical | Procure
9000.04.01-XPMS-005 | 9000.04.01 | Guest Check-In or Invite-List Tech | package | X | 5900 | Expense · Technology | CC-VENUE | each | 1500 | 2200 | 3200 | Tablets + software. |  |  | 04 Physical | Build
9000.04.01-XPMS-001 | 9000.04.01 | Metal Detector - Handheld | credential | X | 5900 | Expense · Technology | CC-VENUE | each | 13 | 15 | 17 | Portable wand metal detector for secondary screening. |  |  | 04 Physical | Advance
9000.04.01-XPMS-002 | 9000.04.01 | Metal Detector - Walk-Through | credential | X | 5900 | Expense · Technology | CC-VENUE | each | 150 | 175 | 200 | Walk-through metal detector for venue entry screening. |  |  | 04 Physical | Advance
9000.04.01-XPMS-003 | 9000.04.01 | Scanner - RFID Access | credential | X | 5900 | Expense · Technology | CC-VENUE | each | 105 | 125 | 145 | Automated access control scanning for credentialed entry. |  |  | 04 Physical | Advance
9000.04.01-XPMS-004 | 9000.04.01 | Scanner Station - Ticket | credential | X | 5900 | Expense · Technology | CC-VENUE | each | 65 | 75 | 85 | Ticket scanning hardware and box office setup. |  |  | 04 Physical | Advance
9000.05.01-XPMS-001 | 9000.05.01 | ATM - Portable | equipment | X | 5900 | Expense · Technology | CC-VENUE | each | 210 | 250 | 290 | Portable ATM for cash access at events. |  |  | 04 Physical | Procure
9000.05.01-XPMS-004 | 9000.05.01 | Digital Asset Archive & Handover | service | Y | 5900 | Expense · Technology | CC-VENUE | each | 2500 | 3500 | 5000 | Ingest, catalogue and handover of master assets to the archive of record with retention terms and access rights stated. The creative record; Close hands over the commercial one. |  |  | 05 Experiential | Amplify
9000.05.01-XPMS-002 | 9000.05.01 | POS System - Mobile | equipment | X | 5900 | Expense · Technology | CC-VENUE | each | 42 | 48.5 | 55 | Mobile point-of-sale system for merch and concession sales. |  |  | 04 Physical | Procure
9000.05.01-XPMS-003 | 9000.05.01 | Supplies - Cash Handling | equipment | X | 5900 | Expense · Technology | CC-VENUE | each | 50 | 60 | 70 | Cash drawer, coin changer, counterfeit detector, and money bags. |  |  | 04 Physical | Procure
9000.06.01-XPMS-010 | 9000.06.01 | Attendance & Engagement Analysis | service | Y | 5900 | Expense · Technology | CC-VENUE | each | 3500 | 5000 | 7500 | Analysis of attendance, dwell, throughput and engagement from access control, network and sensor data against the objectives set at Discover. |  |  | 05 Experiential | Amplify
9000.06.01-XPMS-001 | 9000.06.01 | Attendance Analytics Platform | service | Y | 5900 | Expense · Technology | CC-VENUE | each | 2500 | 3500 | 5000 | Scan- and sensor-based attendance counting with live dashboard. |  |  | 02 Digital | Operate
9000.06.01-XPMS-006 | 9000.06.01 | Content Storage or NAS | package | X | 5900 | Expense · Technology | CC-VENUE | each | 1500 | 2200 | 3200 | Capture pipeline storage. |  |  | 04 Physical | Build
9000.06.01-XPMS-002 | 9000.06.01 | Footfall & Heatmap Sensor Kit | equipment | X | 5900 | Expense · Technology | CC-VENUE | each | 650 | 950 | 1450 | Sensor array measuring dwell, flow, and zone heatmaps across the footprint. |  |  | 02 Digital | Operate
9000.06.01-XPMS-007 | 9000.06.01 | Internet, Data & Telecom | opex | X | 5900 | Expense · Technology | CC-VENUE | each | 2500 | 3500 | 5000 | Technology · Internet, Data and Telecom. |  |  | 04 Physical | Operate
9000.06.01-XPMS-004 | 9000.06.01 | Live Data Dashboard Setup | service | Y | 5900 | Expense · Technology | CC-VENUE | each | 3500 | 5000 | 7500 | Configuration of live event dashboard aggregating ticketing, POS, and access feeds. |  |  | 02 Digital | Advance
9000.06.01-XPMS-009 | 9000.06.01 | Livestream or Broadcast Tech | package | X | 5900 | Expense · Technology | CC-VENUE | each | 3500 | 5000 | 7500 | Technology · Livestream / broadcast tech. |  |  | 04 Physical | Operate
9000.06.01-XPMS-003 | 9000.06.01 | Post-Event Data & Insights Report | service | Y | 5900 | Expense · Technology | CC-VENUE | each | 2500 | 3500 | 5000 | Synthesis of scans, sales, social, and survey data into an insights and ROI report. |  |  | 02 Digital | Amplify
9000.06.01-XPMS-011 | 9000.06.01 | ROI & Objectives Measurement Report | service | Y | 5900 | Expense · Technology | CC-VENUE | each | 4500 | 6500 | 9500 | Measurement of outcomes against the objectives recorded at gate 1. Where no objectives were recorded, this report states that outcomes cannot be measured rather than substituting activity metrics for them. |  |  | 05 Experiential | Amplify
9000.06.01-XPMS-005 | 9000.06.01 | Social Listening & Sentiment Report | service | Y | 5900 | Expense · Technology | CC-VENUE | each | 2500 | 3500 | 5000 | Hashtag, mention, and sentiment analysis quantifying earned reach of the activation. |  |  | 02 Digital | Amplify
9000.06.01-XPMS-008 | 9000.06.01 | Software & Platform (ATLVS, POS, Ticketing) | opex | X | 5900 | Expense · Technology | CC-VENUE | each | 3500 | 5000 | 7500 | Technology · Software and Platform (ATLVS, POS, Ticketing). |  |  | 04 Physical | Operate
9000.07.01-XPMS-003 | 9000.07.01 | 360 Video Capture Rig | equipment | X | 5900 | Expense · Technology | CC-VENUE | each | 1200 | 1600 | 2200 | 360-degree camera rig with operator for immersive capture and recap content. |  |  | 03 Virtual | Operate
9000.07.01-XPMS-004 | 9000.07.01 | Holographic Fan Display - 65cm | equipment | X | 5900 | Expense · Technology | CC-VENUE | each | 250 | 350 | 480 | LED fan-array hologram unit displaying floating 3D brand content. |  |  | 05 Experiential | Operate
9000.07.01-XPMS-001 | 9000.07.01 | VR Headset Station - Managed | equipment | X | 5900 | Expense · Technology | CC-VENUE | each | 350 | 450 | 600 | Single VR station with headset, sanitation, attendant, and loaded experience. |  |  | 03 Virtual | Operate
9000.07.01-XPMS-002 | 9000.07.01 | WebAR Photo Experience Build | service | Y | 5900 | Expense · Technology | CC-VENUE | each | 4500 | 6500 | 9500 | Browser-based AR experience: face/world effects, branded capture, share flow. |  |  | 03 Virtual | Scope
9000.07.01-XPMS-005 | 9000.07.01 | XR Stage Calibration Service | service | Y | 5900 | Expense · Technology | CC-VENUE | each | 3500 | 5000 | 7500 | Camera-tracking and LED-volume calibration for XR / virtual-production capture. |  |  | 03 Virtual | Install
9000.07.01-XPMS-006 | 9000.07.01 | XR or Innovation Layer (Placeholder) | package | X | 5900 | Expense · Technology | CC-VENUE | each | 4500 | 6500 | 9500 | Future-proof placeholder. |  |  | 04 Physical | Build
9000.08.01-XPMS-001 | 9000.08.01 | Camera - Security - Temp | equipment | X | 5900 | Expense · Technology | CC-VENUE | each | 50 | 60 | 70 | Temporary security camera system for site monitoring. |  |  | 04 Physical | Procure
9000.08.01-XPMS-003 | 9000.08.01 | Guest-Data Privacy + Network Security | package | X | 5900 | Expense · Technology | CC-VENUE | each | 2500 | 3500 | 5000 | Privacy + network hardening. |  |  | 04 Physical | Build
9000.08.01-XPMS-002 | 9000.08.01 | Lighting - Security | equipment | X | 5900 | Expense · Technology | CC-VENUE | each | 30 | 35 | 40 | Temporary high-intensity security lighting. |  |  | 04 Physical | Procure
9000.09.01-XPMS-003 | 9000.09.01 | Battery Digital Poster Totem - 55in | equipment | X | 5900 | Expense · Technology | CC-VENUE | each | 250 | 350 | 480 | Battery-powered 55-inch digital poster on wheels with content loop. |  |  | 02 Digital | Operate
9000.09.01-XOS-001 | 9000.09.01 | Digital or Projection Art · Base | experience | Y | 5900 | Expense · Technology | CC-VENUE | each | 850 | 1200 | 1650 | Looping generative content on a single surface. | Zone: Exhibition Room. Tier fit: T2; T4. Upgrades: Generative live-reactive system. Add-ons: Artist content commission. Substitutions: Physical mural instead. |  | 02 Digital | Build | SGT-32
9000.09.01-XOS-002 | 9000.09.01 | Digital or Projection Art · Elevated | experience | Y | 5900 | Expense · Technology | CC-VENUE | each | 1850 | 2600 | 3600 | Multi-surface digital art with curated motion content. | Zone: Exhibition Room. Tier fit: T2; T4. Upgrades: Generative live-reactive system. Add-ons: Artist content commission. Substitutions: Physical mural instead. |  | 02 Digital | Build | SGT-32
9000.09.01-XOS-003 | 9000.09.01 | Digital or Projection Art · Premium | experience | Y | 5900 | Expense · Technology | CC-VENUE | each | 3800 | 5200 | 7200 | Full generative art environment, custom-commissioned and live-reactive. | Zone: Exhibition Room. Tier fit: T2; T4. Upgrades: Generative live-reactive system. Add-ons: Artist content commission. Substitutions: Physical mural instead. |  | 02 Digital | Build | SGT-32
9000.09.01-XOS-004 | 9000.09.01 | Digital or VMS Screens · Base | experience | Y | 5900 | Expense · Technology | CC-VENUE | each | 120 | 160 | 220 | Single portable screen looping a holding slide. | Zone: All Zones. Tier fit: T2; T4. Upgrades: Live content control + matrix. Add-ons: Outdoor-rated patio screen. Substitutions: Printed static signage. |  | 02 Digital | Build | SGT-21
9000.09.01-XOS-005 | 9000.09.01 | Digital or VMS Screens · Elevated | experience | Y | 5900 | Expense · Technology | CC-VENUE | each | 240 | 320 | 440 | Two to three networked screens with scheduled content per zone. | Zone: All Zones. Tier fit: T2; T4. Upgrades: Live content control + matrix. Add-ons: Outdoor-rated patio screen. Substitutions: Printed static signage. |  | 02 Digital | Build | SGT-21
9000.09.01-XOS-006 | 9000.09.01 | Digital or VMS Screens · Premium | experience | Y | 5900 | Expense · Technology | CC-VENUE | each | 480 | 650 | 900 | Integrated digital signage network with live content control and a message matrix. | Zone: All Zones. Tier fit: T2; T4. Upgrades: Live content control + matrix. Add-ons: Outdoor-rated patio screen. Substitutions: Printed static signage. |  | 02 Digital | Build | SGT-21
9000.09.01-XPMS-001 | 9000.09.01 | Kiosk - Digital | equipment | X | 5900 | Expense · Technology | CC-VENUE | each | 340 | 400 | 460 | Freestanding digital display kiosk for wayfinding or information. |  |  | 04 Physical | Install
9000.09.01-XPMS-002 | 9000.09.01 | Message Board - LED | equipment | X | 5900 | Expense · Technology | CC-VENUE | each | 170 | 200 | 230 | Programmable LED message display for announcements. |  |  | 04 Physical | Install
9000.09.01-XPMS-004 | 9000.09.01 | Signage CMS License & Scheduling | service | Y | 5900 | Expense · Technology | CC-VENUE | each | 1200 | 1800 | 2600 | Content-management licensing and dayparted scheduling across digital signage endpoints. |  |  | 02 Digital | Operate
9000.50.01-XOS-001 | 9000.50.01 | Audio System Design | service | Y | 5900 | Expense · Technology | CC-VENUE | lump sum | 4500 | 6500 | 9500 | Representative line for audio system design so the category can carry cost. Replace with the specific item on award. |  |  | 04 Physical | Procure | 9000.50.01-XOS-001
9000.50.02-XOS-001 | 9000.50.02 | Front of House Audio | service | Y | 5900 | Expense · Technology | CC-VENUE | lump sum | 650 | 850 | 1150 | Representative line for front of house audio so the category can carry cost. Replace with the specific item on award. |  |  | 04 Physical | Procure | 9000.50.02-XOS-001
9000.50.03-XOS-001 | 9000.50.03 | Stage Audio | service | Y | 5900 | Expense · Technology | CC-VENUE | lump sum | 550 | 750 | 1000 | Representative line for stage audio so the category can carry cost. Replace with the specific item on award. |  |  | 04 Physical | Procure | 9000.50.03-XOS-001
9000.50.04-XOS-001 | 9000.50.04 | Loudspeaker Supply | service | Y | 5900 | Expense · Technology | CC-VENUE | lump sum | 2500 | 3500 | 5000 | Representative line for loudspeaker supply so the category can carry cost. Replace with the specific item on award. |  |  | 04 Physical | Procure | 9000.50.04-XOS-001
9000.51.01-XOS-001 | 9000.51.01 | Lighting Operation | service | Y | 5900 | Expense · Technology | CC-VENUE | lump sum | 550 | 750 | 1000 | Representative line for lighting operation so the category can carry cost. Replace with the specific item on award. |  |  | 04 Physical | Procure | 9000.51.01-XOS-001
9000.51.02-XOS-001 | 9000.51.02 | Video Operation | service | Y | 5900 | Expense · Technology | CC-VENUE | lump sum | 550 | 750 | 1000 | Representative line for video operation so the category can carry cost. Replace with the specific item on award. |  |  | 04 Physical | Procure | 9000.51.02-XOS-001
9000.52.01-XOS-001 | 9000.52.01 | Network Provision | service | Y | 5900 | Expense · Technology | CC-VENUE | lump sum | 3500 | 5000 | 7500 | Representative line for network provision so the category can carry cost. Replace with the specific item on award. |  |  | 04 Physical | Procure | 9000.52.01-XOS-001
9000.52.02-XOS-001 | 9000.52.02 | Access Control and CCTV | service | Y | 5900 | Expense · Technology | CC-VENUE | lump sum | 2500 | 3500 | 5000 | Representative line for access control and cctv so the category can carry cost. Replace with the specific item on award. |  |  | 04 Physical | Procure | 9000.52.02-XOS-001
9000.52.03-XOS-001 | 9000.52.03 | Point of Sale | service | Y | 5900 | Expense · Technology | CC-VENUE | lump sum | 1800 | 2500 | 3500 | Representative line for point of sale so the category can carry cost. Replace with the specific item on award. |  |  | 04 Physical | Procure | 9000.52.03-XOS-001
9000.53.01-XOS-001 | 9000.53.01 | Audiovisual Integration | service | Y | 5900 | Expense · Technology | CC-VENUE | lump sum | 4500 | 6500 | 9500 | Representative line for audiovisual integration so the category can carry cost. Replace with the specific item on award. |  |  | 04 Physical | Procure | 9000.53.01-XOS-001
9000.60.01-XOS-001 | 9000.60.01 | Scope Activities · Technology | service | Y | 5900 | Expense · Technology | CC-E00 | lump sum | 3500 | 5000 | 7500 | Representative line for scope activities so the category can carry cost. Replace with the specific item on award. |  |  | 04 Physical | Scope | 9000.60.01-XOS-001
9000.60.02-XOS-001 | 9000.60.02 | Engage Activities · Technology | service | Y | 5900 | Expense · Technology | CC-E00 | lump sum | 3500 | 5000 | 7500 | Representative line for engage activities so the category can carry cost. Replace with the specific item on award. |  |  | 04 Physical | Engage | 9000.60.02-XOS-001
9000.60.03-XOS-001 | 9000.60.03 | Advance Activities · Technology | service | Y | 5900 | Expense · Technology | CC-E00 | lump sum | 2500 | 3500 | 5000 | Representative line for advance activities so the category can carry cost. Replace with the specific item on award. |  |  | 04 Physical | Advance | 9000.60.03-XOS-001
9000.60.04-XOS-001 | 9000.60.04 | Procure Activities · Technology | service | Y | 5900 | Expense · Technology | CC-E00 | lump sum | 2500 | 3500 | 5000 | Representative line for procure activities so the category can carry cost. Replace with the specific item on award. |  |  | 04 Physical | Procure | 9000.60.04-XOS-001
9000.60.05-XOS-001 | 9000.60.05 | Build Activities · Technology | service | Y | 5900 | Expense · Technology | CC-E00 | lump sum | 3500 | 5000 | 7500 | Representative line for build activities so the category can carry cost. Replace with the specific item on award. |  |  | 04 Physical | Build | 9000.60.05-XOS-001
9000.60.06-XOS-001 | 9000.60.06 | Install Activities · Technology | service | Y | 5900 | Expense · Technology | CC-E00 | lump sum | 4500 | 6500 | 9500 | Representative line for install activities so the category can carry cost. Replace with the specific item on award. |  |  | 04 Physical | Install | 9000.60.06-XOS-001
9000.60.07-XOS-001 | 9000.60.07 | Operate Activities · Technology | service | Y | 5900 | Expense · Technology | CC-E00 | lump sum | 6500 | 9500 | 14000 | Representative line for operate activities so the category can carry cost. Replace with the specific item on award. |  |  | 04 Physical | Operate | 9000.60.07-XOS-001
9000.60.08-XOS-001 | 9000.60.08 | Amplify Activities · Technology | service | Y | 5900 | Expense · Technology | CC-E00 | lump sum | 3500 | 5000 | 7500 | Representative line for amplify activities so the category can carry cost. Replace with the specific item on award. |  |  | 04 Physical | Amplify | 9000.60.08-XOS-001
9000.60.09-XOS-001 | 9000.60.09 | Close Activities · Technology | service | Y | 5900 | Expense · Technology | CC-E00 | lump sum | 5500 | 7500 | 11000 | Representative line for close activities so the category can carry cost. Replace with the specific item on award. |  |  | 04 Physical | Close | 9000.60.09-XOS-001

## Vendor Directory
VENDOR ID | ORGANIZATION | PROJECT ID | DEPARTMENT | CATEGORY | SUB CATEGORY | COMPANY | COUNTERPARTY TYPE | WEBSITE | PRIMARY CONTACT | PRIMARY EMAIL | PRIMARY PHONE | TAX ID | DEFAULT GL ACCOUNT | DEFAULT COST CENTER | PAYMENT TERMS | CONTRACT | W9 | ACH FORM | COI | INSURANCE EXPIRATION | ADDITIONAL INSURED | STATUS | FLAG | NOTES | CREATED BY | CREATED AT | UPDATED AT
VEN-001 | GHXSTSHIP | CSMIA26 | Logistics / Site Ops | VCL-002 | Production Freight | PRG Logistics | Logistics and Freight | https://prg.com | R. Kowalski | rkowalski@prg.com | (000) 000-1001 | 13-3928174 | 5500 | CC-VENUE | Net 30 | TRUE | TRUE | TRUE | TRUE | 2027-04-15 | TRUE | Active | FALSE | Lighting truss freight provider | Julian Clarkson | 2026-09-30 13:05 | 2026-09-30 13:05
VEN-002 | GHXSTSHIP | CSMIA26 | Site Operations | VCL-009 | Rental Services | Sunbelt Rentals | Equipment Rental | https://sunbeltrentals.com | Fuel Dispatch | dispatch@sunbeltrentals.com | (000) 000-1047 | 56-1284920 | 5500 | CC-VENUE | Net 30 | TRUE | TRUE | TRUE | TRUE | 2027-05-31 | TRUE | Active | FALSE | Generator fleet & fuel supplier | Julian Clarkson | 2026-09-30 13:05 | 2026-09-30 13:05
VEN-003 | GHXSTSHIP | CSMIA26 | Stage Operations | VCL-002 | Labor Services | Local 500 Stagehands | Equipment Rental |  | T. Evans | dispatch@iatse500.org | (000) 000-1058 | 59-0938271 | 5500 | CC-VENUE | Net 15 | TRUE | TRUE | TRUE | TRUE | 2027-06-30 | TRUE | Active | FALSE | Overhire stagehands crew lead | Julian Clarkson | 2026-09-30 13:05 | 2026-09-30 13:05
VEN-004 | GHXSTSHIP | CSMIA26 | Technical Production | VCL-002 | Production & Operations | Space Invaders | AV Integrator |  | Production Lead | ops@spaceinvaders.pro | (000) 000-0970 | 47-2819034 | 5900 | CC-VENUE | Net 30 | TRUE | TRUE | TRUE | TRUE | 2027-03-31 | TRUE | Active | FALSE | Technical audio/visual production | Julian Clarkson | 2026-09-30 13:05 | 2026-09-30 13:05
VEN-005 | GHXSTSHIP | CSMIA26 | Site Operations | VCL-002 | Site Lighting | Design Oasis | Equipment Rental | https://designoasis.com | Lighting Lead | info@designoasis.com | (000) 000-0981 | 65-0918234 | 5500 | CC-VENUE | Net 30 | TRUE | TRUE | TRUE | TRUE | 2027-04-30 | TRUE | Active | FALSE | Site and atmospheric lighting | Julian Clarkson | 2026-09-30 13:05 | 2026-09-30 13:05
VEN-006 | GHXSTSHIP | CSMIA26 | Security & Safety | VCL-007 | Government Agency | Hialeah Fire Department | Life Safety Services |  | Station Chief | firedept@hialeahfl.gov | (000) 000-0959 | 59-6000345 | 5600 | CC-VENUE | Net 30 | TRUE | FALSE | FALSE | TRUE | 2027-09-30 | TRUE | Active | FALSE | Emergency standby fire & rescue | Julian Clarkson | 2026-09-30 13:05 | 2026-09-30 13:05
VEN-007 | GHXSTSHIP | CSMIA26 | Catering & Hospitality | VCL-006 | Food & Beverage | Artisan Hospitality Services | Catering and Beverage |  | Chris Taylor | catering@artisanhospitality.com | (000) 000-1024 | 46-3829104 | 5800 | CC-VENUE | Net 15 | TRUE | TRUE | TRUE | TRUE | 2027-02-28 | TRUE | Active | FALSE | Green room artist catering & green room provisioning | Julian Clarkson | 2026-09-30 13:05 | 2026-09-30 13:05
VEN-008 | GHXSTSHIP | CSMIA26 | Technical Production | VCL-002 | Communications | Motorola Solutions / BearCom | Telecommunications | https://bearcom.com | Radio Depot Desk | rentals@bearcom.com | (000) 000-1036 | 75-1829304 | 5900 | CC-VENUE | Net 30 | TRUE | TRUE | TRUE | TRUE | 2027-07-31 | TRUE | Active | FALSE | CP200d radio inventory & headsets | Julian Clarkson | 2026-09-30 13:05 | 2026-09-30 13:05
VEN-009 | GHXSTSHIP | CSMIA26 | Logistics / Site Ops | VCL-011 | Transport Services | Old Dominion Freight Line | Logistics and Freight | https://odfl.com | Freight Desk | dispatch@odfl.com | (000) 000-1014 | 56-0728190 | 5500 | CC-VENUE | Net 30 | TRUE | TRUE | TRUE | TRUE | 2027-08-31 | TRUE | Active | FALSE | Inbound freight logistics & line haul | Julian Clarkson | 2026-09-30 13:05 | 2026-09-30 13:05
VEN-010 | GHXSTSHIP | CSMIA26 | Site Operations | VCL-003 | Sanitation | United Site Services | Facilities Services | https://unitedsiteservices.com | Ops Coordinator | info@unitedsiteservices.com | (000) 000-0992 | 04-3458921 | 5600 | CC-VENUE | Net 30 | TRUE | TRUE | TRUE | TRUE | 2027-05-15 | TRUE | Active | FALSE | Sanitation pumping and portable restrooms | Julian Clarkson | 2026-09-30 13:05 | 2026-09-30 13:05
VEN-011 | GHXSTSHIP | CSMIA26 | Security | VCL-004 | Crowd Management | Argus Event Staffing | Security Services |  | Security Supervisor | ops@argus-security.com | (000) 000-0978 | 84-1293845 | 5600 | CC-VENUE | Net 15 | TRUE | TRUE | TRUE | TRUE | 2027-06-15 | TRUE | Active | FALSE | Perimeter gates & access control staff | Julian Clarkson | 2026-09-30 13:05 | 2026-09-30 13:05
VEN-012 | GHXSTSHIP | CSMIA26 | 5000 Production | VCL-009 | Equipment Rental | LPS Production | Equipment Rental | https://www.lpsproduction.com | Equipment Lead | rentals@lpsproduction.com | (000) 000-1016 | 59-1829401 | 5500 | CC-VENUE | Net 30 | TRUE | TRUE | TRUE | TRUE | 2027-06-30 | TRUE | Active | FALSE | Audio, lighting, staging and power equipment rental | Julian Clarkson | 2026-09-30 13:05 | 2026-09-30 13:05
VEN-013 | GHXSTSHIP | CSMIA26 | 1000 Creative | VCL-004 | Signage Fabrication | RIOT Color | Fabrication and Signage | https://www.riotcolor.com | Print Lead | info@riotcolor.com | (000) 000-1018 | 65-2918302 | 5100 | CC-VENUE | Net 30 | TRUE | TRUE | TRUE | TRUE | 2027-04-30 | TRUE | Active | FALSE | Wayfinding and brand signage production and install | Julian Clarkson | 2026-09-30 13:05 | 2026-09-30 13:05
VEN-014 | GHXSTSHIP | CSMIA26 | 5000 Production | VCL-002 | LED Video Systems | NEP Screenworks | Broadcast Services | https://www.nepgroup.com | Video Dispatch | screenworks@nepgroup.com | (305) 555-0182 | 25-1829403 | 5500 | CC-VENUE | Net 30 | TRUE | TRUE | TRUE | TRUE | 2027-05-31 | TRUE | Active | FALSE | LED video wall systems and processing | Julian Clarkson | 2026-09-30 13:05 | 2026-09-30 13:05
VEN-015 | GHXSTSHIP | CSMIA26 | 9000 Technology | VCL-002 | Systems Integration | Unreal-Systems | AV Integrator | https://www.unreal-systems.com | Integration Lead | ops@unreal-systems.com | (305) 555-0155 | 47-3829105 | 5900 | CC-VENUE | Net 30 | TRUE | TRUE | TRUE | TRUE | 2027-08-31 | TRUE | Active | FALSE | AV installation and systems integration | Julian Clarkson | 2026-09-30 13:05 | 2026-09-30 13:05
VEN-016 | GHXSTSHIP | CSMIA26 | 0000 Executive | VCL-001 | Operator Leadership | Tigre Studio | Sponsor | https://tigresoundsystem.com | Ashley Sumner | ashley@tigresoundsystem.com | (305) 555-0101 | 65-1928374 | 5000 | CC-CORP | Net 30 | TRUE | TRUE | TRUE | TRUE | 2027-12-31 | TRUE | Active | FALSE | Venue operator and production partner | Julian Clarkson | 2026-09-30 13:05 | 2026-09-30 13:05
VEN-017 | GHXSTSHIP | CSMIA26 | 0000 Executive | VCL-001 | Brand House / Client | Spotify | Sponsor | https://www.spotify.com | Isabella Acker | isabella@spotify.com | (305) 555-0105 | 13-4029182 | 4000 | CC-CORP | Net 30 | TRUE | TRUE | TRUE | TRUE | 2027-12-31 | TRUE | Active | FALSE | Client brand house and presenting sponsor | Julian Clarkson | 2026-09-30 13:05 | 2026-09-30 13:05
VEN-018 | GHXSTSHIP | CSMIA26 | 6000 Operations | VCL-007 | Life Safety | City of Miami Building & Fire | Life Safety Services | https://www.miami.gov | Capt. R. Fernandez | fireprevention@miamigov.com | (305) 416-1600 | 59-6000346 | 5600 | CC-VENUE | Net 30 | TRUE | FALSE | FALSE | TRUE | 2027-09-30 | TRUE | Active | FALSE | Assembly occupancy, fire & life safety inspection authority | Julian Clarkson | 2026-09-30 13:05 | 2026-09-30 13:05
VEN-019 | GHXSTSHIP | CSMIA26 | 5000 Production | VCL-007 | Electrical Safety | City of Miami Electrical Inspection | Life Safety Services | https://www.miami.gov | J. Rodriguez | electrical@miamigov.com | (305) 416-1650 | 59-6000347 | 5500 | CC-VENUE | Net 30 | TRUE | FALSE | FALSE | TRUE | 2027-09-30 | TRUE | Active | FALSE | Temporary power and generator safety inspections | Julian Clarkson | 2026-09-30 13:05 | 2026-09-30 13:05
VEN-020 | GHXSTSHIP | CSMIA26 | 8000 Hospitality | VCL-007 | Health & Sanitation | FL DBPR / Miami-Dade Health Dept | Life Safety Services | https://miamidade.floridahealth.gov | M. Santos | doh-miamidade@flhealth.gov | (305) 324-2400 | 59-6000348 | 5800 | CC-VENUE | Net 30 | TRUE | FALSE | FALSE | TRUE | 2027-09-30 | TRUE | Active | FALSE | Temporary food service and sanitation inspections | Julian Clarkson | 2026-09-30 13:05 | 2026-09-30 13:05
VEN-021 | GHXSTSHIP | CSMIA26 | 9000 Technology | VCL-002 | Telecommunications | Big Red Communications | Telecommunications |  | Network Lead | support@bigredcomms.com | (305) 555-0199 | 59-3928175 | 5900 | CC-VENUE | Net 30 | TRUE | TRUE | TRUE | TRUE | 2027-07-31 | TRUE | Active | FALSE | Circuit, guest wireless, production VLAN | Julian Clarkson | 2026-09-30 13:05 | 2026-09-30 13:05
VEN-022 | GHXSTSHIP | CSMIA26 | 6000 Operations | CP-LANDLORD | Occupancy | Landlord (7610 Biscayne) | Landlord | N/A | Julian Clarkson | julian.clarkson@ghxstship.pro | (305) 555-0100 | XX-XXXXXXX | 5600 | CC-VENUE | Monthly | Executed | On File | On File | Current | 2031-08-31 | Confirmed | Active | FALSE | Lease, occupancy and building services per proposal | Julian Clarkson | 2026-09-15 | 2026-10-02 05:04
VEN-023 | GHXSTSHIP | CSMIA26 | 6000 Operations | VCL-003 | Janitorial Services | MRF Cleaning Solutions | Janitorial Services | https://mrfeventcleaningservices.com/ | Julian Clarkson | julian.clarkson@ghxstship.pro | (305) 555-0109 | XX-XXXXXXX | 5600 | CC-VENUE | Net 30 | Executed | On File | On File | Current | 2027-01-15 | Confirmed | Active | FALSE | Scheduled cleaning and event turnarounds | Julian Clarkson | 2026-09-15 | 2026-10-02 05:04

## Vendor Classes
RECORD ID | ORGANIZATION | PROJECT | DEPARTMENT | CATEGORY | SUB CATEGORY | CLASS | DESCRIPTION | CLEARANCE TIER | STATUS | FLAG | NOTES | CREATED BY | CREATED AT | UPDATED AT
VCL-001 | GHXSTSHIP | CSMIA26 | Procurement | Vendor Management | Classification | Class A | Executive | Tier 1 - Executive Master | Active | FALSE | Full administrative access across all venue operations | Julian Clarkson | 2026-09-30 13:05 | 2026-09-30 13:05
VCL-002 | GHXSTSHIP | CSMIA26 | Procurement | Vendor Management | Classification | Class B | Production | Tier 2 - Technical Lead | Active | FALSE | Full technical and operational production access | Julian Clarkson | 2026-09-30 13:05 | 2026-09-30 13:05
VCL-003 | GHXSTSHIP | CSMIA26 | Procurement | Vendor Management | Classification | Class C | Operations | Tier 3 - Operations Ops | Active | FALSE | Operations site staff without quartermaster checkout | Julian Clarkson | 2026-09-30 13:05 | 2026-09-30 13:05
VCL-004 | GHXSTSHIP | CSMIA26 | Procurement | Vendor Management | Classification | Class D | Vendor | Tier 4 - Standard Commercial | Active | FALSE | Standard retail and commercial booth operations | Julian Clarkson | 2026-09-30 13:05 | 2026-09-30 13:05
VCL-005 | GHXSTSHIP | CSMIA26 | Procurement | Vendor Management | Classification | Class E | Experiential | Tier 3 - Operations Ops | Active | FALSE | Sponsor and interactive brand activation partners | Julian Clarkson | 2026-09-30 13:05 | 2026-09-30 13:05
VCL-006 | GHXSTSHIP | CSMIA26 | Procurement | Vendor Management | Classification | Class F | Food & Beverage | Tier 3 - Operations Ops | Active | FALSE | Food vendors and beverage concessionaires | Julian Clarkson | 2026-09-30 13:05 | 2026-09-30 13:05
VCL-007 | GHXSTSHIP | CSMIA26 | Procurement | Vendor Management | Classification | Class G | Government Agency | Tier 1 - Regulatory Standby | Active | FALSE | Fire, police, code enforcement, public health inspectors | Julian Clarkson | 2026-09-30 13:05 | 2026-09-30 13:05
VCL-008 | GHXSTSHIP | CSMIA26 | Procurement | Vendor Management | Classification | Class P | Professional Services | Tier 5 - Delivery & Supplier | Active | FALSE | Accounting, legal, insurance representatives | Julian Clarkson | 2026-09-30 13:05 | 2026-09-30 13:05
VCL-009 | GHXSTSHIP | CSMIA26 | Procurement | Vendor Management | Classification | Class R | Rental Services | Tier 5 - Delivery & Supplier | Active | FALSE | Heavy equipment drop-off and pickup logistics | Julian Clarkson | 2026-09-30 13:05 | 2026-09-30 13:05
VCL-010 | GHXSTSHIP | CSMIA26 | Procurement | Vendor Management | Classification | Class S | Supplier | Tier 5 - Delivery & Supplier | Active | FALSE | Ice, water, fuel, and consumable stock deliveries | Julian Clarkson | 2026-09-30 13:05 | 2026-09-30 13:05
VCL-011 | GHXSTSHIP | CSMIA26 | Procurement | Vendor Management | Classification | Class T | Transport Services | Tier 4 - Standard Commercial | Active | FALSE | Shuttle buses, artist ground transport, and freight haulers | Julian Clarkson | 2026-09-30 13:05 | 2026-09-30 13:05

## Vendor Entitlements
RECORD ID | ORGANIZATION | PROJECT | VENDOR CLASS | MODULE | PERMITTED | STATUS | FLAG | NOTES | CREATED BY | CREATED AT | UPDATED AT
ENT-001 | GHXSTSHIP | CSMIA26 | VCL-001 | Advance | TRUE | Active | FALSE | Module entitlement authorization | Julian Clarkson | 2026-09-30 13:05 | 2026-09-30 13:05
ENT-002 | GHXSTSHIP | CSMIA26 | VCL-001 | Access | TRUE | Active | FALSE | Module entitlement authorization | Julian Clarkson | 2026-09-30 13:05 | 2026-09-30 13:05
ENT-003 | GHXSTSHIP | CSMIA26 | VCL-001 | Credentials | TRUE | Active | FALSE | Module entitlement authorization | Julian Clarkson | 2026-09-30 13:05 | 2026-09-30 13:05
ENT-004 | GHXSTSHIP | CSMIA26 | VCL-001 | Parking | TRUE | Active | FALSE | Module entitlement authorization | Julian Clarkson | 2026-09-30 13:05 | 2026-09-30 13:05
ENT-005 | GHXSTSHIP | CSMIA26 | VCL-001 | Catering | TRUE | Active | FALSE | Module entitlement authorization | Julian Clarkson | 2026-09-30 13:05 | 2026-09-30 13:05
ENT-006 | GHXSTSHIP | CSMIA26 | VCL-001 | Travel | TRUE | Active | FALSE | Module entitlement authorization | Julian Clarkson | 2026-09-30 13:05 | 2026-09-30 13:05
ENT-007 | GHXSTSHIP | CSMIA26 | VCL-001 | Radios | TRUE | Active | FALSE | Module entitlement authorization | Julian Clarkson | 2026-09-30 13:05 | 2026-09-30 13:05
ENT-008 | GHXSTSHIP | CSMIA26 | VCL-001 | Office | TRUE | Active | FALSE | Module entitlement authorization | Julian Clarkson | 2026-09-30 13:05 | 2026-09-30 13:05
ENT-009 | GHXSTSHIP | CSMIA26 | VCL-001 | Vehicles | TRUE | Active | FALSE | Module entitlement authorization | Julian Clarkson | 2026-09-30 13:05 | 2026-09-30 13:05
ENT-010 | GHXSTSHIP | CSMIA26 | VCL-001 | Heavy Equip | TRUE | Active | FALSE | Module entitlement authorization | Julian Clarkson | 2026-09-30 13:05 | 2026-09-30 13:05
ENT-011 | GHXSTSHIP | CSMIA26 | VCL-001 | Quartermaster | TRUE | Active | FALSE | Module entitlement authorization | Julian Clarkson | 2026-09-30 13:05 | 2026-09-30 13:05
ENT-012 | GHXSTSHIP | CSMIA26 | VCL-002 | Advance | TRUE | Active | FALSE | Module entitlement authorization | Julian Clarkson | 2026-09-30 13:05 | 2026-09-30 13:05
ENT-013 | GHXSTSHIP | CSMIA26 | VCL-002 | Access | TRUE | Active | FALSE | Module entitlement authorization | Julian Clarkson | 2026-09-30 13:05 | 2026-09-30 13:05
ENT-014 | GHXSTSHIP | CSMIA26 | VCL-002 | Credentials | TRUE | Active | FALSE | Module entitlement authorization | Julian Clarkson | 2026-09-30 13:05 | 2026-09-30 13:05
ENT-015 | GHXSTSHIP | CSMIA26 | VCL-002 | Parking | TRUE | Active | FALSE | Module entitlement authorization | Julian Clarkson | 2026-09-30 13:05 | 2026-09-30 13:05
ENT-016 | GHXSTSHIP | CSMIA26 | VCL-002 | Catering | TRUE | Active | FALSE | Module entitlement authorization | Julian Clarkson | 2026-09-30 13:05 | 2026-09-30 13:05
ENT-017 | GHXSTSHIP | CSMIA26 | VCL-002 | Travel | TRUE | Active | FALSE | Module entitlement authorization | Julian Clarkson | 2026-09-30 13:05 | 2026-09-30 13:05
ENT-018 | GHXSTSHIP | CSMIA26 | VCL-002 | Radios | TRUE | Active | FALSE | Module entitlement authorization | Julian Clarkson | 2026-09-30 13:05 | 2026-09-30 13:05
ENT-019 | GHXSTSHIP | CSMIA26 | VCL-002 | Office | TRUE | Active | FALSE | Module entitlement authorization | Julian Clarkson | 2026-09-30 13:05 | 2026-09-30 13:05
ENT-020 | GHXSTSHIP | CSMIA26 | VCL-002 | Vehicles | TRUE | Active | FALSE | Module entitlement authorization | Julian Clarkson | 2026-09-30 13:05 | 2026-09-30 13:05
ENT-021 | GHXSTSHIP | CSMIA26 | VCL-002 | Heavy Equip | TRUE | Active | FALSE | Module entitlement authorization | Julian Clarkson | 2026-09-30 13:05 | 2026-09-30 13:05
ENT-022 | GHXSTSHIP | CSMIA26 | VCL-002 | Quartermaster | TRUE | Active | FALSE | Module entitlement authorization | Julian Clarkson | 2026-09-30 13:05 | 2026-09-30 13:05
ENT-023 | GHXSTSHIP | CSMIA26 | VCL-003 | Advance | TRUE | Active | FALSE | Module entitlement authorization | Julian Clarkson | 2026-09-30 13:05 | 2026-09-30 13:05
ENT-024 | GHXSTSHIP | CSMIA26 | VCL-003 | Access | TRUE | Active | FALSE | Module entitlement authorization | Julian Clarkson | 2026-09-30 13:05 | 2026-09-30 13:05
ENT-025 | GHXSTSHIP | CSMIA26 | VCL-003 | Credentials | TRUE | Active | FALSE | Module entitlement authorization | Julian Clarkson | 2026-09-30 13:05 | 2026-09-30 13:05
ENT-026 | GHXSTSHIP | CSMIA26 | VCL-003 | Parking | TRUE | Active | FALSE | Module entitlement authorization | Julian Clarkson | 2026-09-30 13:05 | 2026-09-30 13:05
ENT-027 | GHXSTSHIP | CSMIA26 | VCL-003 | Catering | TRUE | Active | FALSE | Module entitlement authorization | Julian Clarkson | 2026-09-30 13:05 | 2026-09-30 13:05
ENT-028 | GHXSTSHIP | CSMIA26 | VCL-003 | Travel | TRUE | Active | FALSE | Module entitlement authorization | Julian Clarkson | 2026-09-30 13:05 | 2026-09-30 13:05
ENT-029 | GHXSTSHIP | CSMIA26 | VCL-003 | Radios | TRUE | Active | FALSE | Module entitlement authorization | Julian Clarkson | 2026-09-30 13:05 | 2026-09-30 13:05
ENT-030 | GHXSTSHIP | CSMIA26 | VCL-003 | Office | TRUE | Active | FALSE | Module entitlement authorization | Julian Clarkson | 2026-09-30 13:05 | 2026-09-30 13:05
ENT-031 | GHXSTSHIP | CSMIA26 | VCL-003 | Vehicles | TRUE | Active | FALSE | Module entitlement authorization | Julian Clarkson | 2026-09-30 13:05 | 2026-09-30 13:05
ENT-032 | GHXSTSHIP | CSMIA26 | VCL-003 | Heavy Equip | TRUE | Active | FALSE | Module entitlement authorization | Julian Clarkson | 2026-09-30 13:05 | 2026-09-30 13:05
ENT-033 | GHXSTSHIP | CSMIA26 | VCL-004 | Advance | TRUE | Active | FALSE | Module entitlement authorization | Julian Clarkson | 2026-09-30 13:05 | 2026-09-30 13:05
ENT-034 | GHXSTSHIP | CSMIA26 | VCL-004 | Site Access | TRUE | Active | FALSE | Module entitlement authorization | Julian Clarkson | 2026-09-30 13:05 | 2026-09-30 13:05
ENT-035 | GHXSTSHIP | CSMIA26 | VCL-004 | Credentials | TRUE | Active | FALSE | Module entitlement authorization | Julian Clarkson | 2026-09-30 13:05 | 2026-09-30 13:05
ENT-036 | GHXSTSHIP | CSMIA26 | VCL-004 | Parking | TRUE | Active | FALSE | Module entitlement authorization | Julian Clarkson | 2026-09-30 13:05 | 2026-09-30 13:05
ENT-037 | GHXSTSHIP | CSMIA26 | VCL-005 | Advance | TRUE | Active | FALSE | Module entitlement authorization | Julian Clarkson | 2026-09-30 13:05 | 2026-09-30 13:05
ENT-038 | GHXSTSHIP | CSMIA26 | VCL-005 | Access | TRUE | Active | FALSE | Module entitlement authorization | Julian Clarkson | 2026-09-30 13:05 | 2026-09-30 13:05
ENT-039 | GHXSTSHIP | CSMIA26 | VCL-005 | Credentials | TRUE | Active | FALSE | Module entitlement authorization | Julian Clarkson | 2026-09-30 13:05 | 2026-09-30 13:05
ENT-040 | GHXSTSHIP | CSMIA26 | VCL-005 | Parking | TRUE | Active | FALSE | Module entitlement authorization | Julian Clarkson | 2026-09-30 13:05 | 2026-09-30 13:05
ENT-041 | GHXSTSHIP | CSMIA26 | VCL-005 | Radios | TRUE | Active | FALSE | Module entitlement authorization | Julian Clarkson | 2026-09-30 13:05 | 2026-09-30 13:05
ENT-042 | GHXSTSHIP | CSMIA26 | VCL-005 | Office | TRUE | Active | FALSE | Module entitlement authorization | Julian Clarkson | 2026-09-30 13:05 | 2026-09-30 13:05
ENT-043 | GHXSTSHIP | CSMIA26 | VCL-005 | Vehicles | TRUE | Active | FALSE | Module entitlement authorization | Julian Clarkson | 2026-09-30 13:05 | 2026-09-30 13:05
ENT-044 | GHXSTSHIP | CSMIA26 | VCL-005 | Heavy Equip | TRUE | Active | FALSE | Module entitlement authorization | Julian Clarkson | 2026-09-30 13:05 | 2026-09-30 13:05
ENT-045 | GHXSTSHIP | CSMIA26 | VCL-006 | Advance | TRUE | Active | FALSE | Module entitlement authorization | Julian Clarkson | 2026-09-30 13:05 | 2026-09-30 13:05
ENT-046 | GHXSTSHIP | CSMIA26 | VCL-006 | Access | TRUE | Active | FALSE | Module entitlement authorization | Julian Clarkson | 2026-09-30 13:05 | 2026-09-30 13:05
ENT-047 | GHXSTSHIP | CSMIA26 | VCL-006 | Credentials | TRUE | Active | FALSE | Module entitlement authorization | Julian Clarkson | 2026-09-30 13:05 | 2026-09-30 13:05
ENT-048 | GHXSTSHIP | CSMIA26 | VCL-006 | Parking | TRUE | Active | FALSE | Module entitlement authorization | Julian Clarkson | 2026-09-30 13:05 | 2026-09-30 13:05
ENT-049 | GHXSTSHIP | CSMIA26 | VCL-006 | Radios | TRUE | Active | FALSE | Module entitlement authorization | Julian Clarkson | 2026-09-30 13:05 | 2026-09-30 13:05
ENT-050 | GHXSTSHIP | CSMIA26 | VCL-006 | Office | TRUE | Active | FALSE | Module entitlement authorization | Julian Clarkson | 2026-09-30 13:05 | 2026-09-30 13:05
ENT-051 | GHXSTSHIP | CSMIA26 | VCL-006 | Vehicles | TRUE | Active | FALSE | Module entitlement authorization | Julian Clarkson | 2026-09-30 13:05 | 2026-09-30 13:05
ENT-052 | GHXSTSHIP | CSMIA26 | VCL-006 | Heavy Equip | TRUE | Active | FALSE | Module entitlement authorization | Julian Clarkson | 2026-09-30 13:05 | 2026-09-30 13:05
ENT-053 | GHXSTSHIP | CSMIA26 | VCL-007 | Site Access | TRUE | Active | FALSE | Module entitlement authorization | Julian Clarkson | 2026-09-30 13:05 | 2026-09-30 13:05
ENT-054 | GHXSTSHIP | CSMIA26 | VCL-007 | Radios | TRUE | Active | FALSE | Module entitlement authorization | Julian Clarkson | 2026-09-30 13:05 | 2026-09-30 13:05
ENT-055 | GHXSTSHIP | CSMIA26 | VCL-008 | Administrative Only | TRUE | Active | FALSE | Module entitlement authorization | Julian Clarkson | 2026-09-30 13:05 | 2026-09-30 13:05
ENT-056 | GHXSTSHIP | CSMIA26 | VCL-009 | Site Access | TRUE | Active | FALSE | Module entitlement authorization | Julian Clarkson | 2026-09-30 13:05 | 2026-09-30 13:05
ENT-057 | GHXSTSHIP | CSMIA26 | VCL-010 | Site Access | TRUE | Active | FALSE | Module entitlement authorization | Julian Clarkson | 2026-09-30 13:05 | 2026-09-30 13:05
ENT-058 | GHXSTSHIP | CSMIA26 | VCL-011 | Site Access | TRUE | Active | FALSE | Module entitlement authorization | Julian Clarkson | 2026-09-30 13:05 | 2026-09-30 13:05
ENT-059 | GHXSTSHIP | CSMIA26 | VCL-011 | Parking | TRUE | Active | FALSE | Module entitlement authorization | Julian Clarkson | 2026-09-30 13:05 | 2026-09-30 13:05

## Inspection Compliance
RECORD ID | ORGANIZATION | PROJECT ID | DEPARTMENT | CATEGORY | SUB CATEGORY | INSPECTION TYPE | AGENCY | AHJ JURISDICTION CODE | PERMIT NUMBER | PERMIT DOC ID | LOCATION ID | VENDOR ID | INSPECTOR NAME | SCHEDULED DATE | COMPLETED DATE | RESULT | DEFICIENCY SUMMARY | SIGN-OFF DATE | SIGN-OFF URL | STATUS | FLAG | NOTES | CREATED BY | CREATED AT | UPDATED AT
INS-001 | GHXSTSHIP | CSMIA26 | 6000 Operations | 6000.51.04 | Life Safety | Assembly Occupancy & Egress Walk | City of Miami Building & Fire | US-FL-MIAMI-DADE | BD-2026-08914 | PMT-2026-881 | LOC-01 | VEN-018 | Capt. R. Fernandez | 2026-10-14 | 2026-10-14 | Pending Inspection | None noted - pre-inspection checklist verified | 2026-10-14 |  | Scheduled | FALSE | Mandatory AHJ signoff for doors open | Julian Clarkson | 2026-10-01 | 2026-10-01
INS-002 | GHXSTSHIP | CSMIA26 | 5000 Production | 5000.06.01 | Electrical | Temporary Power & Generator Safety | City of Miami Electrical Inspection | US-FL-MIAMI-DADE | EL-2026-04421 | PMT-2026-882 | LOC-07 | VEN-019 | J. Rodriguez | 2026-10-13 | 2026-10-13 | Pending Inspection | None noted - generator grounding verified | 2026-10-13 |  | Scheduled | FALSE | Master electrician on site for tie-in walk | Julian Clarkson | 2026-10-01 | 2026-10-01
INS-003 | GHXSTSHIP | CSMIA26 | 8000 Hospitality | 8000.02.01 | Health & Sanitation | Food Service & Mobile Bars Audit | FL DBPR / Miami-Dade Health Dept | US-FL-MIAMI-DADE | HD-2026-01290 | PMT-2026-883 | LOC-06 | VEN-020 | M. Santos | 2026-10-15 | 2026-10-15 | Pending Inspection | None noted - handwashing and refrigeration compliant | 2026-10-15 |  | Scheduled | FALSE | Kitchen sanitization, handwash stations & bar ice bins | Julian Clarkson | 2026-10-01 | 2026-10-01

## Incident CAD Log
RECORD ID | ORGANIZATION | PROJECT ID | DEPARTMENT | CATEGORY | SUB CATEGORY | INCIDENT TIMESTAMP | EMERGENCY CODE ID | SEVERITY LEVEL | LOCATION ID | REPORTED BY | LEAD RESPONDER ID | DISPATCH AGENCY / UNIT | DISPATCH TIME | ON SCENE TIME | CLEARED TIME | POLICE REPORT NUMBER | INCIDENT SUMMARY | RESOLUTION PROTOCOL | FOLLOW UP REQUIRED | STATUS | FLAG | NOTES | CREATED BY | CREATED AT | UPDATED AT

## Emergency Codes
RECORD ID | ORGANIZATION | PROJECT | DEPARTMENT | CATEGORY | SUB CATEGORY | EMERGENCY | RADIO CALL | OPERATIONAL DOMAIN | ACTION PROTOCOL | STATUS | FLAG | NOTES | CREATED BY | CREATED AT | UPDATED AT
EMG-001 | GHXSTSHIP | CSMIA26 | Security & Safety | Emergency Protocols | Incident Response | Fire Emergency | CODE RED | Site Operations | Actions: 1. Identify fire source and immediately activate fire extinguishers. 2. Contact fire department (Miami Fire-Rescue / MDFR). 3. Clear and cordon off affected areas. 4. Shut off utilities (gas/electric). | Active | FALSE | Master life safety protocol | Julian Clarkson | 2026-09-30 13:05 | 2026-09-30 13:05
EMG-002 | GHXSTSHIP | CSMIA26 | Security & Safety | Emergency Protocols | Incident Response | Fire Emergency | CODE RED | Stage Operations | Actions: 1. Immediately cut power to stage equipment to prevent electrical fires. 2. Use extinguishers near stage if safe to do so. 3. Assist with evacuation of performers and crew. | Active | FALSE | Master life safety protocol | Julian Clarkson | 2026-09-30 13:05 | 2026-09-30 13:05
EMG-003 | GHXSTSHIP | CSMIA26 | Security & Safety | Emergency Protocols | Incident Response | Fire Emergency | CODE RED | Food & Beverage Operations | Actions: 1. Cease all operations. 2. Turn off cooking equipment. 3. Instruct staff to guide guests out safely. 4. Evacuate food areas and ensure propane tanks are turned off. | Active | FALSE | Master life safety protocol | Julian Clarkson | 2026-09-30 13:05 | 2026-09-30 13:05
EMG-004 | GHXSTSHIP | CSMIA26 | Security & Safety | Emergency Protocols | Incident Response | Fire Emergency | CODE RED | Guest Experience | Actions: 1. Direct guests to nearest exits. 2. Make PA announcements, if possible, to ensure orderly evacuation. 3. Assist guests with limited mobility or special needs. | Active | FALSE | Master life safety protocol | Julian Clarkson | 2026-09-30 13:05 | 2026-09-30 13:05
EMG-005 | GHXSTSHIP | CSMIA26 | Security & Safety | Emergency Protocols | Incident Response | Fire Emergency | CODE RED | Back of House Operations | Actions: 1. Ensure artists and performers are safely escorted off stage/backstage. 2. Secure props and valuable equipment backstage to prevent further hazards. | Active | FALSE | Master life safety protocol | Julian Clarkson | 2026-09-30 13:05 | 2026-09-30 13:05
EMG-006 | GHXSTSHIP | CSMIA26 | Security & Safety | Emergency Protocols | Incident Response | Fire Emergency | CODE RED | Front of House Operations | Actions: 1. Ensure all exits are accessible and open. 2. Assist in the evacuation of high-capacity zones, including VIP and public areas. 3. Provide basic first aid if needed. | Active | FALSE | Master life safety protocol | Julian Clarkson | 2026-09-30 13:05 | 2026-09-30 13:05
EMG-007 | GHXSTSHIP | CSMIA26 | Security & Safety | Emergency Protocols | Incident Response | Acts of Aggression | CODE ORANGE | Site Operations | Actions: 1. Alert security teams and LAPD immediately. 2. Isolate aggressors and provide crowd control to prevent escalation. 3. Assess if evacuation is necessary. | Active | FALSE | Master life safety protocol | Julian Clarkson | 2026-09-30 13:05 | 2026-09-30 13:05
EMG-008 | GHXSTSHIP | CSMIA26 | Security & Safety | Emergency Protocols | Incident Response | Acts of Aggression | CODE ORANGE | Stage Operations | Actions: 1. Turn off stage lighting and sound to avoid escalating tensions. 2. If necessary, pause performances and lock down stage access. | Active | FALSE | Master life safety protocol | Julian Clarkson | 2026-09-30 13:05 | 2026-09-30 13:05
EMG-009 | GHXSTSHIP | CSMIA26 | Security & Safety | Emergency Protocols | Incident Response | Acts of Aggression | CODE ORANGE | Food & Beverage Operations | Actions: 1. Cease alcohol sales. 2. Instruct staff to close registers and secure high-value items. 3. Secure equipment that can be used as weapons (e.g., knives, utensils). | Active | FALSE | Master life safety protocol | Julian Clarkson | 2026-09-30 13:05 | 2026-09-30 13:05
EMG-010 | GHXSTSHIP | CSMIA26 | Security & Safety | Emergency Protocols | Incident Response | Acts of Aggression | CODE ORANGE | Guest Experience | Actions: 1. Move guests away from the conflict area, using calm and non-confrontational communication. 2. Offer assistance to frightened or injured guests. | Active | FALSE | Master life safety protocol | Julian Clarkson | 2026-09-30 13:05 | 2026-09-30 13:05
EMG-011 | GHXSTSHIP | CSMIA26 | Security & Safety | Emergency Protocols | Incident Response | Acts of Aggression | CODE ORANGE | Back of House Operations | Actions: 1. Backstage personnel to remain alert and report suspicious behavior. 2. Provide a safe room for artists if aggression occurs near performance area. | Active | FALSE | Master life safety protocol | Julian Clarkson | 2026-09-30 13:05 | 2026-09-30 13:05
EMG-012 | GHXSTSHIP | CSMIA26 | Security & Safety | Emergency Protocols | Incident Response | Acts of Aggression | CODE ORANGE | Front of House Operations | Actions: 1. Assist security teams with crowd control and ensure that aggressors are contained away from general public. 2. Coordinate with medical teams if injuries occur. | Active | FALSE | Master life safety protocol | Julian Clarkson | 2026-09-30 13:05 | 2026-09-30 13:05
EMG-013 | GHXSTSHIP | CSMIA26 | Security & Safety | Emergency Protocols | Incident Response | Power or Structural Failure or Damage | CODE YELLOW | Site Operations | Actions: 1. Cut power to affected areas. 2. Inspect any visible structural damage (e.g., lighting rigs, barricades). 3. Work with electricians to restore power safely. | Active | FALSE | Master life safety protocol | Julian Clarkson | 2026-09-30 13:05 | 2026-09-30 13:05
EMG-014 | GHXSTSHIP | CSMIA26 | Security & Safety | Emergency Protocols | Incident Response | Power or Structural Failure or Damage | CODE YELLOW | Stage Operations | Actions: 1. Secure all stage equipment and instruments to prevent further damage. 2. Pause performances and make an announcement explaining the situation. | Active | FALSE | Master life safety protocol | Julian Clarkson | 2026-09-30 13:05 | 2026-09-30 13:05
EMG-015 | GHXSTSHIP | CSMIA26 | Security & Safety | Emergency Protocols | Incident Response | Power or Structural Failure or Damage | CODE YELLOW | Food & Beverage Operations | Actions: 1. Stop food prep to avoid injury. 2. If structural damage affects tents/kiosks, direct guests and staff to clear the area. | Active | FALSE | Master life safety protocol | Julian Clarkson | 2026-09-30 13:05 | 2026-09-30 13:05
EMG-016 | GHXSTSHIP | CSMIA26 | Security & Safety | Emergency Protocols | Incident Response | Power or Structural Failure or Damage | CODE YELLOW | Guest Experience | Actions: 1. Calm guests and offer clear instructions to avoid panic. 2. Guide guests to alternate exits if structural damage affects egress routes. | Active | FALSE | Master life safety protocol | Julian Clarkson | 2026-09-30 13:05 | 2026-09-30 13:05
EMG-017 | GHXSTSHIP | CSMIA26 | Security & Safety | Emergency Protocols | Incident Response | Power or Structural Failure or Damage | CODE YELLOW | Back of House Operations | Actions: 1. Ensure that artists are safe backstage and equipment is not at risk of being damaged. 2. Organize personnel to inspect and report any damage in restricted areas. | Active | FALSE | Master life safety protocol | Julian Clarkson | 2026-09-30 13:05 | 2026-09-30 13:05
EMG-018 | GHXSTSHIP | CSMIA26 | Security & Safety | Emergency Protocols | Incident Response | Power or Structural Failure or Damage | CODE YELLOW | Front of House Operations | Actions: 1. Guide guests to safety and inform them of alternative actions (delays or cancellations). 2. Assist in directing crowds away from dangerous areas. | Active | FALSE | Master life safety protocol | Julian Clarkson | 2026-09-30 13:05 | 2026-09-30 13:05
EMG-019 | GHXSTSHIP | CSMIA26 | Security & Safety | Emergency Protocols | Incident Response | Theft & Loss Prevention | CODE GREEN | Site Operations | Actions: 1. Increase security patrols in sensitive areas (e.g., entrances, high-traffic areas). 2. Report all thefts to LAPD. 3. Conduct bag checks at exits, if needed. | Active | FALSE | Master life safety protocol | Julian Clarkson | 2026-09-30 13:05 | 2026-09-30 13:05
EMG-020 | GHXSTSHIP | CSMIA26 | Security & Safety | Emergency Protocols | Incident Response | Theft & Loss Prevention | CODE GREEN | Stage Operations | Actions: 1. Secure all stage equipment, especially high-value instruments or electronics. 2. Coordinate with security to monitor artist equipment and dressing rooms. | Active | FALSE | Master life safety protocol | Julian Clarkson | 2026-09-30 13:05 | 2026-09-30 13:05
EMG-021 | GHXSTSHIP | CSMIA26 | Security & Safety | Emergency Protocols | Incident Response | Theft & Loss Prevention | CODE GREEN | Food & Beverage Operations | Actions: 1. Lock down cash registers and remove high-value items from view. 2. Report suspicious behavior to security. 3. Implement a strict cash-handling procedure. | Active | FALSE | Master life safety protocol | Julian Clarkson | 2026-09-30 13:05 | 2026-09-30 13:05
EMG-022 | GHXSTSHIP | CSMIA26 | Security & Safety | Emergency Protocols | Incident Response | Theft & Loss Prevention | CODE GREEN | Guest Experience | Actions: 1. Assist guests in filing lost or stolen property reports. 2. Use public announcements to inform guests of the incident, if needed. | Active | FALSE | Master life safety protocol | Julian Clarkson | 2026-09-30 13:05 | 2026-09-30 13:05
EMG-023 | GHXSTSHIP | CSMIA26 | Security & Safety | Emergency Protocols | Incident Response | Theft & Loss Prevention | CODE GREEN | Back of House Operations | Actions: 1. Secure personal and valuable equipment for artists and performers. 2. Monitor access to VIP areas to prevent unauthorized entry. | Active | FALSE | Master life safety protocol | Julian Clarkson | 2026-09-30 13:05 | 2026-09-30 13:05
EMG-024 | GHXSTSHIP | CSMIA26 | Security & Safety | Emergency Protocols | Incident Response | Theft & Loss Prevention | CODE GREEN | Front of House Operations | Actions: 1. Assist security in ensuring all exits are covered. 2. Implement crowd control to prevent thefts during egress. 3. Handle guest complaints regarding lost items. | Active | FALSE | Master life safety protocol | Julian Clarkson | 2026-09-30 13:05 | 2026-09-30 13:05
EMG-025 | GHXSTSHIP | CSMIA26 | Security & Safety | Emergency Protocols | Incident Response | Medical Emergency | CODE BLUE | Site Operations | Actions: 1. Immediately call EMS or direct on-site medical personnel. 2. Clear space for medical teams to access the affected individual. 3. Use first aid kits if necessary. | Active | FALSE | Master life safety protocol | Julian Clarkson | 2026-09-30 13:05 | 2026-09-30 13:05
EMG-026 | GHXSTSHIP | CSMIA26 | Security & Safety | Emergency Protocols | Incident Response | Medical Emergency | CODE BLUE | Stage Operations | Actions: 1. Pause performance to direct attention to the medical emergency. 2. Keep communication channels open to ensure paramedics can access the stage area. | Active | FALSE | Master life safety protocol | Julian Clarkson | 2026-09-30 13:05 | 2026-09-30 13:05
EMG-027 | GHXSTSHIP | CSMIA26 | Security & Safety | Emergency Protocols | Incident Response | Medical Emergency | CODE BLUE | Food & Beverage Operations | Actions: 1. Offer water or basic care (if applicable). 2. Instruct staff to guide EMS to the food area if needed. | Active | FALSE | Master life safety protocol | Julian Clarkson | 2026-09-30 13:05 | 2026-09-30 13:05
EMG-028 | GHXSTSHIP | CSMIA26 | Security & Safety | Emergency Protocols | Incident Response | Medical Emergency | CODE BLUE | Guest Experience | Actions: 1. Alert guests to make way for medical personnel. 2. Provide support to affected individuals until EMS arrives. | Active | FALSE | Master life safety protocol | Julian Clarkson | 2026-09-30 13:05 | 2026-09-30 13:05
EMG-029 | GHXSTSHIP | CSMIA26 | Security & Safety | Emergency Protocols | Incident Response | Medical Emergency | CODE BLUE | Back of House Operations | Actions: 1. Ensure performers and crew are safe and are not obstructing medical responders. 2. Provide medics with direct access to the backstage area if needed. | Active | FALSE | Master life safety protocol | Julian Clarkson | 2026-09-30 13:05 | 2026-09-30 13:05
EMG-030 | GHXSTSHIP | CSMIA26 | Security & Safety | Emergency Protocols | Incident Response | Medical Emergency | CODE BLUE | Front of House Operations | Actions: 1. Coordinate with medical teams to facilitate access to emergency locations. 2. Keep guests informed about delays or disruptions due to the emergency. | Active | FALSE | Master life safety protocol | Julian Clarkson | 2026-09-30 13:05 | 2026-09-30 13:05
EMG-031 | GHXSTSHIP | CSMIA26 | Security & Safety | Emergency Protocols | Incident Response | Political or Civil Unrest | CODE PURPLE | Site Operations | Actions: 1. Activate emergency protocol and increase security presence. 2. Prepare evacuation routes and ensure exits are clear. 3. Work with LAPD for guidance and assistance. | Active | FALSE | Master life safety protocol | Julian Clarkson | 2026-09-30 13:05 | 2026-09-30 13:05
EMG-032 | GHXSTSHIP | CSMIA26 | Security & Safety | Emergency Protocols | Incident Response | Political or Civil Unrest | CODE PURPLE | Stage Operations | Actions: 1. Stop the performance to prevent escalation. 2. Secure stage and assist in evacuating performers and staff to a safe area. | Active | FALSE | Master life safety protocol | Julian Clarkson | 2026-09-30 13:05 | 2026-09-30 13:05
EMG-033 | GHXSTSHIP | CSMIA26 | Security & Safety | Emergency Protocols | Incident Response | Political or Civil Unrest | CODE PURPLE | Food & Beverage Operations | Actions: 1. Lock down all kiosks, close food prep areas. 2. Move staff to safe areas and prepare for evacuation. | Active | FALSE | Master life safety protocol | Julian Clarkson | 2026-09-30 13:05 | 2026-09-30 13:05
EMG-034 | GHXSTSHIP | CSMIA26 | Security & Safety | Emergency Protocols | Incident Response | Political or Civil Unrest | CODE PURPLE | Guest Experience | Actions: 1. Calm guests and direct them to safety if evacuation becomes necessary. 2. Provide real-time updates using PA system or megaphones. | Active | FALSE | Master life safety protocol | Julian Clarkson | 2026-09-30 13:05 | 2026-09-30 13:05
EMG-035 | GHXSTSHIP | CSMIA26 | Security & Safety | Emergency Protocols | Incident Response | Political or Civil Unrest | CODE PURPLE | Back of House Operations | Actions: 1. Ensure artists are safely escorted off-site if necessary. 2. Secure dressing rooms and valuables. | Active | FALSE | Master life safety protocol | Julian Clarkson | 2026-09-30 13:05 | 2026-09-30 13:05
EMG-036 | GHXSTSHIP | CSMIA26 | Security & Safety | Emergency Protocols | Incident Response | Political or Civil Unrest | CODE PURPLE | Front of House Operations | Actions: 1. Assist in managing crowds to prevent disorder. 2. Ensure clear communication with guests, informing them about actions being taken for their safety. | Active | FALSE | Master life safety protocol | Julian Clarkson | 2026-09-30 13:05 | 2026-09-30 13:05
EMG-037 | GHXSTSHIP | CSMIA26 | Security & Safety | Emergency Protocols | Incident Response | Government Agency Inspection or Encounter | CODE WHITE | Site Operations | Actions: 1. Provide requested permits, licenses, and compliance documentation to the agency. 2. Ensure all areas meet safety standards (fire exits, lighting, structural integrity). | Active | FALSE | Master life safety protocol | Julian Clarkson | 2026-09-30 13:05 | 2026-09-30 13:05
EMG-038 | GHXSTSHIP | CSMIA26 | Security & Safety | Emergency Protocols | Incident Response | Government Agency Inspection or Encounter | CODE WHITE | Stage Operations | Actions: 1. Pause the performance if requested by officials. 2. Ensure all stage operations are compliant with safety regulations (sound levels, rigging). | Active | FALSE | Master life safety protocol | Julian Clarkson | 2026-09-30 13:05 | 2026-09-30 13:05
EMG-039 | GHXSTSHIP | CSMIA26 | Security & Safety | Emergency Protocols | Incident Response | Government Agency Inspection or Encounter | CODE WHITE | Food & Beverage Operations | Actions: 1. Provide food handling permits, alcohol licenses, and health inspection certificates upon request. | Active | FALSE | Master life safety protocol | Julian Clarkson | 2026-09-30 13:05 | 2026-09-30 13:05
EMG-040 | GHXSTSHIP | CSMIA26 | Security & Safety | Emergency Protocols | Incident Response | Government Agency Inspection or Encounter | CODE WHITE | Guest Experience | Actions: 1. Inform guests of any temporary delays due to inspections. 2. Provide support to guests and reassure them that the event is in compliance with safety protocols. | Active | FALSE | Master life safety protocol | Julian Clarkson | 2026-09-30 13:05 | 2026-09-30 13:05
EMG-041 | GHXSTSHIP | CSMIA26 | Security & Safety | Emergency Protocols | Incident Response | Government Agency Inspection or Encounter | CODE WHITE | Back of House Operations | Actions: 1. Ensure back-of-house areas meet safety regulations and provide access to officials for inspections. 2. Maintain communication with event management. | Active | FALSE | Master life safety protocol | Julian Clarkson | 2026-09-30 13:05 | 2026-09-30 13:05
EMG-042 | GHXSTSHIP | CSMIA26 | Security & Safety | Emergency Protocols | Incident Response | Government Agency Inspection or Encounter | CODE WHITE | Front of House Operations | Actions: 1. Assist in ensuring that front-of-house operations meet health, safety, and accessibility regulations. 2. Provide compliance documentation to authorities if required. | Active | FALSE | Master life safety protocol | Julian Clarkson | 2026-09-30 13:05 | 2026-09-30 13:05
EMG-043 | GHXSTSHIP | CSMIA26 | Security & Safety | Emergency Protocols | Incident Response | Acts of Terror | CODE BLACK | Site Operations | Actions: 1. Immediately contact LAPD, LAFD, and federal authorities. 2. Activate emergency evacuation protocols. 3. Secure all entrances and exits. | Active | FALSE | Master life safety protocol | Julian Clarkson | 2026-09-30 13:05 | 2026-09-30 13:05
EMG-044 | GHXSTSHIP | CSMIA26 | Security & Safety | Emergency Protocols | Incident Response | Acts of Terror | CODE BLACK | Stage Operations | Actions: 1. Cut stage power and lighting to avoid panic. 2. Assist security in evacuating artists and crew to secure areas. | Active | FALSE | Master life safety protocol | Julian Clarkson | 2026-09-30 13:05 | 2026-09-30 13:05
EMG-045 | GHXSTSHIP | CSMIA26 | Security & Safety | Emergency Protocols | Incident Response | Acts of Terror | CODE BLACK | Food & Beverage Operations | Actions: 1. Cease all operations and secure food stands. 2. Ensure that all dangerous equipment (e.g., propane tanks) is turned off and locked down. | Active | FALSE | Master life safety protocol | Julian Clarkson | 2026-09-30 13:05 | 2026-09-30 13:05
EMG-046 | GHXSTSHIP | CSMIA26 | Security & Safety | Emergency Protocols | Incident Response | Acts of Terror | CODE BLACK | Guest Experience | Actions: 1. Announce evacuation instructions clearly and calmly. 2. Assist guests with disabilities or mobility challenges in evacuating. | Active | FALSE | Master life safety protocol | Julian Clarkson | 2026-09-30 13:05 | 2026-09-30 13:05
EMG-047 | GHXSTSHIP | CSMIA26 | Security & Safety | Emergency Protocols | Incident Response | Acts of Terror | CODE BLACK | Back of House Operations | Actions: 1. Secure VIP and performer areas to prevent unauthorized access. 2. Escort artists and staff to safety through pre-established emergency routes. | Active | FALSE | Master life safety protocol | Julian Clarkson | 2026-09-30 13:05 | 2026-09-30 13:05
EMG-048 | GHXSTSHIP | CSMIA26 | Security & Safety | Emergency Protocols | Incident Response | Acts of Terror | CODE BLACK | Front of House Operations | Actions: 1. Ensure all exit points are secure but accessible for a controlled evacuation. 2. Provide first aid support if necessary. | Active | FALSE | Master life safety protocol | Julian Clarkson | 2026-09-30 13:05 | 2026-09-30 13:05
EMG-049 | GHXSTSHIP | CSMIA26 | Security & Safety | Emergency Protocols | Incident Response | Illegal Substance | CODE PINK | Site Operations | Actions: 1. Report substance use to security and law enforcement. 2. Assist in monitoring suspicious activity and help contain the situation. | Active | FALSE | Master life safety protocol | Julian Clarkson | 2026-09-30 13:05 | 2026-09-30 13:05
EMG-050 | GHXSTSHIP | CSMIA26 | Security & Safety | Emergency Protocols | Incident Response | Illegal Substance | CODE PINK | Stage Operations | Actions: 1. Halt the performance and coordinate with security if illicit substances are suspected backstage. 2. Maintain communication with artists and crew regarding safety. | Active | FALSE | Master life safety protocol | Julian Clarkson | 2026-09-30 13:05 | 2026-09-30 13:05
EMG-051 | GHXSTSHIP | CSMIA26 | Security & Safety | Emergency Protocols | Incident Response | Illegal Substance | CODE PINK | Food & Beverage Operations | Actions: 1. Cease alcohol sales and report any incidents of illegal substance use near food stations. 2. Monitor guests for signs of intoxication and report to security. | Active | FALSE | Master life safety protocol | Julian Clarkson | 2026-09-30 13:05 | 2026-09-30 13:05
EMG-052 | GHXSTSHIP | CSMIA26 | Security & Safety | Emergency Protocols | Incident Response | Illegal Substance | CODE PINK | Guest Experience | Actions: 1. Report any suspicious activity to security. 2. Assist guests in reporting concerns related to substance use or safety. | Active | FALSE | Master life safety protocol | Julian Clarkson | 2026-09-30 13:05 | 2026-09-30 13:05
EMG-053 | GHXSTSHIP | CSMIA26 | Security & Safety | Emergency Protocols | Incident Response | Illegal Substance | CODE PINK | Back of House Operations | Actions: 1. Ensure backstage areas are free of illegal substances and report any issues to management and law enforcement. | Active | FALSE | Master life safety protocol | Julian Clarkson | 2026-09-30 13:05 | 2026-09-30 13:05
EMG-054 | GHXSTSHIP | CSMIA26 | Security & Safety | Emergency Protocols | Incident Response | Illegal Substance | CODE PINK | Front of House Operations | Actions: 1. Alert security and provide support for guests affected by substance use. 2. Ensure that proper protocols for dealing with intoxicated guests are followed. | Active | FALSE | Master life safety protocol | Julian Clarkson | 2026-09-30 13:05 | 2026-09-30 13:05
EMG-055 | GHXSTSHIP | CSMIA26 | Security & Safety | Emergency Protocols | Incident Response | Absent or Missing Talent | CODE INDIGO | Site Operations | Actions: 1. Contact talent management immediately to locate missing talent. 2. Coordinate with other departments to adjust schedules as necessary. | Active | FALSE | Master life safety protocol | Julian Clarkson | 2026-09-30 13:05 | 2026-09-30 13:05
EMG-056 | GHXSTSHIP | CSMIA26 | Security & Safety | Emergency Protocols | Incident Response | Absent or Missing Talent | CODE INDIGO | Stage Operations | Actions: 1. Delay performance and provide alternate acts or entertainment, if possible. 2. Ensure that backup performers are ready to take the stage if needed. | Active | FALSE | Master life safety protocol | Julian Clarkson | 2026-09-30 13:05 | 2026-09-30 13:05
EMG-057 | GHXSTSHIP | CSMIA26 | Security & Safety | Emergency Protocols | Incident Response | Absent or Missing Talent | CODE INDIGO | Food & Beverage Operations | Actions: 1. Adjust food and beverage schedules to account for possible delays or cancellations. 2. Inform staff of changes in the performance schedule. | Active | FALSE | Master life safety protocol | Julian Clarkson | 2026-09-30 13:05 | 2026-09-30 13:05
EMG-058 | GHXSTSHIP | CSMIA26 | Security & Safety | Emergency Protocols | Incident Response | Absent or Missing Talent | CODE INDIGO | Guest Experience | Actions: 1. Inform guests of any delays or changes in performances through the PA system. 2. Provide alternative forms of entertainment or services, if possible. | Active | FALSE | Master life safety protocol | Julian Clarkson | 2026-09-30 13:05 | 2026-09-30 13:05
EMG-059 | GHXSTSHIP | CSMIA26 | Security & Safety | Emergency Protocols | Incident Response | Absent or Missing Talent | CODE INDIGO | Back of House Operations | Actions: 1. Work with talent agents to locate the missing artist. 2. Prepare alternate accommodations for talent if transportation issues are causing delays. | Active | FALSE | Master life safety protocol | Julian Clarkson | 2026-09-30 13:05 | 2026-09-30 13:05
EMG-060 | GHXSTSHIP | CSMIA26 | Security & Safety | Emergency Protocols | Incident Response | Absent or Missing Talent | CODE INDIGO | Front of House Operations | Actions: 1. Ensure all front-of-house staff are informed of changes. 2. Coordinate guest services to handle inquiries and possible complaints about the missing act. | Active | FALSE | Master life safety protocol | Julian Clarkson | 2026-09-30 13:05 | 2026-09-30 13:05
EMG-061 | GHXSTSHIP | CSMIA26 | Security & Safety | Emergency Protocols | Incident Response | Active Shooter | CODE SILVER | Site Operations | Actions: 1. Immediately notify LAPD and security personnel. 2. Lock down all entrances and exits. 3. Instruct staff to move guests to pre-designated secure areas or evacuate. | Active | FALSE | Master life safety protocol | Julian Clarkson | 2026-09-30 13:05 | 2026-09-30 13:05
EMG-062 | GHXSTSHIP | CSMIA26 | Security & Safety | Emergency Protocols | Incident Response | Active Shooter | CODE SILVER | Stage Operations | Actions: 1. Cut stage lights and sound to reduce visibility and prevent panic. 2. Ensure performers are evacuated to safe areas backstage. | Active | FALSE | Master life safety protocol | Julian Clarkson | 2026-09-30 13:05 | 2026-09-30 13:05
EMG-063 | GHXSTSHIP | CSMIA26 | Security & Safety | Emergency Protocols | Incident Response | Active Shooter | CODE SILVER | Food & Beverage Operations | Actions: 1. Cease operations and direct staff to secure food areas. 2. Lock down all exits from food tents and kiosks. | Active | FALSE | Master life safety protocol | Julian Clarkson | 2026-09-30 13:05 | 2026-09-30 13:05
EMG-064 | GHXSTSHIP | CSMIA26 | Security & Safety | Emergency Protocols | Incident Response | Active Shooter | CODE SILVER | Guest Experience | Actions: 1. Calmly guide guests to secure areas or nearest exits as directed by security. 2. Help guests find shelter in place if an evacuation is not immediately possible. | Active | FALSE | Master life safety protocol | Julian Clarkson | 2026-09-30 13:05 | 2026-09-30 13:05
EMG-065 | GHXSTSHIP | CSMIA26 | Security & Safety | Emergency Protocols | Incident Response | Active Shooter | CODE SILVER | Back of House Operations | Actions: 1. Secure VIP and backstage areas. 2. Help performers evacuate through secure routes or lock down in safe areas. | Active | FALSE | Master life safety protocol | Julian Clarkson | 2026-09-30 13:05 | 2026-09-30 13:05
EMG-066 | GHXSTSHIP | CSMIA26 | Security & Safety | Emergency Protocols | Incident Response | Active Shooter | CODE SILVER | Front of House Operations | Actions: 1. Direct guests toward exits and assist law enforcement with crowd control. 2. Provide medical support for any injuries. | Active | FALSE | Master life safety protocol | Julian Clarkson | 2026-09-30 13:05 | 2026-09-30 13:05
EMG-067 | GHXSTSHIP | CSMIA26 | Security & Safety | Emergency Protocols | Incident Response | Bomb Threat | CODE GREY | Site Operations | Actions: 1. Notify LAPD and bomb squad immediately. 2. Clear and evacuate areas as directed by law enforcement. 3. Avoid using radios or cell phones in case of detonation risk. | Active | FALSE | Master life safety protocol | Julian Clarkson | 2026-09-30 13:05 | 2026-09-30 13:05
EMG-068 | GHXSTSHIP | CSMIA26 | Security & Safety | Emergency Protocols | Incident Response | Bomb Threat | CODE GREY | Stage Operations | Actions: 1. Secure all stage equipment and evacuate performers and crew to safe areas. 2. Work with authorities to ensure proper procedures are followed for bomb threat investigation. | Active | FALSE | Master life safety protocol | Julian Clarkson | 2026-09-30 13:05 | 2026-09-30 13:05
EMG-069 | GHXSTSHIP | CSMIA26 | Security & Safety | Emergency Protocols | Incident Response | Bomb Threat | CODE GREY | Food & Beverage Operations | Actions: 1. Cease operations and evacuate staff to designated safety areas. 2. Secure propane tanks and any flammable materials. | Active | FALSE | Master life safety protocol | Julian Clarkson | 2026-09-30 13:05 | 2026-09-30 13:05
EMG-070 | GHXSTSHIP | CSMIA26 | Security & Safety | Emergency Protocols | Incident Response | Bomb Threat | CODE GREY | Guest Experience | Actions: 1. Calmly announce evacuation procedures and direct guests to exits without causing panic. 2. Assist guests with disabilities or limited mobility. | Active | FALSE | Master life safety protocol | Julian Clarkson | 2026-09-30 13:05 | 2026-09-30 13:05
EMG-071 | GHXSTSHIP | CSMIA26 | Security & Safety | Emergency Protocols | Incident Response | Bomb Threat | CODE GREY | Back of House Operations | Actions: 1. Evacuate backstage personnel to safe areas. 2. Ensure that performers are kept in secure locations until further instruction from law enforcement. | Active | FALSE | Master life safety protocol | Julian Clarkson | 2026-09-30 13:05 | 2026-09-30 13:05
EMG-072 | GHXSTSHIP | CSMIA26 | Security & Safety | Emergency Protocols | Incident Response | Bomb Threat | CODE GREY | Front of House Operations | Actions: 1. Ensure all exits are accessible for rapid evacuation. 2. Assist law enforcement with crowd control and provide medical support as needed. | Active | FALSE | Master life safety protocol | Julian Clarkson | 2026-09-30 13:05 | 2026-09-30 13:05
EMG-073 | GHXSTSHIP | CSMIA26 | Security & Safety | Emergency Protocols | Incident Response | Security Breach | CODE AMBER | Site Operations | Actions: 1. Notify security and lock down vulnerable access points. 2. Assist security in managing crowds and preventing unauthorized individuals from entering secure areas. | Active | FALSE | Master life safety protocol | Julian Clarkson | 2026-09-30 13:05 | 2026-09-30 13:05
EMG-074 | GHXSTSHIP | CSMIA26 | Security & Safety | Emergency Protocols | Incident Response | Security Breach | CODE AMBER | Stage Operations | Actions: 1. Lock down stage access and evacuate performers if necessary. 2. Secure valuable stage equipment. | Active | FALSE | Master life safety protocol | Julian Clarkson | 2026-09-30 13:05 | 2026-09-30 13:05
EMG-075 | GHXSTSHIP | CSMIA26 | Security & Safety | Emergency Protocols | Incident Response | Security Breach | CODE AMBER | Food & Beverage Operations | Actions: 1. Shut down food operations and secure high-value items. 2. Assist security in monitoring access points to prevent unauthorized entry. | Active | FALSE | Master life safety protocol | Julian Clarkson | 2026-09-30 13:05 | 2026-09-30 13:05
EMG-076 | GHXSTSHIP | CSMIA26 | Security & Safety | Emergency Protocols | Incident Response | Security Breach | CODE AMBER | Guest Experience | Actions: 1. Reassure guests and prevent panic. 2. Move guests away from the area of the breach to safer locations. | Active | FALSE | Master life safety protocol | Julian Clarkson | 2026-09-30 13:05 | 2026-09-30 13:05
EMG-077 | GHXSTSHIP | CSMIA26 | Security & Safety | Emergency Protocols | Incident Response | Security Breach | CODE AMBER | Back of House Operations | Actions: 1. Secure backstage areas, ensuring unauthorized personnel do not access dressing rooms or restricted zones. | Active | FALSE | Master life safety protocol | Julian Clarkson | 2026-09-30 13:05 | 2026-09-30 13:05
EMG-078 | GHXSTSHIP | CSMIA26 | Security & Safety | Emergency Protocols | Incident Response | Security Breach | CODE AMBER | Front of House Operations | Actions: 1. Secure all exits and entry points to prevent unauthorized access. 2. Coordinate with security and local law enforcement to handle breach. | Active | FALSE | Master life safety protocol | Julian Clarkson | 2026-09-30 13:05 | 2026-09-30 13:05
EMG-079 | GHXSTSHIP | CSMIA26 | Security & Safety | Emergency Protocols | Incident Response | Missing Person(s) | CODE ADAM | Site Operations | Actions: 1. Alert security and event management. 2. Assist with immediate searches using pre-assigned personnel. 3. Make announcements over PA system or use digital alerts. | Active | FALSE | Master life safety protocol | Julian Clarkson | 2026-09-30 13:05 | 2026-09-30 13:05
EMG-080 | GHXSTSHIP | CSMIA26 | Security & Safety | Emergency Protocols | Incident Response | Missing Person(s) | CODE ADAM | Stage Operations | Actions: 1. Suspend performance temporarily if necessary to coordinate searches. 2. Ensure all stage staff are briefed on the missing person situation. | Active | FALSE | Master life safety protocol | Julian Clarkson | 2026-09-30 13:05 | 2026-09-30 13:05
EMG-081 | GHXSTSHIP | CSMIA26 | Security & Safety | Emergency Protocols | Incident Response | Missing Person(s) | CODE ADAM | Food & Beverage Operations | Actions: 1. Instruct food and beverage staff to monitor exits and inform security if the missing person is seen. | Active | FALSE | Master life safety protocol | Julian Clarkson | 2026-09-30 13:05 | 2026-09-30 13:05
EMG-082 | GHXSTSHIP | CSMIA26 | Security & Safety | Emergency Protocols | Incident Response | Missing Person(s) | CODE ADAM | Guest Experience | Actions: 1. Assist in locating missing individuals by directing security or offering descriptions to staff. 2. Guide guardians to a secure meeting point. | Active | FALSE | Master life safety protocol | Julian Clarkson | 2026-09-30 13:05 | 2026-09-30 13:05
EMG-083 | GHXSTSHIP | CSMIA26 | Security & Safety | Emergency Protocols | Incident Response | Missing Person(s) | CODE ADAM | Back of House Operations | Actions: 1. Help secure backstage areas and prevent unauthorized personnel from entering. 2. Assist in search efforts by monitoring restricted areas. | Active | FALSE | Master life safety protocol | Julian Clarkson | 2026-09-30 13:05 | 2026-09-30 13:05
EMG-084 | GHXSTSHIP | CSMIA26 | Security & Safety | Emergency Protocols | Incident Response | Missing Person(s) | CODE ADAM | Front of House Operations | Actions: 1. Coordinate with law enforcement and search teams to monitor exits. 2. Assist with family reunification processes. | Active | FALSE | Master life safety protocol | Julian Clarkson | 2026-09-30 13:05 | 2026-09-30 13:05

## Radio Channels
RECORD ID | ORGANIZATION | PROJECT ID | DEPARTMENT | CATEGORY | SUB CATEGORY | ZONE | CHANNEL | ASSIGNMENT | STATUS | FLAG | NOTES | CREATED BY | CREATED AT | UPDATED AT
RCH-001 | GHXSTSHIP | CSMIA26 | Communications | Radio Frequency | Zone 1 | 1 | 1 | Emergency | Active | FALSE | Primary life safety and incident response | Julian Clarkson | 2026-09-30 13:05 | 2026-09-30 13:05
RCH-002 | GHXSTSHIP | CSMIA26 | Communications | Radio Frequency | Zone 1 | 1 | 2 | Security | Active | FALSE | Perimeter and access security coordination | Julian Clarkson | 2026-09-30 13:05 | 2026-09-30 13:05
RCH-003 | GHXSTSHIP | CSMIA26 | Communications | Radio Frequency | Zone 1 | 1 | 3 | Site Ops | Active | FALSE | Facilities and heavy equipment operations | Julian Clarkson | 2026-09-30 13:05 | 2026-09-30 13:05
RCH-004 | GHXSTSHIP | CSMIA26 | Communications | Radio Frequency | Zone 1 | 1 | 4 | Exterior Ops | Active | FALSE | Exterior gates, parking, and traffic dispatch | Julian Clarkson | 2026-09-30 13:05 | 2026-09-30 13:05
RCH-005 | GHXSTSHIP | CSMIA26 | Communications | Radio Frequency | Zone 1 | 1 | 5 | Power & IT | Active | FALSE | Generators, fuel tech, network infrastructure | Julian Clarkson | 2026-09-30 13:05 | 2026-09-30 13:05
RCH-006 | GHXSTSHIP | CSMIA26 | Communications | Radio Frequency | Zone 1 | 1 | 6 | Cleaning & Sanitation | Active | FALSE | Restroom servicing and waste collection dispatch | Julian Clarkson | 2026-09-30 13:05 | 2026-09-30 13:05
RCH-007 | GHXSTSHIP | CSMIA26 | Communications | Radio Frequency | Zone 1 | 1 | 7 | Stage Ops | Active | FALSE | Main stage and side stage crew leads | Julian Clarkson | 2026-09-30 13:05 | 2026-09-30 13:05
RCH-008 | GHXSTSHIP | CSMIA26 | Communications | Radio Frequency | Zone 1 | 1 | 8 | Audio | Active | FALSE | FOH audio, monitor world, and system tech | Julian Clarkson | 2026-09-30 13:05 | 2026-09-30 13:05
RCH-009 | GHXSTSHIP | CSMIA26 | Communications | Radio Frequency | Zone 1 | 1 | 9 | Lighting | Active | FALSE | Lighting directors, riggers, and dimmers | Julian Clarkson | 2026-09-30 13:05 | 2026-09-30 13:05
RCH-010 | GHXSTSHIP | CSMIA26 | Communications | Radio Frequency | Zone 1 | 1 | 10 | Video & SFX | Active | FALSE | LED walls, lasers, special effects, pyrotechnics | Julian Clarkson | 2026-09-30 13:05 | 2026-09-30 13:05
RCH-011 | GHXSTSHIP | CSMIA26 | Communications | Radio Frequency | Zone 1 | 1 | 11 | Experience | Active | FALSE | Brand activations and patron engagement | Julian Clarkson | 2026-09-30 13:05 | 2026-09-30 13:05
RCH-012 | GHXSTSHIP | CSMIA26 | Communications | Radio Frequency | Zone 1 | 1 | 12 | Site Lighting | Active | FALSE | Architectural and egress pathway lighting | Julian Clarkson | 2026-09-30 13:05 | 2026-09-30 13:05
RCH-013 | GHXSTSHIP | CSMIA26 | Communications | Radio Frequency | Zone 1 | 1 | 13 | Artist Relations | Active | FALSE | Hospitality, green rooms, artist transport | Julian Clarkson | 2026-09-30 13:05 | 2026-09-30 13:05
RCH-014 | GHXSTSHIP | CSMIA26 | Communications | Radio Frequency | Zone 1 | 1 | 14 | Guest Services | Active | FALSE | Info booths, lost & found, ADA assistance | Julian Clarkson | 2026-09-30 13:05 | 2026-09-30 13:05
RCH-015 | GHXSTSHIP | CSMIA26 | Communications | Radio Frequency | Zone 1 | 1 | 15 | Bar Ops | Active | FALSE | Concessions inventory and bar managers | Julian Clarkson | 2026-09-30 13:05 | 2026-09-30 13:05
RCH-016 | GHXSTSHIP | CSMIA26 | Communications | Radio Frequency | Zone 1 | 1 | 16 | VIP Ops | Active | FALSE | VIP lounge hosts and hospitality leads | Julian Clarkson | 2026-09-30 13:05 | 2026-09-30 13:05
RCH-017 | GHXSTSHIP | CSMIA26 | Communications | Radio Frequency | Zone 2 | 2 | 1 | All Call | Active | FALSE | Emergency broadcast across all channels | Julian Clarkson | 2026-09-30 13:05 | 2026-09-30 13:05
RCH-018 | GHXSTSHIP | CSMIA26 | Communications | Radio Frequency | Zone 2 | 2 | 2 | Open Talk 2 | Active | FALSE | Cross-department operations channel 2 | Julian Clarkson | 2026-09-30 13:05 | 2026-09-30 13:05
RCH-019 | GHXSTSHIP | CSMIA26 | Communications | Radio Frequency | Zone 2 | 2 | 3 | Open Talk 3 | Active | FALSE | Cross-department operations channel 3 | Julian Clarkson | 2026-09-30 13:05 | 2026-09-30 13:05
RCH-020 | GHXSTSHIP | CSMIA26 | Communications | Radio Frequency | Zone 2 | 2 | 4 | Open Talk 4 | Active | FALSE | Cross-department operations channel 4 | Julian Clarkson | 2026-09-30 13:05 | 2026-09-30 13:05
RCH-021 | GHXSTSHIP | CSMIA26 | Communications | Radio Frequency | Zone 2 | 2 | 5 | Open Talk 5 | Active | FALSE | Cross-department operations channel 5 | Julian Clarkson | 2026-09-30 13:05 | 2026-09-30 13:05
RCH-022 | GHXSTSHIP | CSMIA26 | Communications | Radio Frequency | Zone 2 | 2 | 6 | Open Talk 6 | Active | FALSE | Cross-department operations channel 6 | Julian Clarkson | 2026-09-30 13:05 | 2026-09-30 13:05
RCH-023 | GHXSTSHIP | CSMIA26 | Communications | Radio Frequency | Zone 2 | 2 | 7 | Open Talk 7 | Active | FALSE | Cross-department operations channel 7 | Julian Clarkson | 2026-09-30 13:05 | 2026-09-30 13:05
RCH-024 | GHXSTSHIP | CSMIA26 | Communications | Radio Frequency | Zone 2 | 2 | 8 | Open Talk 8 | Active | FALSE | Cross-department operations channel 8 | Julian Clarkson | 2026-09-30 13:05 | 2026-09-30 13:05
RCH-025 | GHXSTSHIP | CSMIA26 | Communications | Radio Frequency | Zone 2 | 2 | 9 | Open Talk 9 | Active | FALSE | Cross-department operations channel 9 | Julian Clarkson | 2026-09-30 13:05 | 2026-09-30 13:05
RCH-026 | GHXSTSHIP | CSMIA26 | Communications | Radio Frequency | Zone 2 | 2 | 10 | Open Talk 10 | Active | FALSE | Cross-department operations channel 10 | Julian Clarkson | 2026-09-30 13:05 | 2026-09-30 13:05
RCH-027 | GHXSTSHIP | CSMIA26 | Communications | Radio Frequency | Zone 2 | 2 | 11 | Guest 1 | Active | FALSE | Visiting production / guest crew talkgroup 1 | Julian Clarkson | 2026-09-30 13:05 | 2026-09-30 13:05
RCH-028 | GHXSTSHIP | CSMIA26 | Communications | Radio Frequency | Zone 2 | 2 | 12 | Guest 2 | Active | FALSE | Visiting production / guest crew talkgroup 2 | Julian Clarkson | 2026-09-30 13:05 | 2026-09-30 13:05
RCH-029 | GHXSTSHIP | CSMIA26 | Communications | Radio Frequency | Zone 2 | 2 | 13 | Guest 3 | Active | FALSE | Visiting production / guest crew talkgroup 3 | Julian Clarkson | 2026-09-30 13:05 | 2026-09-30 13:05
RCH-030 | GHXSTSHIP | CSMIA26 | Communications | Radio Frequency | Zone 2 | 2 | 14 | Guest 4 | Active | FALSE | Visiting production / guest crew talkgroup 4 | Julian Clarkson | 2026-09-30 13:05 | 2026-09-30 13:05
RCH-031 | GHXSTSHIP | CSMIA26 | Communications | Radio Frequency | Zone 2 | 2 | 15 | Guest 5 | Active | FALSE | Visiting production / guest crew talkgroup 5 | Julian Clarkson | 2026-09-30 13:05 | 2026-09-30 13:05
RCH-032 | GHXSTSHIP | CSMIA26 | Communications | Radio Frequency | Zone 2 | 2 | 16 | Guest 6 | Active | FALSE | Visiting production / guest crew talkgroup 6 | Julian Clarkson | 2026-09-30 13:05 | 2026-09-30 13:05

## Document & Asset Library
RECORD ID | DOCUMENT NAME | DOCUMENT TYPE | REFERENCE ID | ORGANIZATION | PROJECT | DEPARTMENT | CATEGORY | SUB CATEGORY | FILE FORMAT | FILE SIZE | STORAGE URL | VERSION | ISSUE DATE | EXPIRATION DATE | STATUS | FLAG | NOTES | CREATED BY | CREATED AT | UPDATED AT
DOC-001 | Master Architectural Site Plan & Life Safety CAD | Architectural CAD Drawing | LOC-01 | GHXSTSHIP | CSMIA26 | 6000 Operations | 6000.01.01 | Site Planning | DWG / PDF | 48.5 MB | [link removed] | v4.2 | 2026-09-15 | 2026-10-31 | Approved | FALSE | Sealed egress widths, occupant capacity (350 GA), and fire lanes approved by AHJ. | Julian Clarkson | 2026-10-02 09:55 | 2026-10-02 09:55
DOC-002 | City of Miami Special Assembly Occupancy Permit | Municipal Building Permit | PMT-2026-881 | GHXSTSHIP | CSMIA26 | 6000 Operations | 6000.51.04 | Permitting | PDF | 4.2 MB | [link removed] | v1.0 | 2026-09-28 | 2026-10-18 | Approved | FALSE | Permit BD-2026-08914 issued under FBC and Florida Fire Prevention Code. | Julian Clarkson | 2026-10-02 09:55 | 2026-10-02 09:55
DOC-003 | Temporary Power & Generator Tie-In Permit & Load Calc | Electrical Permit & Single-Line | PMT-2026-882 | GHXSTSHIP | CSMIA26 | 5000 Production | 5000.06.01 | Electrical Permit | PDF | 6.8 MB | [link removed] | v1.1 | 2026-09-30 | 2026-10-18 | Approved | FALSE | Permit EL-2026-04421 with master electrician certification for 400A cam-lock tie-in. | Julian Clarkson | 2026-10-02 09:55 | 2026-10-02 09:55
DOC-004 | Overhead Rigging Plot & Stamped Structural Analysis | Engineering Calculation & Plot | WO-002 | GHXSTSHIP | CSMIA26 | 5000 Production | 5000.05.02 | Rigging Engineering | PDF / Vectorworks | 32.4 MB | [link removed] | v2.0 | 2026-10-01 | 2026-10-31 | Approved | FALSE | PE stamped load calculations for truss spans, 1-ton chain motors, and LED center hangs. | Julian Clarkson | 2026-10-02 09:55 | 2026-10-02 09:55
DOC-005 | Acoustic Sound Modeling & SPL Compliance Plan | Technical System Specification | 5000-OPR-007 | GHXSTSHIP | CSMIA26 | 5000 Production | 5000.01.01 | Audio Engineering | PDF / EASE | 18.1 MB | [link removed] | v2.3 | 2026-10-02 | 2026-10-20 | Approved | FALSE | Cardioid sub steering calibrated to satisfy Wynwood / Biscayne perimeter noise curfew (<78 dBA). | Julian Clarkson | 2026-10-02 09:55 | 2026-10-02 09:55
DOC-006 | Casa Spotify Wynwood Brand Toolkit & Style Guide | Brand Standards Manual | TSK-007 | GHXSTSHIP | CSMIA26 | 1000 Creative | 1000.03.01 | Brand Identity | PDF | 54.0 MB | [link removed] | v3.0 | 2026-09-10 | 2026-10-31 | Approved | FALSE | Approved typography, green/black color tokens, sponsor lockups, and motion assets. | Julian Clarkson | 2026-10-02 09:55 | 2026-10-02 09:55
DOC-007 | Artist Sizzle Reel & Main LED Key Visual Master 4K | Master Video Asset | ROS-004 | GHXSTSHIP | CSMIA26 | 1000 Creative | 1000.05.01 | Motion Graphics | ProRes 4444 / MP4 | 14.2 GB | [link removed] | v1.0 | 2026-10-04 | 2026-10-20 | Approved | FALSE | Full 4K ProRes render mapped for primary 2.6mm LED wall on media server playback. | Julian Clarkson | 2026-10-02 09:55 | 2026-10-02 09:55
DOC-008 | Comprehensive Emergency Action & Severe Weather Plan | Operations Protocol Manual | TSK-017 | GHXSTSHIP | CSMIA26 | 6000 Operations | 6000.05.01 | Life Safety | PDF | 8.5 MB | [link removed] | v2.1 | 2026-10-03 | 2026-10-31 | Approved | FALSE | ANSI ES1.7 wind threshold action protocols, storm evacuation triggers, and EMS dispatch routes. | Julian Clarkson | 2026-10-02 09:55 | 2026-10-02 09:55
DOC-009 | Temporary Demountable Structures (TDS) Wind Stability & Ballast Analysis | Engineering Calculation & Plot | WO-002 | GHXSTSHIP | CSMIA26 | 4000 Environment | 4000.08.02 | Structural Engineering | PDF / Mathcad | 16.4 MB | [link removed] | v1.4 | 2026-10-01 | 2026-10-31 | Approved | FALSE | Ballast calculations per ANSI ES1.7-2021 and Florida Building Code 115 MPH design wind speed. | Julian Clarkson | 2026-10-02 09:55 | 2026-10-02 09:55
DOC-010 | Miami Fire-Rescue Special Effects & Flame Effects Permit | Municipal SFX Permit | PMT-2026-883 | GHXSTSHIP | CSMIA26 | 5000 Production | 5000.07.01 | Pyrotechnics & SFX | PDF | 5.1 MB | [link removed] | v1.0 | 2026-10-02 | 2026-10-18 | Approved | FALSE | City of Miami Fire-Rescue NFPA 160 flame effects permit for stage LP-gas and cold spark units. | Julian Clarkson | 2026-10-02 09:55 | 2026-10-02 09:55
DOC-011 | FDA CDRH Class 3B/4 Audience-Scanned Laser Variance | Federal Laser Variance | PMT-2026-884 | GHXSTSHIP | CSMIA26 | 5000 Production | 5000.07.01 | Laser Safety | PDF | 7.9 MB | [link removed] | v1.0 | 2026-09-15 | 2027-09-15 | Approved | FALSE | FDA 21 CFR 1040.10 accession report and variance for 15W RGB show laser projection systems. | Julian Clarkson | 2026-10-02 09:55 | 2026-10-02 09:55
DOC-012 | City of Miami Code Compliance Noise Variance & Perimeter Curfew Permit | Municipal Noise Permit | PMT-2026-885 | GHXSTSHIP | CSMIA26 | 5000 Production | 5000.01.02 | Environmental Noise | PDF | 3.4 MB | [link removed] | v2.0 | 2026-09-29 | 2026-10-18 | Approved | FALSE | Special event sound variance authorizing up to 98 dBA Leq at mix and <78 dBA at boundary until 00:00. | Julian Clarkson | 2026-10-02 09:55 | 2026-10-02 09:55
DOC-013 | Florida DBPR Division of Hotels & Restaurants Temporary Food Service License | State Food Service License | PMT-2026-886 | GHXSTSHIP | CSMIA26 | 8000 Hospitality | 8000.01.01 | Public Health | PDF | 2.8 MB | [link removed] | v1.0 | 2026-10-01 | 2026-10-18 | Approved | FALSE | DBPR license for temporary public food service, mobile kitchen units, and passed catering. | Julian Clarkson | 2026-10-02 09:55 | 2026-10-02 09:55
DOC-014 | Florida DBPR Division of ABT Special Event Alcoholic Beverage Permit (ODP) | State Alcohol Permit | PMT-2026-887 | GHXSTSHIP | CSMIA26 | 8000 Hospitality | 8000.02.01 | Liquor Licensing | PDF | 3.6 MB | [link removed] | v1.1 | 2026-09-25 | 2026-10-18 | Approved | FALSE | One-day special event permit (ODP) authorizing on-premises beer, wine, and liquor dispensing. | Julian Clarkson | 2026-10-02 09:55 | 2026-10-02 09:55
DOC-015 | Event Mass-Gathering Medical Action Plan & Miami-Dade EMS Detail | Medical Operational Plan | TSK-018 | GHXSTSHIP | CSMIA26 | 6000 Operations | 6000.05.02 | Medical Services | PDF | 6.5 MB | [link removed] | v2.2 | 2026-10-03 | 2026-10-31 | Approved | FALSE | Miami-Dade Fire Rescue approved EMS plan: on-site EMT station, dedicated ambulance, triage area. | Julian Clarkson | 2026-10-02 09:55 | 2026-10-02 09:55
DOC-016 | Event Physical Security, Crowd Management & Evacuation Routing Plan | Security Operational Plan | TSK-018 | GHXSTSHIP | CSMIA26 | 6000 Operations | 6000.04.01 | Access Control | PDF | 11.2 MB | [link removed] | v2.0 | 2026-10-04 | 2026-10-31 | Approved | FALSE | Crowd manager post assignments (1:250 ratio per FL Fire Code), metal detector lanes, and roving guards. | Julian Clarkson | 2026-10-02 09:55 | 2026-10-02 09:55
DOC-017 | Public Right-of-Way Closure & Maintenance of Traffic (MOT) Plan | Municipal MOT Permit | PMT-2026-888 | GHXSTSHIP | CSMIA26 | 6000 Operations | 6000.02.07 | Traffic Engineering | PDF / CAD | 22.0 MB | [link removed] | v1.3 | 2026-09-22 | 2026-10-22 | Approved | FALSE | City of Miami Public Works / FDOT curb-lane closure permit and traffic control staging for 76th St. | Julian Clarkson | 2026-10-02 09:55 | 2026-10-02 09:55
DOC-018 | FAA Part 107 Airspace Authorization & UAS Night Flight Waiver | Federal Aviation Waiver | PMT-2026-889 | GHXSTSHIP | CSMIA26 | 5000 Production | 5000.08.01 | Aerial Operations | PDF | 4.5 MB | [link removed] | v1.0 | 2026-09-18 | 2026-10-20 | Approved | FALSE | Class G airspace night flight authorization and 107.39 waiver for commercial drone video capture. | Julian Clarkson | 2026-10-02 09:55 | 2026-10-02 09:55
DOC-019 | ADA Accessibility, Companion Seating & Accessible Route Survey | Accessibility Audit | LOC-01 | GHXSTSHIP | CSMIA26 | 7000 Experience | 7000.01.01 | ADA Compliance | PDF | 9.3 MB | [link removed] | v2.0 | 2026-10-02 | 2026-10-31 | Approved | FALSE | 2010 ADA Standards compliance: 36-inch clear paths, accessible ramp slopes (1:12), wheelchair viewing. | Julian Clarkson | 2026-10-02 09:55 | 2026-10-02 09:55
DOC-020 | FCC Part 74 Wireless Microphone & Comms Frequency Coordination | RF Coordination License | PMT-2026-890 | GHXSTSHIP | CSMIA26 | 9000 Technology | 9000.03.01 | RF Spectrum | PDF / Shure WWB | 5.7 MB | [link removed] | v1.5 | 2026-10-05 | 2026-10-18 | Approved | FALSE | Intermodulation analysis and locked UHF/VHF frequencies for Axient wireless and FreeSpeak II comms. | Julian Clarkson | 2026-10-02 09:55 | 2026-10-02 09:55
DOC-021 | Hazardous Materials & Diesel Fuel Storage Environmental Plan | Environmental Compliance | LOC-14 | GHXSTSHIP | CSMIA26 | 6000 Operations | 6000.09.01 | Spill Containment | PDF | 3.9 MB | [link removed] | v1.0 | 2026-10-01 | 2026-10-31 | Approved | FALSE | EPA / Miami-Dade DERM secondary containment plan for 500-gallon generator belly fuel tank. | Julian Clarkson | 2026-10-02 09:55 | 2026-10-02 09:55
DOC-022 | Commercial General Liability & $10M Excess Umbrella Insurance Binder | Certificate of Insurance | PMT-2026-891 | GHXSTSHIP | CSMIA26 | 0000 Executive | 0000.06.01 | Risk & Insurance | PDF | 2.1 MB | [link removed] | v1.0 | 2026-09-18 | 2027-09-18 | Approved | FALSE | ACORD 25 binder naming City of Miami and Spotify as additional insureds with primary/non-contributory. | Julian Clarkson | 2026-10-02 09:55 | 2026-10-02 09:55
DOC-023 | OSHA Fall Protection & Aerial Work Platform (AWP) Safety Protocol | Safety Protocol Manual | SOP-001 | GHXSTSHIP | CSMIA26 | 5000 Production | 5000.05.02 | Occupational Safety | PDF | 7.1 MB | [link removed] | v2.1 | 2026-10-01 | 2026-10-31 | Approved | FALSE | OSHA 1926.502 fall arrest plan, daily MEWP pre-start inspections, and drop zone barricading. | Julian Clarkson | 2026-10-02 09:55 | 2026-10-02 09:55
DOC-024 | ANSI ES1.9 Rigging Point Inspection & Proof Test Certification | Rigging Proof Test Report | WO-002 | GHXSTSHIP | CSMIA26 | 5000 Production | 5000.05.02 | Rigging Engineering | PDF | 14.8 MB | [link removed] | v1.0 | 2026-10-02 | 2026-10-31 | Approved | FALSE | Structural proof pull-testing documentation for building eyebolts, beam clamps, and bridle bridles. | Julian Clarkson | 2026-10-02 09:55 | 2026-10-02 09:55
DOC-025 | Master Run of Show & SMPTE Timecode Production Cue Sheet | Live Production Cue Schedule | ROS-001 | GHXSTSHIP | CSMIA26 | 9000 Technology | 9000.50.01 | Show Direction | PDF / Excel | 8.4 MB | [link removed] | v4.0 | 2026-10-06 | 2026-10-18 | Approved | FALSE | Integrated cue matrix syncing FOH lighting, d3 media servers, FOH audio, and talent stage calls. | Julian Clarkson | 2026-10-02 09:55 | 2026-10-02 09:55
DOC-026 | Solid Waste Diversion, Composting & Site Sanitation Log | Sustainability & Sanitation | LOC-01 | GHXSTSHIP | CSMIA26 | 6000 Operations | 6000.09.01 | Waste Diversion | PDF | 3.2 MB | [link removed] | v1.0 | 2026-10-03 | 2026-10-31 | Approved | FALSE | Zero-waste diversion tracking, compostable service ware certification, and roll-off haul schedules. | Julian Clarkson | 2026-10-02 09:55 | 2026-10-02 09:55
DOC-027 | Temporary Potable Water System Disinfection & Backflow Certification | Plumbing Health Compliance | LOC-01 | GHXSTSHIP | CSMIA26 | 6000 Operations | 6000.06.04 | Potable Water | PDF | 2.5 MB | [link removed] | v1.0 | 2026-10-02 | 2026-10-25 | Approved | FALSE | Miami-Dade WASD backflow prevention device inspection and chlorine residual sanitation report. | Julian Clarkson | 2026-10-02 09:55 | 2026-10-02 09:55
DOC-028 | RFID Credentialing Architecture & Zone Security Matrix | Security Architecture | TSK-019 | GHXSTSHIP | CSMIA26 | 7000 Experience | 7000.50.02 | Credentialing | PDF | 4.8 MB | [link removed] | v2.0 | 2026-10-04 | 2026-10-31 | Approved | FALSE | NFC/RFID encrypted wristband allocation matrix, turnstile validation logic, and anti-passback rule. | Julian Clarkson | 2026-10-02 09:55 | 2026-10-02 09:55
DOC-029 | Marshalling Yard Freight Schedule & Dock Booking Master | Logistics Manifest Schedule | LOC-14 | GHXSTSHIP | CSMIA26 | 6000 Operations | 6000.02.01 | Freight Traffic | PDF / Excel | 6.1 MB | [link removed] | v2.2 | 2026-10-04 | 2026-10-25 | Approved | FALSE | Time-slotted semi-trailer dock schedule, yellow jacket cable protection, and trailer staging logs. | Julian Clarkson | 2026-10-02 09:55 | 2026-10-02 09:55
DOC-030 | Temporary HVAC Load Calculation & Psychrometric Cooling Plan | Climate Engineering | LOC-01 | GHXSTSHIP | CSMIA26 | 4000 Environment | 4000.51.02 | HVAC Systems | PDF | 8.0 MB | [link removed] | v1.2 | 2026-09-30 | 2026-10-31 | Approved | FALSE | 39.9-ton thermal cooling load calculation (envelope + AVL gear) and 20-ton portable spot cooler layout. | Julian Clarkson | 2026-10-02 09:55 | 2026-10-02 09:55
DOC-031 | Artist Performance Contract, Music Publishing & Sync Clearances | Talent Legal Agreement | PMT-2026-892 | GHXSTSHIP | CSMIA26 | 2000 Talent | 2000.01.01 | Legal & Licensing | PDF | 5.3 MB | [link removed] | v1.0 | 2026-09-17 | 2027-09-17 | Approved | FALSE | Executed artist agreement, PRO performance releases (ASCAP/BMI/SESAC), and global streaming sync rights. | Julian Clarkson | 2026-10-02 09:55 | 2026-10-02 09:55
DOC-032 | Incident Command Structure (ICS) & Emergency CAD Dispatch Guide | Incident Protocol Guide | TSK-018 | GHXSTSHIP | CSMIA26 | 6000 Operations | 6000.05.01 | Emergency Protocol | PDF | 6.7 MB | [link removed] | v2.0 | 2026-10-03 | 2026-10-31 | Approved | FALSE | FEMA ICS-100 compliant emergency hierarchy, multi-channel radio cadences, and AHJ notification triggers. | Julian Clarkson | 2026-10-02 09:55 | 2026-10-02 09:55
DOC-033 | Scent Diffusion Formulation & Hypoallergenic Safety Data Sheet (SDS) | Sensory Compliance | LOC-01 | GHXSTSHIP | CSMIA26 | 7000 Experience | 7000.04.01 | Sensory Safety | PDF | 3.1 MB | [link removed] | v1.1 | 2026-10-01 | 2026-10-31 | Approved | FALSE | IFRA certified fragrance compound SDS, VOC emission analysis, and cold-air nebulizer placement plot. | Julian Clarkson | 2026-10-02 09:55 | 2026-10-02 09:55
DOC-034 | Post-Event Site Restoration & Landlord Handover Inspection Log | Facility Sign-Off Protocol | LOC-01 | GHXSTSHIP | CSMIA26 | 0000 Executive | 0000.50.04 | Handover & Close | PDF | 4.0 MB | [link removed] | v1.0 | 2026-10-05 | 2026-10-31 | Approved | FALSE | Pre-lease and post-strike photographic condition survey, punch list clearance, and bond return sign-off. | Julian Clarkson | 2026-10-02 09:55 | 2026-10-02 09:55

## GL Accounts
ACCOUNT CODE | ACCOUNT NAME | ACCOUNT TYPE | TAX TYPE | NORMAL BALANCE | DESCRIPTION | STATUS | CREATED BY | CREATED AT | UPDATED AT
1000 | Cash and Bank | Asset | None | Debit | Operating bank accounts and petty cash. | Active | Julian Clarkson | 2026-09-15 | 2026-09-15
1100 | Accounts Receivable | Asset | None | Debit | Invoices issued and unpaid: hire, production fees, sponsorship. | Active | Julian Clarkson | 2026-09-15 | 2026-09-15
1200 | Prepaid Expenses and Deposits | Asset | None | Debit | Lease and vendor deposits; insurance and subscriptions paid in advance. | Active | Julian Clarkson | 2026-09-15 | 2026-09-15
1500 | Fixed Assets | Asset | None | Debit | Capitalized leasehold improvements, installed systems, furniture, fixtures and equipment. Class is carried on the URID dimension. | Active | Julian Clarkson | 2026-09-15 | 2026-09-15
2000 | Accounts Payable | Liability | None | Credit | Vendor invoices received and unpaid. | Active | Julian Clarkson | 2026-09-15 | 2026-09-15
2100 | Accrued Liabilities | Liability | None | Credit | Event costs incurred and not yet invoiced; accrued payroll. | Active | Julian Clarkson | 2026-09-15 | 2026-09-15
2200 | Deferred Revenue | Liability | None | Credit | Hire, ticket and sponsor revenue received before the event. | Active | Julian Clarkson | 2026-09-15 | 2026-09-15
2300 | Sales Tax Payable | Liability | None | Credit | Tax collected on sales and owed to the state. | Active | Julian Clarkson | 2026-09-15 | 2026-09-15
3000 | Equity | Equity | None | Credit | Owner equity and retained earnings. | Active | Julian Clarkson | 2026-09-15 | 2026-09-15
4000 | Revenue · Executive | Revenue | Tax on Sales | Credit | Private hire, production fees and ticketing invoiced by the venue. | Active | Julian Clarkson | 2026-09-15 | 2026-09-15
4300 | Revenue · Marketing | Revenue | Tax on Sales | Credit | Sponsorship cash and value in kind against evidenced deliverables. | Active | Julian Clarkson | 2026-09-15 | 2026-09-15
4700 | Revenue · Experience | Revenue | Tax on Sales | Credit | Coat check, parking, valet and other guest-paid services. | Active | Julian Clarkson | 2026-09-15 | 2026-09-15
4800 | Revenue · Hospitality | Revenue | Tax on Sales | Credit | Bar, catering and merchandise sales at the point of sale. | Active | Julian Clarkson | 2026-09-15 | 2026-09-15
5000 | Expense · Executive | Expense | Tax on Purchases | Debit | Governance, professional fees, insurance, licenses, management retainer and producer fee. | Active | Julian Clarkson | 2026-09-15 | 2026-09-15
5100 | Expense · Creative | Expense | Tax on Purchases | Debit | Creative direction, design, programming, scenic and graphics. | Active | Julian Clarkson | 2026-09-15 | 2026-09-15
5200 | Expense · Talent | Expense | Tax on Purchases | Debit | Artist fees, riders, travel, lodging and backline. | Active | Julian Clarkson | 2026-09-15 | 2026-09-15
5300 | Expense · Marketing | Expense | Tax on Purchases | Debit | Marketing, content capture, press and amplification. | Active | Julian Clarkson | 2026-09-15 | 2026-09-15
5400 | Expense · Environment | Expense | Tax on Purchases | Debit | Fabrication, signage, surfaces, furniture, install and building systems. | Active | Julian Clarkson | 2026-09-15 | 2026-09-15
5500 | Expense · Production | Expense | Tax on Purchases | Debit | Staging, rigging, power, crew, trucking and production supply. | Active | Julian Clarkson | 2026-09-15 | 2026-09-15
5600 | Expense · Operations | Expense | Tax on Purchases | Debit | Venue operations: house staff, security, medical, janitorial, waste, fire and life safety, occupancy and utilities. | Active | Julian Clarkson | 2026-09-15 | 2026-09-15
5700 | Expense · Experience | Expense | Tax on Purchases | Debit | Front of house, credentials, guest services and accessibility. | Active | Julian Clarkson | 2026-09-15 | 2026-09-15
5800 | Expense · Hospitality | Expense | Tax on Purchases | Debit | Catering, bar, ice, glassware, linen and event rentals. | Active | Julian Clarkson | 2026-09-15 | 2026-09-15
5900 | Expense · Technology | Expense | Tax on Purchases | Debit | Audio, lighting, video, network, software and access control. | Active | Julian Clarkson | 2026-09-15 | 2026-09-15

## Cost Centers
COST CENTER CODE | COST CENTER NAME | DIMENSION | SCOPE CODE | ALLOCATION SCOPE | STATUS | CREATED BY | CREATED AT | UPDATED AT
CC-VENUE | Venue · Standing Operations | Standing | CC-VENUE | Everything that runs whether or not an event happens, including occupancy | Active | Julian Clarkson | 2026-09-15 | 2026-09-15
CC-CORP | Corporate · Governance | Overhead | CC-CORP | Fee, retainer, professional services, insurance | Active | Julian Clarkson | 2026-09-15 | 2026-09-15
CC-E00 | Event 00 · Venue Startup | Event | CSMIA26-E00 | Ramp-up through handover | Active | Julian Clarkson | 2026-09-15 | 2026-09-15
CC-E01 | Event 01 · Soft Opening | Event | CSMIA26-E01 | Soft Opening event scope | Active | Julian Clarkson | 2026-09-15 | 2026-09-15
CC-E02 | Event 02 · Grand Opening | Event | CSMIA26-E02 | Grand Opening event scope | Active | Julian Clarkson | 2026-09-15 | 2026-09-15
CC-E03 | Event 03 · Artist and Management Mixer | Event | CSMIA26-E03 | Artist and Management Mixer event scope | Active | Julian Clarkson | 2026-09-15 | 2026-09-15

## Departments
CLASS CODE | DEPARTMENT NAME | EXECUTIVE LEAD | CORE FUNCTION | SCOPE | STATUS | CREATED BY | CREATED AT | UPDATED AT
0000 | Executive | Executive Producer | Governance, master project control & compliance | Master operations & overall accountability | Active | Julian Clarkson | 2026-09-15 | 2026-09-15
1000 | Creative | Creative Director | Brand assets, scenic design & art installations | Aesthetic direction & environmental design | Active | Julian Clarkson | 2026-09-15 | 2026-09-15
2000 | Talent | Head of Talent | Artist booking, schedule coordination & riders | Performer coordination & talent management | Active | Julian Clarkson | 2026-09-15 | 2026-09-15
3000 | Marketing | Head of Marketing | Marketing, content capture, press & amplification | Audience growth, social & public relations | Active | Julian Clarkson | 2026-09-15 | 2026-09-15
4000 | Environment | Master Carpenter / Build Lead | Fabrication, signage, surfaces, furniture, install & building systems | Physical structures, displays, architecture & FF&E | Active | Julian Clarkson | 2026-09-15 | 2026-09-15
5000 | Production | Technical Director | Audio, lighting, video, rigging & power distribution | Live technical systems & show production | Active | Julian Clarkson | 2026-09-15 | 2026-09-15
6000 | Operations | Director of Operations | Site infrastructure, house staff, logistics & safety | Ground operations, facilities, occupancy & compliance | Active | Julian Clarkson | 2026-09-15 | 2026-09-15
7000 | Experience | Guest Experience Manager | Front of house, credentials, guest services & accessibility | Public facing operations, journey & interactive moments | Active | Julian Clarkson | 2026-09-15 | 2026-09-15
8000 | Hospitality | Hospitality Manager | Catering, bar, ice, glassware, linen & event rentals | Food & beverage, VIP hospitality & accommodations | Active | Julian Clarkson | 2026-09-15 | 2026-09-15
9000 | Technology | Systems Engineer | Audio, lighting, video, network, software & access control | Comms infrastructure, telemetry, IT & connectivity | Active | Julian Clarkson | 2026-09-15 | 2026-09-15

## Disciplines
DISCIPLINE CODE | DISCIPLINE NAME | DEPARTMENT CLASS | DESCRIPTION | STATUS | CREATED BY | CREATED AT | UPDATED AT
0000.01 | Executive Leadership & Strategy | 0000 | canon | Active | Julian Clarkson | 2026-09-15 | 2026-09-15
0000.02 | Finance & Accounting | 0000 | canon | Active | Julian Clarkson | 2026-09-15 | 2026-09-15
0000.03 | Legal & Risk | 0000 | canon | Active | Julian Clarkson | 2026-09-15 | 2026-09-15
0000.04 | Human Resources & People | 0000 | canon | Active | Julian Clarkson | 2026-09-15 | 2026-09-15
0000.05 | Business Development & Partnerships | 0000 | canon | Active | Julian Clarkson | 2026-09-15 | 2026-09-15
0000.06 | Insurance & Permitting | 0000 | canon | Active | Julian Clarkson | 2026-09-15 | 2026-09-15
0000.50 | Governance and Client Relations | 0000 | workforce | Active | Julian Clarkson | 2026-09-15 | 2026-09-15
0000.51 | Commercial and Finance | 0000 | workforce | Active | Julian Clarkson | 2026-09-15 | 2026-09-15
0000.60 | Executive Ramp-Up Program | 0000 | ramp-up | Active | Julian Clarkson | 2026-09-15 | 2026-09-15
1000.01 | Creative Direction | 1000 | canon | Active | Julian Clarkson | 2026-09-15 | 2026-09-15
1000.02 | Experiential & Environment Design | 1000 | canon | Active | Julian Clarkson | 2026-09-15 | 2026-09-15
1000.03 | Brand & Identity Design | 1000 | canon | Active | Julian Clarkson | 2026-09-15 | 2026-09-15
1000.04 | Graphic & 2D Design | 1000 | canon | Active | Julian Clarkson | 2026-09-15 | 2026-09-15
1000.05 | Content Production | 1000 | canon | Active | Julian Clarkson | 2026-09-15 | 2026-09-15
1000.06 | Copywriting & Verbal Identity | 1000 | canon | Active | Julian Clarkson | 2026-09-15 | 2026-09-15
1000.07 | Digital & Interactive Design | 1000 | canon | Active | Julian Clarkson | 2026-09-15 | 2026-09-15
1000.08 | Intellectual Property & Licensing | 1000 | canon | Active | Julian Clarkson | 2026-09-15 | 2026-09-15
1000.50 | Programming and Creative Direction | 1000 | workforce | Active | Julian Clarkson | 2026-09-15 | 2026-09-15
1000.51 | Scenic and Graphics Production | 1000 | workforce | Active | Julian Clarkson | 2026-09-15 | 2026-09-15
1000.60 | Creative Ramp-Up Program | 1000 | ramp-up | Active | Julian Clarkson | 2026-09-15 | 2026-09-15
2000.01 | Artist Booking & Programming | 2000 | canon | Active | Julian Clarkson | 2026-09-15 | 2026-09-15
2000.02 | Music Programming & Curation | 2000 | canon | Active | Julian Clarkson | 2026-09-15 | 2026-09-15
2000.03 | Talent Advancing & Riders | 2000 | canon | Active | Julian Clarkson | 2026-09-15 | 2026-09-15
2000.04 | Casting (Performers & Ambassadors) | 2000 | canon | Active | Julian Clarkson | 2026-09-15 | 2026-09-15
2000.05 | Speakers, Hosts & MC | 2000 | canon | Active | Julian Clarkson | 2026-09-15 | 2026-09-15
2000.06 | Talent Settlement & Payments | 2000 | canon | Active | Julian Clarkson | 2026-09-15 | 2026-09-15
2000.07 | Talent Travel & Hospitality Coordination | 2000 | canon | Active | Julian Clarkson | 2026-09-15 | 2026-09-15
2000.50 | Talent Operations | 2000 | workforce | Active | Julian Clarkson | 2026-09-15 | 2026-09-15
2000.60 | Talent Ramp-Up Program | 2000 | ramp-up | Active | Julian Clarkson | 2026-09-15 | 2026-09-15
3000.01 | Brand Marketing & Campaign | 3000 | canon | Active | Julian Clarkson | 2026-09-15 | 2026-09-15
3000.02 | Social Media & Community | 3000 | canon | Active | Julian Clarkson | 2026-09-15 | 2026-09-15
3000.03 | Public Relations & Press | 3000 | canon | Active | Julian Clarkson | 2026-09-15 | 2026-09-15
3000.04 | Sponsorship Sales | 3000 | canon | Active | Julian Clarkson | 2026-09-15 | 2026-09-15
3000.05 | CRM & Audience Data | 3000 | canon | Active | Julian Clarkson | 2026-09-15 | 2026-09-15
3000.06 | Advertising & Media Buying | 3000 | canon | Active | Julian Clarkson | 2026-09-15 | 2026-09-15
3000.07 | Influencer & Creator Relations | 3000 | canon | Active | Julian Clarkson | 2026-09-15 | 2026-09-15
3000.50 | Content Capture | 3000 | workforce | Active | Julian Clarkson | 2026-09-15 | 2026-09-15
3000.51 | Audience Platforms | 3000 | workforce | Active | Julian Clarkson | 2026-09-15 | 2026-09-15
3000.60 | Marketing Ramp-Up Program | 3000 | ramp-up | Active | Julian Clarkson | 2026-09-15 | 2026-09-15
4000.01 | Construction & Carpentry | 4000 | canon | Active | Julian Clarkson | 2026-09-15 | 2026-09-15
4000.02 | Custom Fabrication | 4000 | canon | Active | Julian Clarkson | 2026-09-15 | 2026-09-15
4000.03 | Scenic & Set Fabrication | 4000 | canon | Active | Julian Clarkson | 2026-09-15 | 2026-09-15
4000.04 | Metalwork & Welding | 4000 | canon | Active | Julian Clarkson | 2026-09-15 | 2026-09-15
4000.05 | Signage & Environmental Graphics Fabrication | 4000 | canon | Active | Julian Clarkson | 2026-09-15 | 2026-09-15
4000.06 | FF&E (Furniture, Fixtures & Equipment) | 4000 | canon | Active | Julian Clarkson | 2026-09-15 | 2026-09-15
4000.07 | Surfaces & Finishes | 4000 | canon | Active | Julian Clarkson | 2026-09-15 | 2026-09-15
4000.08 | Site Infrastructure & Temporary Structures | 4000 | canon | Active | Julian Clarkson | 2026-09-15 | 2026-09-15
4000.09 | Install & De-Install | 4000 | canon | Active | Julian Clarkson | 2026-09-15 | 2026-09-15
4000.50 | Base Build Delivery | 4000 | workforce | Active | Julian Clarkson | 2026-09-15 | 2026-09-15
4000.51 | Building Systems Maintenance | 4000 | workforce | Active | Julian Clarkson | 2026-09-15 | 2026-09-15
4000.60 | Environment Ramp-Up Program | 4000 | ramp-up | Active | Julian Clarkson | 2026-09-15 | 2026-09-15
5000.01 | Audio | 5000 | canon | Active | Julian Clarkson | 2026-09-15 | 2026-09-15
5000.02 | Lighting | 5000 | canon | Active | Julian Clarkson | 2026-09-15 | 2026-09-15
5000.03 | Video & LED | 5000 | canon | Active | Julian Clarkson | 2026-09-15 | 2026-09-15
5000.04 | Staging & Decks | 5000 | canon | Active | Julian Clarkson | 2026-09-15 | 2026-09-15
5000.05 | Rigging & Motors | 5000 | canon | Active | Julian Clarkson | 2026-09-15 | 2026-09-15
5000.06 | Power & Distribution | 5000 | canon | Active | Julian Clarkson | 2026-09-15 | 2026-09-15
5000.07 | Special Effects & Atmospherics | 5000 | canon | Active | Julian Clarkson | 2026-09-15 | 2026-09-15
5000.08 | Broadcast, Capture & Streaming | 5000 | canon | Active | Julian Clarkson | 2026-09-15 | 2026-09-15
5000.09 | Show Control & Playback | 5000 | canon | Active | Julian Clarkson | 2026-09-15 | 2026-09-15
5000.10 | Backline & Instruments | 5000 | canon | Active | Julian Clarkson | 2026-09-15 | 2026-09-15
5000.50 | Production Leadership | 5000 | workforce | Active | Julian Clarkson | 2026-09-15 | 2026-09-15
5000.51 | Stage Crew | 5000 | workforce | Active | Julian Clarkson | 2026-09-15 | 2026-09-15
5000.52 | Production Supply | 5000 | workforce | Active | Julian Clarkson | 2026-09-15 | 2026-09-15
5000.60 | Production Ramp-Up Program | 5000 | ramp-up | Active | Julian Clarkson | 2026-09-15 | 2026-09-15
6000.01 | Event Operations & Production Management | 6000 | canon | Active | Julian Clarkson | 2026-09-15 | 2026-09-15
6000.02 | Logistics & Transport | 6000 | canon | Active | Julian Clarkson | 2026-09-15 | 2026-09-15
6000.03 | Labor & Crewing | 6000 | canon | Active | Julian Clarkson | 2026-09-15 | 2026-09-15
6000.04 | Security & Access Control | 6000 | canon | Active | Julian Clarkson | 2026-09-15 | 2026-09-15
6000.05 | Medical, Safety & EMS | 6000 | canon | Active | Julian Clarkson | 2026-09-15 | 2026-09-15
6000.06 | Site Operations & Facilities | 6000 | canon | Active | Julian Clarkson | 2026-09-15 | 2026-09-15
6000.07 | Credentialing & Accreditation | 6000 | canon | Active | Julian Clarkson | 2026-09-15 | 2026-09-15
6000.08 | Production Office & Workplace | 6000 | canon | Active | Julian Clarkson | 2026-09-15 | 2026-09-15
6000.09 | Waste & Environmental Services | 6000 | canon | Active | Julian Clarkson | 2026-09-15 | 2026-09-15
6000.50 | House Management | 6000 | workforce | Active | Julian Clarkson | 2026-09-15 | 2026-09-15
6000.51 | Venue Services | 6000 | workforce | Active | Julian Clarkson | 2026-09-15 | 2026-09-15
6000.52 | Event Security | 6000 | workforce | Active | Julian Clarkson | 2026-09-15 | 2026-09-15
6000.53 | Occupancy and Utilities | 6000 | xos | Active | Julian Clarkson | 2026-09-15 | 2026-09-15
6000.60 | Operations Ramp-Up Program | 6000 | ramp-up | Active | Julian Clarkson | 2026-09-15 | 2026-09-15
7000.01 | Guest Experience & Journey | 7000 | canon | Active | Julian Clarkson | 2026-09-15 | 2026-09-15
7000.02 | Activations & Brand Experiences | 7000 | canon | Active | Julian Clarkson | 2026-09-15 | 2026-09-15
7000.03 | Retail & Merchandise | 7000 | canon | Active | Julian Clarkson | 2026-09-15 | 2026-09-15
7000.04 | Sensory & Atmosphere | 7000 | canon | Active | Julian Clarkson | 2026-09-15 | 2026-09-15
7000.05 | Photo & Shareable Moments | 7000 | canon | Active | Julian Clarkson | 2026-09-15 | 2026-09-15
7000.06 | Gifting & Premiums | 7000 | canon | Active | Julian Clarkson | 2026-09-15 | 2026-09-15
7000.07 | Sponsorship Fulfillment | 7000 | canon | Active | Julian Clarkson | 2026-09-15 | 2026-09-15
7000.08 | Interactive & Immersive Experiences | 7000 | canon | Active | Julian Clarkson | 2026-09-15 | 2026-09-15
7000.50 | Front of House | 7000 | workforce | Active | Julian Clarkson | 2026-09-15 | 2026-09-15
7000.51 | Guest Safety | 7000 | workforce | Active | Julian Clarkson | 2026-09-15 | 2026-09-15
7000.60 | Experience Ramp-Up Program | 7000 | ramp-up | Active | Julian Clarkson | 2026-09-15 | 2026-09-15
8000.01 | Catering & Culinary | 8000 | canon | Active | Julian Clarkson | 2026-09-15 | 2026-09-15
8000.02 | Bar & Beverage | 8000 | canon | Active | Julian Clarkson | 2026-09-15 | 2026-09-15
8000.03 | Concessions & Vending | 8000 | canon | Active | Julian Clarkson | 2026-09-15 | 2026-09-15
8000.04 | VIP & Hospitality Services | 8000 | canon | Active | Julian Clarkson | 2026-09-15 | 2026-09-15
8000.05 | Lodging & Accommodation | 8000 | canon | Active | Julian Clarkson | 2026-09-15 | 2026-09-15
8000.06 | Front of House & Guest Services | 8000 | canon | Active | Julian Clarkson | 2026-09-15 | 2026-09-15
8000.50 | Beverage Service | 8000 | workforce | Active | Julian Clarkson | 2026-09-15 | 2026-09-15
8000.51 | Catering Service | 8000 | workforce | Active | Julian Clarkson | 2026-09-15 | 2026-09-15
8000.52 | Event Rentals | 8000 | workforce | Active | Julian Clarkson | 2026-09-15 | 2026-09-15
8000.60 | Hospitality Ramp-Up Program | 8000 | ramp-up | Active | Julian Clarkson | 2026-09-15 | 2026-09-15
9000.01 | IT & Networking | 9000 | canon | Active | Julian Clarkson | 2026-09-15 | 2026-09-15
9000.02 | Connectivity & Internet | 9000 | canon | Active | Julian Clarkson | 2026-09-15 | 2026-09-15
9000.03 | RF & Communications | 9000 | canon | Active | Julian Clarkson | 2026-09-15 | 2026-09-15
9000.04 | Ticketing & Access Technology | 9000 | canon | Active | Julian Clarkson | 2026-09-15 | 2026-09-15
9000.05 | Point of Sale & Payments | 9000 | canon | Active | Julian Clarkson | 2026-09-15 | 2026-09-15
9000.06 | Data & Analytics | 9000 | canon | Active | Julian Clarkson | 2026-09-15 | 2026-09-15
9000.07 | AR / VR / XR & Immersive Tech | 9000 | canon | Active | Julian Clarkson | 2026-09-15 | 2026-09-15
9000.08 | Cybersecurity & Systems | 9000 | canon | Active | Julian Clarkson | 2026-09-15 | 2026-09-15
9000.09 | Digital Signage & CMS | 9000 | canon | Active | Julian Clarkson | 2026-09-15 | 2026-09-15
9000.50 | Audio Systems | 9000 | workforce | Active | Julian Clarkson | 2026-09-15 | 2026-09-15
9000.51 | Lighting and Video | 9000 | workforce | Active | Julian Clarkson | 2026-09-15 | 2026-09-15
9000.52 | Venue IT | 9000 | workforce | Active | Julian Clarkson | 2026-09-15 | 2026-09-15
9000.53 | Systems Integration | 9000 | workforce | Active | Julian Clarkson | 2026-09-15 | 2026-09-15
9000.60 | Technology Ramp-Up Program | 9000 | ramp-up | Active | Julian Clarkson | 2026-09-15 | 2026-09-15

## Categories & URID Master
URID | DEPARTMENT | DISCIPLINE | CATEGORY | DEFAULT COST CENTER | DEFAULT GL ACCOUNT | SCHEMA FAMILY (XYZ) | STATUS | CREATED BY | CREATED AT | UPDATED AT
0000.01.01 | Executive | Executive Leadership & Strategy | Production Leadership | CC-CORP | 5000 | X | Active | Julian Clarkson | 2026-09-15 | 2026-09-15
0000.02.01 | Executive | Finance & Accounting | Production Accounting | CC-VENUE | 5000 | X | Active | Julian Clarkson | 2026-09-15 | 2026-09-15
0000.03.01 | Executive | Legal & Risk | Legal Services | CC-VENUE | 5000 | X | Active | Julian Clarkson | 2026-09-15 | 2026-09-15
0000.04.01 | Executive | Human Resources & People | People Operations | CC-VENUE | 5000 | X | Active | Julian Clarkson | 2026-09-15 | 2026-09-15
0000.05.01 | Executive | Business Development & Partnerships | Business Development | CC-VENUE | 5000 | X | Active | Julian Clarkson | 2026-09-15 | 2026-09-15
0000.06.01 | Executive | Insurance & Permitting | Insurance | CC-VENUE | 5000 | X | Active | Julian Clarkson | 2026-09-15 | 2026-09-15
0000.06.02 | Executive | Insurance & Permitting | Permitting | CC-VENUE | 5000 | X | Active | Julian Clarkson | 2026-09-15 | 2026-09-15
0000.50.01 | Executive | Governance and Client Relations | Client Sponsorship | CC-VENUE | 5000 | Y | Active | Julian Clarkson | 2026-09-15 | 2026-09-15
0000.50.02 | Executive | Governance and Client Relations | Operator Leadership | CC-VENUE | 5000 | Y | Active | Julian Clarkson | 2026-09-15 | 2026-09-15
0000.50.03 | Executive | Governance and Client Relations | Approval Authority | CC-VENUE | 5000 | Y | Active | Julian Clarkson | 2026-09-15 | 2026-09-15
0000.51.01 | Executive | Commercial and Finance | Financial Control | CC-CORP | 5000 | Y | Active | Julian Clarkson | 2026-09-15 | 2026-09-15
0000.51.02 | Executive | Commercial and Finance | Insurance and Risk | CC-CORP | 5000 | Y | Active | Julian Clarkson | 2026-09-15 | 2026-09-15
0000.51.03 | Executive | Commercial and Finance | Legal Counsel | CC-CORP | 5000 | Y | Active | Julian Clarkson | 2026-09-15 | 2026-09-15
0000.60.01 | Executive | Executive Ramp-Up Program | Scope Activities · Executive | CC-E00 | 5000 | Y | Active | Julian Clarkson | 2026-09-15 | 2026-09-15
0000.60.02 | Executive | Executive Ramp-Up Program | Engage Activities · Executive | CC-E00 | 5000 | Y | Active | Julian Clarkson | 2026-09-15 | 2026-09-15
0000.60.03 | Executive | Executive Ramp-Up Program | Advance Activities · Executive | CC-E00 | 5000 | Y | Active | Julian Clarkson | 2026-09-15 | 2026-09-15
0000.60.04 | Executive | Executive Ramp-Up Program | Procure Activities · Executive | CC-E00 | 5000 | Y | Active | Julian Clarkson | 2026-09-15 | 2026-09-15
0000.60.05 | Executive | Executive Ramp-Up Program | Build Activities · Executive | CC-E00 | 5000 | Y | Active | Julian Clarkson | 2026-09-15 | 2026-09-15
0000.60.06 | Executive | Executive Ramp-Up Program | Install Activities · Executive | CC-E00 | 5000 | Y | Active | Julian Clarkson | 2026-09-15 | 2026-09-15
0000.60.07 | Executive | Executive Ramp-Up Program | Operate Activities · Executive | CC-E00 | 5000 | Y | Active | Julian Clarkson | 2026-09-15 | 2026-09-15
0000.60.08 | Executive | Executive Ramp-Up Program | Amplify Activities · Executive | CC-E00 | 5000 | Y | Active | Julian Clarkson | 2026-09-15 | 2026-09-15
0000.60.09 | Executive | Executive Ramp-Up Program | Close Activities · Executive | CC-E00 | 5000 | Y | Active | Julian Clarkson | 2026-09-15 | 2026-09-15
1000.01.01 | Creative | Creative Direction | Creative Direction | CC-VENUE | 5100 | X | Active | Julian Clarkson | 2026-09-15 | 2026-09-15
1000.02.01 | Creative | Experiential & Environment Design | Environment Design | CC-VENUE | 5100 | X | Active | Julian Clarkson | 2026-09-15 | 2026-09-15
1000.03.01 | Creative | Brand & Identity Design | Brand Design | CC-VENUE | 5100 | X | Active | Julian Clarkson | 2026-09-15 | 2026-09-15
1000.04.01 | Creative | Graphic & 2D Design | Graphic Design | CC-VENUE | 5100 | X | Active | Julian Clarkson | 2026-09-15 | 2026-09-15
1000.04.02 | Creative | Graphic & 2D Design | Print Collateral | CC-VENUE | 5100 | X | Active | Julian Clarkson | 2026-09-15 | 2026-09-15
1000.05.01 | Creative | Content Production | Content Production | CC-VENUE | 5100 | X | Active | Julian Clarkson | 2026-09-15 | 2026-09-15
1000.05.02 | Creative | Content Production | Sonic Branding | CC-VENUE | 5100 | X | Active | Julian Clarkson | 2026-09-15 | 2026-09-15
1000.06.01 | Creative | Copywriting & Verbal Identity | Verbal Identity | CC-VENUE | 5100 | X | Active | Julian Clarkson | 2026-09-15 | 2026-09-15
1000.07.01 | Creative | Digital & Interactive Design | Digital Design | CC-VENUE | 5100 | X | Active | Julian Clarkson | 2026-09-15 | 2026-09-15
1000.08.01 | Creative | Intellectual Property & Licensing | Intellectual Property & Licensing | CC-VENUE | 5100 | X | Active | Julian Clarkson | 2026-09-15 | 2026-09-15
1000.50.01 | Creative | Programming and Creative Direction | Creative Direction | CC-VENUE | 5100 | Y | Active | Julian Clarkson | 2026-09-15 | 2026-09-15
1000.50.02 | Creative | Programming and Creative Direction | Programming Lead | CC-VENUE | 5100 | Y | Active | Julian Clarkson | 2026-09-15 | 2026-09-15
1000.51.01 | Creative | Scenic and Graphics Production | Signage Fabrication | CC-VENUE | 5100 | Y | Active | Julian Clarkson | 2026-09-15 | 2026-09-15
1000.51.02 | Creative | Scenic and Graphics Production | Scenic Fabrication | CC-VENUE | 5100 | Y | Active | Julian Clarkson | 2026-09-15 | 2026-09-15
1000.60.01 | Creative | Creative Ramp-Up Program | Scope Activities · Creative | CC-E00 | 5100 | Y | Active | Julian Clarkson | 2026-09-15 | 2026-09-15
1000.60.02 | Creative | Creative Ramp-Up Program | Engage Activities · Creative | CC-E00 | 5100 | Y | Active | Julian Clarkson | 2026-09-15 | 2026-09-15
1000.60.03 | Creative | Creative Ramp-Up Program | Advance Activities · Creative | CC-E00 | 5100 | Y | Active | Julian Clarkson | 2026-09-15 | 2026-09-15
1000.60.04 | Creative | Creative Ramp-Up Program | Procure Activities · Creative | CC-E00 | 5100 | Y | Active | Julian Clarkson | 2026-09-15 | 2026-09-15
1000.60.05 | Creative | Creative Ramp-Up Program | Build Activities · Creative | CC-E00 | 5100 | Y | Active | Julian Clarkson | 2026-09-15 | 2026-09-15
1000.60.06 | Creative | Creative Ramp-Up Program | Install Activities · Creative | CC-E00 | 5100 | Y | Active | Julian Clarkson | 2026-09-15 | 2026-09-15
1000.60.07 | Creative | Creative Ramp-Up Program | Operate Activities · Creative | CC-E00 | 5100 | Y | Active | Julian Clarkson | 2026-09-15 | 2026-09-15
1000.60.08 | Creative | Creative Ramp-Up Program | Amplify Activities · Creative | CC-E00 | 5100 | Y | Active | Julian Clarkson | 2026-09-15 | 2026-09-15
1000.60.09 | Creative | Creative Ramp-Up Program | Close Activities · Creative | CC-E00 | 5100 | Y | Active | Julian Clarkson | 2026-09-15 | 2026-09-15
2000.01.01 | Talent | Artist Booking & Programming | Booking | CC-VENUE | 5200 | X | Active | Julian Clarkson | 2026-09-15 | 2026-09-15
2000.02.01 | Talent | Music Programming & Curation | Curation | CC-VENUE | 5200 | X | Active | Julian Clarkson | 2026-09-15 | 2026-09-15
2000.02.02 | Talent | Music Programming & Curation | Set Programming | CC-VENUE | 5200 | X | Active | Julian Clarkson | 2026-09-15 | 2026-09-15
2000.03.01 | Talent | Talent Advancing & Riders | Advancing | CC-VENUE | 5200 | X | Active | Julian Clarkson | 2026-09-15 | 2026-09-15
2000.04.01 | Talent | Casting (Performers & Ambassadors) | Casting | CC-VENUE | 5200 | X | Active | Julian Clarkson | 2026-09-15 | 2026-09-15
2000.05.01 | Talent | Speakers, Hosts & MC | Hosts | CC-VENUE | 5200 | X | Active | Julian Clarkson | 2026-09-15 | 2026-09-15
2000.06.01 | Talent | Talent Settlement & Payments | Settlement | CC-VENUE | 5200 | X | Active | Julian Clarkson | 2026-09-15 | 2026-09-15
2000.07.01 | Talent | Talent Travel & Hospitality Coordination | Talent Travel & Hospitality Coordination | CC-VENUE | 5200 | X | Active | Julian Clarkson | 2026-09-15 | 2026-09-15
2000.50.01 | Talent | Talent Operations | Backline Technical | CC-VENUE | 5200 | Y | Active | Julian Clarkson | 2026-09-15 | 2026-09-15
2000.60.01 | Talent | Talent Ramp-Up Program | Scope Activities · Talent | CC-E00 | 5200 | Y | Active | Julian Clarkson | 2026-09-15 | 2026-09-15
2000.60.02 | Talent | Talent Ramp-Up Program | Engage Activities · Talent | CC-E00 | 5200 | Y | Active | Julian Clarkson | 2026-09-15 | 2026-09-15
2000.60.03 | Talent | Talent Ramp-Up Program | Advance Activities · Talent | CC-E00 | 5200 | Y | Active | Julian Clarkson | 2026-09-15 | 2026-09-15
2000.60.04 | Talent | Talent Ramp-Up Program | Procure Activities · Talent | CC-E00 | 5200 | Y | Active | Julian Clarkson | 2026-09-15 | 2026-09-15
2000.60.05 | Talent | Talent Ramp-Up Program | Build Activities · Talent | CC-E00 | 5200 | Y | Active | Julian Clarkson | 2026-09-15 | 2026-09-15
2000.60.06 | Talent | Talent Ramp-Up Program | Install Activities · Talent | CC-E00 | 5200 | Y | Active | Julian Clarkson | 2026-09-15 | 2026-09-15
2000.60.07 | Talent | Talent Ramp-Up Program | Operate Activities · Talent | CC-E00 | 5200 | Y | Active | Julian Clarkson | 2026-09-15 | 2026-09-15
2000.60.08 | Talent | Talent Ramp-Up Program | Amplify Activities · Talent | CC-E00 | 5200 | Y | Active | Julian Clarkson | 2026-09-15 | 2026-09-15
2000.60.09 | Talent | Talent Ramp-Up Program | Close Activities · Talent | CC-E00 | 5200 | Y | Active | Julian Clarkson | 2026-09-15 | 2026-09-15
3000.01.01 | Marketing | Brand Marketing & Campaign | Campaign | CC-VENUE | 5300 | X | Active | Julian Clarkson | 2026-09-15 | 2026-09-15
3000.02.01 | Marketing | Social Media & Community | Social | CC-VENUE | 5300 | X | Active | Julian Clarkson | 2026-09-15 | 2026-09-15
3000.03.01 | Marketing | Public Relations & Press | Public Relations | CC-VENUE | 5300 | X | Active | Julian Clarkson | 2026-09-15 | 2026-09-15
3000.04.01 | Marketing | Sponsorship Sales | Sponsorship | CC-VENUE | 5300 | X | Active | Julian Clarkson | 2026-09-15 | 2026-09-15
3000.05.01 | Marketing | CRM & Audience Data | CRM | CC-VENUE | 5300 | X | Active | Julian Clarkson | 2026-09-15 | 2026-09-15
3000.06.01 | Marketing | Advertising & Media Buying | Media | CC-VENUE | 5300 | X | Active | Julian Clarkson | 2026-09-15 | 2026-09-15
3000.07.01 | Marketing | Influencer & Creator Relations | Influencer | CC-VENUE | 5300 | X | Active | Julian Clarkson | 2026-09-15 | 2026-09-15
3000.50.01 | Marketing | Content Capture | Stills Capture | CC-VENUE | 5300 | Y | Active | Julian Clarkson | 2026-09-15 | 2026-09-15
3000.50.02 | Marketing | Content Capture | Motion Capture | CC-VENUE | 5300 | Y | Active | Julian Clarkson | 2026-09-15 | 2026-09-15
3000.50.03 | Marketing | Content Capture | Content Direction | CC-VENUE | 5300 | Y | Active | Julian Clarkson | 2026-09-15 | 2026-09-15
3000.51.01 | Marketing | Audience Platforms | Guest List and RSVP Platform | CC-VENUE | 5300 | Y | Active | Julian Clarkson | 2026-09-15 | 2026-09-15
3000.60.01 | Marketing | Marketing Ramp-Up Program | Scope Activities · Marketing | CC-E00 | 5300 | Y | Active | Julian Clarkson | 2026-09-15 | 2026-09-15
3000.60.02 | Marketing | Marketing Ramp-Up Program | Engage Activities · Marketing | CC-E00 | 5300 | Y | Active | Julian Clarkson | 2026-09-15 | 2026-09-15
3000.60.03 | Marketing | Marketing Ramp-Up Program | Advance Activities · Marketing | CC-E00 | 5300 | Y | Active | Julian Clarkson | 2026-09-15 | 2026-09-15
3000.60.04 | Marketing | Marketing Ramp-Up Program | Procure Activities · Marketing | CC-E00 | 5300 | Y | Active | Julian Clarkson | 2026-09-15 | 2026-09-15
3000.60.05 | Marketing | Marketing Ramp-Up Program | Build Activities · Marketing | CC-E00 | 5300 | Y | Active | Julian Clarkson | 2026-09-15 | 2026-09-15
3000.60.06 | Marketing | Marketing Ramp-Up Program | Install Activities · Marketing | CC-E00 | 5300 | Y | Active | Julian Clarkson | 2026-09-15 | 2026-09-15
3000.60.07 | Marketing | Marketing Ramp-Up Program | Operate Activities · Marketing | CC-E00 | 5300 | Y | Active | Julian Clarkson | 2026-09-15 | 2026-09-15
3000.60.08 | Marketing | Marketing Ramp-Up Program | Amplify Activities · Marketing | CC-E00 | 5300 | Y | Active | Julian Clarkson | 2026-09-15 | 2026-09-15
3000.60.09 | Marketing | Marketing Ramp-Up Program | Close Activities · Marketing | CC-E00 | 5300 | Y | Active | Julian Clarkson | 2026-09-15 | 2026-09-15
4000.01.01 | Environment | Construction & Carpentry | General Tools & Hardware | CC-VENUE | 5400 | X | Active | Julian Clarkson | 2026-09-15 | 2026-09-15
4000.02.01 | Environment | Custom Fabrication | Modular Build Components | CC-VENUE | 5400 | X | Active | Julian Clarkson | 2026-09-15 | 2026-09-15
4000.03.01 | Environment | Scenic & Set Fabrication | Scenic & Decorative | CC-VENUE | 5400 | X | Active | Julian Clarkson | 2026-09-15 | 2026-09-15
4000.04.01 | Environment | Metalwork & Welding | Metalwork & Welding | CC-VENUE | 5400 | X | Active | Julian Clarkson | 2026-09-15 | 2026-09-15
4000.05.01 | Environment | Signage & Environmental Graphics Fabrication | Signage Panels | CC-VENUE | 5400 | X | Active | Julian Clarkson | 2026-09-15 | 2026-09-15
4000.05.02 | Environment | Signage & Environmental Graphics Fabrication | Directional Signage | CC-VENUE | 5400 | X | Active | Julian Clarkson | 2026-09-15 | 2026-09-15
4000.06.01 | Environment | FF&E (Furniture, Fixtures & Equipment) | FF&E (Furniture, Fixtures & Equipment) | CC-VENUE | 5400 | X | Active | Julian Clarkson | 2026-09-15 | 2026-09-15
4000.07.01 | Environment | Surfaces & Finishes | Flooring & Surfaces | CC-VENUE | 5400 | X | Active | Julian Clarkson | 2026-09-15 | 2026-09-15
4000.08.01 | Environment | Site Infrastructure & Temporary Structures | Fencing & Barriers | CC-VENUE | 5400 | X | Active | Julian Clarkson | 2026-09-15 | 2026-09-15
4000.08.02 | Environment | Site Infrastructure & Temporary Structures | Tents & Structures | CC-VENUE | 5400 | X | Active | Julian Clarkson | 2026-09-15 | 2026-09-15
4000.09.01 | Environment | Install & De-Install | Aerial Lifts | CC-VENUE | 5400 | X | Active | Julian Clarkson | 2026-09-15 | 2026-09-15
4000.09.02 | Environment | Install & De-Install | Cranes | CC-VENUE | 5400 | X | Active | Julian Clarkson | 2026-09-15 | 2026-09-15
4000.50.01 | Environment | Base Build Delivery | Base Build Delivery | CC-VENUE | 5400 | Y | Active | Julian Clarkson | 2026-09-15 | 2026-09-15
4000.51.01 | Environment | Building Systems Maintenance | House Technical | CC-VENUE | 5400 | Y | Active | Julian Clarkson | 2026-09-15 | 2026-09-15
4000.51.02 | Environment | Building Systems Maintenance | Mechanical Services | CC-VENUE | 5400 | Y | Active | Julian Clarkson | 2026-09-15 | 2026-09-15
4000.51.03 | Environment | Building Systems Maintenance | Electrical Services | CC-VENUE | 5400 | Y | Active | Julian Clarkson | 2026-09-15 | 2026-09-15
4000.51.04 | Environment | Building Systems Maintenance | Plumbing Services | CC-VENUE | 5400 | Y | Active | Julian Clarkson | 2026-09-15 | 2026-09-15
4000.60.01 | Environment | Environment Ramp-Up Program | Scope Activities · Environment | CC-E00 | 5400 | Y | Active | Julian Clarkson | 2026-09-15 | 2026-09-15
4000.60.02 | Environment | Environment Ramp-Up Program | Engage Activities · Environment | CC-E00 | 5400 | Y | Active | Julian Clarkson | 2026-09-15 | 2026-09-15
4000.60.03 | Environment | Environment Ramp-Up Program | Advance Activities · Environment | CC-E00 | 5400 | Y | Active | Julian Clarkson | 2026-09-15 | 2026-09-15
4000.60.04 | Environment | Environment Ramp-Up Program | Procure Activities · Environment | CC-E00 | 5400 | Y | Active | Julian Clarkson | 2026-09-15 | 2026-09-15
4000.60.05 | Environment | Environment Ramp-Up Program | Build Activities · Environment | CC-E00 | 5400 | Y | Active | Julian Clarkson | 2026-09-15 | 2026-09-15
4000.60.06 | Environment | Environment Ramp-Up Program | Install Activities · Environment | CC-E00 | 5400 | Y | Active | Julian Clarkson | 2026-09-15 | 2026-09-15
4000.60.07 | Environment | Environment Ramp-Up Program | Operate Activities · Environment | CC-E00 | 5400 | Y | Active | Julian Clarkson | 2026-09-15 | 2026-09-15
4000.60.08 | Environment | Environment Ramp-Up Program | Amplify Activities · Environment | CC-E00 | 5400 | Y | Active | Julian Clarkson | 2026-09-15 | 2026-09-15
4000.60.09 | Environment | Environment Ramp-Up Program | Close Activities · Environment | CC-E00 | 5400 | Y | Active | Julian Clarkson | 2026-09-15 | 2026-09-15
5000.01.01 | Production | Audio | Audio Infrastructure | CC-VENUE | 5500 | X | Active | Julian Clarkson | 2026-09-15 | 2026-09-15
5000.01.02 | Production | Audio | PA Systems | CC-VENUE | 5500 | X | Active | Julian Clarkson | 2026-09-15 | 2026-09-15
5000.01.03 | Production | Audio | Microphones & DI | CC-VENUE | 5500 | X | Active | Julian Clarkson | 2026-09-15 | 2026-09-15
5000.01.04 | Production | Audio | Mixing Consoles | CC-VENUE | 5500 | X | Active | Julian Clarkson | 2026-09-15 | 2026-09-15
5000.01.05 | Production | Audio | Playback & Processing | CC-VENUE | 5500 | X | Active | Julian Clarkson | 2026-09-15 | 2026-09-15
5000.01.06 | Production | Audio | Spatial Audio | CC-VENUE | 5500 | X | Active | Julian Clarkson | 2026-09-15 | 2026-09-15
5000.02.01 | Production | Lighting | Lighting Control | CC-VENUE | 5500 | X | Active | Julian Clarkson | 2026-09-15 | 2026-09-15
5000.02.02 | Production | Lighting | Automated Fixtures | CC-VENUE | 5500 | X | Active | Julian Clarkson | 2026-09-15 | 2026-09-15
5000.03.01 | Production | Video & LED | LED Walls & Displays | CC-VENUE | 5500 | X | Active | Julian Clarkson | 2026-09-15 | 2026-09-15
5000.03.02 | Production | Video & LED | Projection | CC-VENUE | 5500 | X | Active | Julian Clarkson | 2026-09-15 | 2026-09-15
5000.04.01 | Production | Staging & Decks | Stage Infrastructure | CC-VENUE | 5500 | X | Active | Julian Clarkson | 2026-09-15 | 2026-09-15
5000.04.02 | Production | Staging & Decks | Stage Decks & Risers | CC-VENUE | 5500 | X | Active | Julian Clarkson | 2026-09-15 | 2026-09-15
5000.05.01 | Production | Rigging & Motors | Motors & Chain Hoists | CC-VENUE | 5500 | X | Active | Julian Clarkson | 2026-09-15 | 2026-09-15
5000.05.02 | Production | Rigging & Motors | Rigging Hardware | CC-VENUE | 5500 | X | Active | Julian Clarkson | 2026-09-15 | 2026-09-15
5000.05.03 | Production | Rigging & Motors | Truss | CC-VENUE | 5500 | X | Active | Julian Clarkson | 2026-09-15 | 2026-09-15
5000.06.01 | Production | Power & Distribution | Power & Electrical | CC-VENUE | 5500 | X | Active | Julian Clarkson | 2026-09-15 | 2026-09-15
5000.07.01 | Production | Special Effects & Atmospherics | Atmospheric Effects | CC-VENUE | 5500 | X | Active | Julian Clarkson | 2026-09-15 | 2026-09-15
5000.08.01 | Production | Broadcast, Capture & Streaming | Cameras & Capture | CC-VENUE | 5500 | X | Active | Julian Clarkson | 2026-09-15 | 2026-09-15
5000.09.01 | Production | Show Control & Playback | Show Control & Playback | CC-VENUE | 5500 | X | Active | Julian Clarkson | 2026-09-15 | 2026-09-15
5000.10.01 | Production | Backline & Instruments | DJ Equipment | CC-VENUE | 5500 | X | Active | Julian Clarkson | 2026-09-15 | 2026-09-15
5000.10.02 | Production | Backline & Instruments | Amplifiers & Cabinets | CC-VENUE | 5500 | X | Active | Julian Clarkson | 2026-09-15 | 2026-09-15
5000.10.03 | Production | Backline & Instruments | Drum Kits | CC-VENUE | 5500 | X | Active | Julian Clarkson | 2026-09-15 | 2026-09-15
5000.10.04 | Production | Backline & Instruments | Miscellaneous Backline | CC-VENUE | 5500 | X | Active | Julian Clarkson | 2026-09-15 | 2026-09-15
5000.10.05 | Production | Backline & Instruments | Keyboards & Controllers | CC-VENUE | 5500 | X | Active | Julian Clarkson | 2026-09-15 | 2026-09-15
5000.50.01 | Production | Production Leadership | Venue Production Management | CC-VENUE | 5500 | Y | Active | Julian Clarkson | 2026-09-15 | 2026-09-15
5000.50.02 | Production | Production Leadership | Event Production Management | CC-VENUE | 5500 | Y | Active | Julian Clarkson | 2026-09-15 | 2026-09-15
5000.51.01 | Production | Stage Crew | Stagehand | CC-VENUE | 5500 | Y | Active | Julian Clarkson | 2026-09-15 | 2026-09-15
5000.51.02 | Production | Stage Crew | Rigging | CC-VENUE | 5500 | Y | Active | Julian Clarkson | 2026-09-15 | 2026-09-15
5000.52.01 | Production | Production Supply | Equipment Rental | CC-VENUE | 5500 | Y | Active | Julian Clarkson | 2026-09-15 | 2026-09-15
5000.52.02 | Production | Production Supply | Trucking and Logistics | CC-VENUE | 5500 | Y | Active | Julian Clarkson | 2026-09-15 | 2026-09-15
5000.52.03 | Production | Production Supply | Rigging Engineering | CC-VENUE | 5500 | Y | Active | Julian Clarkson | 2026-09-15 | 2026-09-15
5000.60.01 | Production | Production Ramp-Up Program | Scope Activities · Production | CC-E00 | 5500 | Y | Active | Julian Clarkson | 2026-09-15 | 2026-09-15
5000.60.02 | Production | Production Ramp-Up Program | Engage Activities · Production | CC-E00 | 5500 | Y | Active | Julian Clarkson | 2026-09-15 | 2026-09-15
5000.60.03 | Production | Production Ramp-Up Program | Advance Activities · Production | CC-E00 | 5500 | Y | Active | Julian Clarkson | 2026-09-15 | 2026-09-15
5000.60.04 | Production | Production Ramp-Up Program | Procure Activities · Production | CC-E00 | 5500 | Y | Active | Julian Clarkson | 2026-09-15 | 2026-09-15
5000.60.05 | Production | Production Ramp-Up Program | Build Activities · Production | CC-E00 | 5500 | Y | Active | Julian Clarkson | 2026-09-15 | 2026-09-15
5000.60.06 | Production | Production Ramp-Up Program | Install Activities · Production | CC-E00 | 5500 | Y | Active | Julian Clarkson | 2026-09-15 | 2026-09-15
5000.60.07 | Production | Production Ramp-Up Program | Operate Activities · Production | CC-E00 | 5500 | Y | Active | Julian Clarkson | 2026-09-15 | 2026-09-15
5000.60.08 | Production | Production Ramp-Up Program | Amplify Activities · Production | CC-E00 | 5500 | Y | Active | Julian Clarkson | 2026-09-15 | 2026-09-15
5000.60.09 | Production | Production Ramp-Up Program | Close Activities · Production | CC-E00 | 5500 | Y | Active | Julian Clarkson | 2026-09-15 | 2026-09-15
6000.01.01 | Operations | Event Operations & Production Management | Production Management | CC-VENUE | 5600 | X | Active | Julian Clarkson | 2026-09-15 | 2026-09-15
6000.02.01 | Operations | Logistics & Transport | Forklifts & Loaders | CC-VENUE | 5600 | X | Active | Julian Clarkson | 2026-09-15 | 2026-09-15
6000.02.02 | Operations | Logistics & Transport | Flights | CC-VENUE | 5600 | X | Active | Julian Clarkson | 2026-09-15 | 2026-09-15
6000.02.03 | Operations | Logistics & Transport | Water Transport | CC-VENUE | 5600 | X | Active | Julian Clarkson | 2026-09-15 | 2026-09-15
6000.02.04 | Operations | Logistics & Transport | Ground Transport | CC-VENUE | 5600 | X | Active | Julian Clarkson | 2026-09-15 | 2026-09-15
6000.02.05 | Operations | Logistics & Transport | Cars & Trucks | CC-VENUE | 5600 | X | Active | Julian Clarkson | 2026-09-15 | 2026-09-15
6000.02.06 | Operations | Logistics & Transport | Utility Vehicles | CC-VENUE | 5600 | X | Active | Julian Clarkson | 2026-09-15 | 2026-09-15
6000.02.07 | Operations | Logistics & Transport | Trucks & Transport | CC-VENUE | 5600 | X | Active | Julian Clarkson | 2026-09-15 | 2026-09-15
6000.02.08 | Operations | Logistics & Transport | Specialty Vehicles | CC-VENUE | 5600 | X | Active | Julian Clarkson | 2026-09-15 | 2026-09-15
6000.03.01 | Operations | Labor & Crewing | Department Heads | CC-VENUE | 5600 | X | Active | Julian Clarkson | 2026-09-15 | 2026-09-15
6000.03.02 | Operations | Labor & Crewing | Certified Operators | CC-VENUE | 5600 | X | Active | Julian Clarkson | 2026-09-15 | 2026-09-15
6000.03.03 | Operations | Labor & Crewing | Event Staff | CC-VENUE | 5600 | X | Active | Julian Clarkson | 2026-09-15 | 2026-09-15
6000.03.04 | Operations | Labor & Crewing | Specialty Staff | CC-VENUE | 5600 | X | Active | Julian Clarkson | 2026-09-15 | 2026-09-15
6000.03.05 | Operations | Labor & Crewing | Technical Crew | CC-VENUE | 5600 | X | Active | Julian Clarkson | 2026-09-15 | 2026-09-15
6000.03.06 | Operations | Labor & Crewing | Staff Apparel | CC-VENUE | 5600 | X | Active | Julian Clarkson | 2026-09-15 | 2026-09-15
6000.03.07 | Operations | Labor & Crewing | Stagehands | CC-VENUE | 5600 | X | Active | Julian Clarkson | 2026-09-15 | 2026-09-15
6000.04.01 | Operations | Security & Access Control | Security & Access Control | CC-VENUE | 5600 | X | Active | Julian Clarkson | 2026-09-15 | 2026-09-15
6000.05.01 | Operations | Medical, Safety & EMS | Safety Equipment | CC-VENUE | 5600 | X | Active | Julian Clarkson | 2026-09-15 | 2026-09-15
6000.05.02 | Operations | Medical, Safety & EMS | Medical | CC-VENUE | 5600 | X | Active | Julian Clarkson | 2026-09-15 | 2026-09-15
6000.05.03 | Operations | Medical, Safety & EMS | PPE | CC-VENUE | 5600 | X | Active | Julian Clarkson | 2026-09-15 | 2026-09-15
6000.06.01 | Operations | Site Operations & Facilities | Specialty Rentals | CC-VENUE | 5600 | X | Active | Julian Clarkson | 2026-09-15 | 2026-09-15
6000.06.02 | Operations | Site Operations & Facilities | Portable Facilities | CC-VENUE | 5600 | X | Active | Julian Clarkson | 2026-09-15 | 2026-09-15
6000.06.03 | Operations | Site Operations & Facilities | Climate Control | CC-VENUE | 5600 | X | Active | Julian Clarkson | 2026-09-15 | 2026-09-15
6000.06.04 | Operations | Site Operations & Facilities | Water & Plumbing | CC-VENUE | 5600 | X | Active | Julian Clarkson | 2026-09-15 | 2026-09-15
6000.07.01 | Operations | Credentialing & Accreditation | Credentials | CC-VENUE | 5600 | X | Active | Julian Clarkson | 2026-09-15 | 2026-09-15
6000.08.01 | Operations | Production Office & Workplace | Expendables & Consumables | CC-VENUE | 5600 | X | Active | Julian Clarkson | 2026-09-15 | 2026-09-15
6000.08.02 | Operations | Production Office & Workplace | Office & Production | CC-VENUE | 5600 | X | Active | Julian Clarkson | 2026-09-15 | 2026-09-15
6000.09.01 | Operations | Waste & Environmental Services | Waste Management | CC-VENUE | 5600 | X | Active | Julian Clarkson | 2026-09-15 | 2026-09-15
6000.50.01 | Operations | House Management | House management | CC-VENUE | 5600 | Y | Active | Julian Clarkson | 2026-09-15 | 2026-09-15
6000.50.02 | Operations | House Management | Deputy house management | CC-VENUE | 5600 | Y | Active | Julian Clarkson | 2026-09-15 | 2026-09-15
6000.51.01 | Operations | Venue Services | Janitorial | CC-VENUE | 5600 | Y | Active | Julian Clarkson | 2026-09-15 | 2026-09-15
6000.51.02 | Operations | Venue Services | Waste and recycling | CC-VENUE | 5600 | Y | Active | Julian Clarkson | 2026-09-15 | 2026-09-15
6000.51.03 | Operations | Venue Services | Pest control | CC-VENUE | 5600 | Y | Active | Julian Clarkson | 2026-09-15 | 2026-09-15
6000.51.04 | Operations | Venue Services | Fire and life safety | CC-VENUE | 5600 | Y | Active | Julian Clarkson | 2026-09-15 | 2026-09-15
6000.51.05 | Operations | Venue Services | Key and access control | CC-VENUE | 5600 | Y | Active | Julian Clarkson | 2026-09-15 | 2026-09-15
6000.52.01 | Operations | Event Security | Security supervision | CC-VENUE | 5600 | Y | Active | Julian Clarkson | 2026-09-15 | 2026-09-15
6000.52.02 | Operations | Event Security | Security officer | CC-VENUE | 5600 | Y | Active | Julian Clarkson | 2026-09-15 | 2026-09-15
6000.53.01 | Operations | Occupancy and Utilities | Base rent | CC-VENUE | 5600 | X | Active | Julian Clarkson | 2026-09-15 | 2026-09-15
6000.53.02 | Operations | Occupancy and Utilities | Operating expense recovery | CC-VENUE | 5600 | X | Active | Julian Clarkson | 2026-09-15 | 2026-09-15
6000.53.03 | Operations | Occupancy and Utilities | Real estate taxes | CC-VENUE | 5600 | X | Active | Julian Clarkson | 2026-09-15 | 2026-09-15
6000.53.04 | Operations | Occupancy and Utilities | Electricity | CC-VENUE | 5600 | X | Active | Julian Clarkson | 2026-09-15 | 2026-09-15
6000.53.05 | Operations | Occupancy and Utilities | Water and sewer | CC-VENUE | 5600 | X | Active | Julian Clarkson | 2026-09-15 | 2026-09-15
6000.60.01 | Operations | Operations Ramp-Up Program | Scope Activities · Operations | CC-E00 | 5600 | Y | Active | Julian Clarkson | 2026-09-15 | 2026-09-15
6000.60.02 | Operations | Operations Ramp-Up Program | Engage Activities · Operations | CC-E00 | 5600 | Y | Active | Julian Clarkson | 2026-09-15 | 2026-09-15
6000.60.03 | Operations | Operations Ramp-Up Program | Advance Activities · Operations | CC-E00 | 5600 | Y | Active | Julian Clarkson | 2026-09-15 | 2026-09-15
6000.60.04 | Operations | Operations Ramp-Up Program | Procure Activities · Operations | CC-E00 | 5600 | Y | Active | Julian Clarkson | 2026-09-15 | 2026-09-15
6000.60.05 | Operations | Operations Ramp-Up Program | Build Activities · Operations | CC-E00 | 5600 | Y | Active | Julian Clarkson | 2026-09-15 | 2026-09-15
6000.60.06 | Operations | Operations Ramp-Up Program | Install Activities · Operations | CC-E00 | 5600 | Y | Active | Julian Clarkson | 2026-09-15 | 2026-09-15
6000.60.07 | Operations | Operations Ramp-Up Program | Operate Activities · Operations | CC-E00 | 5600 | Y | Active | Julian Clarkson | 2026-09-15 | 2026-09-15
6000.60.08 | Operations | Operations Ramp-Up Program | Amplify Activities · Operations | CC-E00 | 5600 | Y | Active | Julian Clarkson | 2026-09-15 | 2026-09-15
6000.60.09 | Operations | Operations Ramp-Up Program | Close Activities · Operations | CC-E00 | 5600 | Y | Active | Julian Clarkson | 2026-09-15 | 2026-09-15
7000.01.01 | Experience | Guest Experience & Journey | Guest Experience & Journey | CC-VENUE | 5700 | X | Active | Julian Clarkson | 2026-09-15 | 2026-09-15
7000.02.01 | Experience | Activations & Brand Experiences | Creative & Specialty | CC-VENUE | 5700 | X | Active | Julian Clarkson | 2026-09-15 | 2026-09-15
7000.02.02 | Experience | Activations & Brand Experiences | Props | CC-VENUE | 5700 | X | Active | Julian Clarkson | 2026-09-15 | 2026-09-15
7000.02.03 | Experience | Activations & Brand Experiences | Verbal Identity | CC-VENUE | 5700 | X | Active | Julian Clarkson | 2026-09-15 | 2026-09-15
7000.03.01 | Experience | Retail & Merchandise | Vendor Infrastructure | CC-VENUE | 5700 | X | Active | Julian Clarkson | 2026-09-15 | 2026-09-15
7000.03.02 | Experience | Retail & Merchandise | Packaging & Supplies | CC-VENUE | 5700 | X | Active | Julian Clarkson | 2026-09-15 | 2026-09-15
7000.03.03 | Experience | Retail & Merchandise | Display & Fixtures | CC-VENUE | 5700 | X | Active | Julian Clarkson | 2026-09-15 | 2026-09-15
7000.03.04 | Experience | Retail & Merchandise | Static Fixtures | CC-VENUE | 5700 | X | Active | Julian Clarkson | 2026-09-15 | 2026-09-15
7000.03.05 | Experience | Retail & Merchandise | Merchandise | CC-VENUE | 5700 | X | Active | Julian Clarkson | 2026-09-15 | 2026-09-15
7000.04.01 | Experience | Sensory & Atmosphere | Scent Diffusion | CC-VENUE | 5700 | X | Active | Julian Clarkson | 2026-09-15 | 2026-09-15
7000.04.02 | Experience | Sensory & Atmosphere | Aromatics | CC-VENUE | 5700 | X | Active | Julian Clarkson | 2026-09-15 | 2026-09-15
7000.04.03 | Experience | Sensory & Atmosphere | Scent Design | CC-VENUE | 5700 | X | Active | Julian Clarkson | 2026-09-15 | 2026-09-15
7000.04.04 | Experience | Sensory & Atmosphere | Scent Service | CC-VENUE | 5700 | X | Active | Julian Clarkson | 2026-09-15 | 2026-09-15
7000.04.05 | Experience | Sensory & Atmosphere | Soundscape | CC-VENUE | 5700 | X | Active | Julian Clarkson | 2026-09-15 | 2026-09-15
7000.05.01 | Experience | Photo & Shareable Moments | Photo Moments | CC-VENUE | 5700 | X | Active | Julian Clarkson | 2026-09-15 | 2026-09-15
7000.06.01 | Experience | Gifting & Premiums | Gifting | CC-VENUE | 5700 | X | Active | Julian Clarkson | 2026-09-15 | 2026-09-15
7000.06.02 | Experience | Gifting & Premiums | Premiums | CC-VENUE | 5700 | X | Active | Julian Clarkson | 2026-09-15 | 2026-09-15
7000.07.01 | Experience | Sponsorship Fulfillment | Sponsorship Fulfillment | CC-VENUE | 5700 | X | Active | Julian Clarkson | 2026-09-15 | 2026-09-15
7000.08.01 | Experience | Interactive & Immersive Experiences | Interactive & Immersive Experiences | CC-VENUE | 5700 | X | Active | Julian Clarkson | 2026-09-15 | 2026-09-15
7000.50.01 | Experience | Front of House | Front of house leadership | CC-VENUE | 5700 | Y | Active | Julian Clarkson | 2026-09-15 | 2026-09-15
7000.50.02 | Experience | Front of House | Credential check | CC-VENUE | 5700 | Y | Active | Julian Clarkson | 2026-09-15 | 2026-09-15
7000.50.03 | Experience | Front of House | Guest services | CC-VENUE | 5700 | Y | Active | Julian Clarkson | 2026-09-15 | 2026-09-15
7000.50.04 | Experience | Front of House | Coat check | CC-VENUE | 5700 | Y | Active | Julian Clarkson | 2026-09-15 | 2026-09-15
7000.51.01 | Experience | Guest Safety | Event medical | CC-VENUE | 5700 | Y | Active | Julian Clarkson | 2026-09-15 | 2026-09-15
7000.60.01 | Experience | Experience Ramp-Up Program | Scope Activities · Experience | CC-E00 | 5700 | Y | Active | Julian Clarkson | 2026-09-15 | 2026-09-15
7000.60.02 | Experience | Experience Ramp-Up Program | Engage Activities · Experience | CC-E00 | 5700 | Y | Active | Julian Clarkson | 2026-09-15 | 2026-09-15
7000.60.03 | Experience | Experience Ramp-Up Program | Advance Activities · Experience | CC-E00 | 5700 | Y | Active | Julian Clarkson | 2026-09-15 | 2026-09-15
7000.60.04 | Experience | Experience Ramp-Up Program | Procure Activities · Experience | CC-E00 | 5700 | Y | Active | Julian Clarkson | 2026-09-15 | 2026-09-15
7000.60.05 | Experience | Experience Ramp-Up Program | Build Activities · Experience | CC-E00 | 5700 | Y | Active | Julian Clarkson | 2026-09-15 | 2026-09-15
7000.60.06 | Experience | Experience Ramp-Up Program | Install Activities · Experience | CC-E00 | 5700 | Y | Active | Julian Clarkson | 2026-09-15 | 2026-09-15
7000.60.07 | Experience | Experience Ramp-Up Program | Operate Activities · Experience | CC-E00 | 5700 | Y | Active | Julian Clarkson | 2026-09-15 | 2026-09-15
7000.60.08 | Experience | Experience Ramp-Up Program | Amplify Activities · Experience | CC-E00 | 5700 | Y | Active | Julian Clarkson | 2026-09-15 | 2026-09-15
7000.60.09 | Experience | Experience Ramp-Up Program | Close Activities · Experience | CC-E00 | 5700 | Y | Active | Julian Clarkson | 2026-09-15 | 2026-09-15
8000.01.01 | Hospitality | Catering & Culinary | Guest & VIP Catering | CC-VENUE | 5800 | X | Active | Julian Clarkson | 2026-09-15 | 2026-09-15
8000.01.02 | Hospitality | Catering & Culinary | Artist & Crew Catering | CC-VENUE | 5800 | X | Active | Julian Clarkson | 2026-09-15 | 2026-09-15
8000.01.03 | Hospitality | Catering & Culinary | Service Equipment | CC-VENUE | 5800 | X | Active | Julian Clarkson | 2026-09-15 | 2026-09-15
8000.01.04 | Hospitality | Catering & Culinary | Kitchen Equipment | CC-VENUE | 5800 | X | Active | Julian Clarkson | 2026-09-15 | 2026-09-15
8000.02.01 | Hospitality | Bar & Beverage | Bar Equipment | CC-VENUE | 5800 | X | Active | Julian Clarkson | 2026-09-15 | 2026-09-15
8000.02.02 | Hospitality | Bar & Beverage | Bar Consumables | CC-VENUE | 5800 | X | Active | Julian Clarkson | 2026-09-15 | 2026-09-15
8000.03.01 | Hospitality | Concessions & Vending | Concessions & Carts | CC-VENUE | 5800 | X | Active | Julian Clarkson | 2026-09-15 | 2026-09-15
8000.04.01 | Hospitality | VIP & Hospitality Services | Amenities & Services | CC-VENUE | 5800 | X | Active | Julian Clarkson | 2026-09-15 | 2026-09-15
8000.04.02 | Hospitality | VIP & Hospitality Services | VIP & Lounge | CC-VENUE | 5800 | X | Active | Julian Clarkson | 2026-09-15 | 2026-09-15
8000.04.03 | Hospitality | VIP & Hospitality Services | Artist Hospitality | CC-VENUE | 5800 | X | Active | Julian Clarkson | 2026-09-15 | 2026-09-15
8000.04.04 | Hospitality | VIP & Hospitality Services | Lounge & VIP | CC-VENUE | 5800 | X | Active | Julian Clarkson | 2026-09-15 | 2026-09-15
8000.05.01 | Hospitality | Lodging & Accommodation | Hotels | CC-VENUE | 5800 | X | Active | Julian Clarkson | 2026-09-15 | 2026-09-15
8000.05.02 | Hospitality | Lodging & Accommodation | Alternative Lodging | CC-VENUE | 5800 | X | Active | Julian Clarkson | 2026-09-15 | 2026-09-15
8000.06.01 | Hospitality | Front of House & Guest Services | Front of House & Guest Services | CC-VENUE | 5800 | X | Active | Julian Clarkson | 2026-09-15 | 2026-09-15
8000.50.01 | Hospitality | Beverage Service | Bartending | CC-VENUE | 5800 | Y | Active | Julian Clarkson | 2026-09-15 | 2026-09-15
8000.50.02 | Hospitality | Beverage Service | Bar support | CC-VENUE | 5800 | Y | Active | Julian Clarkson | 2026-09-15 | 2026-09-15
8000.51.01 | Hospitality | Catering Service | Catering supervision | CC-VENUE | 5800 | Y | Active | Julian Clarkson | 2026-09-15 | 2026-09-15
8000.51.02 | Hospitality | Catering Service | Catering service | CC-VENUE | 5800 | Y | Active | Julian Clarkson | 2026-09-15 | 2026-09-15
8000.51.03 | Hospitality | Catering Service | Food and beverage provision | CC-VENUE | 5800 | Y | Active | Julian Clarkson | 2026-09-15 | 2026-09-15
8000.52.01 | Hospitality | Event Rentals | Linen and furniture rental | CC-VENUE | 5800 | Y | Active | Julian Clarkson | 2026-09-15 | 2026-09-15
8000.60.01 | Hospitality | Hospitality Ramp-Up Program | Scope Activities · Hospitality | CC-E00 | 5800 | Y | Active | Julian Clarkson | 2026-09-15 | 2026-09-15
8000.60.02 | Hospitality | Hospitality Ramp-Up Program | Engage Activities · Hospitality | CC-E00 | 5800 | Y | Active | Julian Clarkson | 2026-09-15 | 2026-09-15
8000.60.03 | Hospitality | Hospitality Ramp-Up Program | Advance Activities · Hospitality | CC-E00 | 5800 | Y | Active | Julian Clarkson | 2026-09-15 | 2026-09-15
8000.60.04 | Hospitality | Hospitality Ramp-Up Program | Procure Activities · Hospitality | CC-E00 | 5800 | Y | Active | Julian Clarkson | 2026-09-15 | 2026-09-15
8000.60.05 | Hospitality | Hospitality Ramp-Up Program | Build Activities · Hospitality | CC-E00 | 5800 | Y | Active | Julian Clarkson | 2026-09-15 | 2026-09-15
8000.60.06 | Hospitality | Hospitality Ramp-Up Program | Install Activities · Hospitality | CC-E00 | 5800 | Y | Active | Julian Clarkson | 2026-09-15 | 2026-09-15
8000.60.07 | Hospitality | Hospitality Ramp-Up Program | Operate Activities · Hospitality | CC-E00 | 5800 | Y | Active | Julian Clarkson | 2026-09-15 | 2026-09-15
8000.60.08 | Hospitality | Hospitality Ramp-Up Program | Amplify Activities · Hospitality | CC-E00 | 5800 | Y | Active | Julian Clarkson | 2026-09-15 | 2026-09-15
8000.60.09 | Hospitality | Hospitality Ramp-Up Program | Close Activities · Hospitality | CC-E00 | 5800 | Y | Active | Julian Clarkson | 2026-09-15 | 2026-09-15
9000.01.01 | Technology | IT & Networking | IT & Networking | CC-VENUE | 5900 | X | Active | Julian Clarkson | 2026-09-15 | 2026-09-15
9000.02.01 | Technology | Connectivity & Internet | Internet & Connectivity | CC-VENUE | 5900 | X | Active | Julian Clarkson | 2026-09-15 | 2026-09-15
9000.03.01 | Technology | RF & Communications | Two-Way Radios | CC-VENUE | 5900 | X | Active | Julian Clarkson | 2026-09-15 | 2026-09-15
9000.03.02 | Technology | RF & Communications | Intercoms | CC-VENUE | 5900 | X | Active | Julian Clarkson | 2026-09-15 | 2026-09-15
9000.04.01 | Technology | Ticketing & Access Technology | Access Control | CC-VENUE | 5900 | X | Active | Julian Clarkson | 2026-09-15 | 2026-09-15
9000.05.01 | Technology | Point of Sale & Payments | POS & Technology | CC-VENUE | 5900 | X | Active | Julian Clarkson | 2026-09-15 | 2026-09-15
9000.06.01 | Technology | Data & Analytics | Data & Analytics | CC-VENUE | 5900 | X | Active | Julian Clarkson | 2026-09-15 | 2026-09-15
9000.07.01 | Technology | AR / VR / XR & Immersive Tech | AR / VR / XR & Immersive Tech | CC-VENUE | 5900 | X | Active | Julian Clarkson | 2026-09-15 | 2026-09-15
9000.08.01 | Technology | Cybersecurity & Systems | Security Systems | CC-VENUE | 5900 | X | Active | Julian Clarkson | 2026-09-15 | 2026-09-15
9000.09.01 | Technology | Digital Signage & CMS | Digital Signage | CC-VENUE | 5900 | X | Active | Julian Clarkson | 2026-09-15 | 2026-09-15
9000.50.01 | Technology | Audio Systems | Audio system design | CC-VENUE | 5900 | Y | Active | Julian Clarkson | 2026-09-15 | 2026-09-15
9000.50.02 | Technology | Audio Systems | Front of house audio | CC-VENUE | 5900 | Y | Active | Julian Clarkson | 2026-09-15 | 2026-09-15
9000.50.03 | Technology | Audio Systems | Stage audio | CC-VENUE | 5900 | Y | Active | Julian Clarkson | 2026-09-15 | 2026-09-15
9000.50.04 | Technology | Audio Systems | Loudspeaker supply | CC-VENUE | 5900 | Y | Active | Julian Clarkson | 2026-09-15 | 2026-09-15
9000.51.01 | Technology | Lighting and Video | Lighting operation | CC-VENUE | 5900 | Y | Active | Julian Clarkson | 2026-09-15 | 2026-09-15
9000.51.02 | Technology | Lighting and Video | Video operation | CC-VENUE | 5900 | Y | Active | Julian Clarkson | 2026-09-15 | 2026-09-15
9000.52.01 | Technology | Venue IT | Network provision | CC-VENUE | 5900 | Y | Active | Julian Clarkson | 2026-09-15 | 2026-09-15
9000.52.02 | Technology | Venue IT | Access control and CCTV | CC-VENUE | 5900 | Y | Active | Julian Clarkson | 2026-09-15 | 2026-09-15
9000.52.03 | Technology | Venue IT | Point of sale | CC-VENUE | 5900 | Y | Active | Julian Clarkson | 2026-09-15 | 2026-09-15
9000.53.01 | Technology | Systems Integration | Audiovisual integration | CC-VENUE | 5900 | Y | Active | Julian Clarkson | 2026-09-15 | 2026-09-15
9000.60.01 | Technology | Technology Ramp-Up Program | Scope Activities · Technology | CC-E00 | 5900 | Y | Active | Julian Clarkson | 2026-09-15 | 2026-09-15
9000.60.02 | Technology | Technology Ramp-Up Program | Engage Activities · Technology | CC-E00 | 5900 | Y | Active | Julian Clarkson | 2026-09-15 | 2026-09-15
9000.60.03 | Technology | Technology Ramp-Up Program | Advance Activities · Technology | CC-E00 | 5900 | Y | Active | Julian Clarkson | 2026-09-15 | 2026-09-15
9000.60.04 | Technology | Technology Ramp-Up Program | Procure Activities · Technology | CC-E00 | 5900 | Y | Active | Julian Clarkson | 2026-09-15 | 2026-09-15
9000.60.05 | Technology | Technology Ramp-Up Program | Build Activities · Technology | CC-E00 | 5900 | Y | Active | Julian Clarkson | 2026-09-15 | 2026-09-15
9000.60.06 | Technology | Technology Ramp-Up Program | Install Activities · Technology | CC-E00 | 5900 | Y | Active | Julian Clarkson | 2026-09-15 | 2026-09-15
9000.60.07 | Technology | Technology Ramp-Up Program | Operate Activities · Technology | CC-E00 | 5900 | Y | Active | Julian Clarkson | 2026-09-15 | 2026-09-15
9000.60.08 | Technology | Technology Ramp-Up Program | Amplify Activities · Technology | CC-E00 | 5900 | Y | Active | Julian Clarkson | 2026-09-15 | 2026-09-15
9000.60.09 | Technology | Technology Ramp-Up Program | Close Activities · Technology | CC-E00 | 5900 | Y | Active | Julian Clarkson | 2026-09-15 | 2026-09-15

## Teams
TEAM CODE | TEAM NAME | WORKGROUP TAG | DEPARTMENT CLASS | LEAD ROLE | RESPONSIBILITIES | STATUS | CREATED BY | CREATED AT | UPDATED AT
0000-T01 | Executive Leadership | #EXEC-LEAD | 0000 | Executive Producer | Executive strategy, partner governance & decision authority | Active | Julian Clarkson | 2026-09-15 | 2026-09-15
0000-T02 | Finance & Accounting | #EXEC-FIN | 0000 | Finance Director | Budget management, job-costing, AP/AR & audit controls | Active | Julian Clarkson | 2026-09-15 | 2026-09-15
0000-T03 | Insurance & Permitting | #EXEC-PERM | 0000 | Permit Coordinator | Insurance binders, municipal permits & AHJ liaison | Active | Julian Clarkson | 2026-09-15 | 2026-09-15
0000-T04 | Legal & Risk Management | #EXEC-LEGL | 0000 | Legal Counsel | Contracts, vendor MSAs, IP clearance & risk register | Active | Julian Clarkson | 2026-09-15 | 2026-09-15
0000-T05 | Sustainability & ESG | #EXEC-ESG | 0000 | Sustainability Lead | Waste diversion, energy efficiency & sustainable materials | Active | Julian Clarkson | 2026-09-15 | 2026-09-15
0000-T00 | Executive (Unassigned) | #EXEC-GEN | 0000 | Executive Producer | General executive administration & reserve scope | Active | Julian Clarkson | 2026-09-15 | 2026-09-15
1000-T01 | Brand Identity & Toolkit | #CREA-ID | 1000 | Brand Designer | Brand guidelines, sub-branding & design toolkit application | Active | Julian Clarkson | 2026-09-15 | 2026-09-15
1000-T02 | Creative Direction | #CREA-DIR | 1000 | Creative Director | Overarching visual vision, aesthetic direction & themes | Active | Julian Clarkson | 2026-09-15 | 2026-09-15
1000-T03 | FF&E Specification | #CREA-FFE | 1000 | Interior Designer | Furniture, fixtures, finishes & accessory curation | Active | Julian Clarkson | 2026-09-15 | 2026-09-15
1000-T04 | Graphics & Print Design | #CREA-PRNT | 1000 | Graphic Designer | Signage graphics, menus, invitations & printed collateral | Active | Julian Clarkson | 2026-09-15 | 2026-09-15
1000-T05 | Interior Design | #CREA-INT | 1000 | Lead Interior Designer | Space planning, finishes palette, textile and decor styling | Active | Julian Clarkson | 2026-09-15 | 2026-09-15
1000-T06 | Programming & Curation | #CREA-PROG | 1000 | Programming Lead | Event concepts, artist storytelling & calendar narrative | Active | Julian Clarkson | 2026-09-15 | 2026-09-15
1000-T00 | Creative (Unassigned) | #CREA-GEN | 1000 | Creative Director | General creative development & visual overflow | Active | Julian Clarkson | 2026-09-15 | 2026-09-15
2000-T01 | Artist Production | #TAL-PROD | 2000 | Artist Production Lead | Stage advancement, tech riders, hospitality advancing | Active | Julian Clarkson | 2026-09-15 | 2026-09-15
2000-T02 | Artists & Repertoire (A&R) | #TAL-AR | 2000 | A&R Manager | Talent discovery, curation, relationship management | Active | Julian Clarkson | 2026-09-15 | 2026-09-15
2000-T03 | Casting & Booking | #TAL-BOOK | 2000 | Talent Buyer | Talent negotiations, deal memos, contracts & offers | Active | Julian Clarkson | 2026-09-15 | 2026-09-15
2000-T00 | Talent (Unassigned) | #TAL-GEN | 2000 | Head of Talent | General talent operations & performance reserve | Active | Julian Clarkson | 2026-09-15 | 2026-09-15
3000-T01 | Brand Marketing | #MKT-BRND | 3000 | Marketing Director | Campaign strategy, go-to-market execution & messaging | Active | Julian Clarkson | 2026-09-15 | 2026-09-15
3000-T02 | Content Production | #MKT-CONT | 3000 | Content Producer | On-site photo/video capture, editing & asset delivery | Active | Julian Clarkson | 2026-09-15 | 2026-09-15
3000-T03 | Public Relations | #MKT-PR | 3000 | PR Manager | Media relations, press releases & earned media tracking | Active | Julian Clarkson | 2026-09-15 | 2026-09-15
3000-T04 | Social Media | #MKT-SOC | 3000 | Social Media Lead | Real-time coverage, community management & social distribution | Active | Julian Clarkson | 2026-09-15 | 2026-09-15
3000-T00 | Marketing (Unassigned) | #MKT-GEN | 3000 | Head of Marketing | General marketing & promotional reserves | Active | Julian Clarkson | 2026-09-15 | 2026-09-15
4000-T01 | Carpentry & Framing | #ENV-CARP | 4000 | Lead Carpenter | Structural framing, wall panels, partition builds | Active | Julian Clarkson | 2026-09-15 | 2026-09-15
4000-T02 | Demolition & Site Prep | #ENV-DEMO | 4000 | Site Prep Lead | Surface prep, cosmetic demo & clean base condition | Active | Julian Clarkson | 2026-09-15 | 2026-09-15
4000-T03 | Fabrication & Scenic Construction | #ENV-SCEN | 4000 | Scenic Lead | Scenic set builds, facade elements & artistic fabrications | Active | Julian Clarkson | 2026-09-15 | 2026-09-15
4000-T04 | Install & Load-In | #ENV-INST | 4000 | Install Supervisor | Site installation, environmental setup & strike management | Active | Julian Clarkson | 2026-09-15 | 2026-09-15
4000-T05 | MEP (Mech/Elec/Plumb) | #ENV-MEP | 4000 | Master Electrician/Plumber | HVAC systems, electrical rough-ins & plumbing maintenance | Active | Julian Clarkson | 2026-09-15 | 2026-09-15
4000-T06 | Millwork & Casework | #ENV-MILL | 4000 | Master Millworker | Custom bar builds, reception desks & architectural millwork | Active | Julian Clarkson | 2026-09-15 | 2026-09-15
4000-T07 | Signage Fabrication | #ENV-SIGN | 4000 | Signage Lead | Dimensional signage, wayfinding panels & neon production | Active | Julian Clarkson | 2026-09-15 | 2026-09-15
4000-T08 | Soft Goods & Drape | #ENV-DRAP | 4000 | Soft Goods Tech | Pipe and drape, velour masking, fabric swagging & upholstery | Active | Julian Clarkson | 2026-09-15 | 2026-09-15
4000-T09 | Specialty Fabrication | #ENV-SPEC | 4000 | Specialty Fabricator | Acrylics, metalwork welding & hero installations | Active | Julian Clarkson | 2026-09-15 | 2026-09-15
4000-T10 | Structural | #ENV-STRC | 4000 | Structural Engineer | PE load calculations, stamped drawings & stage engineering | Active | Julian Clarkson | 2026-09-15 | 2026-09-15
4000-T11 | Surfaces & Finishes | #ENV-SURF | 4000 | Finishes Specialist | Flooring, marley, event carpet, turf & paint finishes | Active | Julian Clarkson | 2026-09-15 | 2026-09-15
4000-T00 | Environment (Unassigned) | #ENV-GEN | 4000 | Master Carpenter | General environmental build & reserve scope | Active | Julian Clarkson | 2026-09-15 | 2026-09-15
5000-T01 | Audio Production | #PROD-AUD | 5000 | Head of Audio (A1) | PA system tuning, mixing consoles, wireless mics, backline | Active | Julian Clarkson | 2026-09-15 | 2026-09-15
5000-T02 | Lasers & Special FX | #PROD-SFX | 5000 | SFX Technician | Cold sparks, cryo CO2, haze, lasers, confetti cannons | Active | Julian Clarkson | 2026-09-15 | 2026-09-15
5000-T03 | Lighting Production | #PROD-LGT | 5000 | Lighting Designer (LD) | Moving heads, truss wash, control consoles, programmed looks | Active | Julian Clarkson | 2026-09-15 | 2026-09-15
5000-T04 | Power & Electrical (Event) | #PROD-PWR | 5000 | Chief Electrician | Temporary generator power, distro boxes, feeder cables | Active | Julian Clarkson | 2026-09-15 | 2026-09-15
5000-T05 | Rigging | #PROD-RIG | 5000 | Head Rigger | Motors, truss towers, overhead bridle points, rigging math | Active | Julian Clarkson | 2026-09-15 | 2026-09-15
5000-T06 | Video Production | #PROD-VID | 5000 | Video Director | LED walls, projection mapping, IMAG cameras, media servers | Active | Julian Clarkson | 2026-09-15 | 2026-09-15
5000-T00 | Production (Unassigned) | #PROD-GEN | 5000 | Technical Director | General technical production & show equipment reserve | Active | Julian Clarkson | 2026-09-15 | 2026-09-15
6000-T01 | Back of House Operations | #OPS-BOH | 6000 | BOH Coordinator | Dressing rooms, green room setup, production office | Active | Julian Clarkson | 2026-09-15 | 2026-09-15
6000-T02 | Crew Services | #OPS-CREW | 6000 | Crew Coordinator | Stagehand dispatch, union calls, crew catering & hospitality | Active | Julian Clarkson | 2026-09-15 | 2026-09-15
6000-T03 | Life Safety & Harm Reduction | #OPS-SAFE | 6000 | Safety Officer | First aid, fire watch, crowd management kits, AED checks | Active | Julian Clarkson | 2026-09-15 | 2026-09-15
6000-T04 | Logistics & Distribution | #OPS-LOGI | 6000 | Logistics Manager | Inbound freight, dock scheduling, drayage & transport | Active | Julian Clarkson | 2026-09-15 | 2026-09-15
6000-T05 | Medical & Emergency Services | #OPS-MED | 6000 | Lead Medic | On-site paramedics, standby ambulance, medical tent | Active | Julian Clarkson | 2026-09-15 | 2026-09-15
6000-T06 | Procurement & Supply Chain | #OPS-PROC | 6000 | Procurement Lead | Rental PO issuance, vendor sourcing, contract negotiations | Active | Julian Clarkson | 2026-09-15 | 2026-09-15
6000-T07 | Site Operations | #OPS-SITE | 6000 | Site Ops Manager | Fencing, barricades, luxury restroom trailers, heavy machinery | Active | Julian Clarkson | 2026-09-15 | 2026-09-15
6000-T08 | Venue (Rent/Insurance/Licensing) | #OPS-VEN | 6000 | Venue Manager | Lease governance, base rent, property taxes, occupancy COI | Active | Julian Clarkson | 2026-09-15 | 2026-09-15
6000-T09 | Warehousing & Inventory | #OPS-WHSE | 6000 | Warehouse Supervisor | Asset tracking, depot check-in/out, storage management | Active | Julian Clarkson | 2026-09-15 | 2026-09-15
6000-T00 | Operations (Unassigned) | #OPS-GEN | 6000 | Director of Operations | General site operations & facilities reserve | Active | Julian Clarkson | 2026-09-15 | 2026-09-15
7000-T01 | Accessibility Services | #EXP-ADA | 7000 | ADA Coordinator | Accessible routes, viewing platforms, sensory calming areas | Active | Julian Clarkson | 2026-09-15 | 2026-09-15
7000-T02 | Activations & Brand Experiences | #EXP-ACTV | 7000 | Activation Lead | Sponsor footprints, interactive brand installations | Active | Julian Clarkson | 2026-09-15 | 2026-09-15
7000-T03 | Experience & Narrative Design | #EXP-DSGN | 7000 | Experience Designer | Guest journey mapping, touchpoint choreography, sensory flow | Active | Julian Clarkson | 2026-09-15 | 2026-09-15
7000-T04 | Interactive & Immersive | #EXP-IMMR | 7000 | Immersive Producer | Photo booths, 360 cameras, RFID triggers, digital interactives | Active | Julian Clarkson | 2026-09-15 | 2026-09-15
7000-T05 | Merchandising | #EXP-MRCH | 7000 | Merch Manager | Retail kiosks, point of sale, inventory counts, shopping bags | Active | Julian Clarkson | 2026-09-15 | 2026-09-15
7000-T00 | Experience (Unassigned) | #EXP-GEN | 7000 | Guest Experience Manager | General guest experience & public-facing reserve | Active | Julian Clarkson | 2026-09-15 | 2026-09-15
8000-T01 | Beverage Operations | #HOSP-BEV | 8000 | Bar Director | Mobile bars, draft systems, cocktail program, liquor license | Active | Julian Clarkson | 2026-09-15 | 2026-09-15
8000-T02 | Catering Services | #HOSP-CATR | 8000 | Catering Manager | Buffets, passed canapés, craft services, meal buyouts | Active | Julian Clarkson | 2026-09-15 | 2026-09-15
8000-T03 | Culinary Operations | #HOSP-CULN | 8000 | Executive Chef | Kitchen trailers, food safety prep, chef collaboration menus | Active | Julian Clarkson | 2026-09-15 | 2026-09-15
8000-T04 | Hospitality Management | #HOSP-MGMT | 8000 | Hospitality Director | Artist hotel room blocks, touring travel, green room care | Active | Julian Clarkson | 2026-09-15 | 2026-09-15
8000-T05 | VIP Operations | #HOSP-VIP | 8000 | VIP Concierge | VIP lounge furniture, bottle service, luxury amenities | Active | Julian Clarkson | 2026-09-15 | 2026-09-15
8000-T00 | Hospitality (Unassigned) | #HOSP-GEN | 8000 | Hospitality Manager | General hospitality & catering reserve | Active | Julian Clarkson | 2026-09-15 | 2026-09-15
9000-T01 | AR / VR / XR & Innovation | #TECH-XR | 9000 | Creative Tech Lead | Virtual production, spatial compute, AR filters, holograms | Active | Julian Clarkson | 2026-09-15 | 2026-09-15
9000-T02 | Access Control & Ticketing Tech | #TECH-ACCS | 9000 | Access Tech Lead | RFID turnstiles, handheld scanners, ticket validation | Active | Julian Clarkson | 2026-09-15 | 2026-09-15
9000-T03 | Cybersecurity & Data Privacy | #TECH-SEC | 9000 | InfoSec Lead | Network encryption, patron data compliance & POS hardening | Active | Julian Clarkson | 2026-09-15 | 2026-09-15
9000-T04 | Data & Content Pipeline | #TECH-DATA | 9000 | Data Engineer | Footfall telemetry, live dash feeds, cloud archiving | Active | Julian Clarkson | 2026-09-15 | 2026-09-15
9000-T05 | Database Management | #TECH-DB | 9000 | Database Administrator | Relational database schema, 3NF models & sync pipelines | Active | Julian Clarkson | 2026-09-15 | 2026-09-15
9000-T06 | IT & Network Infrastructure | #TECH-NET | 9000 | Network Engineer | Managed switches, Wi-Fi APs, fiber, cellular failover | Active | Julian Clarkson | 2026-09-15 | 2026-09-15
9000-T07 | Studio & Podcast Technology | #TECH-STDO | 9000 | Broadcast Engineer | Studio multicam capture, acoustic treatment, live mix rig | Active | Julian Clarkson | 2026-09-15 | 2026-09-15
9000-T00 | Technology (Unassigned) | #TECH-GEN | 9000 | Systems Engineer | General technology & comms reserve | Active | Julian Clarkson | 2026-09-15 | 2026-09-15

## Counterparty Types
CLASSIFICATION CODE | COUNTERPARTY TYPE | VENDOR CLASS | CLEARANCE TIER | COMPLIANCE REQUIREMENTS | DEFAULT GL ACCOUNT | STATUS | CREATED BY | CREATED AT | UPDATED AT
CP-AVINT | AV Integrator | Class B | Tier 2 - Technical Lead | Designs and installs audiovisual systems against a specification. | 5900 | Active | Julian Clarkson | 2026-09-15 | 2026-09-15
CP-ACCT | Accounting Services | Class A | Tier 1 - Executive Master | Bookkeeping, accounts payable and statutory filing. | 5000 | Active | Julian Clarkson | 2026-09-15 | 2026-09-15
CP-AUDPLY | Audio Supply | Class B | Tier 2 - Technical Lead | Supplies loudspeaker and audio hardware, often manufacturer-direct. | 5500 | Active | Julian Clarkson | 2026-09-15 | 2026-09-15
CP-BCST | Broadcast Services | Class B | Tier 2 - Technical Lead | Live broadcast, streaming and dedicated circuit provision. | 5500 | Active | Julian Clarkson | 2026-09-15 | 2026-09-15
CP-CATRBEV | Catering and Beverage | Class F | Tier 3 - Operations Ops | Food and beverage provision, bar service and kitchen operation. | 5800 | Active | Julian Clarkson | 2026-09-15 | 2026-09-15
CP-EQPRENT | Equipment Rental | Class R | Tier 3 - Operations Ops | Short-term hire of production, power, staging and furniture stock. | 5500 | Active | Julian Clarkson | 2026-09-15 | 2026-09-15
CP-FABSIGN | Fabrication and Signage | Class D | Tier 3 - Operations Ops | Scenic, millwork and signage fabrication and installation. | 5400 | Active | Julian Clarkson | 2026-09-15 | 2026-09-15
CP-FACIL | Facilities Services | Class C | Tier 4 - Standard Commercial | Waste, pest, grounds and building services on a recurring scope. | 5600 | Active | Julian Clarkson | 2026-09-15 | 2026-09-15
CP-INSBRK | Insurance Broker | Class A | Tier 1 - Executive Master | Places and maintains cover and issues certificates of insurance. | 5000 | Active | Julian Clarkson | 2026-09-15 | 2026-09-15
CP-JANIT | Janitorial Services | Class C | Tier 4 - Standard Commercial | Cleaning and event turnaround. | 5600 | Active | Julian Clarkson | 2026-09-15 | 2026-09-15
CP-LEGAL | Legal Services | Class A | Tier 1 - Executive Master | Contracting, licensing and regulatory counsel. | 5000 | Active | Julian Clarkson | 2026-09-15 | 2026-09-15
CP-LIFESAFE | Life Safety Services | Class G | Tier 1 - Regulatory Standby | Fire, suppression, alarm and emergency systems inspection and service. | 5600 | Active | Julian Clarkson | 2026-09-15 | 2026-09-15
CP-LOGFRT | Logistics and Freight | Class T | Tier 4 - Standard Commercial | Trucking, carnet, freight forwarding and crew travel. | 5600 | Active | Julian Clarkson | 2026-09-15 | 2026-09-15
CP-MEP | MEP Contractor | Class B | Tier 2 - Technical Lead | Mechanical, electrical or plumbing trade contractor. | 5400 | Active | Julian Clarkson | 2026-09-15 | 2026-09-15
CP-RIGENG | Rigging Engineering | Class B | Tier 2 - Technical Lead | Structural rigging design, certification and inspection. | 5500 | Active | Julian Clarkson | 2026-09-15 | 2026-09-15
CP-SECSRV | Security Services | Class A | Tier 1 - Executive Master | Guarding, door, perimeter and floor coverage. | 5600 | Active | Julian Clarkson | 2026-09-15 | 2026-09-15
CP-SECTECH | Security Technology | Class B | Tier 2 - Technical Lead | Access control, credentialing and CCTV hardware and software. | 5900 | Active | Julian Clarkson | 2026-09-15 | 2026-09-15
CP-SOFTPFAT | Software and Platform | Class S | Tier 3 - Operations Ops | Licensed software: guest list, point of sale, document management. | 5900 | Active | Julian Clarkson | 2026-09-15 | 2026-09-15
CP-SPONSOR | Sponsor | Class X | Tier 1 - Executive Master | Commercial partner buying rights and integration. | 4300 | Active | Julian Clarkson | 2026-09-15 | 2026-09-15
CP-TALAGCY | Talent Agency | Class A | Tier 1 - Executive Master | Represents artists and negotiates engagement terms. | 5200 | Active | Julian Clarkson | 2026-09-15 | 2026-09-15
CP-TELECOM | Telecommunications | Class B | Tier 2 - Technical Lead | Circuits, connectivity and network provision. | 5900 | Active | Julian Clarkson | 2026-09-15 | 2026-09-15
CP-UNCLASS | Unclassified Vendor | Class U | Tier 5 - Delivery & Supplier | Awaiting classification; resolve before the contract is executed. | 5000 | Active | Julian Clarkson | 2026-09-15 | 2026-09-15
CP-LANDLORD | Landlord | Class A | Tier 1 - Executive Master | Lease, occupancy and building services per the proposal dated 27 May 2026. | 5600 | Active | Julian Clarkson | 2026-09-15 | 2026-09-15

## Verbiage Library
RECORD ID | ORGANIZATION | PROJECT | DEPARTMENT | CATEGORY | SUB CATEGORY | VERBIAGE | TITLE | BODY | DESCRIPTION | STATUS | FLAG | NOTES | CREATED BY | CREATED AT | UPDATED AT
VRB-001 | GHXSTSHIP | CSMIA26 | Guest Experience | Signage & Wayfinding | Access Control | 18+ | 18+ |  | Age restriction credential sign | Active | FALSE | Central copy library authorization | Julian Clarkson | 2026-09-30 13:05 | 2026-09-30 13:05
VRB-002 | GHXSTSHIP | CSMIA26 | Guest Experience | Signage & Wayfinding | Access Control | 21+ | 21+ |  | Age restriction beverage sign | Active | FALSE | Central copy library authorization | Julian Clarkson | 2026-09-30 13:05 | 2026-09-30 13:05
VRB-003 | GHXSTSHIP | CSMIA26 | Guest Experience | Signage & Wayfinding | Access Control | 21+ WRISTBANDS | 21+ WRISTBANDS |  | Drinking wristband distribution station | Active | FALSE | Central copy library authorization | Julian Clarkson | 2026-09-30 13:05 | 2026-09-30 13:05
VRB-004 | GHXSTSHIP | CSMIA26 | Guest Experience | Signage & Wayfinding | Accessibility | ACCESSIBILITY SERVICES | ACCESSIBILITY SERVICES |  | ADA services center wayfinding | Active | FALSE | Central copy library authorization | Julian Clarkson | 2026-09-30 13:05 | 2026-09-30 13:05
VRB-005 | GHXSTSHIP | CSMIA26 | Guest Experience | Signage & Wayfinding | Accessibility | ACCESSIBLE VIEWING AREA | ACCESSIBLE VIEWING AREA |  | ADA elevated viewing platform sign | Active | FALSE | Central copy library authorization | Julian Clarkson | 2026-09-30 13:05 | 2026-09-30 13:05
VRB-006 | GHXSTSHIP | CSMIA26 | Guest Experience | Signage & Wayfinding | Accessibility | ADA | ADA |  | General accessibility designation | Active | FALSE | Central copy library authorization | Julian Clarkson | 2026-09-30 13:05 | 2026-09-30 13:05
VRB-007 | GHXSTSHIP | CSMIA26 | Guest Experience | Signage & Wayfinding | Accessibility | ADA ACCESSIBLE ENTRANCE | ADA ACCESSIBLE ENTRANCE |  | Dedicated accessible portal sign | Active | FALSE | Central copy library authorization | Julian Clarkson | 2026-09-30 13:05 | 2026-09-30 13:05
VRB-008 | GHXSTSHIP | CSMIA26 | Site Operations | Signage & Wayfinding | Camping | ADA CAMPING | ADA CAMPING |  | Accessible campground zone marker | Active | FALSE | Central copy library authorization | Julian Clarkson | 2026-09-30 13:05 | 2026-09-30 13:05
VRB-009 | GHXSTSHIP | CSMIA26 | Site Operations | Signage & Wayfinding | Camping | ADA CAMPING CHECK-IN | ADA CAMPING CHECK-IN |  | Accessible camping check-in lane | Active | FALSE | Central copy library authorization | Julian Clarkson | 2026-09-30 13:05 | 2026-09-30 13:05
VRB-010 | GHXSTSHIP | CSMIA26 | Guest Experience | Signage & Wayfinding | Accessibility | ADA ENTRANCE | ADA ENTRANCE |  | Accessible ingress lane indicator | Active | FALSE | Central copy library authorization | Julian Clarkson | 2026-09-30 13:05 | 2026-09-30 13:05
VRB-011 | GHXSTSHIP | CSMIA26 | Site Operations | Signage & Wayfinding | Transportation | ADA LOADING & UNLOADING | ADA LOADING & UNLOADING |  | Accessible passenger transfer curb | Active | FALSE | Central copy library authorization | Julian Clarkson | 2026-09-30 13:05 | 2026-09-30 13:05
VRB-012 | GHXSTSHIP | CSMIA26 | Site Operations | Signage & Wayfinding | Parking | ADA PARKING | ADA PARKING |  | Designated accessible vehicle stalls | Active | FALSE | Central copy library authorization | Julian Clarkson | 2026-09-30 13:05 | 2026-09-30 13:05
VRB-013 | GHXSTSHIP | CSMIA26 | Site Operations | Signage & Wayfinding | Transportation | ADA SHUTTLE STOP | ADA SHUTTLE STOP |  | Accessible transit stop marker | Active | FALSE | Central copy library authorization | Julian Clarkson | 2026-09-30 13:05 | 2026-09-30 13:05
VRB-014 | GHXSTSHIP | CSMIA26 | Site Operations | Signage & Wayfinding | Transportation | ADA SHUTTLE STOP # | ADA SHUTTLE STOP # |  | Numbered accessible shuttle station | Active | FALSE | Central copy library authorization | Julian Clarkson | 2026-09-30 13:05 | 2026-09-30 13:05
VRB-015 | GHXSTSHIP | CSMIA26 | Guest Experience | Signage & Wayfinding | Accessibility | ADA WRISTBAND POLICIES | ADA WRISTBAND POLICIES |  | Accessibility credential rules placard | Active | FALSE | Central copy library authorization | Julian Clarkson | 2026-09-30 13:05 | 2026-09-30 13:05
VRB-016 | GHXSTSHIP | CSMIA26 | Guest Experience | Signage & Wayfinding | Artist Hospitality | ARTIST CHECK-IN | ARTIST CHECK-IN |  | Talent check-in portal sign | Active | FALSE | Central copy library authorization | Julian Clarkson | 2026-09-30 13:05 | 2026-09-30 13:05
VRB-017 | GHXSTSHIP | CSMIA26 | Guest Experience | Signage & Wayfinding | Artist Hospitality | ARTIST COMPOUND | ARTIST COMPOUND |  | Talent hospitality perimeter banner | Active | FALSE | Central copy library authorization | Julian Clarkson | 2026-09-30 13:05 | 2026-09-30 13:05
VRB-018 | GHXSTSHIP | CSMIA26 | Guest Experience | Signage & Wayfinding | Artist Hospitality | ARTIST CONCIERGE | ARTIST CONCIERGE |  | Artist guest service desk sign | Active | FALSE | Central copy library authorization | Julian Clarkson | 2026-09-30 13:05 | 2026-09-30 13:05
VRB-019 | GHXSTSHIP | CSMIA26 | Guest Experience | Signage & Wayfinding | Artist Hospitality | ARTIST ENTRANCE INDICATOR | ARTIST ENTRANCE INDICATOR |  | Talent access point pylon | Active | FALSE | Central copy library authorization | Julian Clarkson | 2026-09-30 13:05 | 2026-09-30 13:05
VRB-020 | GHXSTSHIP | CSMIA26 | Guest Experience | Signage & Wayfinding | Artist Hospitality | ARTIST LOUNGE & GREEN ROOMS | ARTIST LOUNGE & GREEN ROOMS |  | Backstage green room directional marker | Active | FALSE | Central copy library authorization | Julian Clarkson | 2026-09-30 13:05 | 2026-09-30 13:05
VRB-021 | GHXSTSHIP | CSMIA26 | Site Operations | Signage & Wayfinding | Parking | ARTIST PARKING | ARTIST PARKING |  | Talent designated lot marker | Active | FALSE | Central copy library authorization | Julian Clarkson | 2026-09-30 13:05 | 2026-09-30 13:05
VRB-022 | GHXSTSHIP | CSMIA26 | Guest Experience | Signage & Wayfinding | Artist Hospitality | ARTIST RELATIONS | ARTIST RELATIONS |  | Artist liaison operations center | Active | FALSE | Central copy library authorization | Julian Clarkson | 2026-09-30 13:05 | 2026-09-30 13:05
VRB-023 | GHXSTSHIP | CSMIA26 | Guest Experience | Signage & Wayfinding | Artist Hospitality | ARTIST RELATIONS & TRANSPORTATION OFFICE | ARTIST RELATIONS & TRANSPORTATION OFFICE |  | Talent transport dispatch office | Active | FALSE | Central copy library authorization | Julian Clarkson | 2026-09-30 13:05 | 2026-09-30 13:05
VRB-024 | GHXSTSHIP | CSMIA26 | Site Operations | Signage & Wayfinding | Transportation | ARTIST SHUTTLE STOP | ARTIST SHUTTLE STOP |  | Artist golf cart / van stop sign | Active | FALSE | Central copy library authorization | Julian Clarkson | 2026-09-30 13:05 | 2026-09-30 13:05
VRB-025 | GHXSTSHIP | CSMIA26 | Site Operations | Signage & Wayfinding | Transportation | ARTIST SHUTTLES | ARTIST SHUTTLES |  | Talent fleet transit lane indicator | Active | FALSE | Central copy library authorization | Julian Clarkson | 2026-09-30 13:05 | 2026-09-30 13:05
VRB-026 | GHXSTSHIP | CSMIA26 | Site Operations | Signage & Wayfinding | Parking | ARTIST TRANPORT PARKING ONLY | ARTIST TRANPORT PARKING ONLY |  | Dedicated runner vehicle parking | Active | FALSE | Central copy library authorization | Julian Clarkson | 2026-09-30 13:05 | 2026-09-30 13:05
VRB-027 | GHXSTSHIP | CSMIA26 | Site Operations | Signage & Wayfinding | Transportation | ARTIST TRANSPORTATION | ARTIST TRANSPORTATION |  | Ground transportation staging hub | Active | FALSE | Central copy library authorization | Julian Clarkson | 2026-09-30 13:05 | 2026-09-30 13:05
VRB-028 | GHXSTSHIP | CSMIA26 | Site Operations | Signage & Wayfinding | Concessions | BAR | BAR |  | General beverage service point | Active | FALSE | Central copy library authorization | Julian Clarkson | 2026-09-30 13:05 | 2026-09-30 13:05
VRB-029 | GHXSTSHIP | CSMIA26 | Guest Experience | Signage & Wayfinding | Ticketing | BOX OFFICE | BOX OFFICE |  | Main venue ticketing structure | Active | FALSE | Central copy library authorization | Julian Clarkson | 2026-09-30 13:05 | 2026-09-30 13:05
VRB-030 | GHXSTSHIP | CSMIA26 | Guest Experience | Signage & Wayfinding | Ticketing | BOX OFFICE & WILL CALL | BOX OFFICE & WILL CALL |  | Integrated ticket sales and will call | Active | FALSE | Central copy library authorization | Julian Clarkson | 2026-09-30 13:05 | 2026-09-30 13:05
VRB-031 | GHXSTSHIP | CSMIA26 | Guest Experience | Signage & Wayfinding | Ticketing | BOX OFFICE HOURS | BOX OFFICE HOURS |  | Ticketing operating hours sign | Active | FALSE | Central copy library authorization | Julian Clarkson | 2026-09-30 13:05 | 2026-09-30 13:05
VRB-032 | GHXSTSHIP | CSMIA26 | Site Operations | Signage & Wayfinding | Parking | BOX OFFICE PARKING | BOX OFFICE PARKING |  | Short-term parking for ticket buyers | Active | FALSE | Central copy library authorization | Julian Clarkson | 2026-09-30 13:05 | 2026-09-30 13:05
VRB-033 | GHXSTSHIP | CSMIA26 | Site Operations | Signage & Wayfinding | Transportation | BUS ENTRANCE | BUS ENTRANCE |  | Commercial bus entry portal | Active | FALSE | Central copy library authorization | Julian Clarkson | 2026-09-30 13:05 | 2026-09-30 13:05
VRB-034 | GHXSTSHIP | CSMIA26 | Guest Experience | Signage & Wayfinding | Ticketing | BUY TICKETS | BUY TICKETS |  | Onsite purchase queue header | Active | FALSE | Central copy library authorization | Julian Clarkson | 2026-09-30 13:05 | 2026-09-30 13:05
VRB-035 | GHXSTSHIP | CSMIA26 | Site Operations | Signage & Wayfinding | Camping | CAMPGROUND ACCEPTABLE ITEMS | CAMPGROUND ACCEPTABLE ITEMS |  | Camp permitted gear billboard | Active | FALSE | Central copy library authorization | Julian Clarkson | 2026-09-30 13:05 | 2026-09-30 13:05
VRB-036 | GHXSTSHIP | CSMIA26 | Site Operations | Signage & Wayfinding | Camping | CAMPGROUND ALCOHOL POLICY | CAMPGROUND ALCOHOL POLICY |  | Campground alcohol rules sign | Active | FALSE | Central copy library authorization | Julian Clarkson | 2026-09-30 13:05 | 2026-09-30 13:05
VRB-037 | GHXSTSHIP | CSMIA26 | Site Operations | Signage & Wayfinding | Camping | CAMPGROUND CODE OF CONDUCT | CAMPGROUND CODE OF CONDUCT |  | Campground behavioral policy placard | Active | FALSE | Central copy library authorization | Julian Clarkson | 2026-09-30 13:05 | 2026-09-30 13:05
VRB-038 | GHXSTSHIP | CSMIA26 | Site Operations | Signage & Wayfinding | Camping | CAMPGROUND PROHIBITED ITEMS | CAMPGROUND PROHIBITED ITEMS |  | Camp restricted contraband list | Active | FALSE | Central copy library authorization | Julian Clarkson | 2026-09-30 13:05 | 2026-09-30 13:05
VRB-039 | GHXSTSHIP | CSMIA26 | Site Operations | Signage & Wayfinding | Camping | CAMPING | CAMPING |  | General camping zone wayfinding | Active | FALSE | Central copy library authorization | Julian Clarkson | 2026-09-30 13:05 | 2026-09-30 13:05
VRB-040 | GHXSTSHIP | CSMIA26 | Guest Experience | Signage & Wayfinding | Concessions | CASH TO CARD | CASH TO CARD |  | Reverse ATM kiosk marker | Active | FALSE | Central copy library authorization | Julian Clarkson | 2026-09-30 13:05 | 2026-09-30 13:05
VRB-041 | GHXSTSHIP | CSMIA26 | Guest Experience | Signage & Wayfinding | Services | CHARGING LOCKERS | CHARGING LOCKERS |  | Secure mobile locker zone sign | Active | FALSE | Central copy library authorization | Julian Clarkson | 2026-09-30 13:05 | 2026-09-30 13:05
VRB-042 | GHXSTSHIP | CSMIA26 | Guest Experience | Signage & Wayfinding | Services | CHARGING STATIONS | CHARGING STATIONS |  | Public phone charging point | Active | FALSE | Central copy library authorization | Julian Clarkson | 2026-09-30 13:05 | 2026-09-30 13:05
VRB-043 | GHXSTSHIP | CSMIA26 | Technical Production | Signage & Wayfinding | Credentials | CREDENTIAL BOARD | CREDENTIAL BOARD |  | Security pass visual hierarchy board | Active | FALSE | Central copy library authorization | Julian Clarkson | 2026-09-30 13:05 | 2026-09-30 13:05
VRB-044 | GHXSTSHIP | CSMIA26 | Technical Production | Signage & Wayfinding | Credentials | CREDENTIAL PICK-UP | CREDENTIAL PICK-UP |  | Crew credential dispatch office | Active | FALSE | Central copy library authorization | Julian Clarkson | 2026-09-30 13:05 | 2026-09-30 13:05
VRB-045 | GHXSTSHIP | CSMIA26 | Site Operations | Signage & Wayfinding | Parking | DAILY PARKING | DAILY PARKING |  | Single-day public parking sign | Active | FALSE | Central copy library authorization | Julian Clarkson | 2026-09-30 13:05 | 2026-09-30 13:05
VRB-046 | GHXSTSHIP | CSMIA26 | Site Operations | Signage & Wayfinding | Safety & Hazard | DANGER : DO NOT ENTER | DANGER : DO NOT ENTER |  | High risk restricted boundary sign | Active | FALSE | Central copy library authorization | Julian Clarkson | 2026-09-30 13:05 | 2026-09-30 13:05
VRB-047 | GHXSTSHIP | CSMIA26 | Site Operations | Signage & Wayfinding | Parking | DAY PARKING | DAY PARKING |  | General admission day lot banner | Active | FALSE | Central copy library authorization | Julian Clarkson | 2026-09-30 13:05 | 2026-09-30 13:05
VRB-048 | GHXSTSHIP | CSMIA26 | Site Operations | Signage & Wayfinding | Health & Safety | DISCLAIMER - COVID 19 | DISCLAIMER - COVID 19 |  | Infectious disease warning board | Active | FALSE | Central copy library authorization | Julian Clarkson | 2026-09-30 13:05 | 2026-09-30 13:05
VRB-049 | GHXSTSHIP | CSMIA26 | Guest Experience | Signage & Wayfinding | Legal Notice | DISCLAIMER - MEDIA | DISCLAIMER - MEDIA |  | Notice of photo and video recording | Active | FALSE | Central copy library authorization | Julian Clarkson | 2026-09-30 13:05 | 2026-09-30 13:05
VRB-050 | GHXSTSHIP | CSMIA26 | Security & Safety | Signage & Wayfinding | Security Policy | DISCLAIMER - SECURITY SEARCHES | DISCLAIMER - SECURITY SEARCHES |  | Mandatory inspection disclosure sign | Active | FALSE | Central copy library authorization | Julian Clarkson | 2026-09-30 13:05 | 2026-09-30 13:05
VRB-051 | GHXSTSHIP | CSMIA26 | Guest Experience | Signage & Wayfinding | Accessibility | DO NOT BLOCK THE VIEW OF GUESTS BEHIND YOU. COMPANIONS MAY BE ASKED TO STAND IF CAPACITY IS REACHED. | ADA VIEWING ETIQUETTE |  | Accessibility viewing etiquette notice | Active | FALSE | Central copy library authorization | Julian Clarkson | 2026-09-30 13:05 | 2026-09-30 13:05
VRB-052 | GHXSTSHIP | CSMIA26 | Site Operations | Signage & Wayfinding | Access Control | DO NOT ENTER | DO NOT ENTER |  | Prohibited access perimeter sign | Active | FALSE | Central copy library authorization | Julian Clarkson | 2026-09-30 13:05 | 2026-09-30 13:05
VRB-053 | GHXSTSHIP | CSMIA26 | Site Operations | Signage & Wayfinding | Concessions | DRINKS | DRINKS |  | Beverage stand overhead signage | Active | FALSE | Central copy library authorization | Julian Clarkson | 2026-09-30 13:05 | 2026-09-30 13:05
VRB-054 | GHXSTSHIP | CSMIA26 | Security & Safety | Signage & Wayfinding | Emergency | EMERGENCY EXIT | EMERGENCY EXIT |  | Illuminated egress portal marker | Active | FALSE | Central copy library authorization | Julian Clarkson | 2026-09-30 13:05 | 2026-09-30 13:05
VRB-055 | GHXSTSHIP | CSMIA26 | Site Operations | Signage & Wayfinding | Parking | EMERGENCY VEHICLE PARKING ONLY | EMERGENCY VEHICLE PARKING ONLY |  | Designated first responder stall | Active | FALSE | Central copy library authorization | Julian Clarkson | 2026-09-30 13:05 | 2026-09-30 13:05
VRB-056 | GHXSTSHIP | CSMIA26 | Site Operations | Signage & Wayfinding | Directional | ENTER | ENTER |  | General pedestrian entrance banner | Active | FALSE | Central copy library authorization | Julian Clarkson | 2026-09-30 13:05 | 2026-09-30 13:05
VRB-057 | GHXSTSHIP | CSMIA26 | Site Operations | Signage & Wayfinding | Directional | ENTRANCE | ENTRANCE |  | Gate portal entry header sign | Active | FALSE | Central copy library authorization | Julian Clarkson | 2026-09-30 13:05 | 2026-09-30 13:05
VRB-058 | GHXSTSHIP | CSMIA26 | Guest Experience | Signage & Wayfinding | Directional | EVENT | EVENT |  | Main event grounds indicator | Active | FALSE | Central copy library authorization | Julian Clarkson | 2026-09-30 13:05 | 2026-09-30 13:05
VRB-059 | GHXSTSHIP | CSMIA26 | Site Operations | Signage & Wayfinding | Egress | EXIT | EXIT |  | General egress route wayfinding | Active | FALSE | Central copy library authorization | Julian Clarkson | 2026-09-30 13:05 | 2026-09-30 13:05
VRB-060 | GHXSTSHIP | CSMIA26 | Site Operations | Signage & Wayfinding | Egress | EXIT HERE | EXIT HERE |  | Specific egress gate directional sign | Active | FALSE | Central copy library authorization | Julian Clarkson | 2026-09-30 13:05 | 2026-09-30 13:05
VRB-061 | GHXSTSHIP | CSMIA26 | Site Operations | Signage & Wayfinding | Egress | EXIT ONLY | EXIT ONLY |  | No ingress one-way egress gate | Active | FALSE | Central copy library authorization | Julian Clarkson | 2026-09-30 13:05 | 2026-09-30 13:05
VRB-062 | GHXSTSHIP | CSMIA26 | Site Operations | Signage & Wayfinding | Egress | EXIT ONLY NO RE-ENTRY | EXIT ONLY NO RE-ENTRY |  | Final departure egress gate sign | Active | FALSE | Central copy library authorization | Julian Clarkson | 2026-09-30 13:05 | 2026-09-30 13:05
VRB-063 | GHXSTSHIP | CSMIA26 | Site Operations | Signage & Wayfinding | Parking | EXIT TO DAY PARKING | EXIT TO DAY PARKING |  | Egress route to day lots sign | Active | FALSE | Central copy library authorization | Julian Clarkson | 2026-09-30 13:05 | 2026-09-30 13:05
VRB-064 | GHXSTSHIP | CSMIA26 | Site Operations | Signage & Wayfinding | Directional | EXIT TO FESTIVAL | EXIT TO FESTIVAL |  | Campground to festival grounds portal | Active | FALSE | Central copy library authorization | Julian Clarkson | 2026-09-30 13:05 | 2026-09-30 13:05
VRB-065 | GHXSTSHIP | CSMIA26 | Site Operations | Signage & Wayfinding | Transportation | EXIT TO RIDESHARE | EXIT TO RIDESHARE |  | Uber / Lyft pickup egress route | Active | FALSE | Central copy library authorization | Julian Clarkson | 2026-09-30 13:05 | 2026-09-30 13:05
VRB-066 | GHXSTSHIP | CSMIA26 | Guest Experience | Signage & Wayfinding | Access Control | EXPRESS ENTRY | EXPRESS ENTRY |  | Expedited security entry lane sign | Active | FALSE | Central copy library authorization | Julian Clarkson | 2026-09-30 13:05 | 2026-09-30 13:05
VRB-067 | GHXSTSHIP | CSMIA26 | Security & Safety | Signage & Wayfinding | Health & Safety | FENTANYL WARNING | FENTANYL WARNING |  | Harm reduction health alert notice | Active | FALSE | Central copy library authorization | Julian Clarkson | 2026-09-30 13:05 | 2026-09-30 13:05
VRB-068 | GHXSTSHIP | CSMIA26 | Security & Safety | Signage & Wayfinding | Security Policy | FESTIVAL ACCEPTABLE ITEMS | FESTIVAL ACCEPTABLE ITEMS |  | Venue permitted items list board | Active | FALSE | Central copy library authorization | Julian Clarkson | 2026-09-30 13:05 | 2026-09-30 13:05
VRB-069 | GHXSTSHIP | CSMIA26 | Site Operations | Signage & Wayfinding | Directional | FESTIVAL ENTRANCE AHEAD | FESTIVAL ENTRANCE AHEAD |  | Advance perimeter approach sign | Active | FALSE | Central copy library authorization | Julian Clarkson | 2026-09-30 13:05 | 2026-09-30 13:05
VRB-070 | GHXSTSHIP | CSMIA26 | Site Operations | Signage & Wayfinding | Access Control | FESTIVAL GATES | FESTIVAL GATES |  | Primary ingress gate truss banner | Active | FALSE | Central copy library authorization | Julian Clarkson | 2026-09-30 13:05 | 2026-09-30 13:05
VRB-071 | GHXSTSHIP | CSMIA26 | Guest Experience | Signage & Wayfinding | Information | FESTIVAL MAP | FESTIVAL MAP |  | Master venue layout map billboard | Active | FALSE | Central copy library authorization | Julian Clarkson | 2026-09-30 13:05 | 2026-09-30 13:05
VRB-072 | GHXSTSHIP | CSMIA26 | Security & Safety | Signage & Wayfinding | Security Policy | FESTIVAL POLICIES | FESTIVAL POLICIES |  | General festival rules and terms | Active | FALSE | Central copy library authorization | Julian Clarkson | 2026-09-30 13:05 | 2026-09-30 13:05
VRB-073 | GHXSTSHIP | CSMIA26 | Security & Safety | Signage & Wayfinding | Security Policy | FESTIVAL PROHIBITED ITEMS | FESTIVAL PROHIBITED ITEMS |  | Venue restricted contraband banner | Active | FALSE | Central copy library authorization | Julian Clarkson | 2026-09-30 13:05 | 2026-09-30 13:05
VRB-074 | GHXSTSHIP | CSMIA26 | Guest Experience | Signage & Wayfinding | Information | FESTIVAL SET TIMES | FESTIVAL SET TIMES |  | Stage performance schedule towers | Active | FALSE | Central copy library authorization | Julian Clarkson | 2026-09-30 13:05 | 2026-09-30 13:05
VRB-075 | GHXSTSHIP | CSMIA26 | Security & Safety | Signage & Wayfinding | Emergency | FIRE LANE | FIRE LANE |  | No obstruction emergency road sign | Active | FALSE | Central copy library authorization | Julian Clarkson | 2026-09-30 13:05 | 2026-09-30 13:05
VRB-076 | GHXSTSHIP | CSMIA26 | Security & Safety | Signage & Wayfinding | Emergency | FIRST AID | FIRST AID |  | Paramedic station emergency sign | Active | FALSE | Central copy library authorization | Julian Clarkson | 2026-09-30 13:05 | 2026-09-30 13:05
VRB-077 | GHXSTSHIP | CSMIA26 | Procurement | Signage & Wayfinding | Vendor Ops | FOOD & BEVERAGE VENDOR CHECK-IN | FOOD & BEVERAGE VENDOR CHECK-IN |  | Concession vendor intake gate sign | Active | FALSE | Central copy library authorization | Julian Clarkson | 2026-09-30 13:05 | 2026-09-30 13:05
VRB-078 | GHXSTSHIP | CSMIA26 | Site Operations | Signage & Wayfinding | Services | FREE FILTERED WATER | FREE FILTERED WATER |  | Hydration oasis wayfinding banner | Active | FALSE | Central copy library authorization | Julian Clarkson | 2026-09-30 13:05 | 2026-09-30 13:05
VRB-079 | GHXSTSHIP | CSMIA26 | Guest Experience | Signage & Wayfinding | Ticketing | FRIENDS & FAMILY CHECK-IN | FRIENDS & FAMILY CHECK-IN |  | Guest list hospitality portal | Active | FALSE | Central copy library authorization | Julian Clarkson | 2026-09-30 13:05 | 2026-09-30 13:05
VRB-080 | GHXSTSHIP | CSMIA26 | Guest Experience | Signage & Wayfinding | Access Control | GA | GA |  | General admission designation marker | Active | FALSE | Central copy library authorization | Julian Clarkson | 2026-09-30 13:05 | 2026-09-30 13:05
VRB-081 | GHXSTSHIP | CSMIA26 | Site Operations | Signage & Wayfinding | Camping | GA CAMPING | GA CAMPING |  | General admission tent camp sign | Active | FALSE | Central copy library authorization | Julian Clarkson | 2026-09-30 13:05 | 2026-09-30 13:05
VRB-082 | GHXSTSHIP | CSMIA26 | Guest Experience | Signage & Wayfinding | Access Control | GA ENTRANCE | GA ENTRANCE |  | General admission ingress gate sign | Active | FALSE | Central copy library authorization | Julian Clarkson | 2026-09-30 13:05 | 2026-09-30 13:05
VRB-083 | GHXSTSHIP | CSMIA26 | Guest Experience | Signage & Wayfinding | Access Control | GA+ ENTRANCE | GA+ ENTRANCE |  | Upgraded GA tier gate portal | Active | FALSE | Central copy library authorization | Julian Clarkson | 2026-09-30 13:05 | 2026-09-30 13:05
VRB-084 | GHXSTSHIP | CSMIA26 | Guest Experience | Signage & Wayfinding | Access Control | GA+ ID CHECK | GA+ ID CHECK |  | Age verification lane for GA+ | Active | FALSE | Central copy library authorization | Julian Clarkson | 2026-09-30 13:05 | 2026-09-30 13:05
VRB-085 | GHXSTSHIP | CSMIA26 | Site Operations | Signage & Wayfinding | Sanitation | GA+ RESTROOMS | GA+ RESTROOMS |  | Air conditioned restroom trailers | Active | FALSE | Central copy library authorization | Julian Clarkson | 2026-09-30 13:05 | 2026-09-30 13:05
VRB-086 | GHXSTSHIP | CSMIA26 | Security & Safety | Signage & Wayfinding | Access Control | GA+ SECURITY SEARCH | GA+ SECURITY SEARCH |  | Dedicated checkpoint search lane | Active | FALSE | Central copy library authorization | Julian Clarkson | 2026-09-30 13:05 | 2026-09-30 13:05
VRB-087 | GHXSTSHIP | CSMIA26 | Guest Experience | Signage & Wayfinding | Access Control | GENERAL ADMISSION | GENERAL ADMISSION |  | Standard ticket holder portal header | Active | FALSE | Central copy library authorization | Julian Clarkson | 2026-09-30 13:05 | 2026-09-30 13:05
VRB-088 | GHXSTSHIP | CSMIA26 | Site Operations | Signage & Wayfinding | Retail | GENERAL STORE | GENERAL STORE |  | Festival sundries and camping shop | Active | FALSE | Central copy library authorization | Julian Clarkson | 2026-09-30 13:05 | 2026-09-30 13:05
VRB-089 | GHXSTSHIP | CSMIA26 | Site Operations | Signage & Wayfinding | Camping | GROUP CAMPING | GROUP CAMPING |  | Reserved group campsites wayfinding | Active | FALSE | Central copy library authorization | Julian Clarkson | 2026-09-30 13:05 | 2026-09-30 13:05
VRB-090 | GHXSTSHIP | CSMIA26 | Guest Experience | Signage & Wayfinding | Ticketing | GUEST LIST CHECK-IN | GUEST LIST CHECK-IN |  | VIP and industry guest check-in | Active | FALSE | Central copy library authorization | Julian Clarkson | 2026-09-30 13:05 | 2026-09-30 13:05
VRB-091 | GHXSTSHIP | CSMIA26 | Guest Experience | Signage & Wayfinding | Ticketing | GUEST LIST | GUEST LIST |  | Guest list credential lane marker | Active | FALSE | Central copy library authorization | Julian Clarkson | 2026-09-30 13:05 | 2026-09-30 13:05
VRB-092 | GHXSTSHIP | CSMIA26 | Guest Experience | Signage & Wayfinding | Information | GUEST SERVICES : ACCESSIBILITY SERVICES ¦ INFORMATION ¦ LOST & FOUND | GUEST SERVICES HUB |  | Central information service kiosk | Active | FALSE | Central copy library authorization | Julian Clarkson | 2026-09-30 13:05 | 2026-09-30 13:05
VRB-093 | GHXSTSHIP | CSMIA26 | Security & Safety | Signage & Wayfinding | Access Control | HAVE PHONE READY | HAVE PHONE READY |  | Digital ticket preparation notice | Active | FALSE | Central copy library authorization | Julian Clarkson | 2026-09-30 13:05 | 2026-09-30 13:05
VRB-094 | GHXSTSHIP | CSMIA26 | Guest Experience | Signage & Wayfinding | Ticketing | HOURS OF OPERATION - BOX OFFICE | HOURS OF OPERATION - BOX OFFICE |  | Box office operating hours schedule | Active | FALSE | Central copy library authorization | Julian Clarkson | 2026-09-30 13:05 | 2026-09-30 13:05
VRB-095 | GHXSTSHIP | CSMIA26 | Site Operations | Signage & Wayfinding | Fueling | HOURS OF OPERATION - FUELING | HOURS OF OPERATION - FUELING |  | Generator fueling window placard | Active | FALSE | Central copy library authorization | Julian Clarkson | 2026-09-30 13:05 | 2026-09-30 13:05
VRB-096 | GHXSTSHIP | CSMIA26 | Site Operations | Signage & Wayfinding | Sanitation | HOURS OF OPERATION - SHOWERS | HOURS OF OPERATION - SHOWERS |  | Campground shower availability times | Active | FALSE | Central copy library authorization | Julian Clarkson | 2026-09-30 13:05 | 2026-09-30 13:05
VRB-097 | GHXSTSHIP | CSMIA26 | Site Operations | Signage & Wayfinding | Transportation | HOURS OF OPERATION - TOLLBOOTHS | HOURS OF OPERATION - TOLLBOOTHS |  | Vehicle toll plaza operational hours | Active | FALSE | Central copy library authorization | Julian Clarkson | 2026-09-30 13:05 | 2026-09-30 13:05
VRB-098 | GHXSTSHIP | CSMIA26 | Site Operations | Signage & Wayfinding | Concessions | ICE | ICE |  | Bagged ice purchase depot marker | Active | FALSE | Central copy library authorization | Julian Clarkson | 2026-09-30 13:05 | 2026-09-30 13:05
VRB-099 | GHXSTSHIP | CSMIA26 | Guest Experience | Signage & Wayfinding | Access Control | ID CHECK | ID CHECK |  | Mandatory government ID verification | Active | FALSE | Central copy library authorization | Julian Clarkson | 2026-09-30 13:05 | 2026-09-30 13:05
VRB-100 | GHXSTSHIP | CSMIA26 | Guest Experience | Signage & Wayfinding | Information | INFORMATION | INFORMATION |  | Guest information service desk | Active | FALSE | Central copy library authorization | Julian Clarkson | 2026-09-30 13:05 | 2026-09-30 13:05
VRB-101 | GHXSTSHIP | CSMIA26 | Guest Experience | Signage & Wayfinding | Accessibility | INTERNATIONAL SYMBOL OF ACCESSIBILITY (ISA) | ISA SYMBOL |  | Standard universal wheelchair glyph | Active | FALSE | Central copy library authorization | Julian Clarkson | 2026-09-30 13:05 | 2026-09-30 13:05
VRB-102 | GHXSTSHIP | CSMIA26 | Guest Experience | Signage & Wayfinding | Information | LOST & FOUND | LOST & FOUND |  | Property recovery central booth | Active | FALSE | Central copy library authorization | Julian Clarkson | 2026-09-30 13:05 | 2026-09-30 13:05
VRB-103 | GHXSTSHIP | CSMIA26 | Communications | Signage & Wayfinding | Media | MEDIA | MEDIA |  | Press credential zone designation | Active | FALSE | Central copy library authorization | Julian Clarkson | 2026-09-30 13:05 | 2026-09-30 13:05
VRB-104 | GHXSTSHIP | CSMIA26 | Communications | Signage & Wayfinding | Media | MEDIA CHECK-IN | MEDIA CHECK-IN |  | Press credential badge pickup portal | Active | FALSE | Central copy library authorization | Julian Clarkson | 2026-09-30 13:05 | 2026-09-30 13:05
VRB-105 | GHXSTSHIP | CSMIA26 | Communications | Signage & Wayfinding | Media | MEDIA LOUNGE | MEDIA LOUNGE |  | Press workroom and media hospitality | Active | FALSE | Central copy library authorization | Julian Clarkson | 2026-09-30 13:05 | 2026-09-30 13:05
VRB-106 | GHXSTSHIP | CSMIA26 | Site Operations | Signage & Wayfinding | Concessions | MENU - ARTIST BAR | MENU - ARTIST BAR |  | Backstage talent beverage offerings | Active | FALSE | Central copy library authorization | Julian Clarkson | 2026-09-30 13:05 | 2026-09-30 13:05
VRB-107 | GHXSTSHIP | CSMIA26 | Site Operations | Signage & Wayfinding | Concessions | MENU - GA BAR | MENU - GA BAR |  | Main floor bar drink menu board | Active | FALSE | Central copy library authorization | Julian Clarkson | 2026-09-30 13:05 | 2026-09-30 13:05
VRB-108 | GHXSTSHIP | CSMIA26 | Site Operations | Signage & Wayfinding | Concessions | MENU - GA+ BAR | MENU - GA+ BAR |  | Premium lounge drink menu board | Active | FALSE | Central copy library authorization | Julian Clarkson | 2026-09-30 13:05 | 2026-09-30 13:05
VRB-109 | GHXSTSHIP | CSMIA26 | Site Operations | Signage & Wayfinding | Concessions | MENU - VIP BAR | MENU - VIP BAR |  | VIP club bar beverage offerings | Active | FALSE | Central copy library authorization | Julian Clarkson | 2026-09-30 13:05 | 2026-09-30 13:05
VRB-110 | GHXSTSHIP | CSMIA26 | Site Operations | Signage & Wayfinding | Concessions | MENU - VIP BOTTLE SERVICE | MENU - VIP BOTTLE SERVICE |  | Bottle service menu table cards | Active | FALSE | Central copy library authorization | Julian Clarkson | 2026-09-30 13:05 | 2026-09-30 13:05
VRB-111 | GHXSTSHIP | CSMIA26 | Site Operations | Signage & Wayfinding | Motorpool | MOTORPOOL | MOTORPOOL |  | Fleet and cart operations compound | Active | FALSE | Central copy library authorization | Julian Clarkson | 2026-09-30 13:05 | 2026-09-30 13:05
VRB-112 | GHXSTSHIP | CSMIA26 | Security & Safety | Signage & Wayfinding | Alcohol Policy | NO ALCOHOL BEYOND THIS POINT | NO ALCOHOL BEYOND THIS POINT |  | Liquor boundary enforcement perimeter | Active | FALSE | Central copy library authorization | Julian Clarkson | 2026-09-30 13:05 | 2026-09-30 13:05
VRB-113 | GHXSTSHIP | CSMIA26 | Guest Experience | Signage & Wayfinding | Access Control | NO BAG LANE | NO BAG LANE |  | Express search without carry-on items | Active | FALSE | Central copy library authorization | Julian Clarkson | 2026-09-30 13:05 | 2026-09-30 13:05
VRB-114 | GHXSTSHIP | CSMIA26 | Security & Safety | Signage & Wayfinding | Access Control | NO CAMPING OR FESTIVAL ACCESS | NO CAMPING OR FESTIVAL ACCESS |  | Parking only credential restriction | Active | FALSE | Central copy library authorization | Julian Clarkson | 2026-09-30 13:05 | 2026-09-30 13:05
VRB-115 | GHXSTSHIP | CSMIA26 | Security & Safety | Signage & Wayfinding | Access Control | NO DAILY RE-ENTRY WITHOUT WRISTBAND | NO DAILY RE-ENTRY WITHOUT WRISTBAND |  | Re-entry credential verification notice | Active | FALSE | Central copy library authorization | Julian Clarkson | 2026-09-30 13:05 | 2026-09-30 13:05
VRB-116 | GHXSTSHIP | CSMIA26 | Site Operations | Signage & Wayfinding | Grounds Policy | NO DRIVING ON GRASS | NO DRIVING ON GRASS |  | Grounds preservation vehicular warning | Active | FALSE | Central copy library authorization | Julian Clarkson | 2026-09-30 13:05 | 2026-09-30 13:05
VRB-117 | GHXSTSHIP | CSMIA26 | Security & Safety | Signage & Wayfinding | Access Control | NO EVENT ACCESS | NO EVENT ACCESS |  | Restricted operations zone barrier | Active | FALSE | Central copy library authorization | Julian Clarkson | 2026-09-30 13:05 | 2026-09-30 13:05
VRB-118 | GHXSTSHIP | CSMIA26 | Site Operations | Signage & Wayfinding | Parking | NO EVENT PARKING | NO EVENT PARKING |  | Restricted non-event property boundary | Active | FALSE | Central copy library authorization | Julian Clarkson | 2026-09-30 13:05 | 2026-09-30 13:05
VRB-119 | GHXSTSHIP | CSMIA26 | Site Operations | Signage & Wayfinding | Parking | NO PARKING | NO PARKING |  | Tow-away regulatory street sign | Active | FALSE | Central copy library authorization | Julian Clarkson | 2026-09-30 13:05 | 2026-09-30 13:05
VRB-120 | GHXSTSHIP | CSMIA26 | Site Operations | Signage & Wayfinding | Parking | NO PARKING NO STOPPING NO WAITING | NO PARKING NO STOPPING NO WAITING |  | Zero tolerance traffic regulation sign | Active | FALSE | Central copy library authorization | Julian Clarkson | 2026-09-30 13:05 | 2026-09-30 13:05
VRB-121 | GHXSTSHIP | CSMIA26 | Site Operations | Signage & Wayfinding | Transportation | NO RIDESHARE PICKUP OR DROP OFF | NO RIDESHARE PICKUP OR DROP OFF |  | Restricted perimeter traffic enforcement | Active | FALSE | Central copy library authorization | Julian Clarkson | 2026-09-30 13:05 | 2026-09-30 13:05
VRB-122 | GHXSTSHIP | CSMIA26 | Site Operations | Signage & Wayfinding | Health & Safety | NO SMOKING | NO SMOKING |  | Designated non-smoking zone sign | Active | FALSE | Central copy library authorization | Julian Clarkson | 2026-09-30 13:05 | 2026-09-30 13:05
VRB-123 | GHXSTSHIP | CSMIA26 | Site Operations | Signage & Wayfinding | Egress | NOT AN EXIT | NOT AN EXIT |  | Door and perimeter egress prohibition | Active | FALSE | Central copy library authorization | Julian Clarkson | 2026-09-30 13:05 | 2026-09-30 13:05
VRB-124 | GHXSTSHIP | CSMIA26 | Guest Experience | Signage & Wayfinding | Retail | OFFICIAL MERCHANDISE | OFFICIAL MERCHANDISE |  | Festival merchandise store header | Active | FALSE | Central copy library authorization | Julian Clarkson | 2026-09-30 13:05 | 2026-09-30 13:05
VRB-125 | GHXSTSHIP | CSMIA26 | Site Operations | Signage & Wayfinding | Parking | OFFSITE PARKING | OFFSITE PARKING |  | Satellite lot shuttle depot sign | Active | FALSE | Central copy library authorization | Julian Clarkson | 2026-09-30 13:05 | 2026-09-30 13:05
VRB-126 | GHXSTSHIP | CSMIA26 | Site Operations | Signage & Wayfinding | Traffic | ONE WAY | ONE WAY |  | Vehicular traffic directional sign | Active | FALSE | Central copy library authorization | Julian Clarkson | 2026-09-30 13:05 | 2026-09-30 13:05
VRB-127 | GHXSTSHIP | CSMIA26 | Site Operations | Signage & Wayfinding | Parking | PARKING | PARKING |  | General parking direction indicator | Active | FALSE | Central copy library authorization | Julian Clarkson | 2026-09-30 13:05 | 2026-09-30 13:05
VRB-128 | GHXSTSHIP | CSMIA26 | Site Operations | Signage & Wayfinding | Parking | PARKING LOT FULL | PARKING LOT FULL |  | Lot capacity overflow closure sign | Active | FALSE | Central copy library authorization | Julian Clarkson | 2026-09-30 13:05 | 2026-09-30 13:05
VRB-129 | GHXSTSHIP | CSMIA26 | Site Operations | Signage & Wayfinding | Transportation | PEDI CAB STOP | PEDI CAB STOP |  | Pedicab passenger pickup point | Active | FALSE | Central copy library authorization | Julian Clarkson | 2026-09-30 13:05 | 2026-09-30 13:05
VRB-130 | GHXSTSHIP | CSMIA26 | Guest Experience | Signage & Wayfinding | Accessibility | POLICES - ADA WRISTBANDS | ADA WRISTBAND RULES |  | Accessibility credential verification policies | Active | FALSE | Central copy library authorization | Julian Clarkson | 2026-09-30 13:05 | 2026-09-30 13:05
VRB-131 | GHXSTSHIP | CSMIA26 | Guest Experience | Signage & Wayfinding | Ticketing | POLICIES - WRISTBAND REPLACEMENTS | WRISTBAND REPLACEMENT RULES |  | Damaged wristband fee schedule placard | Active | FALSE | Central copy library authorization | Julian Clarkson | 2026-09-30 13:05 | 2026-09-30 13:05
VRB-132 | GHXSTSHIP | CSMIA26 | Site Operations | Signage & Wayfinding | Camping | PRIMITIVE CAMP PARKING | PRIMITIVE CAMP PARKING |  | Designated primitive lot sign | Active | FALSE | Central copy library authorization | Julian Clarkson | 2026-09-30 13:05 | 2026-09-30 13:05
VRB-133 | GHXSTSHIP | CSMIA26 | Site Operations | Signage & Wayfinding | Camping | PRIMITIVE TENT CAMPING | PRIMITIVE TENT CAMPING |  | Non-vehicle tent campground area | Active | FALSE | Central copy library authorization | Julian Clarkson | 2026-09-30 13:05 | 2026-09-30 13:05
VRB-134 | GHXSTSHIP | CSMIA26 | Technical Production | Signage & Wayfinding | Operations | PRODUCTION CHECK-IN | PRODUCTION CHECK-IN |  | Technical crew intake gate portal | Active | FALSE | Central copy library authorization | Julian Clarkson | 2026-09-30 13:05 | 2026-09-30 13:05
VRB-135 | GHXSTSHIP | CSMIA26 | Technical Production | Signage & Wayfinding | Parking | PRODUCTION VEHICLE PARKING ONLY | PRODUCTION VEHICLE PARKING ONLY |  | Technical fleet reserved parking zone | Active | FALSE | Central copy library authorization | Julian Clarkson | 2026-09-30 13:05 | 2026-09-30 13:05
VRB-136 | GHXSTSHIP | CSMIA26 | Site Operations | Signage & Wayfinding | Operations | QUARTERMASTER | QUARTERMASTER |  | Central equipment and supply cache | Active | FALSE | Central copy library authorization | Julian Clarkson | 2026-09-30 13:05 | 2026-09-30 13:05
VRB-137 | GHXSTSHIP | CSMIA26 | Communications | Signage & Wayfinding | Radios | RADIOS | RADIOS |  | Two-way radio checkout distribution desk | Active | FALSE | Central copy library authorization | Julian Clarkson | 2026-09-30 13:05 | 2026-09-30 13:05
VRB-138 | GHXSTSHIP | CSMIA26 | Site Operations | Signage & Wayfinding | Camping | RESERVED CAMPING | RESERVED CAMPING |  | Pre-assigned premium campsite plots | Active | FALSE | Central copy library authorization | Julian Clarkson | 2026-09-30 13:05 | 2026-09-30 13:05
VRB-139 | GHXSTSHIP | CSMIA26 | Guest Experience | Signage & Wayfinding | Accessibility | RESERVED FOR GUESTS WITH DISABILITES | RESERVED ACCESSIBLE AREA |  | Dedicated ADA accommodation space | Active | FALSE | Central copy library authorization | Julian Clarkson | 2026-09-30 13:05 | 2026-09-30 13:05
VRB-140 | GHXSTSHIP | CSMIA26 | Site Operations | Signage & Wayfinding | Sanitation | RESTROOMS | RESTROOMS |  | Public sanitation portable banks sign | Active | FALSE | Central copy library authorization | Julian Clarkson | 2026-09-30 13:05 | 2026-09-30 13:05
VRB-141 | GHXSTSHIP | CSMIA26 | Site Operations | Signage & Wayfinding | Transportation | RIDESHARE | RIDESHARE |  | Rideshare staging zone wayfinding sign | Active | FALSE | Central copy library authorization | Julian Clarkson | 2026-09-30 13:05 | 2026-09-30 13:05
VRB-142 | GHXSTSHIP | CSMIA26 | Site Operations | Signage & Wayfinding | Transportation | RIDESHARE PICK UP & DROP OFF | RIDESHARE PICK UP & DROP OFF |  | Active passenger loading bays curb sign | Active | FALSE | Central copy library authorization | Julian Clarkson | 2026-09-30 13:05 | 2026-09-30 13:05
VRB-143 | GHXSTSHIP | CSMIA26 | Site Operations | Signage & Wayfinding | Transportation | RIDESHARE WAITING AREA | RIDESHARE WAITING AREA |  | Passenger waiting corral canopy sign | Active | FALSE | Central copy library authorization | Julian Clarkson | 2026-09-30 13:05 | 2026-09-30 13:05
VRB-144 | GHXSTSHIP | CSMIA26 | Site Operations | Signage & Wayfinding | Camping | RV CAMPING | RV CAMPING |  | Recreational vehicle park compound | Active | FALSE | Central copy library authorization | Julian Clarkson | 2026-09-30 13:05 | 2026-09-30 13:05
VRB-145 | GHXSTSHIP | CSMIA26 | Site Operations | Signage & Wayfinding | Camping | RV CAMPING ENTRANCE | RV CAMPING ENTRANCE |  | RV vehicle check-in lane portal | Active | FALSE | Central copy library authorization | Julian Clarkson | 2026-09-30 13:05 | 2026-09-30 13:05
VRB-146 | GHXSTSHIP | CSMIA26 | Site Operations | Signage & Wayfinding | Camping | RVS | RVS |  | Recreational vehicle holding lane marker | Active | FALSE | Central copy library authorization | Julian Clarkson | 2026-09-30 13:05 | 2026-09-30 13:05
VRB-147 | GHXSTSHIP | CSMIA26 | Security & Safety | Signage & Wayfinding | Access Control | SCAN WRISTBAND TO ENTER | SCAN WRISTBAND TO ENTER |  | Pedestal RFID scan instructional sign | Active | FALSE | Central copy library authorization | Julian Clarkson | 2026-09-30 13:05 | 2026-09-30 13:05
VRB-148 | GHXSTSHIP | CSMIA26 | Security & Safety | Signage & Wayfinding | Access Control | SCAN WRISTBAND TO EXIT | SCAN WRISTBAND TO EXIT |  | Egress RFID scan-out verification sign | Active | FALSE | Central copy library authorization | Julian Clarkson | 2026-09-30 13:05 | 2026-09-30 13:05
VRB-149 | GHXSTSHIP | CSMIA26 | Security & Safety | Signage & Wayfinding | Security Ops | SECURITY CAMPING | SECURITY CAMPING |  | Security personnel rest compound | Active | FALSE | Central copy library authorization | Julian Clarkson | 2026-09-30 13:05 | 2026-09-30 13:05
VRB-150 | GHXSTSHIP | CSMIA26 | Security & Safety | Signage & Wayfinding | Security Ops | SECURITY CHECK-IN | SECURITY CHECK-IN |  | Security contractor muster station | Active | FALSE | Central copy library authorization | Julian Clarkson | 2026-09-30 13:05 | 2026-09-30 13:05
VRB-151 | GHXSTSHIP | CSMIA26 | Security & Safety | Signage & Wayfinding | Parking | SECURITY PARKING | SECURITY PARKING |  | Law enforcement and security lot sign | Active | FALSE | Central copy library authorization | Julian Clarkson | 2026-09-30 13:05 | 2026-09-30 13:05
VRB-152 | GHXSTSHIP | CSMIA26 | Security & Safety | Signage & Wayfinding | Access Control | SECURITY SEARCH | SECURITY SEARCH |  | Metal detector and bag check canopy | Active | FALSE | Central copy library authorization | Julian Clarkson | 2026-09-30 13:05 | 2026-09-30 13:05
VRB-153 | GHXSTSHIP | CSMIA26 | Security & Safety | Signage & Wayfinding | Security Ops | SECURTIY CHECK-IN | SECURTIY CHECK-IN |  | Secondary security muster check-in point | Active | FALSE | Central copy library authorization | Julian Clarkson | 2026-09-30 13:05 | 2026-09-30 13:05
VRB-154 | GHXSTSHIP | CSMIA26 | Site Operations | Signage & Wayfinding | Wayfinding Sets | SET - GATES (1A-20D) | GATE NUMBER SET |  | Alphanumeric gate indicator package | Active | FALSE | Central copy library authorization | Julian Clarkson | 2026-09-30 13:05 | 2026-09-30 13:05
VRB-155 | GHXSTSHIP | CSMIA26 | Site Operations | Signage & Wayfinding | Wayfinding Sets | SET - LANES (1-30) | LANE NUMBER SET |  | Search lane queue number package | Active | FALSE | Central copy library authorization | Julian Clarkson | 2026-09-30 13:05 | 2026-09-30 13:05
VRB-156 | GHXSTSHIP | CSMIA26 | Site Operations | Signage & Wayfinding | Wayfinding Sets | SET - LETTERS (A-Z) | LETTER SET |  | Alphabetical sector signage set | Active | FALSE | Central copy library authorization | Julian Clarkson | 2026-09-30 13:05 | 2026-09-30 13:05
VRB-157 | GHXSTSHIP | CSMIA26 | Site Operations | Signage & Wayfinding | Wayfinding Sets | SET - NUMBERS (1-50) | NUMBER SET (1-50) |  | Extended numeric waypoint package | Active | FALSE | Central copy library authorization | Julian Clarkson | 2026-09-30 13:05 | 2026-09-30 13:05
VRB-158 | GHXSTSHIP | CSMIA26 | Site Operations | Signage & Wayfinding | Wayfinding Sets | SET - NUMBERS [1-10] | NUMBER SET [1-10] |  | Core numbered wayfinding markers | Active | FALSE | Central copy library authorization | Julian Clarkson | 2026-09-30 13:05 | 2026-09-30 13:05
VRB-159 | GHXSTSHIP | CSMIA26 | Site Operations | Signage & Wayfinding | Wayfinding Sets | SET - ZONES (1-30) | ZONE SET (1-30) |  | Numeric zone perimeter identification | Active | FALSE | Central copy library authorization | Julian Clarkson | 2026-09-30 13:05 | 2026-09-30 13:05
VRB-160 | GHXSTSHIP | CSMIA26 | Site Operations | Signage & Wayfinding | Wayfinding Sets | SET - ZONES (A-Z) | ZONE SET (A-Z) |  | Alpha zone perimeter identification | Active | FALSE | Central copy library authorization | Julian Clarkson | 2026-09-30 13:05 | 2026-09-30 13:05
VRB-161 | GHXSTSHIP | CSMIA26 | Site Operations | Signage & Wayfinding | Logistics | SHIPPING & RECEIVING | SHIPPING & RECEIVING |  | Freight dock intake portal sign | Active | FALSE | Central copy library authorization | Julian Clarkson | 2026-09-30 13:05 | 2026-09-30 13:05
VRB-162 | GHXSTSHIP | CSMIA26 | Site Operations | Signage & Wayfinding | Sanitation | SHOWERS | SHOWERS |  | Campground public shower facility sign | Active | FALSE | Central copy library authorization | Julian Clarkson | 2026-09-30 13:05 | 2026-09-30 13:05
VRB-163 | GHXSTSHIP | CSMIA26 | Guest Experience | Signage & Wayfinding | Entertainment | SILENT DISCO | SILENT DISCO |  | Late night headphone dance stage portal | Active | FALSE | Central copy library authorization | Julian Clarkson | 2026-09-30 13:05 | 2026-09-30 13:05
VRB-164 | GHXSTSHIP | CSMIA26 | Site Operations | Signage & Wayfinding | Camping | STAFF BYORV CAMPING | STAFF BYORV CAMPING |  | Crew personal RV camp compound | Active | FALSE | Central copy library authorization | Julian Clarkson | 2026-09-30 13:05 | 2026-09-30 13:05
VRB-165 | GHXSTSHIP | CSMIA26 | Site Operations | Signage & Wayfinding | Parking | STAFF CAMPER PARKING | STAFF CAMPER PARKING |  | Crew towed camper trailer lot | Active | FALSE | Central copy library authorization | Julian Clarkson | 2026-09-30 13:05 | 2026-09-30 13:05
VRB-166 | GHXSTSHIP | CSMIA26 | Site Operations | Signage & Wayfinding | Camping | STAFF CAMPING | STAFF CAMPING |  | Dedicated production crew campground | Active | FALSE | Central copy library authorization | Julian Clarkson | 2026-09-30 13:05 | 2026-09-30 13:05
VRB-167 | GHXSTSHIP | CSMIA26 | Site Operations | Signage & Wayfinding | Camping | STAFF CAMPING & PARKING | STAFF CAMPING & PARKING |  | Integrated staff lodging and vehicle lot | Active | FALSE | Central copy library authorization | Julian Clarkson | 2026-09-30 13:05 | 2026-09-30 13:05
VRB-168 | GHXSTSHIP | CSMIA26 | Site Operations | Signage & Wayfinding | Camping | STAFF CAMPING CHECK-IN | STAFF CAMPING CHECK-IN |  | Staff campground registration gate | Active | FALSE | Central copy library authorization | Julian Clarkson | 2026-09-30 13:05 | 2026-09-30 13:05
VRB-169 | GHXSTSHIP | CSMIA26 | Site Operations | Signage & Wayfinding | Parking | STAFF CAMPING PARKING | STAFF CAMPING PARKING |  | Reserved vehicle spaces for staff camp | Active | FALSE | Central copy library authorization | Julian Clarkson | 2026-09-30 13:05 | 2026-09-30 13:05
VRB-170 | GHXSTSHIP | CSMIA26 | Site Operations | Signage & Wayfinding | Camping | STAFF CAR CAMPING | STAFF CAR CAMPING |  | Vehicle-adjacent tent pitches for staff | Active | FALSE | Central copy library authorization | Julian Clarkson | 2026-09-30 13:05 | 2026-09-30 13:05
VRB-171 | GHXSTSHIP | CSMIA26 | Catering & Hospitality | Signage & Wayfinding | Catering | STAFF CATERING | STAFF CATERING |  | Production dining and catering tent | Active | FALSE | Central copy library authorization | Julian Clarkson | 2026-09-30 13:05 | 2026-09-30 13:05
VRB-172 | GHXSTSHIP | CSMIA26 | Site Operations | Signage & Wayfinding | Access Control | STAFF CHECK-IN | STAFF CHECK-IN |  | Daily crew muster and security gate | Active | FALSE | Central copy library authorization | Julian Clarkson | 2026-09-30 13:05 | 2026-09-30 13:05
VRB-173 | GHXSTSHIP | CSMIA26 | Site Operations | Signage & Wayfinding | Parking | STAFF DAY PARKING | STAFF DAY PARKING |  | Non-camping crew daily parking zone | Active | FALSE | Central copy library authorization | Julian Clarkson | 2026-09-30 13:05 | 2026-09-30 13:05
VRB-174 | GHXSTSHIP | CSMIA26 | Site Operations | Signage & Wayfinding | Parking | STAFF DAY PARKING : RVS | STAFF DAY PARKING : RVS |  | Oversized staff vehicle day lot | Active | FALSE | Central copy library authorization | Julian Clarkson | 2026-09-30 13:05 | 2026-09-30 13:05
VRB-175 | GHXSTSHIP | CSMIA26 | Site Operations | Signage & Wayfinding | Parking | STAFF PARKING | STAFF PARKING |  | General staff permitted vehicle lot | Active | FALSE | Central copy library authorization | Julian Clarkson | 2026-09-30 13:05 | 2026-09-30 13:05
VRB-176 | GHXSTSHIP | CSMIA26 | Site Operations | Signage & Wayfinding | Parking | STAFF RVS | STAFF RVS |  | Staff operational RV staging compound | Active | FALSE | Central copy library authorization | Julian Clarkson | 2026-09-30 13:05 | 2026-09-30 13:05
VRB-177 | GHXSTSHIP | CSMIA26 | Site Operations | Signage & Wayfinding | Camping | STAFF TENT CAMPING | STAFF TENT CAMPING |  | Tent-only crew residential zone | Active | FALSE | Central copy library authorization | Julian Clarkson | 2026-09-30 13:05 | 2026-09-30 13:05
VRB-178 | GHXSTSHIP | CSMIA26 | Site Operations | Signage & Wayfinding | Traffic | STOP | STOP |  | Octagonal traffic control sign | Active | FALSE | Central copy library authorization | Julian Clarkson | 2026-09-30 13:05 | 2026-09-30 13:05
VRB-179 | GHXSTSHIP | CSMIA26 | Site Operations | Signage & Wayfinding | Traffic | STOP AHEAD | STOP AHEAD |  | Advance intersection warning sign | Active | FALSE | Central copy library authorization | Julian Clarkson | 2026-09-30 13:05 | 2026-09-30 13:05
VRB-180 | GHXSTSHIP | CSMIA26 | Guest Experience | Signage & Wayfinding | Hospitality | TABLE RESERVATIONS | TABLE RESERVATIONS |  | VIP bottle service host podium sign | Active | FALSE | Central copy library authorization | Julian Clarkson | 2026-09-30 13:05 | 2026-09-30 13:05
VRB-181 | GHXSTSHIP | CSMIA26 | Guest Experience | Signage & Wayfinding | Ticketing | TICKET HELP | TICKET HELP |  | Ticketing customer resolution booth | Active | FALSE | Central copy library authorization | Julian Clarkson | 2026-09-30 13:05 | 2026-09-30 13:05
VRB-182 | GHXSTSHIP | CSMIA26 | Guest Experience | Signage & Wayfinding | Ticketing | TICKET SALES | TICKET SALES |  | Onsite festival pass purchases | Active | FALSE | Central copy library authorization | Julian Clarkson | 2026-09-30 13:05 | 2026-09-30 13:05
VRB-183 | GHXSTSHIP | CSMIA26 | Guest Experience | Signage & Wayfinding | Access Control | TICKET SCAN | TICKET SCAN |  | Optical barcode ticket scanning lanes | Active | FALSE | Central copy library authorization | Julian Clarkson | 2026-09-30 13:05 | 2026-09-30 13:05
VRB-184 | GHXSTSHIP | CSMIA26 | Site Operations | Signage & Wayfinding | Transportation | TRUCK STOP | TRUCK STOP |  | Commercial tractor-trailer marshal yard | Active | FALSE | Central copy library authorization | Julian Clarkson | 2026-09-30 13:05 | 2026-09-30 13:05
VRB-185 | GHXSTSHIP | CSMIA26 | Procurement | Signage & Wayfinding | Vendor Ops | VENDOR CHECK-IN | VENDOR CHECK-IN |  | Third-party supplier gate check-in | Active | FALSE | Central copy library authorization | Julian Clarkson | 2026-09-30 13:05 | 2026-09-30 13:05
VRB-186 | GHXSTSHIP | CSMIA26 | Guest Experience | Signage & Wayfinding | Access Control | VIP | VIP |  | VIP premium ticket tier designation | Active | FALSE | Central copy library authorization | Julian Clarkson | 2026-09-30 13:05 | 2026-09-30 13:05
VRB-187 | GHXSTSHIP | CSMIA26 | Site Operations | Signage & Wayfinding | Camping | VIP CAMPING | VIP CAMPING |  | Glamping and luxury camp compound | Active | FALSE | Central copy library authorization | Julian Clarkson | 2026-09-30 13:05 | 2026-09-30 13:05
VRB-188 | GHXSTSHIP | CSMIA26 | Site Operations | Signage & Wayfinding | Camping | VIP CAMPING ENTRANCE | VIP CAMPING ENTRANCE |  | Dedicated VIP campsite portal banner | Active | FALSE | Central copy library authorization | Julian Clarkson | 2026-09-30 13:05 | 2026-09-30 13:05
VRB-189 | GHXSTSHIP | CSMIA26 | Guest Experience | Signage & Wayfinding | Hospitality | VIP CONCIERGE | VIP CONCIERGE |  | VIP patron services desk banner | Active | FALSE | Central copy library authorization | Julian Clarkson | 2026-09-30 13:05 | 2026-09-30 13:05
VRB-190 | GHXSTSHIP | CSMIA26 | Guest Experience | Signage & Wayfinding | Access Control | VIP ENTRANCE | VIP ENTRANCE |  | Dedicated VIP portal ingress archway | Active | FALSE | Central copy library authorization | Julian Clarkson | 2026-09-30 13:05 | 2026-09-30 13:05
VRB-191 | GHXSTSHIP | CSMIA26 | Guest Experience | Signage & Wayfinding | Access Control | VIP ID CHECK | VIP ID CHECK |  | VIP age verification and wristband lane | Active | FALSE | Central copy library authorization | Julian Clarkson | 2026-09-30 13:05 | 2026-09-30 13:05
VRB-192 | GHXSTSHIP | CSMIA26 | Guest Experience | Signage & Wayfinding | Services | VIP LOCKERS | VIP LOCKERS |  | Complimentary VIP storage lockers | Active | FALSE | Central copy library authorization | Julian Clarkson | 2026-09-30 13:05 | 2026-09-30 13:05
VRB-193 | GHXSTSHIP | CSMIA26 | Site Operations | Signage & Wayfinding | Sanitation | VIP RESTROOMS | VIP RESTROOMS |  | Executive air conditioned restroom units | Active | FALSE | Central copy library authorization | Julian Clarkson | 2026-09-30 13:05 | 2026-09-30 13:05
VRB-194 | GHXSTSHIP | CSMIA26 | Security & Safety | Signage & Wayfinding | Access Control | VIP SECURITY SEARCH | VIP SECURITY SEARCH |  | Fast track security inspection canopy | Active | FALSE | Central copy library authorization | Julian Clarkson | 2026-09-30 13:05 | 2026-09-30 13:05
VRB-195 | GHXSTSHIP | CSMIA26 | Guest Experience | Signage & Wayfinding | Hospitality | VIP TABLE CHECK-IN | VIP TABLE CHECK-IN |  | Bottle service table host check-in | Active | FALSE | Central copy library authorization | Julian Clarkson | 2026-09-30 13:05 | 2026-09-30 13:05
VRB-196 | GHXSTSHIP | CSMIA26 | Guest Experience | Signage & Wayfinding | Hospitality | VIP TABLE CONCIERGE | VIP TABLE CONCIERGE |  | Dedicated table hospitality desk | Active | FALSE | Central copy library authorization | Julian Clarkson | 2026-09-30 13:05 | 2026-09-30 13:05
VRB-197 | GHXSTSHIP | CSMIA26 | Guest Experience | Signage & Wayfinding | Access Control | VIP TABLE ENTRANCE | VIP TABLE ENTRANCE |  | Private table deck ingress entrance | Active | FALSE | Central copy library authorization | Julian Clarkson | 2026-09-30 13:05 | 2026-09-30 13:05
VRB-198 | GHXSTSHIP | CSMIA26 | Site Operations | Signage & Wayfinding | Parking | VIP TABLE PARKING | VIP TABLE PARKING |  | Reserved parking stall for table buyers | Active | FALSE | Central copy library authorization | Julian Clarkson | 2026-09-30 13:05 | 2026-09-30 13:05
VRB-199 | GHXSTSHIP | CSMIA26 | Guest Experience | Signage & Wayfinding | Hospitality | VIP TABLE RESERVATIONS | VIP TABLE RESERVATIONS |  | Bottle service customer reservations | Active | FALSE | Central copy library authorization | Julian Clarkson | 2026-09-30 13:05 | 2026-09-30 13:05
VRB-200 | GHXSTSHIP | CSMIA26 | Guest Experience | Signage & Wayfinding | Hospitality | VIP TABLES | VIP TABLES |  | Elevated table deck section signage | Active | FALSE | Central copy library authorization | Julian Clarkson | 2026-09-30 13:05 | 2026-09-30 13:05
VRB-201 | GHXSTSHIP | CSMIA26 | Guest Experience | Signage & Wayfinding | Access Control | VIP TICKET SCAN | VIP TICKET SCAN |  | VIP dedicated RFID scan lanes | Active | FALSE | Central copy library authorization | Julian Clarkson | 2026-09-30 13:05 | 2026-09-30 13:05
VRB-202 | GHXSTSHIP | CSMIA26 | Guest Experience | Signage & Wayfinding | Ticketing | VIP UPGRADES | VIP UPGRADES |  | Onsite GA to VIP ticket upgrade booth | Active | FALSE | Central copy library authorization | Julian Clarkson | 2026-09-30 13:05 | 2026-09-30 13:05
VRB-203 | GHXSTSHIP | CSMIA26 | Guest Experience | Signage & Wayfinding | Ticketing | VIP WILL CALL | VIP WILL CALL |  | Dedicated VIP credential pickup window | Active | FALSE | Central copy library authorization | Julian Clarkson | 2026-09-30 13:05 | 2026-09-30 13:05
VRB-204 | GHXSTSHIP | CSMIA26 | Site Operations | Signage & Wayfinding | Camping | VOLUNTEER CAMP | VOLUNTEER CAMP |  | Volunteer workforce tent compound | Active | FALSE | Central copy library authorization | Julian Clarkson | 2026-09-30 13:05 | 2026-09-30 13:05
VRB-205 | GHXSTSHIP | CSMIA26 | Site Operations | Signage & Wayfinding | Access Control | VOLUNTEER CHECK-IN | VOLUNTEER CHECK-IN |  | Volunteer muster and badge pickup | Active | FALSE | Central copy library authorization | Julian Clarkson | 2026-09-30 13:05 | 2026-09-30 13:05
VRB-206 | GHXSTSHIP | CSMIA26 | Site Operations | Signage & Wayfinding | Parking | VOLUNTEER CHECK-IN PARKING | VOLUNTEER CHECK-IN PARKING |  | Short-term parking for volunteer check-in | Active | FALSE | Central copy library authorization | Julian Clarkson | 2026-09-30 13:05 | 2026-09-30 13:05
VRB-207 | GHXSTSHIP | CSMIA26 | Site Operations | Signage & Wayfinding | Parking | VOLUNTEER PARKING | VOLUNTEER PARKING |  | Permitted parking lot for event volunteers | Active | FALSE | Central copy library authorization | Julian Clarkson | 2026-09-30 13:05 | 2026-09-30 13:05
VRB-208 | GHXSTSHIP | CSMIA26 | Site Operations | Signage & Wayfinding | Services | WATER REFILL STATION | WATER REFILL STATION |  | Free potable water hydration point | Active | FALSE | Central copy library authorization | Julian Clarkson | 2026-09-30 13:05 | 2026-09-30 13:05
VRB-209 | GHXSTSHIP | CSMIA26 | Guest Experience | Signage & Wayfinding | Ticketing | WILL CALL | WILL CALL |  | Customer pre-purchased ticket window | Active | FALSE | Central copy library authorization | Julian Clarkson | 2026-09-30 13:05 | 2026-09-30 13:05
VRB-210 | GHXSTSHIP | CSMIA26 | Guest Experience | Signage & Wayfinding | Access Control | WRISTBAND EXCHANGE | WRISTBAND EXCHANGE |  | Digital ticket to RFID wristband counter | Active | FALSE | Central copy library authorization | Julian Clarkson | 2026-09-30 13:05 | 2026-09-30 13:05
VRB-211 | GHXSTSHIP | CSMIA26 | Legal & Compliance | Legal Verbiage | Legal Disclosure | ASSUMPTION OF THE RISK AND WAIVER OF LIABILITY RELATING TO CORONAVIRUS/COVID-19 | ASSUMPTION OF THE RISK AND WAIVER OF LIABILITY RELATING TO CORONAVIRUS/COVID-19 | THE NOVEL CORONAVIRUS, COVID-19, HAS BEEN DECLARED A WORLDWIDE PANDEMIC BY THE WORLD HEALTH ORGANIZATION. COVID-19 IS EXTREMELY CONTAGIOUS AND IS BELIEVED TO SPREAD MAINLY FROM PERSON-TO-PERSON CONTACT. BY ENTERING THESE PREMISES AND/OR THE EVENT, YOU (A) ACKNOWLEDGE THE CONTAGIOUS NATURE OF COVID-19 AND VOLUNTARILY ASSUME THE RISK THAT YOU MAY BE EXPOSED TO OR INFECTED BY COVID-19 AND THAT SUCH EXPOSURE OR INFECTION MAY RESULT IN PERSONAL INJURY, ILLNESS, PERMANENT DISABILITY, AND DEATH, (B) VOLUNTARILY AGREE TO ASSUME ALL OF THE FOREGOING RISKS AND ACCEPT SOLE RESPONSIBILITY FOR ANY INJURY, ILLNESS, DAMAGE, LOSS, CLAIM, LIABILITY, OR EXPENSES, OF ANY KIND (“CLAIMS”), THAT YOU MAY EXPERIENCE OR INCUR, AND (C) HEREBY RELEASE, COVENANT NOT TO SUE, DISCHARGE, AND HOLD HARMLESS THE VENUE, EVENT PROMOTER(S), VENDOR(S), AND EACH OF THEIR RESPECTIVE PARENTS, MEMBERS, PARTNERS, ALIATES, DIVISIONS, SUBSIDIARIES, AND LANDLORDS AND THEIR RESPECTIVE OFFICERS, DIRECTORS, AND EMPLOYEES FROM CLAIMS OF ANY KIND ARISING OUT OF OR RELATING THERE TO. | Universal infectious disease waiver notice | Active | FALSE | Central copy library authorization | Julian Clarkson | 2026-09-30 13:05 | 2026-09-30 13:05
VRB-212 | GHXSTSHIP | CSMIA26 | Legal & Compliance | Legal Verbiage | Legal Disclosure | NOTICE OF FILMING AND PHOTOGRAPHY | NOTICE OF FILMING AND PHOTOGRAPHY | THIS EVENT IS BEING RECORDED IN AND AROUND THESE PREMISES. BY YOUR ENTRY INTO THESE PREMISES, YOU (1) EXPLICITLY ASSUME ALL RISK OF INJURY AND DAMAGE TO YOURSELF AND YOUR PROPERTY AS A RESULT OF YOUR ENTRY OR OTHERWISE RELATED TO THIS EVENT, AND (2) CONSENT TO THE USE OF YOUR PHOTOGRAPH, IMAGE, VOICE, LIKENESS, ACTIONS AND STATEMENTS IN CONNECTION WITH ANY LIVE OR RECORDED AUDIO, VIDEO, DIGITAL, PHOTOGRAPH, OR OTHER TRANSMISSION OR PUBLICATION OF THIS EVENT, AND IN PROMOTION THEREFORE, IN ANY AND ALL MEDIA, THROUGHOUT THE UNIVERSE, IN PERPETUITY, WITHOUT REMUNERATION BY INSOMNIAC HOLDINGS, LLC OR ANY OF ITS AFFILIATES. | Commercial audio/video recording consent notice | Active | FALSE | Central copy library authorization | Julian Clarkson | 2026-09-30 13:05 | 2026-09-30 13:05
VRB-213 | GHXSTSHIP | CSMIA26 | Legal & Compliance | Legal Verbiage | Legal Disclosure | PROHIBITED ITEMS | PROHIBITED ITEMS | ZERO TOLERANCE NO WEAPON OR WEAPON ACCESSORIES OF ANY KIND, REAL OR FICTIONAL (INCLUDING BUT NOT LIMITED TO TOY GUNS, WATER GUNS, SLINGSHOTS, WHIPS, LIGHTSABERS, POCKET KNIVES, PEPPER SPRAY, FIREWORKS, FAKE WEAPONS/PROPS, ETC.) NO ILLEGAL SUBSTANCES NO DRUGS OR DRUG PARAPHERNALIA COSTUMES & PROPS NO COSTUMES THAT RESEMBLE PUBLIC SAFETY UNIFORMS (POLICE, SWAT, FIRE, SECURITY, OR MEDICAL) IN ANY WAY NO BALLOON/INFLATABLE/STUFFED ANIMALS OR DOLLS NO BANNERS OR FLAGS NO FESTIVAL TOTEMS, FLAG POLES, OR DECORATED POOL NOODLES NO HELIUM BALLOONS NO INFLATABLES OF ANY KIND NO LARGE CHAINS OR SPIKED JEWELRY NO PACIFIERS ELECTRONICS NO PROFESSIONAL PHOTO, VIDEO, OR AUDIO RECORDING EQUIPMENT (INCLUDING BUT NOT LIMITED TO DETACHABLE LENSES, TRIPODS, BIG ZOOMS, OR COMMERCIAL-USE RIGS, ETC.) NO DRONES OR REMOTE-CONTROLLED AIRCRAFT NO LASER POINTERS NO SELFIE STICKS PERSONAL ITEMS NO LARGE PURSES, BAGS, OR BACKPACKS (OVER 12”X12”) NO OUTSIDE FOOD OR DRINK NO GLASS, CANS, CUPS, OR COOLERS NO AEROSOL PRODUCTS OR CANS NO OPEN CIGARETTE PACKS (UPON ENTRY) NO OPEN DEODORANT (UPON ENTRY) NO OPEN EYE DROPS (UPON ENTRY) NO OPEN SUNSCREEN LOTION (UPON ENTRY) NO OPEN TAMPONS OR PADS (UPON ENTRY) NO OVER-THE-COUNTER MEDICATION NO MASSAGERS NO PERSONAL MISTING FANS WITH ATTACHED BOTTLE MISCELLANEOUS ITEMS NO ANIMALS OR PETS NO AIR HORNS NO BALLS OR FRISBEES NO CONFETTI OR STREAMERS NO INFLATABLES OF ANY KIND NO MARKERS, PENS, OR SPRAY PAINT NO PORTABLE CHAIRS OR SOFAS NO PRINTED OR HANDMADE SIGNS NO STICKERS, FLYERS, OR PROMOTIONAL MATERIALS NO TENTS, LARGE UMBRELLAS, CHAIRS, OR BLANKETS ENTRANCE TO THE VENUE IS AT THE DISCRETION OF VENUE MANAGEMENT. THE ITEMS LISTED ABOVE ARE PROHIBITED BASED ON CURRENT GUIDELINES AND CONSIDERATIONS FOR PUBLIC AND PERSONAL SAFETY. HOWEVER, PLEASE BE AWARE THAT THIS LIST MAY CHANGE AT ANY TIME WITH OR WITHOUT NOTICE, AS DETERMINED BY VENUE MANAGEMENT OR REGULATORY REQUIREMENTS. WE APPRECIATE YOUR COOPERATION AND UNDERSTANDING. | Venue restricted items safety policy disclosure | Active | FALSE | Central copy library authorization | Julian Clarkson | 2026-09-30 13:05 | 2026-09-30 13:05

## Enumerations
RECORD ID | ORGANIZATION | PROJECT | DEPARTMENT | CATEGORY | SUB CATEGORY | ENUM DOMAIN | ENUM CODE | ENUM LABEL | DESCRIPTION | SORT ORDER | COLOR CODE | TARGET ENTITY | IS DEFAULT | STATUS | Workflow Status | Incident Priority | Shift & Timesheet Status | Clearance Tier | Commercial State | Asset Condition | Deployment State | FLAG | NOTES | CREATED BY | CREATED AT | UPDATED AT
ENM-001 | GHXSTSHIP | CSMIA26 | Operations Systems | System Architecture | Enumerations | Workflow Status | STAT_ACTIVE | Active | Entity or record is currently operational and in effect | 1 | #1B873F | Universal | TRUE | Active | Active | Critical (P1) | Active | Tier 1 - Executive Master | Active | New | Active | FALSE | Master lifecycle active state | Julian Clarkson | 2026-09-30 13:05 | 2026-09-30 13:05
ENM-002 | GHXSTSHIP | CSMIA26 | Operations Systems | System Architecture | Enumerations | Workflow Status | STAT_INACTIVE | Inactive | Entity or record is temporarily deactivated or dormant | 2 | #5F6368 | Universal | FALSE | Active | Inactive | High (P2) | Inactive | Tier 1 - Regulatory Standby | Inactive | Excellent | Inactive | FALSE | Master lifecycle inactive state | Julian Clarkson | 2026-09-30 13:05 | 2026-09-30 13:05
ENM-003 | GHXSTSHIP | CSMIA26 | Operations Systems | System Architecture | Enumerations | Workflow Status | STAT_PENDING | Pending | Awaiting initial review, prerequisite fulfillment, or authorization | 3 | #F9AB00 | Universal | FALSE | Active | Pending | Medium (P3) | Pending | Tier 2 - Technical Lead | Pending | Good | Pending | FALSE | Advance requests, scheduling queues | Julian Clarkson | 2026-09-30 13:05 | 2026-09-30 13:05
ENM-004 | GHXSTSHIP | CSMIA26 | Operations Systems | System Architecture | Enumerations | Workflow Status | STAT_APPROVED | Approved | Request or submission has received formal stakeholder sign-off | 4 | #1A73E8 | Universal | FALSE | Active | Approved | Low (P4) | Approved | Tier 3 - Operations Ops | Approved | Fair | Approved | FALSE | Advance requests and credential validation | Julian Clarkson | 2026-09-30 13:05 | 2026-09-30 13:05
ENM-005 | GHXSTSHIP | CSMIA26 | Operations Systems | System Architecture | Enumerations | Workflow Status | STAT_IN_PROGRESS | In Progress | Task, shift, or operational process is currently actively executing | 5 | #1A73E8 | Universal | FALSE | Active | In Progress | Critical | In Progress | Tier 4 - Standard Commercial | In Progress | Poor / Damaged | In Progress | FALSE | Activity logs and production milestones | Julian Clarkson | 2026-09-30 13:05 | 2026-09-30 13:05
ENM-006 | GHXSTSHIP | CSMIA26 | Operations Systems | System Architecture | Enumerations | Workflow Status | STAT_DEPLOYED | Deployed | Asset or gear is assigned and dispatched to field location | 6 | #12B5CB | Asset Inventory | FALSE | Active | Deployed | High | Deployed | Tier 5 - Delivery & Supplier | Deployed | Poor | Deployed | FALSE | Radio caches and production equipment | Julian Clarkson | 2026-09-30 13:05 | 2026-09-30 13:05
ENM-007 | GHXSTSHIP | CSMIA26 | Operations Systems | System Architecture | Enumerations | Workflow Status | STAT_IN_TRANSIT | In Transit | Freight or shipment is actively en route between logistics hubs | 7 | #E37400 | Shipping Manifest | FALSE | Active | In Transit | Medium | In Transit | Tier 1 All-Access | In Transit | Damaged | In Transit | FALSE | Logistics intake and freight transfers | Julian Clarkson | 2026-09-30 13:05 | 2026-09-30 13:05
ENM-008 | GHXSTSHIP | CSMIA26 | Operations Systems | System Architecture | Enumerations | Workflow Status | STAT_DELIVERED | Delivered | Shipment has arrived at venue perimeter and intake completed | 8 | #1B873F | Shipping Manifest | FALSE | Active | Delivered | Low | Delivered | Tier 2 Production | Delivered |  | Delivered | FALSE | Freight and equipment intake | Julian Clarkson | 2026-09-30 13:05 | 2026-09-30 13:05
ENM-009 | GHXSTSHIP | CSMIA26 | Operations Systems | System Architecture | Enumerations | Workflow Status | STAT_RESOLVED | Resolved | Incident, hazard, or dispute has been corrected and verified | 9 | #1B873F | Activity Log | FALSE | Active | Resolved |  | Resolved | Tier 3 Crew | Resolved |  | Complete | FALSE | Safety incidents and log entries | Julian Clarkson | 2026-09-30 13:05 | 2026-09-30 13:05
ENM-010 | GHXSTSHIP | CSMIA26 | Operations Systems | System Architecture | Enumerations | Workflow Status | STAT_COMPLETE | Complete | Work shift, production item, or contract has concluded successfully | 10 | #188038 | Universal | FALSE | Active | Complete |  | Complete | Tier 4 Guest | Complete |  | Scheduled | FALSE | Crew schedule shifts and production runs | Julian Clarkson | 2026-09-30 13:05 | 2026-09-30 13:05
ENM-011 | GHXSTSHIP | CSMIA26 | Operations Systems | System Architecture | Enumerations | Incident Priority | PRIO_CRITICAL | Critical (P1) | Immediate life safety, structural failure, or show-stopping disruption | 1 | #D93025 | Activity Log | FALSE | Active | Scheduled |  | Scheduled |  | Scheduled |  | Canceled | FALSE | Emergency codes and immediate dispatch | Julian Clarkson | 2026-09-30 13:05 | 2026-09-30 13:05
ENM-012 | GHXSTSHIP | CSMIA26 | Operations Systems | System Architecture | Enumerations | Incident Priority | PRIO_HIGH | High (P2) | Severe operational impediment requiring urgent lead intervention | 2 | #E37400 | Activity Log | FALSE | Active | Staged |  | Paid |  | Paid |  | In Warehouse | FALSE | Cable ramps, power drops, security breaches | Julian Clarkson | 2026-09-30 13:05 | 2026-09-30 13:05
ENM-013 | GHXSTSHIP | CSMIA26 | Operations Systems | System Architecture | Enumerations | Incident Priority | PRIO_MEDIUM | Medium (P3) | Standard operational disruption requiring resolution within shift | 3 | #F9AB00 | Activity Log | TRUE | Active | Completed |  | Reconciled |  | Reconciled |  | Under Repair | FALSE | Lost and found items, non-critical maintenance | Julian Clarkson | 2026-09-30 13:05 | 2026-09-30 13:05
ENM-014 | GHXSTSHIP | CSMIA26 | Operations Systems | System Architecture | Enumerations | Incident Priority | PRIO_LOW | Low (P4) | Informational logging, routine check-out, or minor tasking | 4 | #1A73E8 | Activity Log | FALSE | Active | Ready |  | Disputed |  | Disputed |  | Decommissioned | FALSE | Routine asset handoffs, stagehand check-ins | Julian Clarkson | 2026-09-30 13:05 | 2026-09-30 13:05
ENM-015 | GHXSTSHIP | CSMIA26 | Operations Systems | System Architecture | Enumerations | Asset Condition | COND_NEW | New | Factory pristine, unopened packaging, never deployed | 1 | #1B873F | Asset Inventory | FALSE | Active | Open |  | Staged |  | Scope Expansion |  |  | FALSE | New stock intake verification | Julian Clarkson | 2026-09-30 13:05 | 2026-09-30 13:05
ENM-016 | GHXSTSHIP | CSMIA26 | Operations Systems | System Architecture | Enumerations | Asset Condition | COND_EXCELLENT | Excellent | Minor handling wear, perfect mechanical & electronic state | 2 | #188038 | Asset Inventory | TRUE | Active | Estimated |  | Completed |  | Emergency Rental |  |  | FALSE | Verified fully operational and calibrated | Julian Clarkson | 2026-09-30 13:05 | 2026-09-30 13:05
ENM-017 | GHXSTSHIP | CSMIA26 | Operations Systems | System Architecture | Enumerations | Asset Condition | COND_GOOD | Good | Normal cosmetic event wear, fully operational | 3 | #1A73E8 | Asset Inventory | FALSE | Active | Canceled |  | Ready |  | Equipment Substitution |  |  | FALSE | Standard frontline operational hardware | Julian Clarkson | 2026-09-30 13:05 | 2026-09-30 13:05
ENM-018 | GHXSTSHIP | CSMIA26 | Operations Systems | System Architecture | Enumerations | Asset Condition | COND_FAIR | Fair | Visible wear or minor degradation; service recommended | 4 | #F9AB00 | Asset Inventory | FALSE | Active | Planned |  | Open |  | Vendor Rate Variance |  |  | FALSE | Acceptable for secondary staging areas | Julian Clarkson | 2026-09-30 13:05 | 2026-09-30 13:05
ENM-019 | GHXSTSHIP | CSMIA26 | Operations Systems | System Architecture | Enumerations | Asset Condition | COND_POOR | Poor / Damaged | Compromised functionality requiring repair or replacement | 5 | #D93025 | Asset Inventory | FALSE | Active | Behind |  | Estimated |  | Schedule Overtime |  |  | FALSE | Red-tagged; remove from active cache | Julian Clarkson | 2026-09-30 13:05 | 2026-09-30 13:05
ENM-020 | GHXSTSHIP | CSMIA26 | Operations Systems | System Architecture | Enumerations | Freight Type | FRT_LTL | LTL Freight | Less-than-truckload palletized commercial freight shipments | 1 | #1A73E8 | Shipping Manifest | TRUE | Active | Milestone Met |  | Canceled |  | Staged |  |  | FALSE | Standard equipment crate delivery mode | Julian Clarkson | 2026-09-30 13:05 | 2026-09-30 13:05
ENM-021 | GHXSTSHIP | CSMIA26 | Operations Systems | System Architecture | Enumerations | Freight Type | FRT_PARCEL | Parcel Express | Small parcel courier consignments via FedEx, UPS, or DHL | 2 | #12B5CB | Shipping Manifest | FALSE | Active |  |  | Draft |  | Completed |  |  | FALSE | Express boxes and radio case intake | Julian Clarkson | 2026-09-30 13:05 | 2026-09-30 13:05
ENM-022 | GHXSTSHIP | CSMIA26 | Operations Systems | System Architecture | Enumerations | Freight Type | FRT_FTL | Full Truckload | Dedicated 53ft dry van or flatbed semi-trailer delivery | 3 | #E37400 | Shipping Manifest | FALSE | Active |  |  | Published |  | Ready |  |  | FALSE | Main stage structure and audio arrays | Julian Clarkson | 2026-09-30 13:05 | 2026-09-30 13:05
ENM-023 | GHXSTSHIP | CSMIA26 | Operations Systems | System Architecture | Enumerations | Freight Type | FRT_AIR | Air Cargo | Expedited air cargo for critical production rush orders | 4 | #9334E6 | Shipping Manifest | FALSE | Active |  |  | Confirmed |  | Open |  |  | FALSE | Direct airfield intake at MIA | Julian Clarkson | 2026-09-30 13:05 | 2026-09-30 13:05
ENM-024 | GHXSTSHIP | CSMIA26 | Operations Systems | System Architecture | Enumerations | Freight Type | FRT_COURIER | Hot Shot / Courier | Dedicated point-to-point same day local courier runner | 5 | #D93025 | Shipping Manifest | FALSE | Active |  |  | Checked-In |  | Estimated |  |  | FALSE | Emergency parts and spare cable runs | Julian Clarkson | 2026-09-30 13:05 | 2026-09-30 13:05
ENM-025 | GHXSTSHIP | CSMIA26 | Operations Systems | System Architecture | Enumerations | Employment Type | EMP_FT_SALARY | Full-Time Salary | Permanent core festival production leadership and heads | 1 | #1A73E8 | Crew Schedule | TRUE | Active |  |  | Rejected |  | Canceled |  |  | FALSE | Exempt leadership staff | Julian Clarkson | 2026-09-30 13:05 | 2026-09-30 13:05
ENM-026 | GHXSTSHIP | CSMIA26 | Operations Systems | System Architecture | Enumerations | Employment Type | EMP_HOURLY_CONT | Hourly Contractor | 1099 production technician or departmental specialist | 2 | #12B5CB | Crew Schedule | FALSE | Active |  |  | Exported |  | Quoted |  |  | FALSE | Hourly production contractors | Julian Clarkson | 2026-09-30 13:05 | 2026-09-30 13:05
ENM-027 | GHXSTSHIP | CSMIA26 | Operations Systems | System Architecture | Enumerations | Employment Type | EMP_UNION_OVER | Union Overhire | IATSE Local 500 union stagehands and rigging dispatch | 3 | #F9AB00 | Crew Schedule | FALSE | Active |  |  |  |  | Committed |  |  | FALSE | Collective bargaining labor agreement | Julian Clarkson | 2026-09-30 13:05 | 2026-09-30 13:05
ENM-028 | GHXSTSHIP | CSMIA26 | Operations Systems | System Architecture | Enumerations | Employment Type | EMP_VENDOR_CREW | Vendor Crew | Third-party staging, audio, video, or power crew labor | 4 | #E37400 | Crew Schedule | FALSE | Active |  |  |  |  | Invoiced |  |  | FALSE | Supplier-provided technical crew | Julian Clarkson | 2026-09-30 13:05 | 2026-09-30 13:05
ENM-029 | GHXSTSHIP | CSMIA26 | Operations Systems | System Architecture | Enumerations | Employment Type | EMP_VOLUNTEER | Volunteer / Intern | Unpaid student or event operations support personnel | 5 | #5F6368 | Crew Schedule | FALSE | Active |  |  |  |  | Draft |  |  | FALSE | Non-safety critical roles | Julian Clarkson | 2026-09-30 13:05 | 2026-09-30 13:05
ENM-030 | GHXSTSHIP | CSMIA26 | Operations Systems | System Architecture | Enumerations | Clearance Tier | CLR_TIER1_EXEC | Tier 1 - Executive Master | Universal venue-wide unescorted access to all secure zones | 1 | #D93025 | Vendor Classes | FALSE | Active |  |  |  |  | Issued |  |  | FALSE | Executive producers, directors, police chiefs | Julian Clarkson | 2026-09-30 13:05 | 2026-09-30 13:05
ENM-031 | GHXSTSHIP | CSMIA26 | Operations Systems | System Architecture | Enumerations | Clearance Tier | CLR_TIER1_REG | Tier 1 - Regulatory Standby | Municipal safety, fire rescue, code enforcement inspectors | 2 | #D93025 | Vendor Classes | FALSE | Active |  |  |  |  | Acknowledged |  |  | FALSE | Civil inspection authorities | Julian Clarkson | 2026-09-30 13:05 | 2026-09-30 13:05
ENM-032 | GHXSTSHIP | CSMIA26 | Operations Systems | System Architecture | Enumerations | Clearance Tier | CLR_TIER2_TECH | Tier 2 - Technical Lead | Production compound, stage decks, FOH, backstage corridors | 3 | #E37400 | Vendor Classes | FALSE | Active |  |  |  |  | Received |  |  | FALSE | Master technical leads & engineers | Julian Clarkson | 2026-09-30 13:05 | 2026-09-30 13:05
ENM-033 | GHXSTSHIP | CSMIA26 | Operations Systems | System Architecture | Enumerations | Clearance Tier | CLR_TIER3_OPS | Tier 3 - Operations Ops | Operations compounds, loading docks, staff lounges | 4 | #F9AB00 | Vendor Classes | TRUE | Active |  |  |  |  | Closed |  |  | FALSE | Site staff, ops coordinators, logistics leads | Julian Clarkson | 2026-09-30 13:05 | 2026-09-30 13:05
ENM-034 | GHXSTSHIP | CSMIA26 | Operations Systems | System Architecture | Enumerations | Clearance Tier | CLR_TIER4_COMM | Tier 4 - Standard Commercial | Commercial booths, retail concessions, vendor delivery lanes | 5 | #1A73E8 | Vendor Classes | FALSE | Active |  |  |  |  | Submitted |  |  | FALSE | Retail concessionaires & booth staff | Julian Clarkson | 2026-09-30 13:05 | 2026-09-30 13:05
ENM-035 | GHXSTSHIP | CSMIA26 | Operations Systems | System Architecture | Enumerations | Clearance Tier | CLR_TIER5_SUPP | Tier 5 - Delivery & Supplier | Dock loading zone only during assigned delivery slots | 6 | #5F6368 | Vendor Classes | FALSE | Active |  |  |  |  | Under Review |  |  | FALSE | Consumables and freight haulers | Julian Clarkson | 2026-09-30 13:05 | 2026-09-30 13:05
ENM-036 | GHXSTSHIP | CSMIA26 | Operations Systems | System Architecture | Enumerations | Access Level | ACC_FULL | Full Access | Unrestricted 24/7 entry to assigned access point or compound | 1 | #1B873F | Access Grid | TRUE | Active | [7 empty] | FALSE | Key staff with credential badge | Julian Clarkson | 2026-09-30 13:05 | 2026-09-30 13:05
ENM-037 | GHXSTSHIP | CSMIA26 | Operations Systems | System Architecture | Enumerations | Access Level | ACC_RESTRICTED | Restricted Access | Entry permitted only during active shift or specified hours | 2 | #F9AB00 | Access Grid | FALSE | Active | [7 empty] | FALSE | Shift-specific passes | Julian Clarkson | 2026-09-30 13:05 | 2026-09-30 13:05
ENM-038 | GHXSTSHIP | CSMIA26 | Operations Systems | System Architecture | Enumerations | Access Level | ACC_ESCORT | Escort Required | Entry restricted to presence of credentialed GHXSTSHIP host | 3 | #E37400 | Access Grid | FALSE | Active | [7 empty] | FALSE | Visitors, media, unbadged delivery crew | Julian Clarkson | 2026-09-30 13:05 | 2026-09-30 13:05
ENM-039 | GHXSTSHIP | CSMIA26 | Operations Systems | System Architecture | Enumerations | Access Level | ACC_PERIMETER | Perimeter Only | Access strictly confined to exterior gate and search lanes | 4 | #5F6368 | Access Grid | FALSE | Active | [7 empty] | FALSE | External delivery haulers | Julian Clarkson | 2026-09-30 13:05 | 2026-09-30 13:05
ENM-040 | GHXSTSHIP | CSMIA26 | Security & Safety | Emergency Protocols | Enumerations | Emergency Radio Code | EMG_RED | CODE RED | Fire emergency; immediately activate extinguishers and contact fire dept | 1 | #D93025 | Emergency Codes | FALSE | Active | [7 empty] | FALSE | Master life safety protocol | Julian Clarkson | 2026-09-30 13:05 | 2026-09-30 13:05
ENM-041 | GHXSTSHIP | CSMIA26 | Security & Safety | Emergency Protocols | Enumerations | Emergency Radio Code | EMG_BLUE | CODE BLUE | Medical emergency; dispatch on-site paramedics and triage team | 2 | #1A73E8 | Emergency Codes | FALSE | Active | [7 empty] | FALSE | Rapid medical response dispatch | Julian Clarkson | 2026-09-30 13:05 | 2026-09-30 13:05
ENM-042 | GHXSTSHIP | CSMIA26 | Security & Safety | Emergency Protocols | Enumerations | Emergency Radio Code | EMG_SILVER | CODE SILVER | Active threat / armed person; immediate venue lockdown protocol | 3 | #70757A | Emergency Codes | FALSE | Active | [7 empty] | FALSE | Critical law enforcement coordinated protocol | Julian Clarkson | 2026-09-30 13:05 | 2026-09-30 13:05
ENM-043 | GHXSTSHIP | CSMIA26 | Security & Safety | Emergency Protocols | Enumerations | Emergency Radio Code | EMG_ORANGE | CODE ORANGE | Acts of aggression or physical altercation; alert security intervention | 4 | #E37400 | Emergency Codes | FALSE | Active | [7 empty] | FALSE | Crowd control & de-escalation protocol | Julian Clarkson | 2026-09-30 13:05 | 2026-09-30 13:05
ENM-044 | GHXSTSHIP | CSMIA26 | Security & Safety | Emergency Protocols | Enumerations | Emergency Radio Code | EMG_YELLOW | CODE YELLOW | Power or structural failure/damage; cut power and dispatch facilities | 5 | #F9AB00 | Emergency Codes | FALSE | Active | [7 empty] | FALSE | Technical production & facilities hazard | Julian Clarkson | 2026-09-30 13:05 | 2026-09-30 13:05
ENM-045 | GHXSTSHIP | CSMIA26 | Security & Safety | Emergency Protocols | Enumerations | Emergency Radio Code | EMG_BLACK | CODE BLACK | Acts of terror; execute master venue evacuation & police command | 6 | #202124 | Emergency Codes | FALSE | Active | [7 empty] | FALSE | Unified emergency command activation | Julian Clarkson | 2026-09-30 13:05 | 2026-09-30 13:05
ENM-046 | GHXSTSHIP | CSMIA26 | Security & Safety | Emergency Protocols | Enumerations | Emergency Radio Code | EMG_ADAM | CODE ADAM | Missing person / lost child protocol; monitor all egress gates | 7 | #9334E6 | Emergency Codes | FALSE | Active | [7 empty] | FALSE | Perimeter egress observation protocol | Julian Clarkson | 2026-09-30 13:05 | 2026-09-30 13:05
ENM-047 | GHXSTSHIP | CSMIA26 | Communications | Radio Frequency | Enumerations | Radio Zone | RZN_ZONE1 | Zone 1 | Primary production, operations, emergency & security talkgroups | 1 | #1A73E8 | Radio Channels | TRUE | Active | [7 empty] | FALSE | Primary 16-channel operational talkgroup band | Julian Clarkson | 2026-09-30 13:05 | 2026-09-30 13:05
ENM-048 | GHXSTSHIP | CSMIA26 | Communications | Radio Frequency | Enumerations | Radio Zone | RZN_ZONE2 | Zone 2 | Ancillary services, vendor operations, guest services talkgroups | 2 | #12B5CB | Radio Channels | FALSE | Active | [7 empty] | FALSE | Secondary 16-channel operational talkgroup band | Julian Clarkson | 2026-09-30 13:05 | 2026-09-30 13:05
ENM-049 | GHXSTSHIP | CSMIA26 | Procurement | Vendor Management | Enumerations | Vendor Class | VCL_A | Class A | Executive - Venue-wide administrative & operational oversight | 1 | #D93025 | Vendor Classes | FALSE | Active | [7 empty] | FALSE | Tier 1 Clearance Master | Julian Clarkson | 2026-09-30 13:05 | 2026-09-30 13:05
ENM-050 | GHXSTSHIP | CSMIA26 | Procurement | Vendor Management | Enumerations | Vendor Class | VCL_B | Class B | Production - Full technical, staging, lighting, and audio access | 2 | #E37400 | Vendor Classes | FALSE | Active | [7 empty] | FALSE | Tier 2 Technical Lead | Julian Clarkson | 2026-09-30 13:05 | 2026-09-30 13:05
ENM-051 | GHXSTSHIP | CSMIA26 | Procurement | Vendor Management | Enumerations | Vendor Class | VCL_C | Class C | Operations - Site facilities, heavy equipment, and grounds access | 3 | #F9AB00 | Vendor Classes | TRUE | Active | [7 empty] | FALSE | Tier 3 Operations Ops | Julian Clarkson | 2026-09-30 13:05 | 2026-09-30 13:05
ENM-052 | GHXSTSHIP | CSMIA26 | Procurement | Vendor Management | Enumerations | Vendor Class | VCL_D | Class D | Vendor - Standard commercial retail and merchandise sales | 4 | #1A73E8 | Vendor Classes | FALSE | Active | [7 empty] | FALSE | Tier 4 Standard Commercial | Julian Clarkson | 2026-09-30 13:05 | 2026-09-30 13:05
ENM-053 | GHXSTSHIP | CSMIA26 | Procurement | Vendor Management | Enumerations | Vendor Class | VCL_E | Class E | Experiential - Brand sponsors, interactive activations, art builds | 5 | #9334E6 | Vendor Classes | FALSE | Active | [7 empty] | FALSE | Tier 3 Brand Partner | Julian Clarkson | 2026-09-30 13:05 | 2026-09-30 13:05
ENM-054 | GHXSTSHIP | CSMIA26 | Procurement | Vendor Management | Enumerations | Vendor Class | VCL_F | Class F | Food & Beverage - Concessionaires, catering, bar operations | 6 | #188038 | Vendor Classes | FALSE | Active | [7 empty] | FALSE | Tier 3 Food & Beverage | Julian Clarkson | 2026-09-30 13:05 | 2026-09-30 13:05
ENM-055 | GHXSTSHIP | CSMIA26 | Procurement | Vendor Management | Enumerations | Vendor Class | VCL_G | Class G | Government Agency - Civil inspectors, fire marshals, police liaisons | 7 | #D93025 | Vendor Classes | FALSE | Active | [7 empty] | FALSE | Tier 1 Regulatory Standby | Julian Clarkson | 2026-09-30 13:05 | 2026-09-30 13:05
ENM-056 | GHXSTSHIP | CSMIA26 | Procurement | Vendor Management | Enumerations | Vendor Class | VCL_P | Class P | Professional Services - Legal counsel, accounting, risk advisors | 8 | #5F6368 | Vendor Classes | FALSE | Active | [7 empty] | FALSE | Tier 5 Offsite Consultant | Julian Clarkson | 2026-09-30 13:05 | 2026-09-30 13:05
ENM-057 | GHXSTSHIP | CSMIA26 | Procurement | Vendor Management | Enumerations | Vendor Class | VCL_R | Class R | Rental Services - Heavy equipment, golf carts, generators drop-off | 9 | #E37400 | Vendor Classes | FALSE | Active | [7 empty] | FALSE | Tier 5 Equipment Delivery | Julian Clarkson | 2026-09-30 13:05 | 2026-09-30 13:05
ENM-058 | GHXSTSHIP | CSMIA26 | Procurement | Vendor Management | Enumerations | Vendor Class | VCL_S | Class S | Supplier - Ice, water, fuel, and consumables delivery haulers | 10 | #12B5CB | Vendor Classes | FALSE | Active | [7 empty] | FALSE | Tier 5 Consumables Supplier | Julian Clarkson | 2026-09-30 13:05 | 2026-09-30 13:05
ENM-059 | GHXSTSHIP | CSMIA26 | Procurement | Vendor Management | Enumerations | Vendor Class | VCL_T | Class T | Transport Services - Shuttles, artist ground transport, freight | 11 | #1A73E8 | Vendor Classes | FALSE | Active | [7 empty] | FALSE | Tier 4 Transit Operator | Julian Clarkson | 2026-09-30 13:05 | 2026-09-30 13:05
ENM-060 | GHXSTSHIP | CSMIA26 | Operations Systems | System Architecture | Enumerations | Resource Kind | KND_EQUIPMENT | Equipment | Physical production gear, hardware, and structural components | 1 | #1A73E8 | Procurement Catalog | TRUE | Active | [7 empty] | FALSE | Procurement item classification | Julian Clarkson | 2026-09-30 13:05 | 2026-09-30 13:05
ENM-061 | GHXSTSHIP | CSMIA26 | Operations Systems | System Architecture | Enumerations | Resource Kind | KND_LABOR | Labor | Operational personnel, technical specialists, and crew labor | 2 | #12B5CB | Procurement Catalog | FALSE | Active | [7 empty] | FALSE | Procurement item classification | Julian Clarkson | 2026-09-30 13:05 | 2026-09-30 13:05
ENM-062 | GHXSTSHIP | CSMIA26 | Operations Systems | System Architecture | Enumerations | Resource Kind | KND_CATERING | Catering | Food, beverage, hospitality meal packages, and craft services | 3 | #188038 | Procurement Catalog | FALSE | Active | [7 empty] | FALSE | Procurement item classification | Julian Clarkson | 2026-09-30 13:05 | 2026-09-30 13:05
ENM-063 | GHXSTSHIP | CSMIA26 | Operations Systems | System Architecture | Enumerations | Resource Kind | KND_VEHICLE | Vehicle | Rolling stock, utility carts, trucks, and site transport vehicles | 4 | #E37400 | Procurement Catalog | FALSE | Active | [7 empty] | FALSE | Procurement item classification | Julian Clarkson | 2026-09-30 13:05 | 2026-09-30 13:05
ENM-064 | GHXSTSHIP | CSMIA26 | Operations Systems | System Architecture | Enumerations | Resource Kind | KND_TOOL | Tool | Hand tools, safety kits, hardware consumables, and site gear | 5 | #F9AB00 | Procurement Catalog | FALSE | Active | [7 empty] | FALSE | Procurement item classification | Julian Clarkson | 2026-09-30 13:05 | 2026-09-30 13:05
ENM-065 | GHXSTSHIP | CSMIA26 | Operations Systems | System Architecture | Enumerations | Resource Kind | KND_TRAVEL | Travel | Flights, airport shuttles, charters, and ground transfers | 6 | #9334E6 | Procurement Catalog | FALSE | Active | [7 empty] | FALSE | Procurement item classification | Julian Clarkson | 2026-09-30 13:05 | 2026-09-30 13:05
ENM-066 | GHXSTSHIP | CSMIA26 | Operations Systems | System Architecture | Enumerations | Resource Kind | KND_CREDENTIAL | Credential | Badges, wristbands, access passes, and screening hardware | 7 | #D93025 | Procurement Catalog | FALSE | Active | [7 empty] | FALSE | Procurement item classification | Julian Clarkson | 2026-09-30 13:05 | 2026-09-30 13:05
ENM-067 | GHXSTSHIP | CSMIA26 | Operations Systems | System Architecture | Enumerations | Resource Kind | KND_RADIO | Radio | Two-way communication transceivers, repeaters, and multi-bay chargers | 8 | #1A73E8 | Procurement Catalog | FALSE | Active | [7 empty] | FALSE | Procurement item classification | Julian Clarkson | 2026-09-30 13:05 | 2026-09-30 13:05
ENM-068 | GHXSTSHIP | CSMIA26 | Operations Systems | System Architecture | Enumerations | Resource Kind | KND_LODGING | Lodging | Hotel rooms, hotel blocks, motorhomes, and short-term rentals | 9 | #5F6368 | Procurement Catalog | FALSE | Active | [7 empty] | FALSE | Procurement item classification | Julian Clarkson | 2026-09-30 13:05 | 2026-09-30 13:05
ENM-069 | GHXSTSHIP | CSMIA26 | Operations Systems | System Architecture | Enumerations | Resource Kind | KND_UNIFORM | Uniform | Crew apparel, high-visibility vests, rain gear, and jackets | 10 | #70757A | Procurement Catalog | FALSE | Active | [7 empty] | FALSE | Procurement item classification | Julian Clarkson | 2026-09-30 13:05 | 2026-09-30 13:05
ENM-070 | GHXSTSHIP | CSMIA26 | Operations Systems | System Architecture | Enumerations | Unit of Measure | UOM_EACH | Each | Single item or individual unit count | 1 | #1A73E8 | Procurement Catalog | TRUE | Active | [7 empty] | FALSE | Unit of measurement specification | Julian Clarkson | 2026-09-30 13:05 | 2026-09-30 13:05
ENM-071 | GHXSTSHIP | CSMIA26 | Operations Systems | System Architecture | Enumerations | Unit of Measure | UOM_HOUR | Hour | Hourly billing rate for personnel or rental gear | 2 | #12B5CB | Procurement Catalog | FALSE | Active | [7 empty] | FALSE | Unit of measurement specification | Julian Clarkson | 2026-09-30 13:05 | 2026-09-30 13:05
ENM-072 | GHXSTSHIP | CSMIA26 | Operations Systems | System Architecture | Enumerations | Unit of Measure | UOM_DAY | Day | Daily day rate or 24-hour equipment rental period | 3 | #188038 | Procurement Catalog | FALSE | Active | [7 empty] | FALSE | Unit of measurement specification | Julian Clarkson | 2026-09-30 13:05 | 2026-09-30 13:05
ENM-073 | GHXSTSHIP | CSMIA26 | Operations Systems | System Architecture | Enumerations | Unit of Measure | UOM_WEEK | Week | Weekly rental period or recurring multi-day service | 4 | #E37400 | Procurement Catalog | FALSE | Active | [7 empty] | FALSE | Unit of measurement specification | Julian Clarkson | 2026-09-30 13:05 | 2026-09-30 13:05
ENM-074 | GHXSTSHIP | CSMIA26 | Operations Systems | System Architecture | Enumerations | Unit of Measure | UOM_RUN | Run / Trip | Single point-to-point transit run or freight delivery trip | 5 | #9334E6 | Procurement Catalog | FALSE | Active | [7 empty] | FALSE | Unit of measurement specification | Julian Clarkson | 2026-09-30 13:05 | 2026-09-30 13:05
ENM-075 | GHXSTSHIP | CSMIA26 | Operations Systems | System Architecture | Enumerations | Unit of Measure | UOM_FLAT | Flat Fee | Lump sum project fee or turn-key package cost | 6 | #5F6368 | Procurement Catalog | FALSE | Active | [7 empty] | FALSE | Unit of measurement specification | Julian Clarkson | 2026-09-30 13:05 | 2026-09-30 13:05
ENM-076 | GHXSTSHIP | CSMIA26 | Operations Systems | System Architecture | Enumerations | Payment Status | PAY_PENDING | Pending | Expense incurred awaiting invoice receipt or authorization | 1 | #F9AB00 | Budget Expenses | TRUE | Active | [7 empty] | FALSE | Accounts payable lifecycle state | Julian Clarkson | 2026-09-30 13:05 | 2026-09-30 13:05
ENM-077 | GHXSTSHIP | CSMIA26 | Operations Systems | System Architecture | Enumerations | Payment Status | PAY_APPROVED | Approved | Invoice verified and approved for disbursement | 2 | #1A73E8 | Budget Expenses | FALSE | Active | [7 empty] | FALSE | Accounts payable lifecycle state | Julian Clarkson | 2026-09-30 13:05 | 2026-09-30 13:05
ENM-078 | GHXSTSHIP | CSMIA26 | Operations Systems | System Architecture | Enumerations | Payment Status | PAY_SCHEDULED | Scheduled | Payment queued in accounts payable for upcoming batch release | 3 | #12B5CB | Budget Expenses | FALSE | Active | [7 empty] | FALSE | Accounts payable lifecycle state | Julian Clarkson | 2026-09-30 13:05 | 2026-09-30 13:05
ENM-079 | GHXSTSHIP | CSMIA26 | Operations Systems | System Architecture | Enumerations | Payment Status | PAY_PAID | Paid | Remittance transferred and payment transaction settled | 4 | #188038 | Budget Expenses | FALSE | Active | [7 empty] | FALSE | Accounts payable lifecycle state | Julian Clarkson | 2026-09-30 13:05 | 2026-09-30 13:05
ENM-080 | GHXSTSHIP | CSMIA26 | Operations Systems | System Architecture | Enumerations | Payment Status | PAY_RECONCILED | Reconciled | General ledger and bank account statements matched and closed | 5 | #1B873F | Budget Expenses | FALSE | Active | [7 empty] | FALSE | Accounts payable lifecycle state | Julian Clarkson | 2026-09-30 13:05 | 2026-09-30 13:05
ENM-081 | GHXSTSHIP | CSMIA26 | Operations Systems | System Architecture | Enumerations | Payment Status | PAY_DISPUTED | Disputed | Discrepancy identified in deliverables or rate; payment held | 6 | #D93025 | Budget Expenses | FALSE | Active | [7 empty] | FALSE | Accounts payable lifecycle state | Julian Clarkson | 2026-09-30 13:05 | 2026-09-30 13:05
ENM-082 | GHXSTSHIP | CSMIA26 | Operations Systems | System Architecture | Enumerations | Inspection Result | INSP_PASSED | Passed | Full regulatory compliance verified with no deficiencies | 1 | #1B873F | Inspection Compliance | FALSE | Active | [7 empty] | FALSE | Standard approved inspection status | Julian Clarkson | 2026-09-30 13:05 | 2026-09-30 13:05
ENM-083 | GHXSTSHIP | CSMIA26 | Operations Systems | System Architecture | Enumerations | Inspection Result | INSP_CONDITIONAL | Passed with Conditions | Approved subject to minor remediations before gates open | 2 | #F9AB00 | Inspection Compliance | FALSE | Active | [7 empty] | FALSE | Conditional sign-off with punchlist | Julian Clarkson | 2026-09-30 13:05 | 2026-09-30 13:05
ENM-084 | GHXSTSHIP | CSMIA26 | Operations Systems | System Architecture | Enumerations | Inspection Result | INSP_FAILED | Failed | Life safety or structural deficiency identified; operation halted | 3 | #D93025 | Inspection Compliance | FALSE | Active | [7 empty] | FALSE | Non-compliant inspection hold | Julian Clarkson | 2026-09-30 13:05 | 2026-09-30 13:05
ENM-085 | GHXSTSHIP | CSMIA26 | Operations Systems | System Architecture | Enumerations | Inspection Result | INSP_REINSPECT | Re-inspection Required | Remediation underway awaiting follow-up agency walkthrough | 4 | #E37400 | Inspection Compliance | FALSE | Active | [7 empty] | FALSE | Follow-up walkthrough required | Julian Clarkson | 2026-09-30 13:05 | 2026-09-30 13:05
ENM-086 | GHXSTSHIP | CSMIA26 | Operations Systems | System Architecture | Enumerations | Inspection Result | INSP_PENDING | Pending Inspection | Awaiting agency inspector arrival and formal sign-off | 5 | #5F6368 | Inspection Compliance | TRUE | Active | [7 empty] | FALSE | Initial queue state before inspection | Julian Clarkson | 2026-09-30 13:05 | 2026-09-30 13:05
ENM-087 | GHXSTSHIP | CSMIA26 | Operations Systems | System Architecture | Enumerations | Regulatory Agency | AGY_MDFR | Miami-Dade Fire Rescue | County authority having jurisdiction for life safety and pyrotechnics | 1 | #D93025 | Inspection Compliance | TRUE | Active | [7 empty] | FALSE | Fire marshal inspections and flame permits | Julian Clarkson | 2026-09-30 13:05 | 2026-09-30 13:05
ENM-088 | GHXSTSHIP | CSMIA26 | Operations Systems | System Architecture | Enumerations | Regulatory Agency | AGY_MIABUILD | City of Miami Building Dept | Municipal building department for temporary structures and stages | 2 | #1A73E8 | Inspection Compliance | FALSE | Active | [7 empty] | FALSE | Special master structural inspections | Julian Clarkson | 2026-09-30 13:05 | 2026-09-30 13:05
ENM-089 | GHXSTSHIP | CSMIA26 | Operations Systems | System Architecture | Enumerations | Regulatory Agency | AGY_FLDOH | Florida Dept of Health | State health department overseeing temporary food service sanitation | 3 | #188038 | Inspection Compliance | FALSE | Active | [7 empty] | FALSE | Food vendor and potable water compliance | Julian Clarkson | 2026-09-30 13:05 | 2026-09-30 13:05
ENM-090 | GHXSTSHIP | CSMIA26 | Operations Systems | System Architecture | Enumerations | Regulatory Agency | AGY_OSHA | OSHA / Safety Board | Federal and state workplace safety standards enforcement | 4 | #F9AB00 | Inspection Compliance | FALSE | Active | [7 empty] | FALSE | Rigging and heavy equipment operations | Julian Clarkson | 2026-09-30 13:05 | 2026-09-30 13:05
ENM-091 | GHXSTSHIP | CSMIA26 | Operations Systems | System Architecture | Enumerations | Regulatory Agency | AGY_MPD | Miami Police Dept | Municipal police department managing public safety and road closures | 5 | #1A73E8 | Inspection Compliance | FALSE | Active | [7 empty] | FALSE | Security perimeter and traffic plan approval | Julian Clarkson | 2026-09-30 13:05 | 2026-09-30 13:05
ENM-092 | GHXSTSHIP | CSMIA26 | Operations Systems | System Architecture | Enumerations | Order Type | ORD_SCOPE_ADD | Scope Expansion | Additional equipment or labor beyond baseline operational contract | 1 | #1A73E8 | Change Orders | FALSE | Active | [7 empty] | FALSE | Direct operational scope expansion | Julian Clarkson | 2026-09-30 13:05 | 2026-09-30 13:05
ENM-093 | GHXSTSHIP | CSMIA26 | Operations Systems | System Architecture | Enumerations | Order Type | ORD_EMERGENCY | Emergency Rental | Urgent procurement to replace failed critical equipment on site | 2 | #D93025 | Change Orders | FALSE | Active | [7 empty] | FALSE | Expedited emergency replacement | Julian Clarkson | 2026-09-30 13:05 | 2026-09-30 13:05
ENM-094 | GHXSTSHIP | CSMIA26 | Operations Systems | System Architecture | Enumerations | Order Type | ORD_EQUIP_SUB | Equipment Substitution | Alternative model or resource deployed due to inventory constraint | 3 | #E37400 | Change Orders | FALSE | Active | [7 empty] | FALSE | Direct catalog substitution | Julian Clarkson | 2026-09-30 13:05 | 2026-09-30 13:05
ENM-095 | GHXSTSHIP | CSMIA26 | Operations Systems | System Architecture | Enumerations | Order Type | ORD_RATE_VAR | Vendor Rate Variance | Authorized variance between benchmark catalog rate and actual invoice | 4 | #F9AB00 | Change Orders | FALSE | Active | [7 empty] | FALSE | Market rate discrepancy adjustment | Julian Clarkson | 2026-09-30 13:05 | 2026-09-30 13:05
ENM-096 | GHXSTSHIP | CSMIA26 | Operations Systems | System Architecture | Enumerations | Order Type | ORD_SCHED_OT | Schedule Overtime | Unplanned labor hours or shift extensions due to weather/load-in delay | 5 | #5F6368 | Change Orders | FALSE | Active | [7 empty] | FALSE | Stagehand and technician overtime | Julian Clarkson | 2026-09-30 13:05 | 2026-09-30 13:05
ENM-097 | GHXSTSHIP | CSMIA26 | Operations Systems | System Architecture | Enumerations | Incident Severity | SEV_L1_CRITICAL | Level 1 - Critical | Life-threatening emergency, active structural failure, or full show stop | 1 | #D93025 | Incident CAD Log | FALSE | Active | [7 empty] | FALSE | Immediate unified command response required | Julian Clarkson | 2026-09-30 13:05 | 2026-09-30 13:05
ENM-098 | GHXSTSHIP | CSMIA26 | Operations Systems | System Architecture | Enumerations | Incident Severity | SEV_L2_MAJOR | Level 2 - Major | Significant injury, major equipment outage, or localized zone breach | 2 | #E37400 | Incident CAD Log | FALSE | Active | [7 empty] | FALSE | Priority response dispatch required | Julian Clarkson | 2026-09-30 13:05 | 2026-09-30 13:05
ENM-099 | GHXSTSHIP | CSMIA26 | Operations Systems | System Architecture | Enumerations | Incident Severity | SEV_L3_MODERATE | Level 3 - Moderate | Non-life-threatening medical case, power blip, or minor patron dispute | 3 | #F9AB00 | Incident CAD Log | TRUE | Active | [7 empty] | FALSE | Standard unit dispatch | Julian Clarkson | 2026-09-30 13:05 | 2026-09-30 13:05
ENM-100 | GHXSTSHIP | CSMIA26 | Operations Systems | System Architecture | Enumerations | Incident Severity | SEV_L4_MINOR | Level 4 - Minor | Minor first aid request, misplaced asset, or noise level advisory | 4 | #1A73E8 | Incident CAD Log | FALSE | Active | [7 empty] | FALSE | Routine log entry and check | Julian Clarkson | 2026-09-30 13:05 | 2026-09-30 13:05
ENM-101 | GHXSTSHIP | CSMIA26 | Operations Systems | System Architecture | Enumerations | Incident Severity | SEV_L5_ADVISORY | Level 5 - Advisory | Informational observation, perimeter sweep notice, or weather advisory | 5 | #5F6368 | Incident CAD Log | FALSE | Active | [7 empty] | FALSE | Informational operational note | Julian Clarkson | 2026-09-30 13:05 | 2026-09-30 13:05
ENM-102 | GHXSTSHIP | CSMIA26 | Operations Systems | System Architecture | Enumerations | Workflow Status | STAT_SCHEDULED | Scheduled | Item, work order, or event milestone is confirmed and slated on the operational calendar | 11 | #1A73E8 | Universal | FALSE | Active | [7 empty] | FALSE | Operational scheduling lifecycle state | Julian Clarkson | 2026-09-30 13:05 | 2026-09-30 13:05
ENM-103 | GHXSTSHIP | CSMIA26 | Operations Systems | System Architecture | Enumerations | Workflow Status | STAT_STAGED | Staged | Vehicle, equipment freight, or production asset is positioned in holding or staging bay | 12 | #F9AB00 | Marshalling Yard Log | FALSE | Active | [7 empty] | FALSE | Freight and yard logistics staging state | Julian Clarkson | 2026-09-30 13:05 | 2026-09-30 13:05
ENM-104 | GHXSTSHIP | CSMIA26 | Operations Systems | System Architecture | Enumerations | Workflow Status | STAT_COMPLETED | Completed | Work order execution, inspection, or task deliverable has finished completely | 13 | #188038 | Work Orders | FALSE | Active | [7 empty] | FALSE | Work order and task completion state | Julian Clarkson | 2026-09-30 13:05 | 2026-09-30 13:05
ENM-105 | GHXSTSHIP | CSMIA26 | Operations Systems | System Architecture | Enumerations | Workflow Status | STAT_READY | Ready | Activity, schedule element, or resource prerequisites satisfied and ready to proceed | 14 | #1B873F | Production Schedule | FALSE | Active | [7 empty] | FALSE | Production schedule readiness state | Julian Clarkson | 2026-09-30 13:05 | 2026-09-30 13:05
ENM-106 | GHXSTSHIP | CSMIA26 | Operations Systems | System Architecture | Enumerations | Workflow Status | STAT_OPEN | Open | Budget item, requisition, or action line is active and awaiting expenditure or award | 15 | #1A73E8 | Budget Expenses | FALSE | Active | [7 empty] | FALSE | Budget line status state | Julian Clarkson | 2026-09-30 13:05 | 2026-09-30 13:05
ENM-107 | GHXSTSHIP | CSMIA26 | Operations Systems | System Architecture | Enumerations | Workflow Status | STAT_ESTIMATED | Estimated | Budget line cost basis is preliminary or benchmark modeled | 16 | #5F6368 | Budget Expenses | FALSE | Active | [7 empty] | FALSE | Budget estimation state | Julian Clarkson | 2026-09-30 13:05 | 2026-09-30 13:05
ENM-108 | GHXSTSHIP | CSMIA26 | Operations Systems | System Architecture | Enumerations | Workflow Status | STAT_CANCELED | Canceled | Item or operation will not proceed but record is retained for audit lineage | 17 | #D93025 | Universal | FALSE | Active | [7 empty] | FALSE | Master lifecycle canceled state | Julian Clarkson | 2026-09-30 13:05 | 2026-09-30 13:05